## Summary
Bucket List — Summary
All buckets side by side · source: inventory_all_20260815_130647.xlsx · as at 15-Aug-2026
BUCKET OVERVIEW
Bucket | Meaning |  | Rows | Projects | Structures | Release Bal. (MT) | Fab (MT) | Galva (MT) | Yard (MT) | Total (MT)
A | Project to start |  | 78 | 78 | 411 |  |  |  |  | 8009.803
B | Raw material incomplete |  | 39 | 27 | 240 | 1725.103 | 2049.722 | 480.525 | 2068.083 | 6323.433
C | RM complete, under production |  | 90 | 55 | 612 | 0 | 1846.768 | 638.183 | 9577.796 | 12062.747
D | Dispatch clearance received |  | 46 | 32 | 334 | 229.121 | 861.064 | 260.087 | 8032.117 | 9382.389
E | Ready, not dispatched |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bucket A is measured as Order Qty; B, C, D and E as pending weight — the two are different measures. Buckets overlap and must not be added together: all 46 D rows also appear in C, and 19 rows appear in both B and C.
BY PROJECT AND MFC BATCH
Project | MFC Batch | A — Project to start |  | B — Raw material incomplete |  | C — RM complete, under production |  | D — Dispatch clearance received |  | E — Ready, not dispatched
|  | MT | Str. | MT | Str. | MT | Str. | MT | Str. | MT | Str.
524 | Z | 1.122 | 1
659 | Z | 0.336 | 1
662 | Z | 48.811 | 4
664 | Z | 20.177 | 4
665 | Z | 2.518 | 1
674 | Z | 0.024 | 1
686 | Z | 3.712 | 1
695 | Z | 62.206 | 14
714 | Z | 2.514 | 2
735 | Z | 8.76 | 1
737 | Z | 1.613 | 1
749 | Z |  | 1
756 | Z | 21.01 | 6
761 | Z | 0.217 | 1
775 | Z | 15.119 | 3
776 | Z | 5.211 | 3
788 | Z | 2.93 | 2
803 | Z | 12.501 | 1
811 | Z | 2.377 | 1
817 | Z | 4.927 | 1
818 | Z | 0.946 | 1
821 | Z |  |  |  |  | 204.204 | 4 | 204.204 | 4
824 | A |  |  |  |  | 77.603 | 9 | 77.603 | 9
824 | B |  |  | 9.297 | 3 | 9.359 | 5
824 | Z |  |  |  |  | 91.997 | 8 | 90.515 | 3
828 | Z | 77.863 | 1
833 | Z | 615.918 | 2
837 | Z | 44.146 | 4
839 | B |  |  |  |  | 5.484 | 3
839 | Z |  |  |  |  | 12.825 | 3
844 | Z | 1.189 | 1
848 | A |  |  |  |  | 53.071 | 6
848 | Z | 2.983 | 1 | 2.438 | 3 | 141.041 | 5 | 141.041 | 5
849 | Z | 10.535 | 3
862 | Z | 3.871 | 1 |  |  | 269.641 | 15
864 | Z | 0.859 | 1
866 | Z | 39.311 | 18 | 6.965 | 2
867 | Z | 0.735 | 1
869 | Z | 8.935 | 3
870 | Z |  |  |  |  | 53.563 | 2 | 33.488 | 1
872 | Z | 41.859 | 3
875 | Z | 36.341 | 4
877 | Z | 8.7 | 3
884 | Z | 575.799 | 21 |  |  | 256.676 | 7 | 256.676 | 7
885 | Z | 44.282 | 5 |  |  | 482.344 | 20 | 478.568 | 17
886 | A |  |  |  |  | 0.573 | 2
886 | B |  |  |  |  | 208.917 | 7 | 208.917 | 7
886 | C |  |  |  |  | 6.448 | 3
888 | A |  |  |  |  | 38.758 | 5 | 38.758 | 5
888 | Z |  |  | 61.422 | 1 | 122.063 | 7 | 181.983 | 7
890 | Z |  |  | 20.07 | 1 | 383.613 | 23 | 334.805 | 10
893 | A |  |  |  |  | 107.504 | 5 | 107.504 | 5
893 | Z |  |  |  |  | 49.354 | 14 | 38.014 | 10
895 | Z | 62.812 | 14
896 | Z | 0.09 | 5
897 | Z | 3.597 | 2 |  |  | 13.77 | 1 | 13.77 | 1
900 | B |  |  | 90.353 | 1 | 225.114 | 2
900 | C |  |  | 166.9 | 1 | 722.72 | 2
903 | A |  |  |  |  | 357.97 | 10 | 357.97 | 10
903 | Z |  |  |  |  | 76.88 | 6 | 76.88 | 6
904 | A |  |  |  |  | 383.209 | 14 | 383.209 | 14
905 | Z | 230.015 | 7 |  |  | 39.165 | 1 | 39.165 | 1
906 | A |  |  |  |  | 38.608 | 8 | 38.608 | 8
906 | B |  |  |  |  | 5.62 | 2
906 | C |  |  |  |  | 13.557 | 10
906 | Z | 8.734 | 4 |  |  | 0.089 | 2
907 | Z | 1177.492 | 30 |  |  | 533.714 | 12 | 533.714 | 12
908 | A |  |  |  |  | 53.359 | 21 | 6.31 | 2
908 | Z |  |  | 294.242 | 9 | 20.388 | 4 | 306.195 | 8
909 | A |  |  |  |  | 43.667 | 7 | 43.667 | 7
909 | Z |  |  |  |  | 56.806 | 13 | 56.806 | 13
910 | Z |  |  | 156.897 | 10
911 | A |  |  |  |  | 5.392 | 2
911 | B |  |  | 38.93 | 1 | 164.755 | 1 | 38.93 | 1
911 | C |  |  |  |  | 90.298 | 2
911 | Z | 20.337 | 3 | 6.799 | 1
912 | A |  |  |  |  | 18.427 | 5
912 | B |  |  | 85.703 | 7
912 | C |  |  | 338.996 | 12
912 | Z | 64.553 | 6 | 32.525 | 8
913 | Z |  |  | 70.175 | 10
914 | Z |  |  |  |  | 30.25 | 8 | 30.25 | 8
917 | A |  |  |  |  | 0.599 | 1
917 | B |  |  |  |  | 86.09 | 7
917 | Z |  |  | 21.769 | 18
918 | B |  |  |  |  | 49.545 | 4 | 43.07 | 3
918 | Z | 0.999 | 2 |  |  | 473.373 | 10 | 473.373 | 10
920 | C |  |  | 42.269 | 11 | 70.958 | 19 | 113.227 | 30
920 | D |  |  | 33.183 | 5 | 73.696 | 19 | 2.241 | 1
920 | Z |  |  |  |  | 217.28 | 18 | 217.28 | 18
921 | Z | 81.697 | 6 |  |  | 1087.023 | 14 | 1087.023 | 14
922 | B |  |  |  |  | 350.908 | 9 | 350.908 | 9
922 | C |  |  |  |  | 114.179 | 7
923 | B |  |  |  |  | 180.454 | 17
923 | Z | 107.354 | 4
924 | Z |  |  |  |  | 13.507 | 7 | 13.507 | 7
926 | A |  |  | 38.211 | 2
926 | B |  |  | 46.58 | 2 | 203.702 | 11
926 | Z |  |  | 11.182 | 18
927 | B |  |  |  |  | 95.68 | 2 | 95.68 | 2
928 | A |  |  |  |  | 5.22 | 2 | 3.125 | 1
928 | B |  |  | 33.726 | 1 | 591.415 | 18
928 | Z | 6.713 | 2
929 | A |  |  | 92.346 | 1 | 22.6 | 1
929 | B |  |  | 257.362 | 5
929 | Z | 84.539 | 1
930 | Z | 352.787 | 2
931 | A |  |  |  |  | 5.503 | 2 | 5.503 | 2
931 | B |  |  |  |  | 424.884 | 6 | 424.884 | 6
931 | Z |  |  |  |  | 2.052 | 2 | 0.763 | 1
932 | A |  |  |  |  | 22.979 | 12
933 | B |  |  |  |  | 879.544 | 4 | 879.544 | 4
933 | C |  |  |  |  | 11.299 | 2
933 | Z |  |  |  |  | 19.225 | 3 | 19.225 | 3
934 | B |  |  |  |  | 252.202 | 17
935 | A |  |  | 1030.128 | 15 | 106.105 | 4 | 1136.233 | 19
935 | B |  |  | 79.585 | 5 | 13.258 | 3 | 92.843 | 8
935 | C |  |  | 8.888 | 3 | 25.094 | 2 | 33.982 | 5
935 | Z | 4.311 | 2
936 | A |  |  |  |  | 70.533 | 10
937 | A |  |  | 74.482 | 14
937 | Z | 352.63 | 11
938 | A |  |  | 6.637 | 2
938 | B |  |  | 16.104 | 1
938 | Z | 5.109 | 1 | 85.266 | 2 | 0.438 | 1
939 | A |  |  |  |  | 268.485 | 9 | 268.485 | 9
940 | C |  |  | 562.697 | 5
940 | Z | 5.756 | 1
941 | B |  |  |  |  | 360.695 | 10
941 | Z |  |  |  |  | 3.943 | 1 | 3.943 | 1
942 | A |  |  | 918.662 | 2
944 | A |  |  |  |  | 31.093 | 2
944 | B |  |  | 711.908 | 3 | 77.122 | 3
945 | A |  |  |  |  | 2.401 | 4
945 | B |  |  |  |  | 25.375 | 5
945 | C |  |  |  |  | 11.054 | 4
946 | A |  |  |  |  | 1.843 | 4
946 | B |  |  |  |  | 5.736 | 4
946 | C |  |  |  |  | 95.698 | 11
947 | A |  |  |  |  | 41.368 | 2
948 | A |  |  | 279.922 | 16 | 0.757 | 2
949 | Z | 12.238 | 1 |  |  | 74.51 | 15
951 | A |  |  | 59.558 | 12
951 | Z | 140.845 | 17
952 | A |  |  |  |  | 18.658 | 2
954 | Z | 12.853 | 5
955 | Z | 22.442 | 7
956 | B |  |  | 352.63 | 11
957 | A |  |  |  |  | 2.987 | 1
958 | A |  |  |  |  | 18.374 | 3
958 | Z | 237.3 | 1
960 | A |  |  | 146.101 | 8
960 | Z | 149.826 | 15
962 | A |  |  |  |  | 10.226 | 8
962 | Z | 121.914 | 15
963 | A |  |  |  |  | 74.281 | 2
963 | Z | 1780.955 | 7
967 | Z | 78.439 | 8
597A | Z | 5.893 | 1
671F | Z | 18.444 | 5
910A | Z | 81.819 | 12
912A | Z |  |  | 32.525 | 8
BPTCL | Z | 8.595 | 1
GETCO | Z | 18.394 | 6
PG | Z | 120.589 | 18
RAILWAY | Z | 0.501 | 6
VR070 | Z | 7.922 | 12
VR073 | Z | 10.361 | 22
VR088 | Z | 6.424 | 11
VS-100 | Z | 0.114 | 1
VS-112 | Z | 440.721 | 1
VS-189 | Z | 32.832 | 2
VS-209 | Z | 400.5 | 11
TOTAL |  | 8009.803 | 411 | 6323.433 | 240 | 12062.747 | 612 | 9382.389 | 334 | 0 | 0

## Summary - 2
Bucket List — All Sheets Side by Side
Each bucket reproduced exactly as it appears on its own worksheet · source: inventory_all_20260815_130647.xlsx · as at 15-Aug-2026
A — Project to start | [6 empty] | B — Raw material incomplete | [6 empty] | C — RM complete, under production | [6 empty] | D — Dispatch clearance received | [6 empty] | E — Ready, not dispatched
Project | MFC Batch | Colour | Date of Client MFC | Project Start Date | Structures | Order Qty (MT) | Project | MFC Batch | Rel. Bal. | Fab | Galva | Yard | Structures | Project | MFC Batch | Rel. Bal. | Fab | Galva | Yard | Structures | Project | MFC Batch | Rel. Bal. | Fab | Galva | Yard | Structures | Side | Project | MFC Batch | Release Balance (MT) | Fab+Galva (MT) | Yard (MT) | Structures
906 | Z | Blue |  |  | 4 | 8.734 | 824 | B | 0.247 | 8.897 | 0 | 0.153 | 3 | 821 | Z | 0 | 10.29 | 0 | 193.914 | 4 | 821 | Z | 0 | 10.29 | 0 | 193.914 | 4
907 | Z | White |  |  | 30 | 1177.492 | 848 | Z | 2.438 | 0 | 0 | 0 | 3 | 824 | A | 0 | 2.372 | 4.462 | 70.769 | 9 | 824 | A | 0 | 2.372 | 4.462 | 70.769 | 9
911 | Z | Blue |  |  | 3 | 20.337 | 866 | Z | 6.965 | 0 | 0 | 0 | 2 | 824 | B | 0 | 9.05 | 0 | 0.309 | 5 | 824 | Z | 0 | 1.907 | 0.139 | 88.469 | 3
929 | Z |  |  |  | 1 | 84.539 | 888 | Z | 0.135 | 0 | 0 | 61.287 | 1 | 824 | Z | 0 | 2.8 | 0.53 | 88.667 | 8 | 848 | Z | 0 | 0 | 0 | 141.041 | 5
923 | Z |  |  |  | 4 | 107.354 | 890 | Z | 3.345 | 0 | 0 | 16.725 | 1 | 839 | B | 0 | 5.185 | 0.119 | 0.18 | 3 | 870 | Z | 0 | 0 | 0 | 33.488 | 1
928 | Z |  |  |  | 2 | 6.713 | 900 | B | 4.427 | 18.133 | 4.826 | 62.967 | 1 | 839 | Z | 0 | 0 | 0 | 12.825 | 3 | 884 | Z | 0 | 0.101 | 1.052 | 255.523 | 7
960 | Z |  |  |  | 15 | 149.826 | 900 | C | 13.554 | 86.012 | 26.939 | 40.395 | 1 | 848 | A | 0 | 40.795 | 7.433 | 4.843 | 6 | 885 | Z | 0 | 3.061 | 0.514 | 474.993 | 17
935 | Z |  |  |  | 2 | 4.311 | 908 | Z | 117.794 | 0 | 0 | 176.448 | 9 | 848 | Z | 0 | 0 | 0 | 141.041 | 5 | 886 | B | 0 | 0.016 | 0.065 | 208.836 | 7
524 | Z |  |  |  | 1 | 1.122 | 910 | Z | 128.919 | 27.262 | 0 | 0.716 | 10 | 862 | Z | 0 | 39.977 | 44.633 | 185.031 | 15 | 888 | A | 0 | 5.532 | 0.4 | 32.826 | 5
597A | Z |  |  |  | 1 | 5.893 | 911 | B | 1.426 | 21.736 | 8.475 | 7.293 | 1 | 870 | Z | 0 | 3.882 | 1.091 | 48.59 | 2 | 888 | Z | 0.135 | 0 | 0 | 181.848 | 7
659 | Z |  |  |  | 1 | 0.336 | 911 | Z | 3.99 | 2.809 | 0 | 0 | 1 | 884 | Z | 0 | 0.101 | 1.052 | 255.523 | 7 | 890 | Z | 3.345 | 0 | 0 | 331.46 | 10
662 | Z |  |  |  | 4 | 48.811 | 912 | B | 49.759 | 34.687 | 0.361 | 0.896 | 7 | 885 | Z | 0 | 4.953 | 1.136 | 476.255 | 20 | 893 | A | 0 | 27.192 | 1.376 | 78.936 | 5
664 | Z |  |  |  | 4 | 20.177 | 912 | C | 180.845 | 124.794 | 18.003 | 15.354 | 12 | 886 | A | 0 | 0 | 0 | 0.573 | 2 | 893 | Z | 0 | 0 | 0 | 38.014 | 10
665 | Z |  |  |  | 1 | 2.518 | 912 | Z | 32.525 | 0 | 0 | 0 | 8 | 886 | B | 0 | 0.016 | 0.065 | 208.836 | 7 | 897 | Z | 0 | 0 | 0 | 13.77 | 1
671F | Z |  |  |  | 5 | 18.444 | 912A | Z | 32.525 | 0 | 0 | 0 | 8 | 886 | C | 0 | 0.397 | 0.526 | 5.525 | 3 | 903 | A | 0 | 7.742 | 2.019 | 348.209 | 10
674 | Z |  |  |  | 1 | 0.024 | 913 | Z | 70.175 | 0 | 0 | 0 | 10 | 888 | A | 0 | 5.532 | 0.4 | 32.826 | 5 | 903 | Z | 0 | 3.114 | 1.268 | 72.498 | 6
686 | Z |  |  |  | 1 | 3.712 | 917 | Z | 14.423 | 7.23 | 0.116 | 0 | 18 | 888 | Z | 0 | 1.502 | 0 | 120.561 | 7 | 904 | A | 0 | 0.91 | 0.803 | 381.496 | 14
695 | Z |  |  |  | 14 | 62.206 | 920 | C | 0.142 | 9.099 | 4.953 | 28.075 | 11 | 890 | Z | 0 | 45.912 | 2.56 | 335.141 | 23 | 905 | Z | 0 | 0 | 0 | 39.165 | 1
714 | Z |  |  |  | 2 | 2.514 | 920 | D | 0.072 | 14.743 | 0.732 | 17.636 | 5 | 893 | A | 0 | 27.192 | 1.376 | 78.936 | 5 | 906 | A | 0 | 5.14 | 1.9 | 31.568 | 8
735 | Z |  |  |  | 1 | 8.76 | 926 | A | 3.461 | 20.255 | 6.97 | 7.525 | 2 | 893 | Z | 0 | 2.578 | 0.626 | 46.15 | 14 | 907 | Z | 0 | 18.478 | 8.102 | 507.134 | 12
737 | Z |  |  |  | 1 | 1.613 | 926 | B | 7.991 | 18.529 | 5.534 | 14.526 | 2 | 897 | Z | 0 | 0 | 0 | 13.77 | 1 | 908 | A | 0 | 0.012 | 0.015 | 6.283 | 2
749 | Z |  |  |  | 1 | 0 | 926 | Z | 11.182 | 0 | 0 | 0 | 18 | 900 | B | 0 | 111.348 | 39.762 | 74.004 | 2 | 908 | Z | 112.249 | 0.374 | 0.153 | 193.419 | 8
756 | Z |  |  |  | 6 | 21.01 | 928 | B | 0.013 | 0.98 | 2.06 | 30.673 | 1 | 900 | C | 0 | 335.827 | 96.038 | 290.855 | 2 | 909 | A | 0 | 0 | 2.117 | 41.55 | 7
761 | Z |  |  |  | 1 | 0.217 | 929 | A | 0.191 | 16.326 | 0.341 | 75.488 | 1 | 903 | A | 0 | 7.742 | 2.019 | 348.209 | 10 | 909 | Z | 0 | 0 | 0.029 | 56.777 | 13
775 | Z |  |  |  | 3 | 15.119 | 929 | B | 23.546 | 93.998 | 8.347 | 131.471 | 5 | 903 | Z | 0 | 3.114 | 1.268 | 72.498 | 6 | 911 | B | 1.426 | 21.736 | 8.475 | 7.293 | 1
776 | Z |  |  |  | 3 | 5.211 | 935 | A | 101.986 | 460.027 | 134.642 | 333.473 | 15 | 904 | A | 0 | 0.91 | 0.803 | 381.496 | 14 | 914 | Z | 0 | 0 | 0 | 30.25 | 8
788 | Z |  |  |  | 2 | 2.93 | 935 | B | 7.449 | 39.89 | 7.343 | 24.903 | 5 | 905 | Z | 0 | 0 | 0 | 39.165 | 1 | 918 | B | 0 | 0 | 0 | 43.07 | 3
803 | Z |  |  |  | 1 | 12.501 | 935 | C | 2.389 | 3.646 | 1.641 | 1.212 | 3 | 906 | A | 0 | 5.14 | 1.9 | 31.568 | 8 | 918 | Z | 0 | 0 | 0 | 473.373 | 10
811 | Z |  |  |  | 1 | 2.377 | 937 | A | 32.55 | 41.932 | 0 | 0 | 14 | 906 | B | 0 | 3.134 | 0.228 | 2.258 | 2 | 920 | C | 0.142 | 24.676 | 9.292 | 79.117 | 30
817 | Z |  |  |  | 1 | 4.927 | 938 | A | 3.343 | 3.011 | 0 | 0.283 | 2 | 906 | C | 0 | 13.557 | 0 | 0 | 10 | 920 | D | 0 | 0.291 | 0.626 | 1.324 | 1
818 | Z |  |  |  | 1 | 0.946 | 938 | B | 16.019 | 0.085 | 0 | 0 | 1 | 906 | Z | 0 | 0.004 | 0 | 0.085 | 2 | 920 | Z | 0 | 0.016 | 0 | 217.264 | 18
828 | Z |  |  |  | 1 | 77.863 | 938 | Z | 76.408 | 8.858 | 0 | 0 | 2 | 907 | Z | 0 | 18.478 | 8.102 | 507.134 | 12 | 921 | Z | 0 | 0.463 | 0.707 | 1085.853 | 14
833 | Z |  |  |  | 2 | 615.918 | 940 | C | 226.9 | 208.787 | 33.419 | 93.591 | 5 | 908 | A | 0 | 7.527 | 1.881 | 43.951 | 21 | 922 | B | 0 | 48.239 | 11.213 | 291.456 | 9
837 | Z |  |  |  | 4 | 44.146 | 942 | A | 28.238 | 112.297 | 140.97 | 637.157 | 2 | 908 | Z | 0 | 1.304 | 0.905 | 18.179 | 4 | 924 | Z | 0 | 0 | 0 | 13.507 | 7
844 | Z |  |  |  | 1 | 1.189 | 944 | B | 83.436 | 270.68 | 69.809 | 287.983 | 3 | 909 | A | 0 | 0 | 2.117 | 41.55 | 7 | 927 | B | 0 | 0 | 0.828 | 94.852 | 2
848 | Z | Blue |  |  | 1 | 2.983 | 948 | A | 143.706 | 136.216 | 0 | 0 | 16 | 909 | Z | 0 | 0 | 0.029 | 56.777 | 13 | 928 | A | 0 | 0.408 | 0.068 | 2.649 | 1
849 | Z |  |  |  | 3 | 10.535 | 951 | A | 44.913 | 14.645 | 0 | 0 | 12 | 911 | A | 0 | 0.515 | 3.207 | 1.67 | 2 | 931 | A | 0 | 0.016 | 1.738 | 3.749 | 2
862 | Z | White |  |  | 1 | 3.871 | 956 | B | 204.143 | 145.792 | 0.842 | 1.853 | 11 | 911 | B | 0 | 16.05 | 28.795 | 119.91 | 1 | 931 | B | 0 | 0.341 | 0.238 | 424.305 | 6
864 | Z |  |  |  | 1 | 0.859 | 960 | A | 43.533 | 98.366 | 4.202 | 0 | 8 | 911 | C | 0 | 54.134 | 7.467 | 28.697 | 2 | 931 | Z | 0 | 0 | 0 | 0.763 | 1
866 | Z | Yellow |  |  | 18 | 39.311 | B - Raw Material Incomplete SUMMARY | [6 empty] | 912 | A | 0 | 13.312 | 0.915 | 4.2 | 5 | 933 | B | 0 | 14.184 | 14.355 | 851.005 | 4
867 | Z |  |  |  | 1 | 0.735 | Total Release Balance |  | 1725.103 | 1725.103 |  |  |  | 914 | Z | 0 | 0 | 0 | 30.25 | 8 | 933 | Z | 0 | 0 | 0 | 19.225 | 3
869 | Z |  |  |  | 3 | 8.935 | Under Production |  |  | 2530.247 |  |  |  | 917 | A | 0 | 0.439 | 0.062 | 0.098 | 1 | 935 | A | 101.986 | 487.533 | 161.328 | 385.386 | 19
872 | Z |  |  |  | 3 | 41.859 | Total Yard |  |  |  |  | 2068.083 |  | 917 | B | 0 | 28.018 | 18.54 | 39.532 | 7 | 935 | B | 7.449 | 47.612 | 9.361 | 28.421 | 8
875 | Z |  |  |  | 4 | 36.341 | Operation Weight |  |  | 4598.33 |  |  |  | 918 | B | 0 | 6.475 | 0 | 43.07 | 4 | 935 | C | 2.389 | 14.612 | 7.709 | 9.272 | 5
877 | Z |  |  |  | 3 | 8.7 | Grand Total Weight |  |  | 6323.433 |  |  |  | 918 | Z | 0 | 0 | 0 | 473.373 | 10 | 939 | A | 0 | 114.696 | 9.735 | 144.054 | 9
884 | Z | Yellow |  |  | 21 | 575.799 | TOTAL |  | 1725.103 | 2049.722 | 480.525 | 2068.083 |  | 920 | C | 0 | 15.577 | 4.339 | 51.042 | 19 | 941 | Z | 0 | 0 | 0 | 3.943 | 1
885 | Z | Blue |  |  | 5 | 44.282 | [7 empty] | 920 | D | 0 | 40.332 | 3.229 | 30.135 | 19 | D - Dispatch Clearance SUMMARY
895 | Z |  |  |  | 14 | 62.812 | [7 empty] | 920 | Z | 0 | 0.016 | 0 | 217.264 | 18 | Total Release Balance |  | 229.121 | 229.121
896 | Z |  |  |  | 5 | 0.09 | [7 empty] | 921 | Z | 0 | 0.463 | 0.707 | 1085.853 | 14 | Under Production |  |  | 1121.151
897 | Z | White |  |  | 2 | 3.597 | [7 empty] | 922 | B | 0 | 48.239 | 11.213 | 291.456 | 9 | Total Yard |  |  |  |  | 8032.117
905 | Z | Yellow |  |  | 7 | 230.015 | [7 empty] | 922 | C | 0 | 59.101 | 15.268 | 39.81 | 7 | Operation Weight |  |  | 9153.268
910A | Z |  |  |  | 12 | 81.819 | [7 empty] | 923 | B | 0 | 19.205 | 10.314 | 150.935 | 17 | Grand Total Weight |  |  | 9382.389
912 | Z | Blue |  |  | 6 | 64.553 | [7 empty] | 924 | Z | 0 | 0 | 0 | 13.507 | 7 | TOTAL |  | 229.121 | 861.064 | 260.087 | 8032.117
918 | Z | White |  |  | 2 | 0.999 | [7 empty] | 926 | B | 0 | 54.199 | 29.581 | 119.922 | 11
921 | Z | Yellow |  |  | 6 | 81.697 | [7 empty] | 927 | B | 0 | 0 | 0.828 | 94.852 | 2
930 | Z |  |  |  | 2 | 352.787 | [7 empty] | 928 | A | 0 | 0.81 | 1.678 | 2.732 | 2
937 | Z |  |  |  | 11 | 352.63 | [7 empty] | 928 | B | 0 | 30.274 | 26.953 | 534.188 | 18
938 | Z | Blue |  |  | 1 | 5.109 | [7 empty] | 929 | A | 0 | 4.373 | 1.472 | 16.755 | 1
940 | Z |  |  |  | 1 | 5.756 | [7 empty] | 931 | A | 0 | 0.016 | 1.738 | 3.749 | 2
949 | Z | Blue |  |  | 1 | 12.238 | [7 empty] | 931 | B | 0 | 0.341 | 0.238 | 424.305 | 6
951 | Z |  |  |  | 17 | 140.845 | [7 empty] | 931 | Z | 0 | 1.289 | 0 | 0.763 | 2
954 | Z |  |  |  | 5 | 12.853 | [7 empty] | 932 | A | 0 | 19.777 | 1.532 | 1.67 | 12
955 | Z |  |  |  | 7 | 22.442 | [7 empty] | 933 | B | 0 | 14.184 | 14.355 | 851.005 | 4
958 | Z |  |  |  | 1 | 237.3 | [7 empty] | 933 | C | 0 | 4.924 | 0.216 | 6.159 | 2
962 | Z |  |  |  | 15 | 121.914 | [7 empty] | 933 | Z | 0 | 0 | 0 | 19.225 | 3
963 | Z |  |  |  | 7 | 1780.955 | [7 empty] | 934 | B | 0 | 117.889 | 37.468 | 96.845 | 17
967 | Z |  |  |  | 8 | 78.439 | [7 empty] | 935 | A | 0 | 27.506 | 26.686 | 51.913 | 4
BPTCL | Z |  |  |  | 1 | 8.595 | [7 empty] | 935 | B | 0 | 7.722 | 2.018 | 3.518 | 3
GETCO | Z |  |  |  | 6 | 18.394 | [7 empty] | 935 | C | 0 | 10.966 | 6.068 | 8.06 | 2
PG | Z |  |  |  | 18 | 120.589 | [7 empty] | 936 | A | 0 | 41.606 | 2.022 | 26.905 | 10
RAILWAY | Z |  |  |  | 6 | 0.501 | [7 empty] | 938 | Z | 0 | 0.438 | 0 | 0 | 1
VR070 | Z |  |  |  | 12 | 7.922 | [7 empty] | 939 | A | 0 | 114.696 | 9.735 | 144.054 | 9
VR073 | Z |  |  |  | 22 | 10.361 | [7 empty] | 941 | B | 0 | 97.084 | 76.07 | 187.541 | 10
VR088 | Z |  |  |  | 11 | 6.424 | [7 empty] | 941 | Z | 0 | 0 | 0 | 3.943 | 1
VS-100 | Z |  |  |  | 1 | 0.114 | [7 empty] | 944 | A | 0 | 0 | 0 | 31.093 | 2
VS-112 | Z |  |  |  | 1 | 440.721 | [7 empty] | 944 | B | 0 | 12.827 | 10.931 | 53.364 | 3
VS-189 | Z |  |  |  | 2 | 32.832 | [7 empty] | 945 | A | 0 | 0 | 0.207 | 2.194 | 4
VS-209 | Z |  |  |  | 11 | 400.5 | [7 empty] | 945 | B | 0 | 25.375 | 0 | 0 | 5
TOTAL | [5 empty] | 8009.803 | [7 empty] | 945 | C | 0 | 11.054 | 0 | 0 | 4
[14 empty] | 946 | A | 0 | 1.399 | 0.444 | 0 | 4
[14 empty] | 946 | B | 0 | 4.434 | 0.502 | 0.8 | 4
[14 empty] | 946 | C | 0 | 95.698 | 0 | 0 | 11
[14 empty] | 947 | A | 0 | 25.33 | 0.865 | 15.173 | 2
[14 empty] | 948 | A | 0 | 0.757 | 0 | 0 | 2
[14 empty] | 949 | Z | 0 | 74.51 | 0 | 0 | 15
[14 empty] | 952 | A | 0 | 11.461 | 7.197 | 0 | 2
[14 empty] | 957 | A | 0 | 2.987 | 0 | 0 | 1
[14 empty] | 958 | A | 0 | 0.553 | 0.736 | 17.085 | 3
[14 empty] | 962 | A | 0 | 10.226 | 0 | 0 | 8
[14 empty] | 963 | A | 0 | 9.568 | 53.526 | 11.187 | 2
C - RM Complete SUMMARY
[14 empty] | Total Release Balance |  | 0 | 0
[14 empty] | Under Production |  |  | 2484.951
[14 empty] | Total Yard |  |  |  |  | 9577.796
[14 empty] | Operation Weight |  |  | 12062.747
[14 empty] | Grand Total Weight |  |  | 12062.747
[14 empty] | TOTAL |  | 0 | 1846.768 | 638.183 | 9577.796

## A - Project to Start
Project | MFC Batch | Colour | Date of Client MFC | Project Start Date | Structures | Order Qty (MT)
906 | Z | Blue |  |  | 4 | 8.734
907 | Z | White |  |  | 30 | 1177.492
911 | Z | Blue |  |  | 3 | 20.337
929 | Z |  |  |  | 1 | 84.539
923 | Z |  |  |  | 4 | 107.354
928 | Z |  |  |  | 2 | 6.713
960 | Z |  |  |  | 15 | 149.826
935 | Z |  |  |  | 2 | 4.311
524 | Z |  |  |  | 1 | 1.122
597A | Z |  |  |  | 1 | 5.893
659 | Z |  |  |  | 1 | 0.336
662 | Z |  |  |  | 4 | 48.811
664 | Z |  |  |  | 4 | 20.177
665 | Z |  |  |  | 1 | 2.518
671F | Z |  |  |  | 5 | 18.444
674 | Z |  |  |  | 1 | 0.024
686 | Z |  |  |  | 1 | 3.712
695 | Z |  |  |  | 14 | 62.206
714 | Z |  |  |  | 2 | 2.514
735 | Z |  |  |  | 1 | 8.76
737 | Z |  |  |  | 1 | 1.613
749 | Z |  |  |  | 1 | 0
756 | Z |  |  |  | 6 | 21.01
761 | Z |  |  |  | 1 | 0.217
775 | Z |  |  |  | 3 | 15.119
776 | Z |  |  |  | 3 | 5.211
788 | Z |  |  |  | 2 | 2.93
803 | Z |  |  |  | 1 | 12.501
811 | Z |  |  |  | 1 | 2.377
817 | Z |  |  |  | 1 | 4.927
818 | Z |  |  |  | 1 | 0.946
828 | Z |  |  |  | 1 | 77.863
833 | Z |  |  |  | 2 | 615.918
837 | Z |  |  |  | 4 | 44.146
844 | Z |  |  |  | 1 | 1.189
848 | Z | Blue |  |  | 1 | 2.983
849 | Z |  |  |  | 3 | 10.535
862 | Z | White |  |  | 1 | 3.871
864 | Z |  |  |  | 1 | 0.859
866 | Z | Yellow |  |  | 18 | 39.311
867 | Z |  |  |  | 1 | 0.735
869 | Z |  |  |  | 3 | 8.935
872 | Z |  |  |  | 3 | 41.859
875 | Z |  |  |  | 4 | 36.341
877 | Z |  |  |  | 3 | 8.7
884 | Z | Yellow |  |  | 21 | 575.799
885 | Z | Blue |  |  | 5 | 44.282
895 | Z |  |  |  | 14 | 62.812
896 | Z |  |  |  | 5 | 0.09
897 | Z | White |  |  | 2 | 3.597
905 | Z | Yellow |  |  | 7 | 230.015
910A | Z |  |  |  | 12 | 81.819
912 | Z | Blue |  |  | 6 | 64.553
918 | Z | White |  |  | 2 | 0.999
921 | Z | Yellow |  |  | 6 | 81.697
930 | Z |  |  |  | 2 | 352.787
937 | Z |  |  |  | 11 | 352.63
938 | Z | Blue |  |  | 1 | 5.109
940 | Z |  |  |  | 1 | 5.756
949 | Z | Blue |  |  | 1 | 12.238
951 | Z |  |  |  | 17 | 140.845
954 | Z |  |  |  | 5 | 12.853
955 | Z |  |  |  | 7 | 22.442
958 | Z |  |  |  | 1 | 237.3
962 | Z |  |  |  | 15 | 121.914
963 | Z |  |  |  | 7 | 1780.955
967 | Z |  |  |  | 8 | 78.439
BPTCL | Z |  |  |  | 1 | 8.595
GETCO | Z |  |  |  | 6 | 18.394
PG | Z |  |  |  | 18 | 120.589
RAILWAY | Z |  |  |  | 6 | 0.501
VR070 | Z |  |  |  | 12 | 7.922
VR073 | Z |  |  |  | 22 | 10.361
VR088 | Z |  |  |  | 11 | 6.424
VS-100 | Z |  |  |  | 1 | 0.114
VS-112 | Z |  |  |  | 1 | 440.721
VS-189 | Z |  |  |  | 2 | 32.832
VS-209 | Z |  |  |  | 11 | 400.5
TOTAL | [5 empty] | 8009.803

## Pre-B - Awaiting Colour Assign
Project | MFC Batch | Rel. Bal. | Fab | Galva | Yard | Structures
951 | Z | 363.566 | 21.923 | 0 | 0 | 13
VS-33 | Z | 88.144 | 115.468 | 0 | 1137.06 | 2
Pre-B - Awaiting Colour Assign SUMMARY
Total Release Balance |  | 451.71 | 451.71
Under Production |  |  | 137.391
Total Yard |  |  |  |  | 1137.06
Operation Weight |  |  | 1274.451
Grand Total Weight |  |  | 1726.161
TOTAL |  | 451.71 | 137.391 | 0 | 1137.06

## B - Raw Material Incomplete
Project | MFC Batch | Rel. Bal. | Fab | Galva | Yard | Structures
824 | B | 0.247 | 8.897 | 0 | 0.153 | 3
848 | Z | 2.438 | 0 | 0 | 0 | 3
866 | Z | 6.965 | 0 | 0 | 0 | 2
888 | Z | 0.135 | 0 | 0 | 61.287 | 1
890 | Z | 3.345 | 0 | 0 | 16.725 | 1
900 | B | 4.427 | 18.133 | 4.826 | 62.967 | 1
900 | C | 13.554 | 86.012 | 26.939 | 40.395 | 1
908 | Z | 117.794 | 0 | 0 | 176.448 | 9
910 | Z | 128.919 | 27.262 | 0 | 0.716 | 10
911 | B | 1.426 | 21.736 | 8.475 | 7.293 | 1
911 | Z | 3.99 | 2.809 | 0 | 0 | 1
912 | B | 49.759 | 34.687 | 0.361 | 0.896 | 7
912 | C | 180.845 | 124.794 | 18.003 | 15.354 | 12
912 | Z | 32.525 | 0 | 0 | 0 | 8
912A | Z | 32.525 | 0 | 0 | 0 | 8
913 | Z | 70.175 | 0 | 0 | 0 | 10
917 | Z | 14.423 | 7.23 | 0.116 | 0 | 18
920 | C | 0.142 | 9.099 | 4.953 | 28.075 | 11
920 | D | 0.072 | 14.743 | 0.732 | 17.636 | 5
926 | A | 3.461 | 20.255 | 6.97 | 7.525 | 2
926 | B | 7.991 | 18.529 | 5.534 | 14.526 | 2
926 | Z | 11.182 | 0 | 0 | 0 | 18
928 | B | 0.013 | 0.98 | 2.06 | 30.673 | 1
929 | A | 0.191 | 16.326 | 0.341 | 75.488 | 1
929 | B | 23.546 | 93.998 | 8.347 | 131.471 | 5
935 | A | 101.986 | 460.027 | 134.642 | 333.473 | 15
935 | B | 7.449 | 39.89 | 7.343 | 24.903 | 5
935 | C | 2.389 | 3.646 | 1.641 | 1.212 | 3
937 | A | 32.55 | 41.932 | 0 | 0 | 14
938 | A | 3.343 | 3.011 | 0 | 0.283 | 2
938 | B | 16.019 | 0.085 | 0 | 0 | 1
938 | Z | 76.408 | 8.858 | 0 | 0 | 2
940 | C | 226.9 | 208.787 | 33.419 | 93.591 | 5
942 | A | 28.238 | 112.297 | 140.97 | 637.157 | 2
944 | B | 83.436 | 270.68 | 69.809 | 287.983 | 3
948 | A | 143.706 | 136.216 | 0 | 0 | 16
951 | A | 44.913 | 14.645 | 0 | 0 | 12
956 | B | 204.143 | 145.792 | 0.842 | 1.853 | 11
960 | A | 43.533 | 98.366 | 4.202 | 0 | 8
B - Raw Material Incomplete SUMMARY
Total Release Balance |  | 1725.103 | 1725.103
Under Production |  |  | 2530.247
Total Yard |  |  |  |  | 2068.083
Operation Weight |  |  | 4598.33
Grand Total Weight |  |  | 6323.433
TOTAL |  | 1725.103 | 2049.722 | 480.525 | 2068.083

## C - RM Complete
Project | MFC Batch | Rel. Bal. | Fab | Galva | Yard | Structures
821 | Z | 0 | 10.29 | 0 | 193.914 | 4
824 | A | 0 | 2.372 | 4.462 | 70.769 | 9
824 | B | 0 | 9.05 | 0 | 0.309 | 5
824 | Z | 0 | 2.8 | 0.53 | 88.667 | 8
839 | B | 0 | 5.185 | 0.119 | 0.18 | 3
839 | Z | 0 | 0 | 0 | 12.825 | 3
848 | A | 0 | 40.795 | 7.433 | 4.843 | 6
848 | Z | 0 | 0 | 0 | 141.041 | 5
862 | Z | 0 | 39.977 | 44.633 | 185.031 | 15
870 | Z | 0 | 3.882 | 1.091 | 48.59 | 2
884 | Z | 0 | 0.101 | 1.052 | 255.523 | 7
885 | Z | 0 | 4.953 | 1.136 | 476.255 | 20
886 | A | 0 | 0 | 0 | 0.573 | 2
886 | B | 0 | 0.016 | 0.065 | 208.836 | 7
886 | C | 0 | 0.397 | 0.526 | 5.525 | 3
888 | A | 0 | 5.532 | 0.4 | 32.826 | 5
888 | Z | 0 | 1.502 | 0 | 120.561 | 7
890 | Z | 0 | 45.912 | 2.56 | 335.141 | 23
893 | A | 0 | 27.192 | 1.376 | 78.936 | 5
893 | Z | 0 | 2.578 | 0.626 | 46.15 | 14
897 | Z | 0 | 0 | 0 | 13.77 | 1
900 | B | 0 | 111.348 | 39.762 | 74.004 | 2
900 | C | 0 | 335.827 | 96.038 | 290.855 | 2
903 | A | 0 | 7.742 | 2.019 | 348.209 | 10
903 | Z | 0 | 3.114 | 1.268 | 72.498 | 6
904 | A | 0 | 0.91 | 0.803 | 381.496 | 14
905 | Z | 0 | 0 | 0 | 39.165 | 1
906 | A | 0 | 5.14 | 1.9 | 31.568 | 8
906 | B | 0 | 3.134 | 0.228 | 2.258 | 2
906 | C | 0 | 13.557 | 0 | 0 | 10
906 | Z | 0 | 0.004 | 0 | 0.085 | 2
907 | Z | 0 | 18.478 | 8.102 | 507.134 | 12
908 | A | 0 | 7.527 | 1.881 | 43.951 | 21
908 | Z | 0 | 1.304 | 0.905 | 18.179 | 4
909 | A | 0 | 0 | 2.117 | 41.55 | 7
909 | Z | 0 | 0 | 0.029 | 56.777 | 13
911 | A | 0 | 0.515 | 3.207 | 1.67 | 2
911 | B | 0 | 16.05 | 28.795 | 119.91 | 1
911 | C | 0 | 54.134 | 7.467 | 28.697 | 2
912 | A | 0 | 13.312 | 0.915 | 4.2 | 5
914 | Z | 0 | 0 | 0 | 30.25 | 8
917 | A | 0 | 0.439 | 0.062 | 0.098 | 1
917 | B | 0 | 28.018 | 18.54 | 39.532 | 7
918 | B | 0 | 6.475 | 0 | 43.07 | 4
918 | Z | 0 | 0 | 0 | 473.373 | 10
920 | C | 0 | 15.577 | 4.339 | 51.042 | 19
920 | D | 0 | 40.332 | 3.229 | 30.135 | 19
920 | Z | 0 | 0.016 | 0 | 217.264 | 18
921 | Z | 0 | 0.463 | 0.707 | 1085.853 | 14
922 | B | 0 | 48.239 | 11.213 | 291.456 | 9
922 | C | 0 | 59.101 | 15.268 | 39.81 | 7
923 | B | 0 | 19.205 | 10.314 | 150.935 | 17
924 | Z | 0 | 0 | 0 | 13.507 | 7
926 | B | 0 | 54.199 | 29.581 | 119.922 | 11
927 | B | 0 | 0 | 0.828 | 94.852 | 2
928 | A | 0 | 0.81 | 1.678 | 2.732 | 2
928 | B | 0 | 30.274 | 26.953 | 534.188 | 18
929 | A | 0 | 4.373 | 1.472 | 16.755 | 1
931 | A | 0 | 0.016 | 1.738 | 3.749 | 2
931 | B | 0 | 0.341 | 0.238 | 424.305 | 6
931 | Z | 0 | 1.289 | 0 | 0.763 | 2
932 | A | 0 | 19.777 | 1.532 | 1.67 | 12
933 | B | 0 | 14.184 | 14.355 | 851.005 | 4
933 | C | 0 | 4.924 | 0.216 | 6.159 | 2
933 | Z | 0 | 0 | 0 | 19.225 | 3
934 | B | 0 | 117.889 | 37.468 | 96.845 | 17
935 | A | 0 | 27.506 | 26.686 | 51.913 | 4
935 | B | 0 | 7.722 | 2.018 | 3.518 | 3
935 | C | 0 | 10.966 | 6.068 | 8.06 | 2
936 | A | 0 | 41.606 | 2.022 | 26.905 | 10
938 | Z | 0 | 0.438 | 0 | 0 | 1
939 | A | 0 | 114.696 | 9.735 | 144.054 | 9
941 | B | 0 | 97.084 | 76.07 | 187.541 | 10
941 | Z | 0 | 0 | 0 | 3.943 | 1
944 | A | 0 | 0 | 0 | 31.093 | 2
944 | B | 0 | 12.827 | 10.931 | 53.364 | 3
945 | A | 0 | 0 | 0.207 | 2.194 | 4
945 | B | 0 | 25.375 | 0 | 0 | 5
945 | C | 0 | 11.054 | 0 | 0 | 4
946 | A | 0 | 1.399 | 0.444 | 0 | 4
946 | B | 0 | 4.434 | 0.502 | 0.8 | 4
946 | C | 0 | 95.698 | 0 | 0 | 11
947 | A | 0 | 25.33 | 0.865 | 15.173 | 2
948 | A | 0 | 0.757 | 0 | 0 | 2
949 | Z | 0 | 74.51 | 0 | 0 | 15
952 | A | 0 | 11.461 | 7.197 | 0 | 2
957 | A | 0 | 2.987 | 0 | 0 | 1
958 | A | 0 | 0.553 | 0.736 | 17.085 | 3
962 | A | 0 | 10.226 | 0 | 0 | 8
963 | A | 0 | 9.568 | 53.526 | 11.187 | 2
C - RM Complete SUMMARY
Total Release Balance |  | 0 | 0
Under Production |  |  | 2484.951
Total Yard |  |  |  |  | 9577.796
Operation Weight |  |  | 12062.747
Grand Total Weight |  |  | 12062.747
TOTAL |  | 0 | 1846.768 | 638.183 | 9577.796

## D - Dispatch Clearance
Project | MFC Batch | Rel. Bal. | Fab | Galva | Yard | Structures
821 | Z | 0 | 10.29 | 0 | 193.914 | 4
824 | A | 0 | 2.372 | 4.462 | 70.769 | 9
824 | Z | 0 | 1.907 | 0.139 | 88.469 | 3
848 | Z | 0 | 0 | 0 | 141.041 | 5
870 | Z | 0 | 0 | 0 | 33.488 | 1
884 | Z | 0 | 0.101 | 1.052 | 255.523 | 7
885 | Z | 0 | 3.061 | 0.514 | 474.993 | 17
886 | B | 0 | 0.016 | 0.065 | 208.836 | 7
888 | A | 0 | 5.532 | 0.4 | 32.826 | 5
888 | Z | 0.135 | 0 | 0 | 181.848 | 7
890 | Z | 3.345 | 0 | 0 | 331.46 | 10
893 | A | 0 | 27.192 | 1.376 | 78.936 | 5
893 | Z | 0 | 0 | 0 | 38.014 | 10
897 | Z | 0 | 0 | 0 | 13.77 | 1
903 | A | 0 | 7.742 | 2.019 | 348.209 | 10
903 | Z | 0 | 3.114 | 1.268 | 72.498 | 6
904 | A | 0 | 0.91 | 0.803 | 381.496 | 14
905 | Z | 0 | 0 | 0 | 39.165 | 1
906 | A | 0 | 5.14 | 1.9 | 31.568 | 8
907 | Z | 0 | 18.478 | 8.102 | 507.134 | 12
908 | A | 0 | 0.012 | 0.015 | 6.283 | 2
908 | Z | 112.249 | 0.374 | 0.153 | 193.419 | 8
909 | A | 0 | 0 | 2.117 | 41.55 | 7
909 | Z | 0 | 0 | 0.029 | 56.777 | 13
911 | B | 1.426 | 21.736 | 8.475 | 7.293 | 1
914 | Z | 0 | 0 | 0 | 30.25 | 8
918 | B | 0 | 0 | 0 | 43.07 | 3
918 | Z | 0 | 0 | 0 | 473.373 | 10
920 | C | 0.142 | 24.676 | 9.292 | 79.117 | 30
920 | D | 0 | 0.291 | 0.626 | 1.324 | 1
920 | Z | 0 | 0.016 | 0 | 217.264 | 18
921 | Z | 0 | 0.463 | 0.707 | 1085.853 | 14
922 | B | 0 | 48.239 | 11.213 | 291.456 | 9
924 | Z | 0 | 0 | 0 | 13.507 | 7
927 | B | 0 | 0 | 0.828 | 94.852 | 2
928 | A | 0 | 0.408 | 0.068 | 2.649 | 1
931 | A | 0 | 0.016 | 1.738 | 3.749 | 2
931 | B | 0 | 0.341 | 0.238 | 424.305 | 6
931 | Z | 0 | 0 | 0 | 0.763 | 1
933 | B | 0 | 14.184 | 14.355 | 851.005 | 4
933 | Z | 0 | 0 | 0 | 19.225 | 3
935 | A | 101.986 | 487.533 | 161.328 | 385.386 | 19
935 | B | 7.449 | 47.612 | 9.361 | 28.421 | 8
935 | C | 2.389 | 14.612 | 7.709 | 9.272 | 5
939 | A | 0 | 114.696 | 9.735 | 144.054 | 9
941 | Z | 0 | 0 | 0 | 3.943 | 1
D - Dispatch Clearance SUMMARY
Total Release Balance |  | 229.121 | 229.121
Under Production |  |  | 1121.151
Total Yard |  |  |  |  | 8032.117
Operation Weight |  |  | 9153.268
Grand Total Weight |  |  | 9382.389
TOTAL |  | 229.121 | 861.064 | 260.087 | 8032.117

## E - Ready Not Dispatched
Side | Project | MFC Batch | Release Balance (MT) | Fab+Galva (MT) | Yard (MT) | Structures