## OrderReview
Vijay Transmission Pvt. Ltd.
Order Review
As On Date :08/07/2026
Project Code : [All]
| Tower Type | Tower Sub Type | Weight / Set (MT) | Order Qty. |  | WO Order Qty. |  | BOM Label | Progress |  |  |  |  | Balance
|  |  |  | Sets | Weight | Sets | Weight (MT) |  | Release (MT) | Fabrication (MT) | Galvanising (MT) | Inspection (MT) | Despatch (MT) | Work Order(MT) | Release (MT) | Fabrication (MT) | Galvanising (MT) | Inspection (MT) | Despatch (MT)
| Project Code : 524 |  | Client : LARSEN & TOUBRO LIMITED - VT524 | [11 empty] | Order Dt. : 28/11/2019
| SS | COLUMN | 1.122 | 1 | 1.122 |  |  | Mass
|  | Sub Total | 1.122 | 1 | 1.122
| Project Code : 590 |  | Client : KANTI PRASAD MITTAL(NIT-11) VT590 | [11 empty] | Order Dt. : 24/06/2022
| HISOW | EQUIPMENT | 0.745 | 3 | 2.236 |  |  | Proto
|  | Sub Total | 0.745 | 3 | 2.236
| Project Code : 597A |  | Client : VSPL ENERGY PRIVATE LIMITED (SAGALI-NAHARLAGUN) VT597A | [11 empty] | Order Dt. : 24/03/2022
| DD- | NORMAL TOWER | 0.421 | 14 | 5.893 |  |  | Mass
|  | Sub Total | 0.421 | 14 | 5.893
| Project Code : 659 |  | Client : MAXWELL CONSTRUCTIONS VT659 | [11 empty] | Order Dt. : 15/05/2022
| SS | COLUMN | 0.336 | 1 | 0.336 |  |  | Mass
|  | Sub Total | 0.336 | 1 | 0.336
| Project Code : 662 |  | Client : LARSEN & TOUBRO LIMITED - VT662 | [11 empty] | Order Dt. : 02/09/2021
| 3G02 | COLUMN | 2.300 | 4 | 9.200 |  |  | Mass
| 3G02B | BEAM | 1.107 | 3 | 3.321 |  |  | Mass
| 3G04 | COLUMN | 1.579 | 16 | 25.258 |  |  | Mass
| 3G04B | BEAM | 1.103 | 10 | 11.032 |  |  | Mass
|  | Sub Total | 6.089 | 33 | 48.811
| Project Code : 664 |  | Client : ODISHA POWER TRANSMISSION CORPORATION LTD - VT664 | [11 empty] | Order Dt. : 31/08/2021
| 2OC1 | S.S.T | 0.962 | 1 | 0.962 |  |  | Mass
| 2OC1A | S.S.T | 1.826 | 1 | 1.826 |  |  | Mass
| 2OC24M | +24 MTR EXTN | 15.912 | 1 | 15.912 |  |  | Mass
| 2OC3M | +3 MTR EXTN | 1.477 | 1 | 1.477 |  |  | Mass
|  | Sub Total | 20.177 | 4 | 20.177
| Project Code : 665 |  | Client : SMS INDIA PVT LTD - VT665 | [11 empty] | Order Dt. : 31/05/2022
| LCLM | NORMAL TOWER | 2.518 | 1 | 2.518 |  |  | Pre
|  | Sub Total | 2.518 | 1 | 2.518
| Project Code : 671F |  | Client : PINGGAO GROUP ENGINEERING CO. LTD - VT671F | [11 empty] | Order Dt. : 21/03/2022
| 20X625 | FOUNDATION BOLTS | 0.002 | 84 | 0.160 |  |  | Mass
| 24X825 | FOUNDATION BOLTS | 0.004 | 1085 | 3.829 |  |  | Mass
| 28X925 | FOUNDATION BOLTS | 0.005 | 242 | 1.169 |  |  | Mass
| 40X1225 | FOUNDATION BOLTS | 0.013 | 78 | 1.003 |  |  | Mass
| 80X2070 | FOUNDATION BOLTS | 0.085 | 145 | 12.283 |  |  | Mass
|  | Sub Total | 0.109 | 1634 | 18.444
| Project Code : 674 |  | Client : BGR ENERGY SYSTEMS LIMITED - VT674 | [11 empty] | Order Dt. : 15/10/2021
| B | S.P.S | 0.004 | 6 | 0.024 |  |  | Mass
|  | Sub Total | 0.004 | 6 | 0.024
| Project Code : 686 |  | Client : PINGGAO GROUP ENGINEERING CO. LTD - VT686 | [11 empty] | Order Dt. : 02/06/2022
| 1CVT | EQUIPMENT | 0.155 | 24 | 3.712 |  |  | Proto
|  | Sub Total | 0.155 | 24 | 3.712
| Project Code : 695 |  | Client : VSPL ENERGY PRIVATE LIMITED 695 | [11 empty] | Order Dt. : 25/02/2022
| 2QC1 | NORMAL TOWER | 0.976 | 3 | 2.928 |  |  | Pre
| 2QC15 | +1.5 MTR EXTN | 3.189 | 3 | 9.567 |  |  | Pre
| 2QC3A | +3 MTR EXTN | 0.530 | 3 | 1.589 |  |  | Pre
| 2QC3M | +3 MTR EXTN | 0.997 | 7 | 6.982 |  |  | Pre
| 2QC45 | +4.5 MTR EXTN | 2.605 | 1 | 2.605 |  |  | Pre
| 2QCL | NORMAL TOWER | 0.609 | 6 | 3.656 |  |  | Pre
| 2QD1 | NORMAL TOWER | 1.259 | 2 | 2.518 |  |  | Pre
| 2QD15 | +1.5 MTR EXTN | 3.980 | 1 | 3.980 |  |  | Pre
| 2QD3A | +4.5 MTR EXTN | 3.256 | 2 | 6.512 |  |  | Pre
| 2QD3M | +3 MTR EXTN | 1.244 | 4 | 4.975 |  |  | Pre
| 2QD6 | +6 MTR EXTN | 1.004 | 3 | 3.013 |  |  | Pre
| 2QD75 | +7 MTR EXTN | 5.038 | 2 | 10.076 |  |  | Pre
| 2QD9 | +9 MTR EXTN | 1.473 | 1 | 1.473 |  |  | Pre
| 2QDL | NORMAL TOWER | 0.777 | 3 | 2.332 |  |  | Pre
|  | Sub Total | 26.937 | 41 | 62.206
| Project Code : 714 |  | Client : VOLT-AGE ENERGY PVT LTD. 714 | [11 empty] | Order Dt. : 20/07/2022
| 3PTJ | EQUIPMENT | 0.285 | 1 | 0.285 |  |  | Proto
| 3PTW | EQUIPMENT | 0.279 | 8 | 2.229 |  |  | Proto
|  | Sub Total | 0.564 | 9 | 2.514
| Project Code : 735. |  | Client : BHARAT SANCHAR NIGAM LIMITED - VT735. | [11 empty] | Order Dt. : 04/04/2023
| 40M | NORMAL TOWER | 8.760 | 1 | 8.760 |  |  | Pre
|  | Sub Total | 8.760 | 1 | 8.760
| Project Code : 737 |  | Client : SIDDHARTHA ENGINEERING LIMITED - VT737 | [11 empty] | Order Dt. : 27/12/2022
| 1DA2 | STUB | 0.201 | 8 | 1.604 | 1 | 0.200 | Proto | 0.201 | 0.201 | 0.201 | 0.201 | 0.201 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 7 | 1.404 | Mass | 1.404 | 1.404 | 1.404 | 1.404 | 1.404 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DA3 | NORMAL TOWER | 2.833 | 9 | 25.494 | 1 | 2.832 | Proto | 2.833 | 2.833 | 2.833 | 2.833 | 0.445 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 2.388
| 1DA6M | +6 MTR EXTN | 0.809 | 2 | 1.619 | 1 | 0.811 | Proto | 0.809 | 0.809 | 0.809 | 0.809 | 0.001 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.808
| 1DC2 | STUB | 0.503 | 3 | 1.508 | 1 | 0.503 | Proto | 0.503 | 0.503 | 0.503 | 0.503 | 0.503 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 2 | 1.005 | Mass | 1.006 | 1.006 | 1.006 | 1.006 | 1.006 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DC3 | NORMAL TOWER | 4.865 | 4 | 19.460 | 1 | 4.864 | Proto | 4.865 | 4.865 | 4.865 | 4.865 | 1.971 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 2.894
| 1DD2 | STUB | 0.605 | 4 | 2.422 | 1 | 0.605 | Proto | 0.605 | 0.605 | 0.605 | 0.605 | 0.605 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 3 | 1.816 | Mass | 1.816 | 1.816 | 1.816 | 1.816 | 1.816 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DD3 | NORMAL TOWER | 6.129 | 5 | 30.647 | 1 | 6.111 | Proto | 6.112 | 6.112 | 6.112 | 6.113 | 2.755 | 0.000 | 0.001 | 0.000 | 0.000 | -0.001 | 3.359
| 1DD6M | +6 MTR EXTN | 1.892 | 2 | 3.784 | 1 | 1.891 | Proto | 1.892 | 1.892 | 1.892 | 1.892 | 1.205 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.687
| 2MA2 | STUB | 0.518 | 4 | 2.070 | 1 | 0.518 | Proto | 0.518 | 0.518 | 0.518 | 0.518 | 0.518 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 3 | 1.552 | Mass | 1.553 | 1.553 | 1.553 | 1.553 | 1.553 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2MA3 | NORMAL TOWER | 9.058 | 4 | 36.233 | 1 | 9.033 | Proto | 9.058 | 9.058 | 9.058 | 9.058 | 9.058 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 3 | 27.181 | Mass | 27.175 | 27.175 | 27.175 | 27.175 | 27.175 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2MA6M | +6 MTR EXTN | 1.712 | 4 | 6.850 | 4 | 6.855 | Proto | 6.850 | 6.850 | 6.850 | 6.850 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 6.850
| 2MB2 | STUB | 0.962 | 3 | 2.886 | 1 | 0.962 | Proto | 0.962 | 0.962 | 0.962 | 0.962 | 0.962 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 2 | 1.925 | Mass | 1.924 | 1.924 | 1.924 | 1.924 | 1.924 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2MB3 | NORMAL TOWER | 14.301 | 3 | 42.903 | 1 | 14.295 | Proto | 14.301 | 14.098 | 14.199 | 14.301 | 14.301 | 0.000 | 0.000 | 0.203 | -0.101 | -0.101 | 0.000
[6 empty] | 2 | 28.621 | Mass | 28.602 | 28.602 | 28.602 | 28.602 | 28.602 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2MB6M | +6 MTR EXTN | 2.809 | 3 | 8.428 | 3 | 8.428 | Proto | 8.428 | 8.428 | 8.428 | 8.428 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 8.428
| 2MD2 | STUB | 2.504 | 5 | 12.521 | 5 | 12.520 | Mass | 12.521 | 12.521 | 12.521 | 12.521 | 12.521 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2MD3 | NORMAL TOWER | 24.924 | 7 | 174.471 | 1 | 24.920 | Proto | 24.924 | 24.924 | 24.924 | 24.924 | 18.784 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 6.140
[6 empty] | 5 | 124.638 | Mass | 124.622 | 124.622 | 124.622 | 124.622 | 117.965 | 24.920 | 0.000 | 0.000 | 0.000 | 0.000 | 6.657
| 2MD3M | +3 MTR EXTN | 2.771 | 1 | 2.771 | 1 | 2.772 | Proto | 2.771 | 2.771 | 2.771 | 2.771 | 2.771 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2MD6M | +6 MTR EXTN | 5.646 | 4 | 22.584 | 1 | 5.649 | Proto | 5.646 | 5.585 | 5.585 | 5.646 | 5.646 | 0.000 | 0.000 | 0.061 | 0.000 | -0.061 | 0.000
[6 empty] | 3 | 16.943 | Mass | 16.938 | 16.938 | 16.938 | 16.938 | 16.938 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| AA2 | STUB | 0.147 | 109 | 16.027 | 1 | 0.147 | Proto | 0.147 | 0.147 | 0.147 | 0.147 | 0.147 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 108 | 15.880 | Mass | 15.880 | 15.880 | 15.880 | 15.880 | 15.880 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| AA3 | NORMAL TOWER | 2.857 | 109 | 311.367 | 1 | 2.862 | Proto | 2.857 | 2.857 | 2.857 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| AA3M | +3 MTR EXTN | 0.502 | 62 | 31.145 | 1 | 0.504 | Proto | 0.502 | 0.502 | 0.502 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| AA6M | +6 MTR EXTN | 1.056 | 9 | 9.505 | 1 | 1.058 | Proto | 1.056 | 1.056 | 1.056 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| AB2 | STUB | 0.210 | 32 | 6.735 | 1 | 0.211 | Proto | 0.210 | 0.210 | 0.210 | 0.210 | 0.210 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 31 | 6.524 | Mass | 6.525 | 6.525 | 6.525 | 6.525 | 6.525 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| AB3 | NORMAL TOWER | 3.644 | 34 | 123.881 | 1 | 3.638 | Proto | 3.644 | 3.644 | 3.644 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| AB3M | +3 MTR EXTN | 0.692 | 8 | 5.537 | 1 | 0.692 | Proto | 0.692 | 0.692 | 0.692 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| AB6M | +6 MTR EXTN | 1.444 | 1 | 1.444 | 1 | 1.442 | Proto | 1.444 | 1.444 | 1.444 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| AC2 | STUB | 0.237 | 7 | 1.658 | 1 | 0.236 | Proto | 0.237 | 0.237 | 0.237 | 0.237 | 0.237 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 6 | 1.421 | Mass | 1.421 | 1.421 | 1.421 | 1.421 | 1.421 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| AC3 | NORMAL TOWER | 3.907 | 7 | 27.349 | 1 | 3.911 | Proto | 3.907 | 3.907 | 3.907 |  |  | 0.000 | 0.004 | 0.000 | 0.000
| AC3M | +3 MTR EXTN | 0.761 | 4 | 3.043 | 1 | 0.760 | Proto | 0.761 | 0.761 | 0.761 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| AD2 | STUB | 0.302 | 7 | 2.111 | 1 | 0.301 | Proto | 0.302 | 0.302 | 0.302 | 0.302 | 0.302 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 6 | 1.809 | Mass | 1.809 | 1.809 | 1.809 | 1.809 | 1.809 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| AD3 | NORMAL TOWER | 4.621 | 7 | 32.345 | 1 | 4.628 | Proto | 4.621 | 4.621 | 4.621 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| AD3M | +3 MTR EXTN | 0.878 | 3 | 2.634 | 1 | 0.877 | Proto | 0.878 | 0.878 | 0.878 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| AD6M | +6 MTR EXTN | 1.845 | 2 | 3.689 | 1 | 1.842 | Proto | 1.845 | 1.845 | 1.845 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| DT2 | STUB | 0.309 | 2 | 0.618 | 1 | 0.309 | Proto | 0.309 | 0.309 | 0.309 | 0.309 | 0.309 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 1 | 0.309 | Mass | 0.309 | 0.309 | 0.309 | 0.309 | 0.309 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| DT3 | NORMAL TOWER | 3.849 | 2 | 7.698 | 1 | 3.630 | Proto | 3.623 | 3.623 | 3.623 | 3.623 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 3.623
| IS | COLUMN | 0.219 | 1 | 0.219 | 1 | 0.220 | Mass | 0.219 | 0.219 | 0.219 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.328 | 1 | 0.329 | Mass | 0.328 | 0.328 | 0.328 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| MD2 | STUB | 0.503 | 2 | 1.006 | 1 | 0.503 | Proto | 0.503 | 0.503 | 0.503 | 0.503 | 0.503 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 1 | 0.503 | Mass | 0.503 | 0.503 | 0.503 | 0.503 | 0.503 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| MD3 | NORMAL TOWER | 12.307 | 3 | 36.922 | 1 | 12.305 | Proto | 12.307 | 12.307 | 12.307 | 12.307 | 5.356 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 6.951
| MD3M | +3 MTR EXTN | 1.584 | 2 | 3.169 | 1 | 1.587 | Proto | 1.584 | 1.584 | 1.584 | 1.584 | 0.358 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.226
| OFS-14.05.2023 | NORMAL TOWER | 1.613 | 1 | 1.613 | 1 | 1.610 | Mass | 1.613 | 1.613 | 1.613 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| SC | NORMAL TOWER | 1.613 | 1 | 1.613 |  |  | Mass
|  |  |  | 1 | 0.005 | 1 | 0.005 | Mass | 0.005 | 0.005 | 0.005 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 186.902 | 492 | 1029.916 | 234 | 378.907 |  | 378.879 | 378.616 | 378.717 | 354.509 | 304.499 | 24.920 | 0.006 | 0.264 | -0.101 | -0.164 | 50.010
| Project Code : 749 |  | Client : ENERGY SOLUTIONS PVT LTD - VT749 | [11 empty] | Order Dt. : 23/02/2023
| H/W | COLUMN | 0.000 | 1 | 0.000 |  |  | Mass
|  | Sub Total | 0.000 | 1 | 0.000
| Project Code : 756 |  | Client : AK DAS ASSOCIATES LTD.- VT756 | [11 empty] | Order Dt. : 21/03/2023
| 2BPI | EQUIPMENT | 0.237 | 18 | 4.272 |  |  | Pre
| 2CTS | EQUIPMENT | 0.335 | 6 | 2.012 |  |  | Pre
| 2CVTS | EQUIPMENT | 0.227 | 6 | 1.365 |  |  | Pre
| 2ISO | EQUIPMENT | 1.477 | 2 | 2.953 |  |  | Pre
| 2ISOW | EQUIPMENT | 1.389 | 6 | 8.331 |  |  | Pre
| 2LA | EQUIPMENT | 0.346 | 6 | 2.077 |  |  | Pre
|  | Sub Total | 4.011 | 44 | 21.010
| Project Code : 758 |  | Client : SMS INDIA PVT. LTD.- VT758 | [11 empty] | Order Dt. : 14/04/2023
| 2CVT | EQUIPMENT | 0.191 | 4 | 0.766 | 4 | 0.769 | Mass | 0.766 | 0.766 | 0.766 | 0.766 | 0.766 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2HBPI | EQUIPMENT | 0.248 | 30 | 7.447 | 30 | 7.436 | Mass | 7.447 | 7.447 | 7.447 | 7.436 | 7.447 | 0.012 | -0.011 | 0.000 | 0.000 | 0.011 | -0.011
| 6HBPI | EQUIPMENT | 0.239 | 9 | 2.151 | 9 | 2.120 | Proto | 2.151 | 2.151 | 2.151 | 2.151 | 2.151 | 0.000 | -0.031 | 0.000 | 0.000 | 0.000 | 0.000
| IS | COLUMN | 0.382 | 1 | 0.382 | 1 | 0.382 | Mass | 0.382 | 0.382 | 0.382 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| LM | COLUMN | 3.300 | 3 | 9.901 | 3 | 9.890 | Mass | 9.901 | 9.901 | 9.901 | 9.902 | 9.901 | 0.004 | -0.007 | 0.000 | 0.000 | 0.000 | 0.000
| SC | NORMAL TOWER | 0.279 | 1 | 0.279 | 1 | 0.280 | Mass | 0.279 | 0.279 | 0.279 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 4.640 | 48 | 20.926 | 48 | 20.877 |  | 20.926 | 20.926 | 20.926 | 20.255 | 20.265 | 0.016 | -0.049 | 0.000 | 0.000 | 0.010 | -0.010
| Project Code : 761 |  | Client : ENERGY SOLUTIONS PVT LTD - VT761 | [11 empty] | Order Dt. : 17/04/2023
| SS | COLUMN | 0.217 | 1 | 0.217 |  |  | Mass
|  | Sub Total | 0.217 | 1 | 0.217
| Project Code : 775 |  | Client : FLOWMORE LIMITED - VT775 | [11 empty] | Order Dt. : 25/07/2023
| IS | COLUMN | 0.476 | 1 | 0.476 | 1 | 0.477 | Mass | 0.476 | 0.476 | 0.476 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 4.030 | 1 | 4.032 | Mass | 4.030 | 4.030 | 4.030 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 64.073 | 1 | 64.076 | Mass | 64.073 | 64.073 | 64.073 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 6.677 | 1 | 6.677 | Mass | 6.677 | 6.677 | 6.677 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 3.083 | 1 | 3.082 | Mass | 3.083 | 3.083 | 3.083 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 2.931 | 1 | 2.930 | Mass | 2.931 | 2.931 | 2.931 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 3.391 | 1 | 3.392 | Mass | 3.391 | 3.391 | 3.391 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 5.500 | 1 | 5.497 | Mass | 5.500 | 5.500 | 5.500 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| OA3M | +3 MTR EXTN | 0.759 | 2 | 1.518 | 1 | 0.758 | Mass | 0.759 | 0.759 | 0.759 | 0.759 | 0.559 | 0.758 | 0.000 | 0.000 | 0.000 | 0.000 | 0.200
| OA6M | +6 MTR EXTN | 1.506 | 10 | 15.062 | 5 | 7.531 | Mass | 7.531 | 7.531 | 7.531 | 7.531 | 2.264 | 7.531 | 0.000 | 0.000 | 0.000 | 0.000 | 5.267
| OB2 | STUB | 0.438 | 7 | 3.065 | 5 | 2.190 | Mass | 2.189 | 2.189 | 2.189 | 2.189 | 1.314 | 0.875 | 0.000 | 0.000 | 0.000 | 0.000 | 0.876
| OB3 | NORMAL TOWER | 6.487 | 4 | 25.949 | 2 | 12.977 | Mass | 12.974 | 12.974 | 12.974 | 12.976 | 3.530 | 12.973 | 0.002 | 0.000 | 0.000 | -0.002 | 9.446
| OB3M | +3 MTR EXTN | 1.354 | 17 | 23.024 | 10 | 13.541 | Mass | 13.543 | 13.543 | 13.543 | 13.543 | 3.014 | 9.483 | 0.000 | 0.000 | 0.000 | 0.000 | 10.529
| OB6M | +6 MTR EXTN | 2.337 | 11 | 25.706 | 6 | 14.023 | Mass | 14.022 | 14.022 | 14.022 | 14.022 | 9.270 | 11.686 | 0.000 | 0.000 | 0.000 | 0.000 | 4.752
| OC1 | S.S.T | 1.006 | 1 | 1.006 |  |  | Mass
| OC15M | +15 MTR EXTN | 8.658 | 32 | 277.047 | 14 | 121.210 | Mass | 121.208 | 121.208 | 121.208 | 121.208 | 99.995 | 155.844 | 0.000 | 0.000 | 0.000 | 0.000 | 21.213
| OC1A | S.S.T | 2.083 | 5 | 10.416 | 3 | 6.250 | Mass | 6.250 | 6.250 | 6.250 | 6.250 | 2.083 | 4.167 | 0.000 | 0.000 | 0.000 | 0.000 | 4.166
| OC-1A | S.S.T | 1.423 | 1 | 1.423 |  |  | Pre
| OC2 | STUB | 0.776 | 44 | 34.164 | 28 | 21.741 | Mass | 21.741 | 21.741 | 21.741 | 21.741 | 10.761 | 12.423 | 0.000 | 0.000 | 0.000 | 0.000 | 10.980
| OC24M | +24 MTR EXTN | 15.912 | 3 | 47.735 | 2 | 31.821 | Proto | 31.823 | 31.823 | 31.823 | 31.823 | 23.683 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 8.140
| OC2A | STUB | 1.067 | 36 | 38.422 | 16 | 17.076 | Mass | 17.076 | 17.076 | 17.076 | 17.076 | 14.942 | 21.346 | 0.000 | 0.000 | 0.000 | 0.000 | 2.135
| OC3 | NORMAL TOWER | 9.204 | 70 | 644.271 | 41 | 377.355 | Mass | 377.358 | 377.251 | 377.251 | 377.358 | 188.613 | 266.917 | 0.000 | 0.108 | 0.000 | -0.108 | 188.745
| OC3M | +3 MTR EXTN | 1.477 | 17 | 25.115 | 10 | 14.773 | Mass | 14.773 | 14.773 | 14.773 | 14.773 | 6.740 | 10.344 | 0.000 | 0.000 | 0.000 | 0.000 | 8.033
| OC6M | +6 MTR EXTN | 2.736 | 40 | 109.449 | 25 | 68.407 | Mass | 68.406 | 68.406 | 68.406 | 68.406 | 46.490 | 41.045 | 0.000 | 0.000 | 0.000 | 0.000 | 21.915
| SC | NORMAL TOWER | 0.003 | 1 | 0.003 | 1 | 0.003 | Mass | 0.003 | 0.003 | 0.003 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.034 | 1 | 0.034 | Mass | 0.034 | 0.034 | 0.034 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.004 | 1 | 0.004 | Mass | 0.004 | 0.004 | 0.004 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| UR2 | STUB | 0.692 | 4 | 2.769 | 2 | 1.384 | Mass | 1.384 | 1.384 | 1.384 | 1.384 | 1.384 | 1.384 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| UR3 | NORMAL TOWER | 12.690 | 1 | 12.690 |  |  | Mass
| UR6M | +6 MTR EXTN | 4.195 | 3 | 12.584 | 1 | 4.196 | Mass | 4.195 | 4.195 | 4.195 | 4.195 | 3.247 | 8.388 | 0.000 | 0.000 | 0.000 | 0.000 | 0.947
|  | Sub Total | 165.003 | 319 | 1401.617 | 182 | 805.437 |  | 805.436 | 805.328 | 805.328 | 715.235 | 417.890 | 565.164 | 0.002 | 0.108 | 0.000 | -0.110 | 297.345
| Project Code : 776 |  | Client : ODISHA POWER TRANSMISSION CORPORATION LTD -VT776 | [11 empty] | Order Dt. : 28/07/2023
| 2OA1 | S.S.T | 0.644 | 1 | 0.644 |  |  | Pre
| 2OA2 | STUB | 0.232 | 1 | 0.232 |  |  | Pre
| 2OA3 | NORMAL TOWER | 4.335 | 1 | 4.335 |  |  | Pre
|  | Sub Total | 5.211 | 3 | 5.211
| Project Code : 784 |  | Client : SARJAN REALITIES PRIVATE LIMITED - VT784 | [11 empty] | Order Dt. : 06/09/2023
| 3NCT | EQUIPMENT | 0.087 | 7 | 0.612 | 7 | 0.611 | Proto | 0.612 | 0.612 | 0.612 | 0.612 | 0.612 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4G1 | BEAM | 3.968 | 2 | 7.937 | 2 | 7.936 | Mass | 7.937 | 7.937 | 7.937 | 7.937 | 7.937 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4GA | BEAM | 4.434 | 2 | 8.868 | 2 | 8.867 | Mass | 8.868 | 8.868 | 8.868 | 8.868 | 8.868 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4TG | COLUMN | 4.798 | 4 | 19.192 | 4 | 19.195 | Mass | 19.192 | 19.192 | 19.192 | 19.192 | 19.192 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4TH | COLUMN | 7.998 | 3 | 23.993 | 3 | 23.994 | Mass | 23.993 | 23.993 | 23.993 | 23.993 | 23.993 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 21.286 | 18 | 60.602 | 18 | 60.603 |  | 60.602 | 60.602 | 60.602 | 60.602 | 60.602 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : 788 |  | Client : SIKHA ELECTRIC STORES VT788 | [11 empty] | Order Dt. : 24/09/2023
| 1DD1 | S.S.T | 0.994 | 1 | 0.994 |  |  | Pre
| 1DD1A | S.S.T | 1.936 | 1 | 1.936 |  |  | Pre
|  | Sub Total | 2.930 | 2 | 2.930
| Project Code : 790. |  | Client : ASSOCIATED POWER STRUCTURES PVT.LTD. - VT790 | [11 empty] | Order Dt. : 06/10/2023
| AP-861R-2DD | STUB | 0.619 | 5 | 3.097 | 5 | 3.097 | Mass | 3.097 | 3.097 | 3.097 | 3.097 | 3.097 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| AP-861R-DA | S.S.T | 0.522 | 1 | 0.522 | 1 | 0.522 | Mass | 0.522 | 0.522 | 0.522 | 0.522 | 0.522 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 13 | 45.233 | 13 | 45.235 | Mass | 45.233 | 45.233 | 45.233 | 45.233 | 45.233 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 4 | 2.818 | 4 | 2.819 | Mass | 2.818 | 2.818 | 2.818 | 2.818 | 2.818 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 4 | 4.194 | 4 | 4.192 | Mass | 4.194 | 4.194 | 4.194 | 4.194 | 4.194 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| AP-861R-DA-BC | STUB | 0.182 | 13 | 2.366 | 13 | 2.366 | Mass | 2.366 | 2.366 | 2.366 | 2.366 | 2.366 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| AP-861R-DB | NORMAL TOWER | 4.835 | 2 | 9.671 | 2 | 9.673 | Mass | 9.671 | 9.671 | 9.671 | 9.671 | 9.671 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 3 | 2.569 | 3 | 2.570 | Mass | 2.569 | 2.569 | 2.569 | 2.569 | 2.569 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 3 | 4.364 | 3 | 4.365 | Mass | 4.364 | 4.364 | 4.364 | 4.364 | 4.364 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| AP-861R-DB-BC | STUB | 0.283 | 2 | 0.567 | 2 | 0.567 | Mass | 0.567 | 0.567 | 0.567 | 0.567 | 0.567 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| AP-861R-DC | STUB | 0.341 | 6 | 2.045 | 6 | 2.045 | Mass | 2.045 | 2.045 | 2.045 | 2.045 | 2.045 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 3 | 8.060 | 3 | 8.060 | Mass | 8.060 | 8.060 | 8.060 | 8.060 | 8.060 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 3 | 13.033 | 3 | 13.028 | Mass | 13.033 | 13.033 | 13.033 | 13.033 | 13.033 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| AP-861R-DD | S.S.T | 1.284 | 1 | 1.284 | 1 | 1.284 | Mass | 1.284 | 1.284 | 1.284 | 1.284 | 1.284 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 27 | 206.500 | 27 | 206.502 | Mass | 206.500 | 206.500 | 206.500 | 206.500 | 206.500 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 10 | 4.812 | 10 | 4.812 | Mass | 4.812 | 4.812 | 4.812 | 4.812 | 4.812 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 6 | 21.766 | 6 | 21.765 | Mass | 21.766 | 21.766 | 21.766 | 21.766 | 21.766 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 4 | 22.070 | 4 | 22.071 | Mass | 22.070 | 22.070 | 22.070 | 22.070 | 22.070 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 5 | 3.156 | 5 | 3.156 | Mass | 3.156 | 3.156 | 3.156 | 3.156 | 3.156 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 2 | 1.262 | 2 | 1.263 | Mass | 1.262 | 1.262 | 1.262 | 1.262 | 1.262 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 1.671 | 1 | 1.674 | Mass | 1.671 | 1.671 | 1.671 | 1.671 | 1.671 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 2.172 | 1 | 2.171 | Mass | 2.172 | 2.172 | 2.172 | 2.172 | 2.172 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.631 | 1 | 0.631 | Mass | 0.631 | 0.631 | 0.631 | 0.631 | 0.631 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 14.947 | 1 | 14.951 | Mass | 14.947 | 14.947 | 14.947 | 14.947 | 14.947 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 3 | 22.769 | 3 | 22.771 | Mass | 22.769 | 22.769 | 22.769 | 22.769 | 22.769 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 2 | 17.948 | 2 | 17.950 | Mass | 17.948 | 17.948 | 17.948 | 17.948 | 17.948 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| AP-861R-DD-BC | STUB | 0.485 | 27 | 13.092 | 27 | 13.092 | Mass | 13.092 | 13.092 | 13.092 | 13.092 | 13.092 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 77.649 | 153 | 432.619 | 153 | 432.632 |  | 432.620 | 432.620 | 432.620 | 432.620 | 432.620 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : 798 |  | Client : GODREJ & BOYCE MFG. CO. LTD VT798 | [11 empty] | Order Dt. : 09/12/2023
| 1B1 | BEAM | 0.875 | 4 | 3.501 | 4 | 3.496 | Proto | 3.501 | 3.501 | 3.501 | 3.501 | 1.062 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 2.438
| 1B2 | BEAM | 0.747 | 6 | 4.482 | 6 | 4.483 | Proto | 4.482 | 4.482 | 4.482 | 4.482 | 2.208 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 2.274
| 1B3 | BEAM | 0.756 | 2 | 1.512 | 2 | 1.512 | Proto | 1.512 | 1.512 | 1.512 | 1.512 | 0.772 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.740
| 1B4 | BEAM | 0.749 | 2 | 1.497 | 2 | 1.497 | Proto | 1.497 | 1.497 | 1.497 | 1.497 | 0.772 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.726
| 1BPI | EQUIPMENT | 0.184 | 14 | 2.573 | 14 | 2.574 | Proto | 2.573 | 2.573 | 2.573 | 2.573 | 1.519 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.054
| 1BPIB | EQUIPMENT | 0.535 | 48 | 25.665 | 48 | 25.666 | Mass | 25.665 | 25.665 | 25.665 | 25.665 | 25.665 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1CT | EQUIPMENT | 0.133 | 18 | 2.390 | 18 | 2.391 | Proto | 2.390 | 2.390 | 2.390 | 2.390 | 0.893 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.497
| 1CTA | EQUIPMENT | 0.139 | 3 | 0.416 | 3 | 0.416 | Proto | 0.416 | 0.416 | 0.416 | 0.416 | 0.150 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.265
| 1CVT | EQUIPMENT | 0.131 | 18 | 2.357 | 18 | 2.359 | Proto | 2.357 | 2.357 | 2.357 | 2.357 | 0.700 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.658
| 1DD2 | STUB | 0.301 | 1 | 0.301 | 1 | 0.301 | Mass | 0.301 | 0.301 | 0.301 | 0.301 | 0.301 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DD3 | NORMAL TOWER | 7.287 | 1 | 7.287 | 1 | 7.219 | Proto | 7.220 | 7.220 | 7.220 | 7.287 | 7.144 | 0.000 | 0.002 | 0.000 | 0.000 | -0.067 | 0.143
| 1ISO | EQUIPMENT | 0.746 | 22 | 16.417 | 22 | 16.416 | Proto | 16.417 | 16.417 | 16.417 | 16.417 | 11.299 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 5.118
| 1LA | EQUIPMENT | 0.164 | 18 | 2.956 | 18 | 2.956 | Proto | 2.956 | 2.956 | 2.956 | 2.956 | 0.809 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 2.147
| 1T1 | COLUMN | 1.205 | 3 | 3.616 | 3 | 3.614 | Proto | 3.616 | 3.616 | 3.616 | 3.616 | 1.650 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.965
| 1T2 | COLUMN | 1.556 | 3 | 4.667 | 3 | 4.668 | Proto | 4.667 | 4.667 | 4.667 | 4.667 | 3.837 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.830
| 1T3 | COLUMN | 1.191 | 1 | 1.191 | 1 | 1.195 | Proto | 1.191 | 1.191 | 1.191 | 1.191 | 0.385 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.806
| 1T4 | COLUMN | 1.421 | 6 | 8.524 | 6 | 8.526 | Proto | 8.524 | 8.524 | 8.524 | 8.524 | 3.008 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 5.516
| 1T5 | COLUMN | 1.588 | 1 | 1.588 | 1 | 1.587 | Proto | 1.588 | 1.588 | 1.588 | 1.588 | 0.589 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.999
| 1T6 | COLUMN | 1.254 | 2 | 2.508 | 2 | 2.506 | Proto | 2.508 | 2.508 | 2.508 | 2.508 | 2.008 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.500
| 1T7 | COLUMN | 1.396 | 2 | 2.792 | 2 | 2.792 | Proto | 2.792 | 2.792 | 2.792 | 2.792 | 1.095 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.697
| 1T8 | COLUMN | 1.594 | 1 | 1.594 | 1 | 1.592 | Proto | 1.594 | 1.594 | 1.594 | 1.594 | 1.469 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.124
| 3BPI | EQUIPMENT | 0.258 | 24 | 6.183 | 24 | 6.182 | Mass | 6.183 | 6.183 | 6.183 | 6.183 | 6.183 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3C1 | NORMAL TOWER | 0.758 | 4 | 3.031 | 4 | 3.028 | Proto | 3.031 | 3.031 | 3.031 | 3.031 | 0.355 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 2.677
| 3C2 | NORMAL TOWER | 0.705 | 4 | 2.818 | 4 | 2.814 | Proto | 2.818 | 2.818 | 2.818 | 2.818 | 2.074 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.744
| 3C3 | NORMAL TOWER | 0.736 | 2 | 1.472 | 2 | 1.469 | Proto | 1.472 | 1.472 | 1.472 | 1.472 | 0.926 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.546
| 3CT | EQUIPMENT | 0.245 | 2 | 0.489 | 2 | 0.490 | Proto | 0.489 | 0.489 | 0.489 | 0.489 | 0.295 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.194
| 3CTA | EQUIPMENT | 0.239 | 6 | 1.433 | 6 | 1.433 | Proto | 1.433 | 1.433 | 1.433 | 1.433 | 0.206 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.227
| 3HGF | EQUIPMENT | 0.197 | 6 | 1.181 | 6 | 1.179 | Proto | 1.181 | 1.181 | 1.181 | 1.181 | 1.181 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3ISO | EQUIPMENT | 0.350 | 15 | 5.252 | 15 | 5.248 | Proto | 5.252 | 5.252 | 5.252 | 5.252 | 1.805 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 3.446
| 3LA | EQUIPMENT | 0.249 | 4 | 0.996 | 4 | 0.998 | Proto | 0.996 | 0.996 | 0.996 | 0.996 | 0.337 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.659
| 3PT | EQUIPMENT | 0.219 | 8 | 1.753 | 8 | 1.757 | Proto | 1.753 | 1.753 | 1.753 | 1.753 | 1.753 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| CB1 | BEAM | 0.400 | 2 | 0.801 | 2 | 0.799 | Proto | 0.801 | 0.801 | 0.801 | 0.801 | 0.323 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.478
| CB2 | BEAM | 0.401 | 4 | 1.603 | 4 | 1.601 | Proto | 1.603 | 1.603 | 1.603 | 1.603 | 0.646 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.958
| IS | COLUMN | 0.105 | 1 | 0.105 | 1 | 0.104 | Mass | 0.105 | 0.105 | 0.105 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.285 | 1 | 0.284 | Mass | 0.285 | 0.285 | 0.285 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| LM1 | COLUMN | 1.084 | 1 | 1.084 | 1 | 1.084 | Proto | 1.084 | 1.084 | 1.084 | 1.084 | 0.577 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.507
| LM2 | COLUMN | 1.084 | 1 | 1.084 | 1 | 1.084 | Mass | 1.084 | 1.084 | 1.084 | 1.084 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.084
| LM3 | NORMAL TOWER | 0.623 | 1 | 0.623 | 1 | 0.625 | Proto | 0.623 | 0.623 | 0.623 | 0.623 | 0.401 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.222
| LM4 | NORMAL TOWER | 0.623 | 1 | 0.623 | 1 | 0.625 | Mass | 0.623 | 0.623 | 0.623 | 0.623 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.623
| LM5 | NORMAL TOWER | 0.623 | 1 | 0.623 | 1 | 0.625 | Mass | 0.623 | 0.623 | 0.623 | 0.623 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.623
| LM6 | NORMAL TOWER | 0.623 | 1 | 0.623 | 1 | 0.625 | Mass | 0.623 | 0.623 | 0.623 | 0.623 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.623
| SC | NORMAL TOWER | 0.326 | 1 | 0.326 | 1 | 0.329 | Mass | 0.326 | 0.326 | 0.326 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 34.083 | 266 | 130.222 | 266 | 130.149 |  | 130.154 | 130.154 | 130.154 | 129.504 | 84.396 | 0.000 | 0.002 | 0.000 | 0.000 | -0.067 | 45.109
| Project Code : 802. |  | Client : MANIPAL ENERGY & INFRATECH LTD- VT802. | [11 empty] | Order Dt. : 23/02/2024
|  |  |  | 1 | 0.007 | 1 | 0.007 | Mass | 0.007 | 0.007 | 0.007 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 0.007 | 1 | 0.007 | 1 | 0.007 |  | 0.007 | 0.007 | 0.007 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : 803. |  | Client : JYOTI ENGINEERING WORKS - VT803. | [11 empty] | Order Dt. : 20/03/2024
| SS | NORMAL TOWER | 12.501 | 1 | 12.501 |  |  | Pre
|  | Sub Total | 12.501 | 1 | 12.501
| Project Code : 807 |  | Client : GE T&D INDIA LTD ( ADANI KHAVDA PROJECT )-VT807 | [11 empty] | Order Dt. : 09/02/2024
| 1BPI | EQUIPMENT | 0.241 | 7 | 1.685 | 1 | 0.239 | Proto | 0.241 | 0.241 | 0.241 | 0.241 | 0.241 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 6 | 1.445 | Mass | 1.445 | 1.445 | 1.445 | 1.445 | 1.445 | -0.002 | 0.001 | 0.000 | 0.000 | -0.001 | 0.001
| 1BPI2 | EQUIPMENT | 0.291 | 1 | 0.291 | 1 | 0.290 | Proto | 0.291 | 0.291 | 0.291 | 0.291 | 0.291 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1NCT | EQUIPMENT | 0.201 | 1 | 0.201 | 1 | 0.203 | Proto | 0.201 | 0.201 | 0.201 | 0.201 | 0.199 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.002
| 3BPI3 | EQUIPMENT | 0.188 | 14 | 2.630 | 1 | 0.191 | Proto | 0.188 | 0.188 | 0.188 | 0.188 | 0.188 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 13 | 2.449 | Mass | 2.443 | 2.443 | 2.443 | 2.445 | 2.443 | -0.002 | 0.003 | 0.000 | 0.000 | -0.003 | 0.003
| 3HBPI2 | EQUIPMENT | 0.296 | 39 | 11.557 | 1 | 0.297 | Proto | 0.296 | 0.296 | 0.296 | 0.297 | 0.296 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 38 | 11.273 | Mass | 11.260 | 11.260 | 11.260 | 11.273 | 11.260 | -0.011 | 0.012 | 0.000 | 0.000 | -0.012 | 0.012
| 3LBPI1 | EQUIPMENT | 0.218 | 12 | 2.616 | 1 | 0.219 | Proto | 0.218 | 0.208 | 0.208 | 0.219 | 0.215 | 0.000 | 0.001 | 0.010 | 0.000 | -0.011 | 0.004
[6 empty] | 11 | 2.410 | Mass | 2.398 | 2.398 | 2.398 | 2.409 | 2.364 | -0.011 | 0.011 | 0.000 | 0.000 | -0.011 | 0.046
| 3NCT | EQUIPMENT | 0.178 | 4 | 0.713 | 1 | 0.178 | Proto | 0.178 | 0.176 | 0.176 | 0.178 | 0.178 | 0.000 | 0.000 | 0.002 | 0.000 | -0.002 | 0.000
[6 empty] | 3 | 0.536 | Mass | 0.535 | 0.535 | 0.535 | 0.535 | 0.535 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4CVTJ | EQUIPMENT | 0.185 | 11 | 2.034 | 1 | 0.184 | Proto | 0.185 | 0.185 | 0.185 | 0.185 | 0.185 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 10 | 1.849 | Mass | 1.849 | 1.849 | 1.849 | 1.848 | 1.644 | 0.002 | -0.002 | 0.000 | 0.000 | 0.002 | 0.203
| 4CVTW | EQUIPMENT | 0.173 | 16 | 2.769 | 1 | 0.173 | Proto | 0.173 | 0.173 | 0.173 | 0.173 | 0.173 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 15 | 2.593 | Mass | 2.596 | 2.596 | 2.596 | 2.595 | 2.512 | 0.001 | -0.001 | 0.000 | 0.000 | 0.001 | 0.083
| 4G1 | BEAM | 3.012 | 8 | 24.097 | 3 | 9.213 | Proto | 9.272 | 9.272 | 9.272 | 9.211 | 9.272 | 0.000 | -0.061 | 0.000 | 0.000 | 0.061 | -0.061
[6 empty] | 5 | 14.765 | Mass | 14.825 | 14.825 | 14.825 | 14.764 | 12.401 | 6.322 | -0.061 | 0.000 | 0.000 | 0.061 | 2.364
| 4HBPI | EQUIPMENT | 0.581 | 67 | 38.908 | 1 | 0.581 | Proto | 0.581 | 0.581 | 0.581 | 0.579 | 0.581 | 0.000 | -0.002 | 0.000 | 0.000 | 0.002 | -0.002
[6 empty] | 66 | 38.262 | Mass | 38.327 | 38.327 | 38.327 | 38.257 | 37.321 | 0.070 | -0.070 | 0.000 | 0.000 | 0.070 | 0.937
| 4HLA | EQUIPMENT | 0.590 | 28 | 16.528 | 1 | 0.586 | Proto | 0.590 | 0.590 | 0.590 | 0.588 | 0.590 | 0.000 | -0.002 | 0.000 | 0.000 | 0.002 | -0.002
[6 empty] | 21 | 12.371 | Mass | 12.396 | 12.396 | 12.396 | 12.373 | 11.321 | 3.571 | -0.023 | 0.000 | 0.000 | 0.023 | 1.053
| 4LA | EQUIPMENT | 0.239 | 30 | 7.162 | 1 | 0.240 | Proto | 0.239 | 0.239 | 0.239 | 0.239 | 0.239 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 29 | 6.920 | Mass | 6.923 | 6.923 | 6.923 | 6.923 | 6.769 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.154
| 4LBPI | EQUIPMENT | 0.232 | 28 | 6.501 | 1 | 0.233 | Proto | 0.232 | 0.232 | 0.232 | 0.232 | 0.232 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 27 | 6.266 | Mass | 6.269 | 6.269 | 6.269 | 6.269 | 6.193 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.076
| 4TA | NORMAL TOWER | 3.392 | 8 | 27.139 | 2 | 6.725 | Proto | 6.785 | 6.785 | 6.785 | 6.730 | 6.785 | 0.000 | -0.055 | 0.000 | 0.000 | 0.055 | -0.055
[6 empty] | 6 | 20.213 | Mass | 20.354 | 20.354 | 20.354 | 20.217 | 19.192 | 3.533 | -0.138 | 0.000 | 0.000 | 0.138 | 1.025
| 4TB | NORMAL TOWER | 4.289 | 5 | 21.445 | 2 | 8.532 | Proto | 8.578 | 8.578 | 8.578 | 8.535 | 8.578 | 0.000 | -0.043 | 0.000 | 0.000 | 0.043 | -0.043
[6 empty] | 3 | 12.840 | Mass | 12.867 | 12.867 | 12.867 | 12.845 | 10.923 | 4.308 | -0.022 | 0.000 | 0.000 | 0.022 | 1.922
| 4WT | EQUIPMENT | 0.498 | 18 | 8.958 | 1 | 0.503 | Proto | 0.498 | 0.498 | 0.498 | 0.498 | 0.498 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 17 | 8.460 | Mass | 8.461 | 8.461 | 8.461 | 8.462 | 8.309 | -0.001 | 0.001 | 0.000 | 0.000 | -0.001 | 0.153
| 6HBPI1 | EQUIPMENT | 0.316 | 71 | 22.425 | 1 | 0.315 | Proto | 0.316 | 0.316 | 0.316 | 0.316 | 0.316 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 38 | 12.003 | Mass | 12.002 | 12.002 | 12.002 | 12.002 | 12.002 | 10.110 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 6LBPI2 | EQUIPMENT | 0.284 | 26 | 7.395 | 1 | 0.283 | Proto | 0.284 | 0.280 | 0.280 | 0.284 | 0.284 | 0.000 | 0.000 | 0.005 | 0.000 | -0.005 | 0.000
[6 empty] | 25 | 7.104 | Mass | 7.111 | 7.111 | 7.111 | 7.105 | 7.111 | 0.005 | -0.005 | 0.000 | 0.000 | 0.005 | -0.005
| 6LBPI3 | EQUIPMENT | 0.210 | 23 | 4.833 | 1 | 0.210 | Proto | 0.210 | 0.201 | 0.201 | 0.210 | 0.210 | 0.000 | 0.000 | 0.010 | 0.000 | -0.009 | 0.000
[6 empty] | 22 | 4.622 | Mass | 4.623 | 4.623 | 4.623 | 4.620 | 4.623 | 0.002 | -0.003 | 0.000 | 0.000 | 0.003 | -0.003
| 7BPI | EQUIPMENT | 0.512 | 104 | 53.223 | 1 | 0.511 | Proto | 0.512 | 0.512 | 0.512 | 0.510 | 0.512 | 0.000 | -0.001 | 0.000 | 0.000 | 0.001 | -0.001
[6 empty] | 103 | 52.653 | Mass | 52.711 | 52.711 | 52.711 | 52.654 | 50.812 | 0.057 | -0.057 | 0.000 | 0.000 | 0.057 | 1.842
| 7CVTJ | EQUIPMENT | 0.355 | 14 | 4.974 | 1 | 0.355 | Proto | 0.355 | 0.355 | 0.355 | 0.355 | 0.355 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 13 | 4.618 | Mass | 4.618 | 4.618 | 4.618 | 4.618 | 4.352 | 0.000 | -0.001 | 0.000 | 0.000 | 0.001 | 0.265
| 7CVTW | EQUIPMENT | 0.341 | 4 | 1.365 | 1 | 0.341 | Proto | 0.341 | 0.341 | 0.341 | 0.341 | 0.341 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 3 | 1.020 | Mass | 1.024 | 1.024 | 1.024 | 1.024 | 1.024 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 7GA | BEAM | 2.420 | 10 | 24.204 | 2 | 4.817 | Proto | 4.841 | 4.841 | 4.841 | 4.821 | 4.841 | 0.000 | -0.020 | 0.000 | 0.000 | 0.020 | -0.020
[6 empty] | 8 | 19.324 | Mass | 19.363 | 19.363 | 19.363 | 19.324 | 17.115 | 2.465 | -0.039 | 0.000 | 0.000 | 0.039 | 2.209
| 7GB | BEAM | 1.383 | 20 | 27.651 | 4 | 5.474 | Proto | 5.530 | 5.442 | 5.442 | 5.472 | 5.530 | 0.000 | -0.058 | 0.088 | 0.000 | -0.030 | -0.058
[6 empty] | 16 | 22.006 | Mass | 22.121 | 22.121 | 22.121 | 22.005 | 20.379 | 4.270 | -0.116 | 0.000 | 0.000 | 0.116 | 1.626
| 7LA | EQUIPMENT | 0.494 | 54 | 26.652 | 1 | 0.493 | Proto | 0.494 | 0.272 | 0.272 | 0.494 | 0.272 | 0.000 | 0.000 | 0.222 | 0.000 | -0.222 | 0.222
[6 empty] | 53 | 26.161 | Mass | 26.159 | 26.159 | 26.159 | 26.161 | 25.255 | -0.002 | 0.002 | 0.000 | 0.000 | -0.002 | 0.906
| 7TA | NORMAL TOWER | 8.957 | 20 | 179.146 | 4 | 35.644 | Proto | 35.829 | 35.802 | 35.802 | 35.626 | 35.829 | 0.000 | -0.203 | 0.027 | 0.000 | 0.176 | -0.203
[6 empty] | 16 | 142.906 | Mass | 143.317 | 143.317 | 143.317 | 142.911 | 137.817 | 27.271 | -0.406 | 0.000 | 0.000 | 0.406 | 5.094
| 7TAGW | NORMAL TOWER | 0.441 | 20 | 8.811 | 4 | 1.741 | Proto | 1.762 | 1.762 | 1.762 | 1.744 | 1.762 | 0.000 | -0.019 | 0.000 | 0.000 | 0.019 | -0.019
[6 empty] | 16 | 7.014 | Mass | 7.049 | 7.049 | 7.049 | 7.012 | 6.387 | 1.362 | -0.037 | 0.000 | 0.000 | 0.037 | 0.625
| 7WT | EQUIPMENT | 0.748 | 12 | 8.982 | 1 | 0.750 | Proto | 0.748 | 0.748 | 0.748 | 0.747 | 0.748 | 0.000 | -0.001 | 0.000 | 0.000 | 0.001 | -0.001
[6 empty] | 11 | 8.223 | Mass | 8.233 | 8.121 | 8.121 | 8.224 | 7.909 | 0.011 | -0.010 | 0.112 | 0.000 | -0.103 | 0.315
| IS | COLUMN | 0.018 | 1 | 0.018 | 1 | 0.019 | Mass | 0.018 | 0.018 | 0.018 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.133 | 1 | 0.134 | Mass | 0.133 | 0.133 | 0.133 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.022 | 1 | 0.021 | Mass | 0.022 | 0.022 | 0.022 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.031 | 1 | 0.031 | Mass | 0.031 | 0.031 | 0.031 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.146 | 1 | 0.145 | Mass | 0.146 | 0.011 | 0.011 |  |  | 0.000 | 0.000 | 0.135 | 0.000
|  |  |  | 1 | 0.146 | 1 | 0.145 | Mass | 0.146 | 0.111 | 0.111 |  |  | 0.000 | 0.000 | 0.035 | 0.000
|  |  |  | 1 | 0.647 | 1 | 0.649 | Mass | 0.647 | 0.647 | 0.643 |  |  | 0.000 | 0.000 | 0.000 | 0.004
|  |  |  | 1 | 0.312 | 1 | 0.312 | Mass | 0.312 | 0.204 | 0.204 |  |  | 0.000 | 0.000 | 0.108 | 0.000
| LM | NORMAL TOWER | 11.986 | 5 | 59.928 | 5 | 59.576 | Proto | 59.748 | 59.748 | 59.748 | 59.748 | 59.748 | 0.000 | -0.174 | 0.000 | 0.000 | 0.000 | 0.000
| SC | NORMAL TOWER | 0.155 | 1 | 0.155 | 1 | 0.156 | Mass | 0.155 | 0.155 | 0.155 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.026 | 1 | 0.027 | Mass | 0.026 | 0.026 | 0.026 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.137 | 1 | 0.135 | Mass | 0.137 | 0.084 | 0.084 |  |  | 0.000 | 0.000 | 0.053 | 0.000
|  |  |  | 1 | 0.051 | 1 | 0.051 | Mass | 0.051 | 0.051 | 0.051 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 75.850 | 692 | 606.647 | 654 | 591.228 |  | 592.820 | 592.013 | 592.009 | 589.575 | 568.906 | 63.331 | -1.594 | 0.807 | 0.004 | 0.944 | 20.669
| Project Code : 811 |  | Client : ASSOCIATED POWER STRUCTURES PVT.LTD. - VT811 | [11 empty] | Order Dt. : 28/02/2024
| 1PT | EQUIPMENT | 0.247 | 6 | 1.485 | 6 | 1.485 | Mass | 1.485 | 1.485 | 1.485 | 1.485 | 1.485 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2CT | EQUIPMENT | 0.337 | 24 | 8.083 | 24 | 8.084 | Mass | 8.083 | 8.083 | 8.083 | 8.083 | 8.083 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2IVT | EQUIPMENT | 0.236 | 18 | 4.249 | 18 | 4.120 | Mass | 4.249 | 4.249 | 4.249 | 4.121 | 4.249 | 0.128 | -0.128 | 0.000 | 0.000 | 0.128 | -0.128
| 2LA | EQUIPMENT | 0.348 | 18 | 6.262 | 18 | 6.262 | Proto | 6.262 | 6.262 | 6.262 | 6.262 | 6.262 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2TISO | EQUIPMENT | 1.189 | 2 | 2.377 |  |  | Proto
| IS | COLUMN | 0.072 | 1 | 0.072 | 1 | 0.072 | Mass | 0.072 | 0.072 | 0.072 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| Q3 | COLUMN | 0.005 | 10 | 0.051 | 10 | 0.051 | Mass | 0.051 | 0.051 | 0.051 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| SC | NORMAL TOWER | 0.006 | 1 | 0.006 | 1 | 0.006 | Mass | 0.006 | 0.006 | 0.006 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 2.441 | 80 | 22.585 | 78 | 20.080 |  | 20.208 | 20.208 | 20.208 | 19.950 | 20.078 | 0.128 | -0.128 | 0.000 | 0.000 | 0.128 | -0.128
| Project Code : 817 |  | Client : POWER ENGINEERS - VT817 | [11 empty] | Order Dt. : 22/04/2024
| CMS6M | +6 MTR EXTN | 4.927 | 1 | 4.927 |  |  | Pre
|  | Sub Total | 4.927 | 1 | 4.927
| Project Code : 818 |  | Client : POWER ENGINEERS - VT817 | [11 empty] | Order Dt. : 28/04/2024
| WTC | EQUIPMENT | 0.236 | 4 | 0.946 |  |  | Mass
|  | Sub Total | 0.236 | 4 | 0.946
| Project Code : 821 |  | Client : MEGHA ENGINEERING & INFRASTRUCTURES LTD - VT821 | [11 empty] | Order Dt. : 10/05/2024
| 1DB3 | NORMAL TOWER | 4.637 | 10 | 46.368 | 10 | 46.367 | Mass | 46.368 | 46.368 | 46.368 | 46.368 | 46.368 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DB3M | +3 MTR EXTN | 0.855 | 2 | 1.709 | 2 | 1.707 | Mass | 1.709 | 1.709 | 1.709 | 1.709 | 1.709 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DB6M | +6 MTR EXTN | 1.481 | 2 | 2.962 | 2 | 2.958 | Mass | 2.962 | 2.962 | 2.962 | 2.962 | 2.962 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DD18M | +18 MTR EXTN | 6.946 | 3 | 20.837 | 3 | 20.839 | Mass | 20.837 | 20.837 | 20.837 | 20.837 | 20.837 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DD3 | NORMAL TOWER | 6.091 | 15 | 91.366 | 15 | 91.370 | Mass | 91.366 | 91.366 | 91.366 | 91.366 | 91.366 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DD6M | +6 MTR EXTN | 2.091 | 3 | 6.274 | 3 | 6.277 | Mass | 6.274 | 6.274 | 6.274 | 6.274 | 6.274 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DD9M | +9 MTR EXTN | 2.992 | 9 | 26.932 | 9 | 26.933 | Mass | 26.932 | 26.932 | 26.932 | 26.932 | 26.932 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DB3 | NORMAL TOWER | 6.257 | 5 | 31.283 | 2 | 12.503 | Mass | 12.513 | 12.513 | 12.513 | 12.513 | 12.501 | 18.783 | 0.000 | 0.000 | 0.000 | 0.000 | 0.012
| 2DD3 | NORMAL TOWER | 8.489 | 10 | 84.891 | 10 | 84.887 | Mass | 84.891 | 76.504 | 76.339 | 83.055 | 67.913 | 0.000 | 0.000 | 8.387 | 0.166 | -6.717 | 15.142
| 2DD6M | +6 MTR EXTN | 3.087 | 5 | 15.435 | 5 | 15.436 | Mass | 15.435 | 12.348 | 12.348 | 15.417 | 12.348 | 0.000 | 0.000 | 3.087 | 0.000 | -3.070 | 3.070
| 2DD9M | +9 MTR EXTN | 4.031 | 4 | 16.124 | 4 | 16.128 | Mass | 16.124 | 16.124 | 16.124 | 16.124 | 16.124 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| IS | COLUMN | 1.294 | 1 | 1.294 | 1 | 1.292 | Mass | 1.294 | 1.294 | 1.280 |  |  | 0.000 | 0.000 | 0.000 | 0.015
|  |  |  | 1 | 2.748 | 1 | 2.748 | Mass | 2.748 | 2.742 | 2.742 |  |  | 0.000 | 0.000 | 0.006 | 0.000
|  | Sub Total | 50.999 | 70 | 348.223 | 67 | 329.445 |  | 329.454 | 317.974 | 317.794 | 323.559 | 305.335 | 18.783 | 0.000 | 11.480 | 0.180 | -9.786 | 18.224
| Project Code : 824. |  | Client : TOSHIBA TRANSMISSION & DISTRIBUTION SYSTEMS (INDIA) PVT LTD -VT824 | [11 empty] | Order Dt. : 27/06/2025
| 1DP | EQUIPMENT | 0.423 | 2 | 0.846 | 1 | 0.422 | Proto | 0.423 |  |  |  |  | 0.000 | 0.000 | 0.423
| 22CT | EQUIPMENT | 0.194 | 3 | 0.581 | 1 | 0.194 | Proto | 0.194 |  |  |  |  | 0.000 | 0.000 | 0.194
| 22ISO | EQUIPMENT | 0.349 | 3 | 1.046 | 1 | 0.347 | Proto | 0.349 |  |  |  |  | 0.000 | 0.000 | 0.349
| 22PT | EQUIPMENT | 0.194 | 3 | 0.583 | 1 | 0.194 | Proto | 0.194 |  |  |  |  | 0.000 | 0.000 | 0.194
| 2CVT | EQUIPMENT | 0.262 | 10 | 2.616 | 1 | 0.261 | Proto | 0.262 |  |  |  |  | 0.000 | 0.000 | 0.262
| 2GB1 | BEAM | 2.080 | 15 | 31.197 | 15 | 31.199 | Mass | 31.197 | 31.197 | 31.190 | 31.197 | 31.164 | 0.000 | 0.000 | 0.000 | 0.007 | -0.007 | 0.033
| 2GB2 | BEAM | 2.353 | 20 | 47.061 | 20 | 47.060 | Mass | 47.061 | 47.061 | 47.061 | 47.061 | 47.058 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.003
| 2GT1 | COLUMN | 2.879 | 24 | 69.093 | 24 | 69.090 | Mass | 69.093 | 69.093 | 69.093 | 69.093 | 68.750 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.342
| 2GT2 | COLUMN | 7.495 | 13 | 97.430 | 13 | 97.421 | Mass | 97.430 | 97.430 | 97.430 | 97.430 | 97.338 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.093
| 2HBPI1 | EQUIPMENT | 0.268 | 63 | 16.912 | 63 | 16.915 | Proto | 0.000 |  |  | 16.912 |  | 0.000 | 16.912 | 0.000 |  | -16.912 | 16.912
| 2HBPI2 | EQUIPMENT | 0.288 | 18 | 5.190 | 18 | 5.192 | Proto | 0.000 |  |  | 5.190 |  | 0.000 | 5.190 | 0.000 |  | -5.190 | 5.190
| 2HLA1 | EQUIPMENT | 0.264 | 27 | 7.136 | 27 | 7.135 | Proto | 0.000 |  |  | 7.136 |  | 0.000 | 7.136 | 0.000 |  | -7.136 | 7.136
| 2HLA2 | EQUIPMENT | 0.287 | 12 | 3.440 | 12 | 3.439 | Proto | 0.000 |  |  | 3.440 |  | 0.000 | 3.440 | 0.000 |  | -3.440 | 3.440
| 2LA | EQUIPMENT | 0.218 | 15 | 3.273 | 15 | 3.272 | Proto | 0.000 |  |  | 3.273 |  | 0.000 | 3.273 | 0.000 |  | -3.273 | 3.273
| 4BPI | EQUIPMENT | 0.257 | 24 | 6.171 | 24 | 6.170 | Proto | 0.000 |  |  | 6.171 |  | 0.000 | 6.171 | 0.000 |  | -6.171 | 6.171
| 4CVT | EQUIPMENT | 0.313 | 18 | 5.641 | 1 | 0.315 | Proto | 0.313 |  |  |  |  | 0.000 | 0.000 | 0.313
| 4GB1 | BEAM | 4.233 | 13 | 55.035 | 13 | 55.038 | Mass | 55.035 | 54.944 | 54.823 | 55.035 | 54.900 | 0.000 | 0.000 | 0.091 | 0.121 | -0.212 | 0.135
| 4GB2 | BEAM | 4.896 | 6 | 29.374 | 6 | 29.374 | Mass | 29.374 | 29.374 | 29.374 | 29.374 | 29.374 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4GT1 | COLUMN | 4.765 | 18 | 85.768 | 18 | 85.774 | Mass | 85.768 | 85.689 | 85.768 | 85.768 | 85.654 | 0.000 | 0.000 | 0.079 | -0.079 | 0.000 | 0.114
| 4GT2 | COLUMN | 12.309 | 8 | 98.469 | 8 | 98.464 | Mass | 98.469 | 98.390 | 98.469 | 98.469 | 98.397 | 0.000 | 0.000 | 0.078 | -0.078 | 0.000 | 0.072
| 4HBPI | EQUIPMENT | 0.316 | 18 | 5.688 | 18 | 11.377 | Proto | 5.688 | 5.349 | 4.529 | 5.688 |  | 0.000 | 5.688 | 0.340 | 0.820 | -1.160 | 5.688
| 4HLA | EQUIPMENT | 0.275 | 15 | 4.122 | 15 | 4.283 | Proto | 4.283 | 0.256 | 0.256 | 4.122 |  | 0.000 | 0.000 | 4.027 | 0.000 | -3.866 | 4.122
| 4LA | EQUIPMENT | 0.226 | 18 | 4.074 | 18 | 4.080 | Proto | 0.000 |  |  | 4.074 |  | 0.000 | 4.074 | 0.000 |  | -4.074 | 4.074
| 6HBPI | EQUIPMENT | 0.348 | 12 | 4.175 | 1 | 0.347 | Proto | 0.348 |  |  |  |  | 0.000 | 0.000 | 0.348
| 6HLA | EQUIPMENT | 0.275 | 12 | 3.299 | 1 | 0.275 | Proto | 0.275 |  |  |  |  | 0.000 | 0.000 | 0.275
| 6LA | EQUIPMENT | 0.240 | 3 | 0.721 | 1 | 0.240 | Proto | 0.240 |  |  |  |  | 0.000 | 0.000 | 0.240
| IS | NORMAL TOWER | 0.285 | 1 | 0.285 | 1 | 0.286 | Mass | 0.285 | 0.186 | 0.182 |  |  | 0.000 | 0.000 | 0.099 | 0.004
| K1P | EQUIPMENT | 0.110 | 1 | 0.110 | 1 | 0.109 | Proto | 0.110 |  |  |  |  | 0.000 | 0.000 | 0.110
| LM | NORMAL TOWER | 3.300 | 8 | 26.404 | 8 | 25.718 | Mass | 25.721 | 21.972 | 14.021 | 26.372 |  | 0.683 | 0.000 | 3.749 | 7.951 | -12.351 | 26.372
| OCS | EQUIPMENT | 0.070 | 2 | 0.141 | 1 | 0.072 | Proto | 0.070 |  |  |  |  | 0.000 | 0.000 | 0.070
| SC | NORMAL TOWER | 0.048 | 1 | 0.048 | 1 | 0.048 | Mass | 0.048 |  |  |  |  | 0.000 | 0.000 | 0.048
|  |  |  | 1 | 0.403 | 1 | 0.402 | Mass | 0.403 | 0.403 | 0.016 |  |  | 0.000 | 0.000 | 0.000 | 0.387
|  | Sub Total | 50.224 | 407 | 616.332 | 349 | 604.513 |  | 552.633 | 541.343 | 532.210 | 595.805 | 512.635 | 0.683 | 51.884 | 11.290 | 9.133 | -63.792 | 83.169
| Project Code : 825 |  | Client : LC INFRA PROJECTS PRIVATE LIMITED - VT825 | [11 empty] | Order Dt. : 26/05/2024
| APR | PEAK | 0.093 | 57 | 5.326 | 57 | 5.272 | Mass | 5.326 | 5.326 | 5.326 | 5.273 | 5.326 | 0.054 | -0.054 | 0.000 | 0.000 | 0.054 | -0.054
| CCM | COLUMN | 0.360 | 96 | 34.598 | 96 | 34.446 | Mass | 34.598 | 34.598 | 34.598 | 34.445 | 34.598 | 0.154 | -0.153 | 0.000 | 0.000 | 0.153 | -0.153
| EKR | COLUMN | 0.849 | 59 | 50.101 | 59 | 49.999 | Mass | 50.101 | 50.101 | 50.101 | 50.001 | 50.101 | 0.103 | -0.100 | 0.000 | 0.000 | 0.100 | -0.100
| IS | COLUMN | 2.324 | 1 | 2.324 | 1 | 2.329 | Mass | 2.324 | 2.324 | 2.324 | 2.324 | 2.324 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| XMM. | MAST | 0.038 | 1 | 0.038 | 1 | 0.038 | Mass | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| XPM | COLUMN | 0.084 | 145 | 12.194 | 145 | 12.220 | Mass | 12.194 | 12.194 | 12.194 | 12.221 | 12.194 | -0.028 | 0.027 | 0.000 | 0.000 | -0.027 | 0.027
| YMM | COLUMN | 0.021 | 145 | 3.095 | 145 | 3.091 | Mass | 3.095 | 3.095 | 3.095 | 3.091 | 3.095 | 0.004 | -0.004 | 0.000 | 0.000 | 0.004 | -0.004
| YMM1. | COLUMN | 0.021 | 69 | 1.473 | 69 | 1.472 | Mass | 1.473 | 1.473 | 1.473 | 1.473 | 1.473 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| YPM. | PEAK | 0.136 | 1 | 0.136 | 1 | 0.137 | Mass | 0.136 | 0.136 | 0.136 | 0.136 | 0.136 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 3.928 | 574 | 109.285 | 574 | 109.004 |  | 109.285 | 109.285 | 109.285 | 109.002 | 109.285 | 0.287 | -0.283 | 0.000 | 0.000 | 0.283 | -0.283
| Project Code : 827 |  | Client : LC INFRA PROJECTS PRIVATE LIMITED - VT827 | [11 empty] | Order Dt. : 31/05/2024
| 2DA3 | NORMAL TOWER | 4.176 | 1 | 4.176 | 1 | 4.184 | Proto | 4.176 | 4.176 | 4.176 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| 2DB3 | NORMAL TOWER | 7.401 | 1 | 7.401 | 1 | 7.394 | Proto | 7.401 | 7.401 | 7.401 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| DB2 | S.S.T | 0.821 | 8 | 6.566 | 8 | 6.564 | Mass | 6.566 | 6.566 | 6.566 | 6.566 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 6.566
| DC2 | S.S.T | 1.058 | 6 | 6.346 | 6 | 6.344 | Mass | 6.346 | 6.346 | 6.346 | 6.346 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 6.346
| DC2A | S.S.T | 1.565 | 6 | 9.391 | 6 | 9.390 | Mass | 9.391 | 9.391 | 9.391 | 9.391 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 9.391
| DC2B | S.S.T | 1.565 | 1 | 1.565 | 1 | 1.565 | Mass | 1.565 | 1.565 | 1.565 | 1.565 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.565
| IS | COLUMN | 0.155 | 1 | 0.155 | 1 | 0.156 | Mass | 0.155 | 0.155 | 0.155 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 16.741 | 24 | 35.600 | 24 | 35.597 |  | 35.600 | 35.600 | 35.600 | 23.869 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 23.869
| Project Code : 828 |  | Client : SKY ENGINEERING AND CONTRACTORS (VT828) | [11 empty] | Order Dt. : 27/05/2024
| A14S | EQUIPMENT | 0.519 | 150 | 77.863 |  |  | Mass
|  | Sub Total | 0.519 | 150 | 77.863
| Project Code : 833 |  | Client : VSPL ENERGY PRIVATE LIMITED -VT833 | [11 empty] | Order Dt. : 14/07/2024
| 2QC | NORMAL TOWER | 24.251 | 5 | 121.254 |  |  | Pre
|  |  |  | 1 | 2.500 |  |  | Pre
|  |  |  | 1 | 0.976 |  |  | Pre
|  |  |  | 1 | 1.172 |  |  | Pre
|  |  |  | 3 | 1.875 |  |  | Pre
|  |  |  | 2 | 6.378 |  |  | Pre
|  |  |  | 3 | 4.581 |  |  | Pre
| 2QD | NORMAL TOWER | 30.343 | 13 | 394.462 |  |  | Pre
|  |  |  | 5 | 6.294 |  |  | Pre
|  |  |  | 6 | 18.657 |  |  | Pre
|  |  |  | 6 | 7.553 |  |  | Pre
|  |  |  | 1 | 5.765 |  |  | Pre
|  |  |  | 6 | 4.679 |  |  | Pre
|  |  |  | 12 | 14.924 |  |  | Pre
|  |  |  | 3 | 1.858 |  |  | Pre
|  |  |  | 2 | 6.530 |  |  | Pre
|  |  |  | 6 | 6.172 |  |  | Pre
|  |  |  | 7 | 10.288 |  |  | Pre
|  | Sub Total | 84.383 | 83 | 615.918
| Project Code : 837 |  | Client : ODISHA POWER TRANSMISSION CORPORATION LTD -VT837 | [11 empty] | Order Dt. : 06/08/2024
| 1PC1 | S.S.T | 0.876 | 5 | 4.381 | 5 | 4.382 | Mass | 4.381 | 4.381 | 4.381 | 4.381 | 4.381 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1PC2 | STUB | 0.609 | 19 | 11.569 | 19 | 11.569 | Mass | 11.569 | 11.569 | 11.569 | 11.569 | 11.569 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1PC3 | NORMAL TOWER | 5.561 | 19 | 105.657 | 19 | 105.657 | Mass | 105.657 | 105.657 | 105.657 | 105.657 | 105.303 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.354
| 1PC3M | +3 MTR EXTN | 1.150 | 5 | 5.752 | 5 | 5.750 | Mass | 5.752 | 5.752 | 5.752 | 5.318 | 3.451 | 0.000 | 0.000 | 0.000 | 0.000 | 0.434 | 1.867
| 1PC6M | +6 MTR EXTN | 2.419 | 16 | 38.707 | 16 | 38.708 | Mass | 38.707 | 38.707 | 38.707 | 38.707 | 35.727 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 2.980
|  |  |  | 2 | 2.538 | 2 | 2.537 | Mass | 2.538 | 2.538 | 2.538 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| 2OC1 | S.S.T | 1.006 | 1 | 1.006 | 1 | 1.007 | Mass | 1.006 | 1.006 | 1.006 | 1.006 | 1.006 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2OC15M | +15 MTR EXTN | 8.658 | 3 | 25.973 |  |  | Mass
| 2OC2 | STUB | 0.776 | 3 | 2.329 | 3 | 2.330 | Mass | 2.329 | 2.329 | 2.329 | 2.329 | 0.776 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.553
| 2OC24M | +24 MTR EXTN | 15.912 | 3 | 47.735 | 3 | 47.734 | Proto | 47.735 | 47.735 | 47.735 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| 2OC2A | STUB | 1.067 | 4 | 4.269 |  |  | Mass
| 2OC3 | NORMAL TOWER | 9.190 | 10 | 91.903 | 4 | 36.761 | Mass | 36.761 | 36.761 | 36.761 | 36.761 | 24.393 | 55.141 | 0.000 | 0.000 | 0.000 | 0.000 | 12.368
| 2OC6M | +6 MTR EXTN | 2.736 | 2 | 5.472 |  |  | Mass
| 2UR1 | S.S.T | 1.553 | 4 | 6.211 | 4 | 6.211 | Mass | 6.211 | 6.211 | 6.211 | 6.211 | 6.211 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2UR2 | STUB | 0.692 | 11 | 7.614 | 11 | 7.614 | Mass | 7.614 | 7.614 | 7.614 | 7.614 | 7.614 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2UR3 | NORMAL TOWER | 12.678 | 11 | 139.455 | 11 | 139.455 | Mass | 139.455 | 139.455 | 139.455 | 135.717 | 114.099 | 0.000 | 0.000 | 0.000 | 0.000 | 3.738 | 21.618
|  |  |  | 1 | 4.417 | 1 | 4.415 | Mass | 4.417 | 4.417 | 4.417 | 4.417 | 4.417 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2UR6M | +6 MTR EXTN | 4.193 | 11 | 46.121 | 11 | 46.125 | Mass | 46.121 | 46.121 | 46.121 | 45.546 | 37.736 | 0.000 | 0.000 | 0.000 | 0.000 | 0.575 | 7.810
|  |  |  | 1 | 2.573 | 1 | 2.573 | Mass | 2.573 | 2.573 | 2.573 | 2.573 | 2.573 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| IS | COLUMN | 13.803 | 1 | 13.803 | 1 | 13.804 | Mass | 13.803 | 13.803 | 13.803 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.706 | 1 | 0.704 | Mass | 0.706 | 0.706 | 0.706 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 4.282 | 1 | 4.281 | Mass | 4.282 | 4.282 | 4.282 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 1.354 | 1 | 1.354 | Mass | 1.354 | 1.354 | 1.354 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| OA3M | +3 MTR EXTN | 0.759 | 9 | 6.832 | 9 | 6.834 | Mass | 6.832 | 6.832 | 6.832 | 2.110 | 0.001 | 0.000 | 0.000 | 0.000 | 0.000 | 4.722 | 2.109
| OA6M | +6 MTR EXTN | 1.506 | 5 | 7.531 | 5 | 7.531 | Mass | 7.531 | 7.531 | 7.531 | 7.531 | 5.407 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 2.124
| SC | NORMAL TOWER | 0.110 | 1 | 0.110 | 1 | 0.110 | Mass | 0.110 | 0.110 | 0.110 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.014 | 1 | 0.014 | Mass | 0.014 | 0.014 | 0.014 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| UR3 | NORMAL TOWER | 12.678 | 11 | 139.455 | 11 | 139.455 | Mass | 139.455 | 139.455 | 139.455 | 37.942 | 23.122 | 0.000 | 0.000 | 0.000 | 0.000 | 101.513 | 14.820
| UR6M | +6 MTR EXTN | 4.216 | 2 | 8.432 |  |  | Mass
|  | Sub Total | 116.764 | 164 | 736.201 | 147 | 636.915 |  | 636.914 | 636.914 | 636.914 | 455.390 | 387.787 | 55.141 | 0.000 | 0.000 | 0.000 | 110.982 | 67.603
| Project Code : 839 |  | Client : STERLING AND WILSON PVT LTD - VT839 | [11 empty] | Order Dt. : 06/08/2024
| 1G1 | BEAM | 0.742 | 2 | 1.484 | 2 | 1.486 | Proto | 1.484 | 1.484 | 1.484 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| 1T1S | NORMAL TOWER | 1.129 | 2 | 2.258 | 2 | 2.254 | Proto | 2.258 | 2.258 | 2.258 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| 2CT | EQUIPMENT | 0.361 | 6 | 2.167 | 6 | 2.164 | Proto | 2.167 | 2.167 | 2.167 | 2.167 | 2.167 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2ISO | EQUIPMENT | 1.486 | 5 | 7.430 | 5 | 7.432 | Proto | 7.430 | 7.430 | 7.430 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| 2LCSE | EQUIPMENT | 0.220 | 6 | 1.321 | 6 | 1.316 | Proto | 1.321 |  |  |  |  | 0.000 | 0.000 | 1.321
| 2P1S | COLUMN | 4.429 | 3 | 13.286 | 3 | 13.282 | Proto | 13.286 | 13.286 | 13.286 | 13.286 | 13.286 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2Q1 | BEAM | 1.701 | 2 | 3.402 | 2 | 3.403 | Proto | 3.402 | 3.402 | 3.209 | 3.402 | 3.402 | 0.000 | 0.000 | 0.000 | 0.193 | -0.193 | 0.000
| 2SA | EQUIPMENT | 0.349 | 9 | 3.137 | 9 | 3.134 | Proto | 3.137 | 3.137 | 3.137 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| 3BPI | EQUIPMENT | 0.180 | 15 | 2.697 | 15 | 2.695 | Proto | 2.697 | 2.697 | 2.697 | 2.697 | 2.697 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3BPT | EQUIPMENT | 0.167 | 6 | 1.003 | 6 | 1.004 | Proto | 1.003 | 1.003 | 1.003 | 1.003 | 1.003 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3CT | EQUIPMENT | 0.163 | 12 | 1.952 | 12 | 1.952 | Proto | 1.952 | 1.952 | 1.952 | 1.952 | 1.952 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3HGF | EQUIPMENT | 0.241 | 2 | 0.483 | 2 | 0.482 | Proto | 0.483 | 0.483 | 0.483 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| 3ISO | EQUIPMENT | 0.324 | 4 | 1.297 | 4 | 1.292 | Proto | 1.297 | 0.023 | 0.023 |  |  | 0.000 | 0.000 | 1.274 | 0.000
| 3ISOW | EQUIPMENT | 0.318 | 9 | 2.866 | 9 | 2.869 | Proto | 2.866 |  |  |  |  | 0.000 | 0.000 | 2.866
| 3LA | EQUIPMENT | 0.263 | 6 | 1.578 | 6 | 1.576 | Proto | 1.578 | 1.578 | 1.578 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| 3MCT | EQUIPMENT | 0.163 | 3 | 0.488 | 3 | 0.486 | Proto | 0.488 | 0.488 | 0.488 | 0.488 | 0.488 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3MVT | EQUIPMENT | 0.167 | 3 | 0.501 | 3 | 0.501 | Proto | 0.501 | 0.501 | 0.501 | 0.501 | 0.501 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 3 | 0.511 | 3 | 0.510 | Proto | 0.511 | 0.511 | 0.511 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| G4 | BEAM | 0.285 | 10 | 2.851 | 10 | 2.848 | Mass | 2.851 | 2.851 | 2.851 | 2.851 | 2.851 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| G6 | BEAM | 0.358 | 3 | 1.074 | 3 | 1.075 | Mass | 1.074 | 1.074 | 1.074 | 1.074 | 1.074 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| IS | COLUMN | 2.181 | 1 | 2.181 | 1 | 2.179 | Mass | 2.181 | 2.181 | 2.181 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.239 | 1 | 0.241 | Mass | 0.239 | 0.239 | 0.239 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.286 | 1 | 0.288 | Mass | 0.286 | 0.286 | 0.286 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| T8S | NORMAL TOWER | 0.675 | 15 | 10.124 | 15 | 10.127 | Mass | 10.124 | 10.124 | 10.124 | 10.124 | 10.124 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| T9S | NORMAL TOWER | 0.506 | 8 | 4.046 | 8 | 4.052 | Mass | 4.046 | 4.046 | 4.046 | 4.046 | 4.046 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 17.103 | 137 | 68.662 | 137 | 68.648 |  | 68.660 | 63.201 | 63.008 | 43.590 | 43.590 | 0.000 | 0.000 | 5.460 | 0.193 | -0.193 | 0.000
| Project Code : 840 |  | Client : BALAJI ELECTRICALS VT840 | [11 empty] | Order Dt. : 04/10/2024
| 1DA | +0. MTR EXTN. | 0.701 | 2 | 1.402 | 2 | 1.375 | Mass | 1.402 | 1.402 | 1.402 | 1.377 | 1.402 | 0.022 | -0.026 | 0.000 | 0.000 | 0.025 | -0.025
| 1DA2 | STUB | 0.142 | 2 | 0.284 | 2 | 0.281 | Mass | 0.284 | 0.284 | 0.284 | 0.281 | 0.284 | 0.004 | -0.004 | 0.000 | 0.000 | 0.003 | -0.003
| 1DA3 | NORMAL TOWER | 2.224 | 2 | 4.448 | 2 | 4.378 | Mass | 4.448 | 4.448 | 4.448 | 4.378 | 4.448 | 0.059 | -0.071 | 0.000 | 0.000 | 0.070 | -0.070
| 1DB | +0. MTR EXTN. | 0.862 | 8 | 6.898 | 8 | 6.790 | Mass | 6.898 | 6.898 | 6.898 | 6.793 | 6.898 | 0.102 | -0.106 | 0.000 | 0.000 | 0.105 | -0.105
| 1DB2 | STUB | 0.253 | 8 | 2.027 | 8 | 2.004 | Mass | 2.027 | 2.027 | 2.027 | 2.011 | 2.027 | 0.021 | -0.020 | 0.000 | 0.000 | 0.016 | -0.016
| 1DB3 | NORMAL TOWER | 3.839 | 8 | 30.712 | 8 | 30.302 | Mass | 30.712 | 30.712 | 30.712 | 30.360 | 30.712 | 0.416 | -0.409 | 0.000 | 0.000 | 0.352 | -0.352
| 1DB3M | +3 MTR EXTN | 0.866 | 2 | 1.732 | 2 | 1.707 | Mass | 1.732 | 1.732 | 1.732 | 1.709 | 1.732 | 0.022 | -0.023 | 0.000 | 0.000 | 0.023 | -0.023
| 1DB6M | +6 MTR EXTN | 1.507 | 3 | 4.520 | 3 | 4.440 | Mass | 4.520 | 4.520 | 4.520 | 4.444 | 4.520 | 0.079 | -0.077 | 0.000 | 0.000 | 0.075 | -0.075
| 1DC | +0. MTR EXTN. | 0.937 | 4 | 3.750 | 4 | 3.705 | Mass | 3.750 | 3.750 | 3.750 | 3.708 | 3.750 | 0.042 | -0.042 | 0.000 | 0.000 | 0.042 | -0.042
| 1DC2 | STUB | 0.282 | 4 | 1.129 | 4 | 1.130 | Mass | 1.129 | 1.129 | 1.129 | 1.128 | 1.129 | 0.000 | -0.001 | 0.000 | 0.000 | 0.001 | -0.001
| 1DC3 | NORMAL TOWER | 3.899 | 4 | 15.597 | 4 | 15.399 | Mass | 15.597 | 15.597 | 15.597 | 15.451 | 15.597 | 0.190 | -0.196 | 0.000 | 0.000 | 0.145 | -0.145
| 1DC3M | +3 MTR EXTN | 1.026 | 1 | 1.026 | 1 | 1.015 | Mass | 1.026 | 1.026 | 1.026 | 1.017 | 1.026 | 0.009 | -0.010 | 0.000 | 0.000 | 0.010 | -0.010
| 1DC6M | +6 MTR EXTN | 1.828 | 1 | 1.828 | 1 | 1.813 | Mass | 1.828 | 1.828 | 1.828 | 1.810 | 1.828 | 0.015 | -0.018 | 0.000 | 0.000 | 0.018 | -0.018
| 1DD | +0. MTR EXTN. | 1.083 | 48 | 51.968 | 26 | 27.853 | Mass | 28.149 | 28.149 | 28.149 | 27.817 | 20.141 | 24.120 | -0.300 | 0.000 | 0.000 | 0.332 | 7.677
| 1DD18M | +18 MTR EXTN | 7.021 | 26 | 182.552 | 13 | 90.295 | Mass | 91.276 | 91.276 | 91.276 | 90.299 | 21.064 | 92.261 | -0.982 | 0.000 | 0.000 | 0.978 | 69.235
| 1DD2 | STUB | 0.351 | 12 | 4.218 | 11 | 3.856 | Mass | 3.866 | 3.866 | 3.866 | 3.855 | 3.793 | 0.364 | -0.011 | 0.000 | 0.000 | 0.011 | 0.062
| 1DD2A | STUB | 0.406 | 14 | 5.689 | 8 | 3.251 | Mass | 3.251 | 3.251 | 3.251 | 3.251 | 1.626 | 2.437 | 0.000 | 0.000 | 0.000 | 0.000 | 1.626
| 1DD3 | NORMAL TOWER | 5.077 | 48 | 243.719 | 26 | 130.516 | Mass | 132.014 | 132.014 | 132.014 | 126.697 | 96.432 | 113.203 | -1.496 | 0.000 | 0.000 | 5.317 | 30.265
| 1DD6M | +6 MTR EXTN | 2.118 | 3 | 6.354 | 3 | 6.277 | Mass | 6.354 | 6.354 | 6.354 | 6.274 | 6.354 | 0.080 | -0.081 | 0.000 | 0.000 | 0.080 | -0.080
| 1DD9M | +9 MTR EXTN | 3.029 | 10 | 30.289 | 6 | 17.954 | Mass | 18.174 | 18.174 | 18.174 | 17.955 | 9.087 | 12.335 | -0.219 | 0.000 | 0.000 | 0.219 | 8.868
| IS | NORMAL TOWER | 2.668 | 1 | 2.668 | 1 | 2.670 | Mass | 2.668 | 2.668 | 2.668 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.040 | 1 | 0.040 | Mass | 0.040 | 0.040 | 0.040 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| SC | NORMAL TOWER | 0.092 | 1 | 0.092 | 1 | 0.092 | Mass | 0.092 | 0.092 | 0.092 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 40.254 | 213 | 602.942 | 145 | 357.143 |  | 361.238 | 361.238 | 361.238 | 350.616 | 233.850 | 245.781 | -4.092 | 0.000 | 0.000 | 7.822 | 116.766
| Project Code : 840. |  | Client : SIKHA ELECTRIC STORES - VT840 | [11 empty] | Order Dt. : 27/01/2025
| 1DA2 | STUB | 0.142 | 22 | 3.128 | 20 | 2.843 | Mass | 2.844 | 2.844 | 2.844 | 2.844 | 2.844 | 0.284 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DB2 | STUB | 0.253 | 28 | 7.094 | 20 | 5.067 | Mass | 5.067 | 5.067 | 5.067 | 5.067 | 4.934 | 2.027 | 0.000 | 0.000 | 0.000 | 0.000 | 0.133
| 1DC2 | STUB | 0.282 | 13 | 3.671 | 9 | 2.543 | Mass | 2.541 | 2.541 | 2.541 | 2.541 | 2.541 | 1.129 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DD2 | STUB | 0.351 | 13 | 4.569 | 7 | 2.461 | Mass | 2.460 | 2.460 | 2.460 | 2.460 | 2.460 | 2.109 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DD2A | STUB | 0.406 | 2 | 0.813 |  |  | Mass
| IS | COLUMN | 0.478 | 1 | 0.478 | 1 | 0.478 | Mass | 0.478 | 0.478 | 0.478 | 0.478 | 0.478 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| SC | NORMAL TOWER | 0.073 | 1 | 0.073 | 1 | 0.073 | Mass | 0.073 | 0.073 | 0.073 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 1.986 | 80 | 19.826 | 58 | 13.465 |  | 13.463 | 13.463 | 13.463 | 13.390 | 13.257 | 5.549 | 0.000 | 0.000 | 0.000 | 0.000 | 0.133
| Project Code : 844 |  | Client : BHARAT BIJLEE LIMITED - VT844 | [11 empty] | Order Dt. : 28/09/2024
| IS | COLUMN | 1.189 | 1 | 1.189 |  |  | Mass
|  | Sub Total | 1.189 | 1 | 1.189
| Project Code : 847 |  | Client : TEXMACO RAIL & ENGINERING LTD - VT847 | [11 empty] | Order Dt. : 11/01/2025
| 3B03 | COLUMN | 0.973 | 3 | 2.920 | 3 | 2.910 | Mass | 2.920 | 2.920 | 2.920 | 2.914 | 2.471 | 0.016 | -0.010 | 0.000 | 0.000 | 0.007 | 0.443
| 3B04 | COLUMN | 1.525 | 3 | 4.575 | 3 | 4.561 | Mass | 4.575 | 4.575 | 4.575 | 4.565 | 3.579 | 0.016 | -0.010 | 0.000 | 0.000 | 0.010 | 0.986
| 3C05 | EQUIPMENT | 0.218 | 21 | 4.588 | 21 | 4.587 | Mass | 4.588 | 4.588 | 4.588 | 4.588 | 4.588 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3D02 | EQUIPMENT | 0.690 | 20 | 13.796 | 20 | 13.772 | Mass | 13.796 | 13.796 | 13.796 | 13.771 | 13.107 | 0.025 | -0.025 | 0.000 | 0.000 | 0.025 | 0.664
| 3G02 | COLUMN | 1.997 | 13 | 25.959 | 13 | 25.930 | Mass | 25.959 | 25.959 | 25.959 | 25.931 | 24.438 | 0.030 | -0.028 | 0.000 | 0.000 | 0.028 | 1.493
| 3G02B | BEAM | 1.129 | 9 | 10.157 | 9 | 10.132 | Mass | 10.157 | 10.157 | 10.157 | 10.131 | 8.981 | 0.024 | -0.025 | 0.000 | 0.000 | 0.025 | 1.150
| 3K02 | EQUIPMENT | 0.167 | 8 | 1.334 | 8 | 1.334 | Mass | 1.334 | 1.334 | 1.334 | 1.334 | 1.128 | 0.000 | 0.001 | 0.000 | 0.000 | 0.000 | 0.206
| 3L04 | EQUIPMENT | 0.130 | 18 | 2.344 | 18 | 2.349 | Mass | 2.344 | 2.344 | 2.344 | 2.347 | 1.181 | -0.003 | 0.003 | 0.000 | 0.000 | -0.003 | 1.166
| 3P02 | EQUIPMENT | 0.194 | 30 | 5.817 | 30 | 5.824 | Mass | 5.817 | 5.817 | 5.817 | 5.818 | 5.817 | -0.008 | 0.008 | 0.000 | 0.000 | 0.000 | 0.000
| 3V04 | EQUIPMENT | 0.229 | 6 | 1.373 | 6 | 1.371 | Mass | 1.373 | 1.373 | 1.373 | 1.368 | 0.410 | 0.008 | -0.005 | 0.000 | 0.000 | 0.005 | 0.958
| A | COLUMN | 0.350 | 1 | 0.350 | 1 | 0.350 | Mass | 0.350 | 0.350 | 0.350 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| AAGT | COLUMN | 5.282 | 8 | 42.258 | 8 | 42.157 | Mass | 42.258 | 42.258 | 42.258 | 42.170 | 39.092 | 0.116 | -0.105 | 0.000 | 0.000 | 0.087 | 3.078
| ABA | COLUMN | 2.238 | 5 | 11.188 | 5 | 11.269 | Mass | 11.188 | 11.188 | 11.188 | 11.267 | 9.280 | -0.066 | 0.080 | 0.000 | 0.000 | -0.080 | 1.987
| ABM | COLUMN | 2.381 | 10 | 23.812 | 10 | 23.992 | Mass | 23.812 | 23.812 | 23.812 | 23.985 | 21.496 | -0.166 | 0.173 | 0.000 | 0.000 | -0.173 | 2.489
| ACT | EQUIPMENT | 0.271 | 18 | 4.884 | 18 | 4.857 | Mass | 4.884 | 4.884 | 4.884 | 4.857 | 4.784 | 0.027 | -0.027 | 0.000 | 0.000 | 0.027 | 0.073
| AGB | BEAM | 1.186 | 14 | 16.599 | 14 | 16.565 | Mass | 16.599 | 16.599 | 16.599 | 16.563 | 14.623 | 0.035 | -0.036 | 0.000 | 0.000 | 0.036 | 1.940
| AGT | COLUMN | 2.987 | 13 | 38.835 | 13 | 38.803 | Mass | 38.835 | 38.835 | 38.835 | 38.801 | 35.306 | 0.049 | -0.034 | 0.000 | 0.000 | 0.034 | 3.495
| AITCH | EQUIPMENT | 2.056 | 23 | 47.297 | 23 | 46.926 | Mass | 47.297 | 47.297 | 47.297 | 46.926 | 46.697 | 0.372 | -0.372 | 0.000 | 0.000 | 0.372 | 0.229
| ALA | EQUIPMENT | 0.127 | 12 | 1.524 | 12 | 1.508 | Mass | 1.524 | 1.524 | 1.524 | 1.509 | 1.352 | 0.014 | -0.014 | 0.000 | 0.000 | 0.014 | 0.158
| API | EQUIPMENT | 0.204 | 51 | 10.379 | 51 | 10.396 | Mass | 10.379 | 10.379 | 10.379 | 10.386 | 9.700 | -0.020 | 0.018 | 0.000 | 0.000 | -0.008 | 0.687
| APT | EQUIPMENT | 0.271 | 12 | 3.256 | 12 | 3.237 | Mass | 3.256 | 3.256 | 3.256 | 3.238 | 3.019 | 0.019 | -0.018 | 0.000 | 0.000 | 0.018 | 0.219
|  | Sub Total | 24.605 | 298 | 273.245 | 298 | 272.830 |  | 273.245 | 273.245 | 273.245 | 272.469 | 251.050 | 0.488 | -0.428 | 0.000 | 0.000 | 0.426 | 21.419
| Project Code : 848 |  | Client : SIDDHARTHA ENGINEERING LIMITED - VT848 | [11 empty] | Order Dt. : 04/10/2024
| 2BPI | EQUIPMENT | 0.174 | 44 | 7.649 | 44 | 7.649 | Proto | 7.649 | 0.540 |  |  |  | 0.000 | 0.000 | 7.109 | 0.540
| 2CT | EQUIPMENT | 0.277 | 18 | 4.985 | 18 | 4.984 | Proto | 4.985 |  |  |  |  | 0.000 | 0.000 | 4.985
| 2HLA | EQUIPMENT | 0.301 | 6 | 1.804 | 6 | 1.804 | Proto | 1.804 | 0.063 |  |  |  | 0.000 | 0.000 | 1.741 | 0.063
| 2ISO | EQUIPMENT | 1.606 | 2 | 3.212 | 2 | 3.212 | Proto | 3.212 | 0.046 | 0.011 |  |  | 0.000 | 0.000 | 3.166 | 0.036
| 2ISOW | EQUIPMENT | 1.585 | 22 | 34.863 | 22 | 34.861 | Proto | 34.863 | 2.269 |  |  |  | 0.000 | 0.000 | 32.594 | 2.269
| 2IVT | EQUIPMENT | 0.249 | 12 | 2.983 |  |  | Pre
| 2P1S | COLUMN | 4.040 | 34 | 137.347 | 25 | 100.854 | Mass | 100.991 | 100.991 | 100.991 | 100.858 | 91.564 | 36.490 | -0.136 | 0.000 | 0.000 | 0.133 | 9.293
| 2Q1 | BEAM | 1.601 | 20 | 32.030 | 8 | 12.746 | Mass | 12.812 | 12.812 | 12.812 | 12.745 | 11.120 | 19.283 | -0.067 | 0.000 | 0.000 | 0.067 | 1.625
| 2Q3 | BEAM | 2.465 | 12 | 29.577 | 10 | 24.465 | Mass | 24.648 | 24.648 | 24.648 | 24.464 | 23.212 | 5.114 | -0.184 | 0.000 | 0.000 | 0.184 | 1.252
| 2SA | EQUIPMENT | 0.206 | 6 | 1.236 | 6 | 1.236 | Proto | 1.236 | 0.063 |  |  |  | 0.000 | 0.000 | 1.174 | 0.063
| 3BPI | EQUIPMENT | 0.184 | 22 | 4.054 | 22 | 4.053 | Proto | 4.054 | 0.264 |  |  |  | 0.000 | 0.000 | 3.790 | 0.264
| 3CTS | EQUIPMENT | 0.162 | 15 | 2.430 | 15 | 2.429 | Proto | 2.430 |  |  |  |  | 0.000 | 0.000 | 2.430
| 3G4 | BEAM | 0.287 | 10 | 2.871 | 10 | 2.848 | Mass | 2.871 | 2.871 | 2.871 | 2.871 | 2.111 | 0.020 | -0.020 | 0.000 | 0.000 | 0.000 | 0.760
| 3G4X | BEAM | 0.287 | 4 | 1.148 | 4 | 1.141 | Mass | 1.148 | 1.148 | 1.148 | 1.148 | 0.701 | 0.009 | -0.008 | 0.000 | 0.000 | 0.000 | 0.448
| 3G6 | BEAM | 0.361 | 4 | 1.442 | 4 | 1.433 | Mass | 1.442 | 1.442 | 1.442 | 1.443 | 1.189 | 0.013 | -0.011 | 0.000 | 0.000 | 0.000 | 0.254
| 3HGF | EQUIPMENT | 0.453 | 2 | 0.905 |  |  | Proto
| 3ISO | EQUIPMENT | 0.776 | 4 | 3.106 |  |  | Proto
| 3ISOW | EQUIPMENT | 0.757 | 16 | 12.108 |  |  | Proto
| 3IVTS | EQUIPMENT | 0.160 | 3 | 0.479 | 3 | 0.478 | Proto | 0.479 |  |  |  |  | 0.000 | 0.000 | 0.479
| 3SA | EQUIPMENT | 0.187 | 6 | 1.124 | 6 | 1.124 | Proto | 1.124 | 0.063 |  |  |  | 0.000 | 0.000 | 1.062 | 0.063
| 3T8S | NORMAL TOWER | 0.677 | 11 | 7.444 | 11 | 7.426 | Mass | 7.444 | 7.444 | 7.444 | 7.451 | 3.748 | 0.026 | -0.019 | 0.000 | 0.000 | -0.007 | 3.703
| 3T9S | NORMAL TOWER | 0.506 | 14 | 7.090 | 14 | 7.081 | Mass | 7.090 | 7.090 | 7.090 | 7.096 | 4.730 | 0.010 | -0.009 | 0.000 | 0.000 | -0.007 | 2.366
| IS | COLUMN | 0.208 | 1 | 0.208 | 1 | 0.209 | Mass | 0.208 | 0.208 | 0.208 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.350 | 1 | 0.351 | Mass | 0.350 | 0.349 | 0.349 |  |  | 0.000 | 0.000 | 0.001 | 0.000
|  | Sub Total | 17.859 | 289 | 300.445 | 232 | 220.384 |  | 220.842 | 162.311 | 159.014 | 158.076 | 138.375 | 60.965 | -0.455 | 58.531 | 3.297 | 0.370 | 19.701
| Project Code : 849 |  | Client : POWER TECH INFRA - VT849 | [11 empty] | Order Dt. : 05/10/2024
| 2DD6M | +6 MTR EXTN | 5.215 | 1 | 5.215 |  |  | Pre
| 2NMD2 | STUB | 2.621 | 1 | 2.621 |  |  | Pre
| 2NMD3M | +3 MTR EXTN | 2.699 | 1 | 2.699 |  |  | Pre
|  | Sub Total | 10.535 | 3 | 10.535
| Project Code : 850 |  | Client : ABHISEK CONTECH (INDIA) PVT. LTD. -VT850 | [11 empty] | Order Dt. : 05/10/2024
| MA2 | STUB | 0.870 | 2 | 1.741 | 2 | 1.737 | Proto | 1.741 | 1.741 | 1.741 | 1.741 | 1.741 | 0.000 | -0.002 | 0.000 | 0.000 | 0.000 | 0.000
| MA3 | NORMAL TOWER | 14.788 | 10 | 147.881 | 1 | 14.716 | Proto | 14.786 | 14.786 | 14.786 | 14.719 | 14.597 | 0.000 | -0.067 | 0.000 | 0.000 | 0.067 | 0.122
| MA3M | +3 MTR EXTN | 1.746 | 7 | 12.224 | 1 | 1.736 | Proto | 1.746 | 1.746 | 1.746 | 1.737 | 0.387 | 0.000 | -0.009 | 0.000 | 0.000 | 0.009 | 1.350
| MB2 | STUB | 1.310 | 1 | 1.310 | 1 | 1.309 | Proto | 1.310 | 1.310 | 1.310 | 1.310 | 1.310 | 0.000 | -0.001 | 0.000 | 0.000 | 0.000 | 0.000
| MB3 | NORMAL TOWER | 23.289 | 8 | 186.314 | 1 | 23.264 | Proto | 23.289 | 23.289 | 23.289 | 23.261 | 19.545 | 0.000 | -0.028 | 0.000 | 0.000 | 0.028 | 3.716
| MB3M | +3 MTR EXTN | 2.857 | 2 | 5.715 | 2 | 5.702 | Proto | 5.715 | 5.715 | 5.715 | 5.715 | 5.544 | 0.000 | -0.010 | 0.000 | 0.000 | 0.000 | 0.171
| MB6M | +6 MTR EXTN | 4.831 | 3 | 14.493 | 3 | 14.454 | Proto | 14.493 | 14.493 | 14.493 | 14.493 | 14.375 | 0.000 | -0.041 | 0.000 | 0.000 | 0.000 | 0.118
| MC15M | +15 MTR EXTN | 16.247 | 4 | 64.988 | 1 | 16.161 | Proto | 16.247 | 16.247 | 16.247 | 16.155 | 16.206 | 0.000 | -0.092 | 0.000 | 0.000 | 0.092 | -0.052
| MC3 | NORMAL TOWER | 29.560 | 9 | 266.043 | 1 | 29.445 | Proto | 29.560 | 29.560 | 29.560 | 29.450 | 29.299 | 0.000 | -0.110 | 0.000 | 0.000 | 0.110 | 0.151
| MC3M | +3 MTR EXTN | 3.658 | 1 | 3.658 | 1 | 3.642 | Proto | 3.658 | 3.658 | 3.658 | 3.658 | 3.658 | 0.000 | -0.017 | 0.000 | 0.000 | 0.000 | 0.000
| MC6M | +6 MTR EXTN | 6.178 | 3 | 18.534 | 3 | 18.436 | Proto | 18.534 | 18.534 | 18.534 | 18.534 | 18.066 | 0.000 | -0.100 | 0.000 | 0.000 | 0.000 | 0.468
| OA3 | NORMAL TOWER | 4.334 | 2 | 8.667 | 2 | 8.667 | Mass | 8.667 | 8.667 | 8.667 | 8.667 | 8.552 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.115
| OA3M | +3 MTR EXTN | 0.759 | 2 | 1.518 | 2 | 1.517 | Mass | 1.518 | 1.518 | 1.518 | 1.518 | 1.518 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| OB2 | STUB | 0.438 | 1 | 0.438 | 1 | 0.438 | Mass | 0.438 | 0.438 | 0.438 | 0.438 | 0.438 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| OB3 | NORMAL TOWER | 6.481 | 1 | 6.481 | 1 | 6.481 | Mass | 6.481 | 6.481 | 6.481 | 6.481 | 6.147 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.334
| OB6M | +6 MTR EXTN | 2.337 | 1 | 2.337 |  |  | Mass
|  | Sub Total | 119.684 | 57 | 742.342 | 23 | 147.705 |  | 148.183 | 148.183 | 148.183 | 147.876 | 141.384 | 0.000 | -0.479 | 0.000 | 0.000 | 0.307 | 6.492
| Project Code : 851 |  | Client : SIDDHARTHA ENGINEERING LIMITED - VT851 | [11 empty] | Order Dt. : 10/10/2024
| OC2 | STUB | 0.776 | 10 | 7.764 | 4 | 3.106 | Mass | 3.106 | 3.106 | 3.106 | 3.106 | 3.106 | 4.658 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| OC3 | NORMAL TOWER | 9.190 | 10 | 91.903 | 4 | 36.761 | Mass | [5 empty] | 55.141 | 36.761
| OC3M | +3 MTR EXTN | 1.488 | 1 | 1.488 | 1 | 1.490 | Mass | [5 empty] | 0.000 | 1.488
|  | Sub Total | 11.455 | 21 | 101.155 | 9 | 41.357 |  | 3.106 | 3.106 | 3.106 | 3.106 | 3.106 | 59.799 | 38.249 | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : 862 |  | Client : MEGHA ENGINEERING & INFRASTRUCTURES LTD - VT862 | [11 empty] | Order Dt. : 18/12/2024
| B02 | STUB | 0.269 | 3 | 0.808 | 3 | 0.808 | Proto | 0.808 | 0.808 | 0.808 | 0.808 | 0.808 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| B03 | NORMAL TOWER | 4.500 | 3 | 13.499 | 3 | 13.493 | Proto | 13.289 | 13.289 | 10.553 |  |  | 0.000 | 0.210 | 0.000 | 2.736
| B03M | +3 MTR EXTN | 0.936 | 1 | 0.936 | 1 | 0.937 | Proto | 0.936 | 0.936 | 0.625 |  |  | 0.000 | 0.000 | 0.000 | 0.312
| B06M | +6 MTR EXTN | 1.649 | 1 | 1.649 | 1 | 1.646 | Proto | 1.649 | 1.604 | 1.428 |  |  | 0.000 | 0.000 | 0.045 | 0.176
| B302 | STUB | 0.440 | 2 | 0.880 | 2 | 0.881 | Proto | 0.880 | 0.880 | 0.880 | 0.880 | 0.880 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| B303 | NORMAL TOWER | 7.304 | 2 | 14.608 | 2 | 14.612 | Proto | 14.608 | 14.608 | 11.024 |  |  | 0.000 | 0.000 | 0.000 | 3.584
| B6010M | +10M Body Extn | 7.993 | 3 | 23.979 | 3 | 23.966 | Proto | 23.979 | 23.668 | 21.499 |  |  | 0.000 | 0.000 | 0.310 | 2.169
| B602 | STUB | 0.582 | 6 | 3.494 | 6 | 3.495 | Proto | 3.494 | 3.494 | 3.494 | 3.494 | 3.494 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| B603 | NORMAL TOWER | 8.963 | 6 | 53.776 | 6 | 53.777 | Proto | 52.322 | 52.322 | 47.393 |  |  | 0.000 | 1.454 | 0.000 | 4.929
| B606M | +6 MTR EXTN | 4.804 | 1 | 4.804 | 1 | 4.803 | Proto | 4.700 | 4.654 | 4.075 |  |  | 0.000 | 0.103 | 0.046 | 0.579
| E602 | STUB | 0.554 | 6 | 3.326 | 6 | 3.327 | Proto | 3.326 | 3.326 | 3.326 | 3.326 | 3.326 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| E603 | NORMAL TOWER | 6.234 | 6 | 37.403 | 6 | 37.393 | Proto | 37.403 | 37.403 | 34.393 |  |  | 0.000 | 0.000 | 0.000 | 3.010
| E603M | +3 MTR EXTN | 1.314 | 2 | 2.627 | 2 | 2.628 | Proto | 2.627 | 2.396 | 1.542 |  |  | 0.000 | 0.000 | 0.231 | 0.855
| E606M | +6 MTR EXTN | 2.813 | 4 | 11.251 | 4 | 11.255 | Proto | 11.251 | 11.171 | 9.550 |  |  | 0.000 | 0.000 | 0.080 | 1.621
| MC602 | STUB | 1.464 | 1 | 1.464 | 1 | 1.464 | Proto | 1.464 | 1.464 | 1.464 | 1.464 | 1.464 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| MC603 | NORMAL TOWER | 22.792 | 1 | 22.792 | 1 | 22.810 | Proto | 22.792 | 0.648 | 0.349 |  |  | 0.000 | 0.000 | 22.144 | 0.299
| NBB9010M | +10M Body Extn | 10.317 | 1 | 10.317 | 1 | 10.318 | Proto | 10.317 | 6.103 | 1.002 |  |  | 0.000 | 0.000 | 4.214 | 5.102
| NBB902 | STUB | 3.871 | 2 | 7.741 | 2 | 7.742 | Proto | 7.741 | 7.741 | 7.741 | 7.741 | 7.741 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| NBB902. | +6 MTR EXTN | 3.871 | 1 | 3.871 |  |  | Pre
| NBB902A | STUB | 3.873 | 1 | 3.873 | 1 | 3.873 | Proto | 3.873 | 3.873 | 3.873 | 3.873 | 3.873 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| NBB902B | STUB | 3.281 | 1 | 3.281 | 1 | 3.280 | Proto | 3.281 | 3.281 | 3.281 | 3.281 | 3.281 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| NBB903 | NORMAL TOWER | 15.778 | 3 | 47.334 | 3 | 47.331 | Proto | 47.334 | 47.334 | 29.420 |  |  | 0.000 | -0.001 | 0.000 | 17.915
| NBB904 | NORMAL TOWER | 11.767 | 1 | 11.767 | 1 | 11.773 | Proto | 11.767 | 0.186 | 0.129 |  |  | 0.000 | 0.000 | 11.581 | 0.057
| NBB906M | +6 MTR EXTN | 6.449 | 2 | 12.897 | 2 | 12.897 | Proto | 12.897 | 11.502 | 6.969 |  |  | 0.000 | 0.000 | 1.395 | 4.533
|  | Sub Total | 131.818 | 60 | 298.377 | 59 | 294.509 |  | 292.741 | 252.694 | 204.818 | 24.868 | 24.868 | 0.000 | 1.766 | 40.047 | 47.876 | 0.000 | 0.000
| Project Code : 864 |  | Client : PRAKASH ELECTRICAL ENGINEERING CORPORATION. - VT864 | [11 empty] | Order Dt. : 09/12/2024
| IS | COLUMN | 0.859 | 1 | 0.859 |  |  | Mass
|  | Sub Total | 0.859 | 1 | 0.859
| Project Code : 866 |  | Client : ASIATIC TRADERS - VT866 | [11 empty] | Order Dt. : 23/12/2024
| E01 | STUB | 0.500 | 1 | 0.500 |  |  | Pre
| E010M | +10M Body Extn | 2.699 | 1 | 2.699 |  |  | Pre
| E02 | STUB | 0.225 | 1 | 0.225 |  |  | Pre
| E03 | NORMAL TOWER | 3.320 | 1 | 3.320 |  |  | Pre
| E03M | +3 MTR EXTN | 0.726 | 1 | 0.726 |  |  | Pre
| E06M | +6 MTR EXTN | 1.601 | 1 | 1.601 |  |  | Pre
| E301 | STUB | 1.012 | 1 | 1.012 |  |  | Pre
| E3010M | +10M Body Extn | 3.818 | 1 | 3.818 |  |  | Pre
| E302 | STUB | 0.371 | 1 | 0.371 |  |  | Pre
| E303 | NORMAL TOWER | 4.974 | 1 | 4.974 |  |  | Pre
| E303M | +3 MTR EXTN | 1.040 | 1 | 1.040 |  |  | Pre
| E306M | +6 MTR EXTN | 2.229 | 1 | 2.229 |  |  | Pre
| E601 | STUB | 1.163 | 1 | 1.163 |  |  | Pre
| E6010M | +10M Body Extn | 4.805 | 1 | 4.805 |  |  | Pre
| E602 | STUB | 0.555 | 1 | 0.555 |  |  | Pre
| E603 | NORMAL TOWER | 6.189 | 1 | 6.189 |  |  | Pre
| E603M | +3 MTR EXTN | 1.300 | 1 | 1.300 |  |  | Pre
| E606M | +6 MTR EXTN | 2.784 | 1 | 2.784 |  |  | Pre
|  | Sub Total | 39.311 | 18 | 39.311
| Project Code : 866. |  | Client : SIEMENS ENERGY IN LTD - VT866 | [11 empty] | Order Dt. : 17/11/2025
| 1ACOMB | EQUIPMENT | 0.419 | 6 | 2.516 | 6 | 2.517 | Proto | 2.516 | 2.189 | 2.174 | 2.516 | 1.029 | 0.000 | 0.000 | 0.328 | 0.015 | -0.342 | 1.487
| 1BCOMB | EQUIPMENT | 0.508 | 6 | 3.045 | 6 | 3.042 | Proto | 3.045 | 2.751 | 2.734 | 3.045 | 0.973 | 0.000 | 0.000 | 0.294 | 0.017 | -0.311 | 2.072
| 1COMB | EQUIPMENT | 0.488 | 6 | 2.930 | 6 | 2.929 | Proto | 2.930 | 2.599 | 2.578 | 2.930 | 0.974 | 0.000 | 0.000 | 0.330 | 0.021 | -0.352 | 1.956
| 2CTU | EQUIPMENT | 0.362 | 6 | 2.172 | 6 | 2.175 | Proto | 2.172 | 1.720 | 1.693 | 2.172 | 0.678 | 0.000 | 0.000 | 0.452 | 0.027 | -0.480 | 1.494
| 2HLA | EQUIPMENT | 0.257 | 6 | 1.544 | 6 | 1.544 | Proto | 1.544 | 1.544 | 1.538 | 1.544 | 0.508 | 0.000 | 0.000 | 0.000 | 0.005 | -0.005 | 1.035
| 3COM2 | EQUIPMENT | 0.197 | 6 | 1.183 | 6 | 1.181 | Proto | 1.183 | 1.183 | 1.141 | 1.183 | 0.464 | 0.000 | 0.000 | 0.000 | 0.042 | -0.042 | 0.719
| 3COM3 | EQUIPMENT | 0.313 | 6 | 1.880 | 6 | 1.878 | Proto | 1.880 | 1.880 | 1.860 | 1.880 | 0.862 | 0.000 | 0.000 | 0.000 | 0.020 | -0.020 | 1.019
| 3CT | EQUIPMENT | 0.128 | 4 | 0.510 | 4 | 0.505 | Proto | 0.510 | 0.510 | 0.502 | 0.510 | 0.101 | 0.000 | 0.000 | 0.000 | 0.009 | -0.009 | 0.409
| 3CTJ | EQUIPMENT | 0.140 | 2 | 0.281 | 2 | 0.277 | Proto | 0.281 | 0.281 | 0.277 | 0.281 | 0.102 | 0.000 | 0.000 | 0.000 | 0.004 | -0.004 | 0.179
| 3ISO | EQUIPMENT | 0.282 | 4 | 1.127 | 4 | 1.122 | Proto | 1.127 | 1.127 | 1.112 | 1.127 | 0.762 | 0.000 | 0.000 | 0.000 | 0.015 | -0.015 | 0.366
| 3KIT | EQUIPMENT | 0.334 | 2 | 0.667 | 2 | 0.671 | Proto | 0.667 | 0.667 | 0.667 | 0.667 | 0.432 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.236
| 3LA | EQUIPMENT | 0.138 | 6 | 0.827 | 6 | 0.824 | Proto | 0.827 |  |  | 0.827 |  | 0.000 | 0.000 | 0.827 |  | -0.827 | 0.827
| B | COLUMN | 4.513 | 1 | 4.513 |  |  | Mass
| IS | COLUMN | 3.937 | 1 | 3.937 | 1 | 3.934 | Mass | 3.937 |  |  |  |  | 0.000 | 0.000 | 3.937
| LM | COLUMN | 8.851 | 4 | 35.405 | 4 | 35.397 | Proto | 35.405 | 34.763 | 34.230 | 35.405 | 21.910 | 0.000 | 0.000 | 0.642 | 0.533 | -1.176 | 13.495
| R | COLUMN | 2.452 | 1 | 2.452 |  |  | Mass
|  | Sub Total | 23.320 | 67 | 64.989 | 65 | 57.996 |  | 58.026 | 51.214 | 50.506 | 54.089 | 28.795 | 0.000 | 0.000 | 6.812 | 0.709 | -3.583 | 25.294
| Project Code : 867 |  | Client : GVPR ENGINEERS LIMITED - VT867 | [11 empty] | Order Dt. : 24/12/2024
| IS | COLUMN | 0.735 | 1 | 0.735 |  |  | Mass
|  | Sub Total | 0.735 | 1 | 0.735
| Project Code : 869 |  | Client : STELMEC LIMITED - VT869 | [11 empty] | Order Dt. : 11/01/2025
| 1DS2 | STUB | 0.303 | 6 | 1.820 | 6 | 1.820 | Mass | 1.820 | 1.820 | 1.820 | 1.820 | 1.820 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DS3 | NORMAL TOWER | 4.602 | 6 | 27.615 | 6 | 27.616 | Mass | 27.615 | 27.615 | 27.615 | 27.615 | 27.612 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.003
| 1DS3M | +3 MTR EXTN | 1.243 | 3 | 3.730 | 3 | 3.728 | Mass | 3.730 | 3.730 | 3.730 | 3.730 | 3.730 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| IS | COLUMN | 0.862 | 1 | 0.862 | 1 | 0.862 | Mass | 0.862 |  |  |  |  | 0.000 | 0.000 | 0.862
| MAN2 | STUB | 0.739 | 3 | 2.216 | 2 | 1.477 | Mass | 1.477 | 1.477 | 1.477 | 1.477 | 0.796 | 0.739 | 0.000 | 0.000 | 0.000 | 0.000 | 0.681
| MAN2A | STUB | 0.809 | 1 | 0.809 |  |  | Mass
| MAN3 | NORMAL TOWER | 10.540 | 4 | 42.161 | 2 | 21.079 | Mass | 21.080 | 21.080 | 21.080 | 21.080 | 21.080 | 21.079 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| MAN3M | +3 MTR EXTN | 2.059 | 1 | 2.059 |  |  | Mass
| MAN6M | +6 MTR EXTN | 2.059 | 4 | 8.236 | 2 | 4.122 | Mass | 4.118 | 4.118 | 4.118 | 4.118 | 0.016 | 4.122 | 0.000 | 0.000 | 0.000 | 0.000 | 4.102
| MAN9M | +9 MTR EXTN | 3.274 | 1 | 3.274 | 1 | 3.277 | Proto | 3.274 | 3.059 |  |  |  | 0.000 | 0.000 | 0.215 | 3.059
| MCN | COLUMN | 3.208 | 1 | 3.208 | 1 | 3.210 | Mass | 3.208 | 3.208 | 3.208 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| MCN2 | STUB | 2.379 | 17 | 40.440 | 6 | 14.862 | Proto | 14.864 | 14.273 | 14.273 | 14.862 | 14.273 | 0.000 | -0.003 | 0.591 | 0.000 | -0.589 | 0.589
[6 empty] | 11 | 25.577 | Mass | 25.576 | 24.985 | 24.985 | 25.576 | 24.689 | 12.484 | 0.000 | 0.591 | 0.000 | -0.591 | 0.887
| MCN3 | NORMAL TOWER | 25.675 | 17 | 436.471 | 13 | 333.783 | Mass | 333.772 | 333.772 | 333.509 | 333.772 | 333.181 | 102.699 | 0.000 | 0.000 | 0.263 | -0.263 | 0.591
| MCN3M | +3 MTR EXTN | 2.940 | 8 | 23.519 | 6 | 17.644 | Mass | 17.640 | 17.368 | 17.368 | 17.640 | 14.781 | 5.879 | 0.000 | 0.272 | 0.000 | -0.272 | 2.858
| MCN6M | +6 MTR EXTN | 5.860 | 7 | 41.021 | 6 | 35.460 | Mass | 35.161 | 35.161 | 35.161 | 35.451 | 35.161 | 5.574 | 0.290 | 0.000 | 0.000 | -0.290 | 0.290
| MCN9M | +9 MTR EXTN | 8.854 | 1 | 8.854 |  |  | Mass
| MDN2 | STUB | 3.013 | 7 | 21.092 | 5 | 15.063 | Mass | 15.066 | 15.066 | 15.066 | 15.064 | 15.066 | 6.029 | -0.002 | 0.000 | 0.000 | 0.002 | -0.002
| MDN3 | NORMAL TOWER | 32.529 | 5 | 162.645 | 2 | 65.052 | Mass | 65.058 | 65.058 | 65.058 | 65.058 | 65.058 | 97.616 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| MDN3M | +3 MTR EXTN | 3.625 | 1 | 3.625 |  |  | Mass
| MDN6M | +6 MTR EXTN | 7.247 | 3 | 21.740 | 2 | 14.486 | Mass | 14.493 | 14.493 | 14.493 | 14.493 | 14.493 | 7.245 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| ND2 | STUB | 0.494 | 2 | 0.987 | 2 | 0.987 | Proto | 0.987 | 0.987 | 0.987 | 0.987 | 0.987 | 0.000 | -0.001 | 0.000 | 0.000 | 0.000 | 0.000
| ND3 | NORMAL TOWER | 6.301 | 2 | 12.602 | 2 | 12.594 | Proto | 12.602 | 12.602 | 12.531 | 12.602 | 0.000 | 0.000 | -0.003 | 0.000 | 0.071 | -0.071 | 12.602
| ND3M | +3 MTR EXTN | 1.223 | 1 | 1.223 |  |  | Pre
| ND6M | +6 MTR EXTN | 2.549 | 2 | 5.097 | 2 | 5.092 | Proto | 5.097 | 5.085 | 5.008 | 5.097 | 0.001 | 0.000 | -0.005 | 0.013 | 0.077 | -0.089 | 5.096
| S | NORMAL TOWER | 0.180 | 1 | 0.180 | 1 | 0.181 | Mass | 0.180 | 0.007 |  |  |  | 0.000 | 0.000 | 0.173 | 0.007
| SC | NORMAL TOWER | 0.052 | 1 | 0.052 | 1 | 0.051 | Mass | 0.052 | 0.029 | 0.029 |  |  | 0.000 | 0.000 | 0.023 | 0.000
| SR | COLUMN | 5.653 | 1 | 5.653 |  |  | Mass
|  | Sub Total | 140.650 | 107 | 881.191 | 83 | 608.023 |  | 607.733 | 604.994 | 601.517 | 600.443 | 572.747 | 263.466 | 0.277 | 2.739 | 3.477 | -2.162 | 27.696
| Project Code : 870 |  | Client : STELMEC LIMITED - VT870 | [11 empty] | Order Dt. : 11/01/2025
| 2AB | BEAM | 0.880 | 4 | 3.520 | 4 | 3.520 | Mass | 3.520 | 3.520 | 3.520 | 3.520 | 3.520 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2AG | COLUMN | 1.956 | 5 | 9.782 | 5 | 9.787 | Mass | 9.782 | 9.782 | 9.782 | 9.782 | 9.782 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2AP | PEAK | 0.080 | 5 | 0.399 | 5 | 0.400 | Mass | 0.399 | 0.399 | 0.399 | 0.399 | 0.399 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2CCB | EQUIPMENT | 0.148 | 8 | 1.180 | 8 | 1.180 | Mass | 1.180 | 1.180 | 1.180 | 1.180 | 1.180 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2LAB | EQUIPMENT | 0.163 | 19 | 3.105 | 19 | 3.106 | Mass | 3.105 | 3.105 | 3.105 | 3.105 | 3.105 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2WTB | EQUIPMENT | 0.304 | 8 | 2.432 | 8 | 2.431 | Mass | 2.432 | 2.432 | 2.432 | 2.432 | 2.432 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3ISOD | EQUIPMENT | 0.345 | 7 | 2.418 | 6 | 2.068 | Mass | 2.073 | 2.073 | 2.073 | 2.073 | 2.060 | 0.346 | 0.000 | 0.000 | 0.000 | 0.000 | 0.013
| 3MCT | EQUIPMENT | 0.237 | 1 | 0.237 | 1 | 0.238 | Mass | 0.237 | 0.237 | 0.237 | 0.237 | 0.205 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.032
| 3MPT | EQUIPMENT | 0.243 | 3 | 0.730 | 3 | 0.730 | Mass | 0.730 | 0.730 | 0.730 | 0.730 | 0.716 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.014
| 4B1MS | BEAM | 4.186 | 8 | 33.488 | 8 | 33.477 | Mass | 33.488 | 33.488 | 33.488 | 33.488 | 33.488 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4B2 | BEAM | 1.554 | 3 | 4.661 | 3 | 4.663 | Mass | 4.661 | 4.661 | 4.661 | 4.661 | 4.661 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4B3 | BEAM | 3.811 | 6 | 22.864 | 6 | 22.865 | Mass | 22.864 | 22.864 | 22.864 | 22.864 | 22.864 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4BPI | EQUIPMENT | 0.256 | 20 | 5.117 | 20 | 5.116 | Mass | 5.117 | 5.117 | 5.117 | 5.117 | 4.870 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.246
| 4CVT | EQUIPMENT | 0.214 | 12 | 2.566 | 12 | 2.567 | Mass | 2.566 | 2.566 | 2.536 | 2.566 | 2.566 | 0.000 | 0.000 | 0.000 | 0.031 | -0.031 | 0.000
| 4ISO | EQUIPMENT | 1.532 | 2 | 3.064 | 2 | 3.068 | Mass | 3.064 | 3.064 | 3.064 | 3.064 | 3.061 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.003
| 4LA | EQUIPMENT | 0.225 | 28 | 6.300 | 28 | 6.300 | Mass | 6.300 | 6.300 | 6.300 | 6.300 | 6.203 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.097
| 4T1 | NORMAL TOWER | 3.844 | 14 | 53.814 | 14 | 53.811 | Mass | 53.814 | 53.814 | 53.814 | 53.814 | 53.814 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4T3 | NORMAL TOWER | 5.867 | 6 | 35.203 | 6 | 35.200 | Mass | 35.203 | 35.203 | 35.203 | 35.203 | 35.203 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4T5 | NORMAL TOWER | 8.554 | 3 | 25.661 | 3 | 25.669 | Mass | 25.661 | 25.661 | 25.661 | 25.661 | 25.661 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4TP | COLUMN | 0.301 | 23 | 6.924 | 23 | 6.923 | Mass | 6.924 | 6.924 | 6.924 | 6.924 | 6.924 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4WT | EQUIPMENT | 0.307 | 8 | 2.455 | 8 | 2.455 | Mass | 2.455 | 2.455 | 2.455 | 2.455 | 2.455 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| BPIC | EQUIPMENT | 0.115 | 16 | 1.834 | 16 | 1.834 | Mass | 1.834 | 1.834 | 1.834 | 1.834 | 1.834 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| BPID | EQUIPMENT | 0.140 | 14 | 1.964 | 14 | 1.966 | Mass | 1.964 | 1.964 | 1.964 | 1.964 | 1.964 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| BPID2 | EQUIPMENT | 0.177 | 10 | 1.772 | 10 | 1.777 | Mass | 1.772 | 1.772 | 1.772 | 1.772 | 1.768 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.004
| BPID3 | EQUIPMENT | 0.140 | 2 | 0.280 | 2 | 0.280 | Mass | 0.280 | 0.280 | 0.280 | 0.280 | 0.232 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.048
| CCC | EQUIPMENT | 0.109 | 8 | 0.871 | 8 | 0.870 | Mass | 0.871 | 0.871 | 0.871 | 0.871 | 0.871 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| CTC | EQUIPMENT | 0.122 | 12 | 1.458 | 12 | 1.459 | Mass | 1.458 | 1.458 | 1.458 | 1.458 | 1.458 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| FD | BEAM | 0.502 | 2 | 1.005 | 2 | 0.999 | Mass | 1.005 | 1.005 | 1.005 | 1.005 | 1.005 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| FE | BEAM | 0.465 | 4 | 1.860 | 4 | 1.856 | Mass | 1.860 | 1.860 | 1.860 | 1.860 | 1.860 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| FG | NORMAL TOWER | 1.060 | 6 | 6.359 | 6 | 6.359 | Mass | 6.359 | 6.359 | 6.359 | 6.359 | 6.359 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| FH | NORMAL TOWER | 0.540 | 4 | 2.159 | 4 | 2.160 | Mass | 2.159 | 2.159 | 2.159 | 2.159 | 2.159 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| FP | PEAK | 0.069 | 10 | 0.694 | 10 | 0.694 | Mass | 0.694 | 0.694 | 0.694 | 0.694 | 0.694 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| HA | BEAM | 0.250 | 3 | 0.749 | 3 | 0.744 | Mass | 0.749 | 0.749 | 0.749 | 0.749 | 0.749 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| HGF | EQUIPMENT | 0.197 | 2 | 0.394 | 2 | 0.394 | Mass | 0.394 | 0.394 | 0.394 | 0.394 | 0.392 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.002
| HH | NORMAL TOWER | 0.377 | 6 | 2.264 | 6 | 2.263 | Mass | 2.264 | 2.264 | 2.264 | 2.264 | 2.264 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| HP | PEAK | 0.036 | 6 | 0.217 | 6 | 0.217 | Mass | 0.217 | 0.217 | 0.217 | 0.217 | 0.217 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| IS | COLUMN | 3.484 | 1 | 3.484 | 1 | 3.484 | Mass | 3.484 | 3.484 | 3.484 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.034 | 1 | 0.035 | Mass | 0.034 | 0.034 | 0.034 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.044 | 1 | 0.045 | Mass | 0.044 | 0.044 | 0.044 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.944 | 1 | 0.943 | Mass | 0.944 | 0.944 | 0.944 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| ISOC | EQUIPMENT | 0.579 | 5 | 2.896 | 4 | 2.318 | Mass | 2.317 | 2.299 | 2.299 | 2.317 | 2.317 | 0.578 | 0.000 | 0.018 | 0.000 | -0.018 | 0.000
| ISOCW | EQUIPMENT | 0.554 | 4 | 2.214 | 4 | 2.214 | Mass | 2.214 | 2.214 | 2.214 | 2.214 | 2.214 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| LAC | EQUIPMENT | 0.117 | 13 | 1.516 | 13 | 1.517 | Mass | 1.516 | 1.516 | 1.516 | 1.516 | 1.430 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.086
| LAD | EQUIPMENT | 0.223 | 8 | 1.783 | 7 | 1.558 | Mass | 1.560 | 1.560 | 1.560 | 1.560 | 1.560 | 0.223 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| LCLM | NORMAL TOWER | 2.509 | 8 | 20.075 | 8 | 20.076 | Mass | 20.075 | 14.027 | 11.362 |  |  | 0.000 | 0.000 | 6.048 | 2.666
| NCT | EQUIPMENT | 0.126 | 3 | 0.379 | 3 | 0.381 | Mass | 0.379 | 0.379 | 0.379 | 0.379 | 0.366 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.014
| SC | NORMAL TOWER | 0.007 | 1 | 0.007 | 1 | 0.007 | Mass | 0.007 | 0.007 |  |  |  | 0.000 | 0.000 | 0.000 | 0.007
| WTC | EQUIPMENT | 0.238 | 8 | 1.905 | 8 | 1.903 | Mass | 1.905 | 1.905 | 1.905 | 1.905 | 1.905 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 48.165 | 352 | 285.081 | 349 | 283.927 |  | 283.933 | 277.868 | 275.164 | 259.345 | 258.786 | 1.147 | 0.000 | 6.066 | 2.703 | -0.049 | 0.558
| Project Code : 872 |  | Client : REMELEX PRIVATE LIMITED - VT872 | [11 empty] | Order Dt. : 11/02/2025
| 2ND3 | NORMAL TOWER | 6.308 | 5 | 31.540 |  |  | Pre
| 2ND3M | +3 MTR EXTN | 1.232 | 3 | 3.695 |  |  | Pre
| 2ND6M | +6 MTR EXTN | 1.325 | 5 | 6.624 |  |  | Pre
|  | Sub Total | 8.865 | 13 | 41.859
| Project Code : 875 |  | Client : KAPISH POWER CONSTRUCTION PVT LTD - VT875 | [11 empty] | Order Dt. : 22/03/2025
| 1DD2 | STUB | 0.351 | 4 | 1.406 |  |  | Mass
| 1DD3 | NORMAL TOWER | 6.160 | 4 | 24.641 |  |  | Mass
| 1DD6M | +6 MTR EXTN | 2.118 | 2 | 4.236 |  |  | Mass
| 1DD9M | +9 MTR EXTN | 3.029 | 2 | 6.058 |  |  | Mass
|  | Sub Total | 11.658 | 12 | 36.341
| Project Code : 876 |  | Client : GUJARAT ENERGY TRANSMISSION CORPORATION LIMITED - VT876 | [11 empty] | Order Dt. : 08/02/2025
| 1BA2 | BEAM | 0.564 | 9 | 5.073 | 9 | 5.065 | Mass | 5.073 | 5.073 | 5.073 | 5.073 | 5.073 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1BC2 | BEAM | 0.381 | 6 | 2.286 | 6 | 2.287 | Mass | 2.286 | 2.286 | 2.286 | 2.286 | 2.286 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1CPC2 | NORMAL TOWER | 0.843 | 22 | 18.555 | 22 | 18.555 | Mass | 18.555 | 18.555 | 18.555 | 18.555 | 18.555 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1LA | EQUIPMENT | 0.166 | 15 | 2.491 | 15 | 2.489 | Proto | 2.491 | 2.491 | 2.491 | 2.491 | 2.491 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1PT | EQUIPMENT | 0.165 | 12 | 1.977 | 12 | 1.977 | Proto | 1.977 | 1.977 | 1.977 | 1.977 | 1.977 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| IS | COLUMN | 0.090 | 1 | 0.090 | 1 | 0.091 | Mass | 0.090 | 0.090 | 0.090 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 2.209 | 65 | 30.472 | 65 | 30.464 |  | 30.471 | 30.471 | 30.471 | 30.381 | 30.381 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : 877 |  | Client : GROMA INFRASTRUCTURE LIMITED - VT877 | [11 empty] | Order Dt. : 18/02/2025
| 4DB2 | STUB | 0.811 | 1 | 0.811 |  |  | Pre
| 4DB3M | +3 MTR EXTN | 3.062 | 1 | 3.062 |  |  | Pre
| 4DB6M | +6 MTR EXTN | 4.827 | 1 | 4.827 |  |  | Pre
|  | Sub Total | 8.700 | 3 | 8.700
| Project Code : 879 |  | Client : SRVS SOLARS PRIVATE LIMITED - VT879 | [11 empty] | Order Dt. : 03/03/2025
| IS | NORMAL TOWER | 0.319 | 1 | 0.319 | 1 | 0.319 | Mass | 0.319 | 0.319 | 0.319 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 0.319 | 1 | 0.319 | 1 | 0.319 |  | 0.319 | 0.319 | 0.319 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : 880 |  | Client : ISHWARI ENGINEERS PVT LTD - VT880 | [11 empty] | Order Dt. : 13/03/2025
|  |  |  | 1 | 29.807 |  |  | Mass
|  | Sub Total | 29.807 | 1 | 29.807
| Project Code : 882 |  | Client : THE TATA POWER COMPANY LTD. -VT882 | [11 empty] | Order Dt. : 31/03/2025
| DF10M | +10M Body Extn | 10.275 | 3 | 30.824 | 3 | 30.823 | Mass | 30.824 | 30.824 | 30.824 | 30.824 | 29.813 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.011
| DF2 | STUB | 1.924 | 8 | 15.394 | 8 | 15.393 | Mass | 15.394 | 15.394 | 15.394 | 15.394 | 15.187 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.207
| DF3 | NORMAL TOWER | 45.062 | 7 | 315.435 | 7 | 315.451 | Mass | 315.435 | 315.435 | 315.435 | 315.442 | 305.904 | -0.008 | 0.007 | 0.000 | 0.000 | -0.007 | 9.538
| DF-5 | NORMAL TOWER | 40.422 | 1 | 40.422 | 1 | 40.418 | Mass | 40.422 | 40.422 | 40.422 | 40.424 | 36.867 | 0.000 | 0.002 | 0.000 | 0.000 | -0.002 | 3.557
| DF5M | +5.0 Mtr. Extn. | 4.980 | 2 | 9.959 | 2 | 9.958 | Mass | 9.959 | 9.959 | 9.959 | 9.959 | 9.627 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.333
| DM2 | STUB | 1.338 | 1 | 1.338 | 1 | 1.336 | Mass | 1.338 | 1.338 | 1.338 | 1.338 | 1.145 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.193
| DM3 | NORMAL TOWER | 15.711 | 1 | 15.711 | 1 | 15.713 | Mass | 15.711 | 15.711 | 15.711 | 15.711 | 12.822 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 2.890
| DNEH10M | +10M Body Extn | 4.786 | 1 | 4.786 | 1 | 4.785 | Mass | 4.786 | 4.786 | 4.786 | 4.786 | 4.407 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.379
| DNEH2 | STUB | 0.557 | 4 | 2.229 | 4 | 2.230 | Mass | 2.229 | 2.229 | 2.229 | 2.229 | 2.229 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| DNEH3 | NORMAL TOWER | 9.286 | 4 | 37.144 | 4 | 37.145 | Mass | 37.144 | 37.144 | 37.144 | 37.144 | 31.986 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 5.158
| DNEH-5 | NORMAL TOWER | 8.435 | 2 | 16.869 | 2 | 16.866 | Mass | 16.869 | 16.869 | 16.869 | 16.869 | 14.171 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 2.698
| IS | COLUMN | 1.171 | 1 | 1.171 | 1 | 1.166 | Mass | 1.171 | 1.171 | 1.171 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| SC | NORMAL TOWER | 0.392 | 1 | 0.392 | 1 | 0.393 | Mass | 0.392 | 0.392 | 0.392 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.006 | 1 | 0.006 | Mass | 0.006 | 0.006 | 0.006 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 144.345 | 37 | 491.680 | 37 | 491.683 |  | 491.682 | 491.682 | 491.682 | 490.122 | 464.159 | -0.008 | 0.008 | 0.000 | 0.000 | -0.008 | 25.963
| Project Code : 884. |  | Client : ASHOKA BUILDCON LIMITED - VT884 | [11 empty] | Order Dt. : 01/04/2025
| 2DA2 | STUB | 0.171 | 64 | 10.945 | 20 | 3.420 | Mass | 3.420 | 3.420 | 3.420 | 3.420 | 3.420 | 7.524 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DA2E | STUB | 0.181 | 78 | 14.116 | 36 | 6.514 | Mass | 6.515 | 6.515 | 6.515 | 6.515 | 6.515 | 7.600 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DA3 | NORMAL TOWER | 3.872 | 142 | 549.854 | 31 | 120.035 | Mass | 120.038 | 120.038 | 120.038 | 120.038 | 120.038 | 429.807 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DA3M | +3 MTR EXTN | 0.533 | 52 | 27.702 | 15 | 7.988 | Mass | 7.991 | 7.991 | 7.991 | 7.991 | 7.991 | 19.711 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DA6M | +6 MTR EXTN | 0.993 | 25 | 24.834 |  |  | Mass
| 2DA9M | +9 MTR EXTN | 1.785 | 1 | 1.785 |  |  | Mass
| 2DC2 | STUB | 0.306 | 37 | 11.304 | 24 | 7.332 | Mass | 7.332 | 7.332 | 7.332 | 7.332 | 7.332 | 3.972 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DC3 | NORMAL TOWER | 5.823 | 37 | 215.466 | 2 | 11.644 | Mass | 11.647 | 11.647 | 11.647 | 11.647 | 11.647 | 203.821 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DC3M | +3 MTR EXTN | 1.354 | 11 | 14.895 | 1 | 1.352 | Mass | 1.354 | 1.354 | 1.354 | 1.354 | 1.354 | 13.542 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DC6M | +6 MTR EXTN | 1.961 | 3 | 5.883 |  |  | Mass
| 2DC9M | +9 MTR EXTN | 3.697 | 2 | 7.394 |  |  | Mass
| 2DD12M | +12 MTR EXTN | 5.828 | 8 | 46.622 |  |  | Mass
| 2DD18M | +18 MTR EXTN | 9.922 | 4 | 39.686 | 2 | 19.839 | Mass | 19.843 | 19.843 | 19.843 | 19.843 | 19.843 | 19.839 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DD2 | STUB | 0.419 | 39 | 16.350 | 28 | 11.739 | Mass | 11.738 | 11.738 | 11.738 | 11.738 | 11.738 | 4.611 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DD21M | +21.0 Mtr. Extn. | 10.210 | 3 | 30.631 |  |  | Proto
| 2DD2A | STUB | 0.419 | 12 | 5.031 | 10 | 4.193 | Mass | 4.192 | 4.192 | 4.192 | 4.192 | 4.192 | 0.839 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DD2B | STUB | 0.447 | 3 | 1.342 | 1 | 0.447 | Mass | 0.447 | 0.447 | 0.447 | 0.447 | 0.447 | 0.895 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DD3 | NORMAL TOWER | 7.508 | 46 | 345.360 | 6 | 45.047 | Mass | 45.047 | 45.047 | 45.047 | 45.047 | 45.047 | 300.303 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DD3M | +3 MTR EXTN | 1.673 | 7 | 11.709 |  |  | Mass
| 2DD6M | +6 MTR EXTN | 2.657 | 7 | 18.602 | 3 | 7.975 | Mass | 7.972 | 7.972 | 7.972 | 7.972 | 7.972 | 10.630 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DD9M | +9 MTR EXTN | 3.723 | 1 | 3.723 |  |  | Mass
| 2DW2 | STUB | 0.339 | 14 | 4.750 | 14 | 4.749 | Proto | 4.750 | 4.750 | 4.750 | 4.750 | 4.750 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DW3 | NORMAL TOWER | 8.079 | 14 | 113.103 |  |  | Proto
| 2MA2 | STUB | 0.420 | 6 | 2.521 | 6 | 2.521 | Mass | 2.521 | 2.521 | 2.521 | 2.521 | 2.521 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2MA3 | NORMAL TOWER | 11.566 | 6 | 69.398 |  |  | Mass
| 2MA3M | +3 MTR EXTN | 1.645 | 2 | 3.290 |  |  | Mass
| 2MA6M | +6 MTR EXTN | 2.893 | 3 | 8.678 |  |  | Mass
| 2MA9M | +9 MTR EXTN | 3.642 | 1 | 3.642 |  |  | Proto
| 2MC2 | STUB | 0.906 | 2 | 1.812 | 2 | 1.812 | Mass | 1.812 | 1.812 | 1.812 | 1.812 | 1.812 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2MC3 | NORMAL TOWER | 19.203 | 2 | 38.406 |  |  | Mass
| 2MC3M | +3 MTR EXTN | 3.145 | 1 | 3.145 | 1 | 3.148 | Proto | 3.145 | 3.145 | 3.145 | 3.145 | 3.090 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.055
| 2MC6M | +6 MTR EXTN | 4.777 | 1 | 4.777 | 1 | 4.775 | Proto | 4.777 | 4.777 | 4.772 | 4.777 | 4.724 | 0.000 | 0.000 | 0.000 | 0.006 | -0.006 | 0.053
| 2MD18M | +18 MTR EXTN | 24.395 | 2 | 48.790 | 2 | 48.783 | Proto | 48.790 | 48.769 | 48.063 | 48.790 | 46.297 | 0.000 | 0.000 | 0.021 | 0.706 | -0.727 | 2.493
| 2MD2 | STUB | 0.966 | 8 | 7.727 | 8 | 7.727 | Mass | 7.727 | 7.727 | 7.727 | 7.727 | 7.727 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2MD2A | STUB | 0.986 | 2 | 1.972 | 1 | 0.986 | Proto | 0.986 | 0.986 | 0.986 | 0.986 | 0.986 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2MD3 | NORMAL TOWER | 25.556 | 10 | 255.555 | 3 | 76.675 | Mass | 76.667 | 76.667 | 76.667 | 76.667 | 76.667 | 178.896 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2MD3M | +3 MTR EXTN | 4.982 | 1 | 4.982 | 1 | 4.986 | Mass | 4.982 | 4.982 | 4.982 | 4.982 | 4.982 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2MD6M | +6 MTR EXTN | 7.343 | 2 | 14.687 |  |  | Mass
| 2MDN2 | STUB | 3.014 | 2 | 6.028 | 1 | 3.012 | Mass | 3.014 | 3.014 | 3.014 | 3.014 | 3.014 | 3.012 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2MDN3 | NORMAL TOWER | 32.525 | 2 | 65.049 |  |  | Mass
| 2MDN3M | +3 MTR EXTN | 3.625 | 1 | 3.625 |  |  | Mass
| 2ND2 | STUB | 0.496 | 3 | 1.487 | 2 | 0.992 | Mass | 0.991 | 0.991 | 0.991 | 0.991 | 0.991 | 0.495 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2ND3 | NORMAL TOWER | 6.308 | 3 | 18.924 |  |  | Pre
| 2ND6M | +6 MTR EXTN | 1.325 | 1 | 1.325 |  |  | Pre
| 4DA2 | STUB | 0.359 | 7 | 2.510 | 7 | 2.510 | Proto | 2.510 | 2.510 | 2.510 | 2.510 | 2.510 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4DA3 | NORMAL TOWER | 10.468 | 7 | 73.275 | 7 | 73.283 | Proto | 73.275 | 72.960 | 72.488 | 73.275 | 72.369 | 0.000 | 0.000 | 0.315 | 0.471 | -0.786 | 0.905
| 4DA3M | +3 MTR EXTN | 1.422 | 2 | 2.844 | 2 | 2.844 | Proto | 2.844 | 2.844 | 2.844 | 2.844 | 2.820 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.024
| 4DA6M | +6 MTR EXTN | 2.316 | 1 | 2.316 | 1 | 2.321 | Proto | 2.316 | 2.284 | 2.284 | 2.316 | 2.283 | 0.000 | 0.000 | 0.033 | 0.000 | -0.033 | 0.033
| 4DC2 | STUB | 0.966 | 4 | 3.865 | 4 | 3.865 | Mass | 3.865 | 3.865 | 3.865 | 3.865 | 3.865 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4DC3 | NORMAL TOWER | 22.210 | 4 | 88.841 |  |  | Mass
| 4DD15M | +15 MTR EXTN | 15.376 | 2 | 30.751 | 2 | 30.741 | Proto | 30.751 | 30.751 | 30.686 | 30.751 | 30.671 | 0.000 | -0.015 | 0.000 | 0.065 | -0.065 | 0.080
| 4DD2 | STUB | 0.966 | 7 | 6.764 | 2 | 1.933 | Proto | 1.932 | 1.932 | 1.932 | 1.932 | 1.932 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 5 | 4.832 | Mass | 4.831 | 4.831 | 4.831 | 4.831 | 4.831 | 0.965 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4DD2A | STUB | 0.966 | 2 | 1.932 | 2 | 1.933 | Proto | 1.932 | 1.932 | 1.932 | 1.932 | 1.932 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4DD3 | NORMAL TOWER | 22.260 | 9 | 200.338 | 4 | 89.033 | Proto | 89.039 | 89.039 | 88.701 | 89.039 | 87.834 | 0.000 | -0.006 | 0.000 | 0.338 | -0.338 | 1.205
| 4DD3M | +3 MTR EXTN | 4.197 | 1 | 4.197 | 1 | 4.197 | Proto | 4.197 | 4.197 | 4.197 | 4.197 | 4.197 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4QD2 | STUB | 3.563 | 4 | 14.250 |  |  | Pre
| IS | COLUMN | 1.026 | 1 | 1.026 | 1 | 1.025 | Mass | 1.026 | 1.026 | 1.022 |  |  | 0.000 | 0.000 | 0.000 | 0.003
| SC | NORMAL TOWER | 0.009 | 1 | 0.009 | 1 | 0.009 | Mass | 0.009 |  |  |  |  | 0.000 | 0.000 | 0.009
| SR | COLUMN | 2.046 | 1 | 2.046 | 1 | 2.047 | Mass | 2.046 |  |  |  |  | 0.000 | 0.000 | 2.046
|  | Sub Total | 320.735 | 724 | 2521.871 | 261 | 628.264 |  | 628.275 | 625.851 | 624.261 | 625.193 | 620.345 | 1206.462 | -0.021 | 2.424 | 1.590 | -1.955 | 4.849
| Project Code : 885 |  | Client : MBH POWER PRIVATE LIMITED - VT885 | [11 empty] | Order Dt. : 03/05/2025
| 2BPI | EQUIPMENT | 0.238 | 54 | 12.864 | 54 | 12.863 | Proto | 12.864 | 12.864 | 12.770 | 12.864 |  | 0.000 | 0.000 | 0.000 | 0.094 | -0.094 | 12.864
| 2CT | EQUIPMENT | 0.337 | 18 | 6.062 | 18 | 6.062 | Proto | 6.062 | 6.062 | 6.062 | 6.062 | 6.062 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2ISO | EQUIPMENT | 1.482 | 2 | 2.964 | 2 | 2.962 | Proto | 2.964 | 2.964 | 2.964 | 2.964 | 2.964 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2ISOW | EQUIPMENT | 1.438 | 22 | 31.631 | 22 | 31.627 | Proto | 31.631 | 31.631 | 31.631 | 31.631 | 31.631 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2IVT | EQUIPMENT | 0.229 | 12 | 2.747 | 12 | 2.746 | Proto | 2.747 | 2.747 | 2.747 | 2.747 | 2.747 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2LA | EQUIPMENT | 0.348 | 12 | 4.174 | 12 | 4.176 | Proto | 4.174 | 4.174 | 4.174 | 4.174 | 4.174 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2P1S | COLUMN | 4.040 | 35 | 141.387 | 35 | 141.386 | Mass | 141.387 | 141.387 | 141.387 | 141.387 | 141.306 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.081
| 2Q1 | BEAM | 1.601 | 24 | 38.436 | 24 | 38.434 | Mass | 38.436 | 38.436 | 38.436 | 38.436 | 38.434 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.001
| 2Q3 | BEAM | 2.465 | 12 | 29.577 | 8 | 19.716 | Mass | 19.718 | 19.718 | 19.718 | 19.718 | 19.621 | 9.859 | 0.000 | 0.000 | 0.000 | 0.000 | 0.097
| 3BPI | EQUIPMENT | 0.170 | 23 | 3.914 | 23 | 3.915 | Mass | 3.914 | 3.914 | 3.914 | 3.914 | 3.914 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3CT | EQUIPMENT | 0.151 | 24 | 3.618 | 24 | 3.616 | Mass | 3.618 | 3.618 | 3.618 | 3.618 | 3.618 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3G4 | BEAM | 0.287 | 11 | 3.158 | 9 | 2.583 | Mass | 2.584 | 2.584 | 2.584 | 2.584 | 2.554 | 0.573 | 0.000 | 0.000 | 0.000 | 0.000 | 0.030
| 3G4X | BEAM | 0.287 | 5 | 1.436 | 5 | 1.436 | Mass | 1.436 | 1.436 | 1.436 | 1.436 | 1.419 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.016
| 3G6 | BEAM | 0.361 | 5 | 1.803 | 5 | 1.800 | Mass | 1.803 | 1.803 | 1.803 | 1.803 | 1.800 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.003
| 3HGF | EQUIPMENT | 0.239 | 2 | 0.477 | 2 | 0.477 | Proto | 0.477 |  |  |  |  | 0.000 | 0.000 | 0.477
| 3IVT | EQUIPMENT | 0.157 | 3 | 0.472 | 3 | 0.473 | Mass | 0.472 | 0.472 | 0.472 | 0.472 | 0.472 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3LA | EQUIPMENT | 0.159 | 6 | 0.952 | 6 | 0.953 | Proto | 0.952 |  |  |  |  | 0.000 | 0.000 | 0.952
| 3S8 | EQUIPMENT | 0.269 | 1 | 0.269 |  |  | Pre
|  |  |  | 22 | 5.957 | 22 | 5.958 | Mass | 5.957 | 5.957 | 5.957 | 5.957 | 5.957 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3SI | EQUIPMENT | 0.271 | 7 | 1.895 | 7 | 1.896 | Mass | 1.895 | 1.819 | 0.961 | 1.895 |  | 0.000 | 0.000 | 0.076 | 0.858 | -0.934 | 1.895
| 3T8S | NORMAL TOWER | 0.677 | 13 | 8.797 | 12 | 8.120 | Mass | 8.121 | 8.121 | 8.121 | 8.121 | 8.118 | 0.675 | 0.000 | 0.000 | 0.000 | 0.000 | 0.003
| 3T9S | NORMAL TOWER | 0.506 | 15 | 7.596 | 13 | 6.581 | Mass | 6.583 | 6.583 | 6.583 | 6.583 | 6.577 | 1.014 | 0.000 | 0.000 | 0.000 | 0.000 | 0.006
| IS | COLUMN | 0.442 | 1 | 0.442 | 1 | 0.443 | Mass | 0.442 |  |  |  |  | 0.000 | 0.000 | 0.442
|  |  |  | 1 | 0.536 | 1 | 0.537 | Mass | 0.536 | 0.353 | 0.353 |  |  | 0.000 | 0.000 | 0.183 | 0.000
|  |  |  | 1 | 0.035 | 1 | 0.035 | Mass | 0.035 | 0.008 |  |  |  | 0.000 | 0.000 | 0.026 | 0.008
|  |  |  | 1 | 0.035 | 1 | 0.035 | Mass | 0.035 | 0.004 |  |  |  | 0.000 | 0.000 | 0.031 | 0.004
|  |  |  | 1 | 0.062 | 1 | 0.060 | Mass | 0.062 | 0.030 | 0.030 |  |  | 0.000 | 0.000 | 0.032 | 0.000
|  |  |  | 1 | 0.062 | 1 | 0.060 | Mass | 0.062 |  |  |  |  | 0.000 | 0.000 | 0.062
| OA1 | S.S.T | 0.648 | 1 | 0.648 | 1 | 0.648 | Mass | 0.648 | 0.648 | 0.648 | 0.631 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.631
| OA2 | STUB | 0.232 | 12 | 2.781 | 12 | 2.782 | Mass | 2.781 | 2.781 | 2.781 | 2.781 | 2.781 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| OA3 | NORMAL TOWER | 4.348 | 17 | 73.917 | 17 | 73.918 | Mass | 73.917 | 73.917 | 73.917 | 73.915 | 73.885 | 0.002 | -0.003 | 0.000 | 0.000 | 0.003 | 0.030
| OA3M | +3 MTR EXTN | 0.763 | 4 | 3.053 | 2 | 1.526 | Mass | 1.527 | 1.527 | 1.527 | 1.527 | 1.527 | 1.526 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| OA6M | +6 MTR EXTN | 1.515 | 9 | 13.634 | 4 | 6.061 | Mass | 6.060 | 6.060 | 6.060 | 6.060 | 6.060 | 7.576 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| OB1 | S.S.T | 0.896 | 1 | 0.896 | 1 | 0.897 | Mass | 0.896 | 0.896 | 0.896 | 0.896 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.896
| OB2 | STUB | 0.438 | 6 | 2.626 | 6 | 2.626 | Mass | 2.626 | 2.188 | 2.188 | 2.626 | 2.188 | 0.000 | 0.000 | 0.438 | 0.000 | -0.438 | 0.438
| OB3 | NORMAL TOWER | 6.512 | 8 | 52.095 | 8 | 52.093 | Mass | 52.095 | 48.646 | 45.749 | 52.003 | 45.573 | 0.000 | 0.000 | 3.448 | 2.897 | -6.254 | 6.430
| OB3M | +3 MTR EXTN | 1.358 | 2 | 2.716 | 1 | 1.355 | Mass | 1.358 | 1.358 | 1.358 | 1.358 | 1.358 | 1.355 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| OB6M | +6 MTR EXTN | 2.346 | 3 | 7.038 | 1 | 2.347 | Mass | 2.346 | 1.506 | 0.087 |  |  | 4.690 | 0.000 | 0.839 | 1.419
| OC1 | S.S.T | 1.016 | 1 | 1.016 | 1 | 1.015 | Mass | 1.016 | 1.016 | 1.016 | 1.016 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.016
| OC15M | +15 MTR EXTN | 8.696 | 2 | 17.393 |  |  | Mass
| OC1A | S.S.T | 2.095 | 1 | 2.095 |  |  | Mass
| OC2 | STUB | 0.777 | 8 | 6.214 |  |  | Mass
| OC2A | STUB | 1.067 | 2 | 2.134 |  |  | Mass
| OC3 | NORMAL TOWER | 9.237 | 14 | 129.323 | 9 | 83.137 | Mass | 83.136 | 83.136 | 83.136 | 83.136 | 83.025 | 46.170 | 0.000 | 0.000 | 0.000 | 0.000 | 0.111
| OC3M | +3 MTR EXTN | 1.488 | 2 | 2.976 | 1 | 1.490 | Mass | 1.488 | 1.488 | 1.488 | 1.488 | 1.488 | 1.490 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| OC6M | +6 MTR EXTN | 2.741 | 6 | 16.446 |  |  | Mass
| Q1X | BEAM | 1.689 | 4 | 6.758 | 4 | 6.849 | Proto | 6.758 | 6.758 | 6.691 | 6.758 |  | 0.000 | 0.089 | 0.000 | 0.066 | -0.066 | 6.758
| SC | NORMAL TOWER | 0.004 | 1 | 0.004 | 1 | 0.004 | Mass | 0.004 | 0.004 |  |  |  | 0.000 | 0.000 | 0.000 | 0.004
|  | Sub Total | 65.020 | 438 | 655.121 | 393 | 535.698 |  | 535.623 | 528.615 | 523.265 | 530.559 | 499.253 | 74.930 | 0.086 | 7.008 | 5.351 | -7.783 | 31.306
| Project Code : 886 |  | Client : MAA HARSIDDHI INFRA DEVELOPERS PVT. LTD - VT886 | [11 empty] | Order Dt. : 19/04/2025
| 1CC | COLUMN | 0.741 | 2 | 1.483 | 2 | 1.487 | Proto | 1.483 | 0.698 | 0.545 |  |  | 0.000 | 0.000 | 0.785 | 0.153
| 1CC2 | STUB | 0.140 | 2 | 0.280 | 2 | 0.280 | Proto | 0.280 | 0.280 | 0.280 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| 1CE | COLUMN | 0.575 | 4 | 2.301 | 4 | 2.302 | Proto | 2.301 | 1.671 | 1.105 |  |  | 0.000 | 0.000 | 0.630 | 0.566
| 1CE2 | STUB | 0.073 | 4 | 0.293 | 4 | 0.293 | Proto | 0.293 | 0.293 | 0.293 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| 1GA | BEAM | 0.666 | 4 | 2.664 | 4 | 2.664 | Proto | 2.664 | 0.983 | 0.843 |  |  | 0.000 | 0.000 | 1.682 | 0.140
| DN2 | NORMAL TOWER | 2.685 | 34 | 91.286 | 34 | 91.288 | Mass | 91.286 | 91.286 | 91.282 | 91.286 | 83.321 | 0.000 | 0.000 | 0.000 | 0.004 | -0.004 | 7.965
| DN2E | +3 MTR EXTN | 0.475 | 23 | 10.925 | 23 | 10.926 | Mass | 10.925 | 10.925 | 10.920 | 10.925 | 10.473 | 0.000 | 0.000 | 0.000 | 0.005 | -0.005 | 0.452
| DN2E. | +6 MTR EXTN | 0.999 | 8 | 7.995 | 8 | 7.993 | Mass | 7.995 | 7.995 | 7.995 | 7.995 | 7.851 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.144
| DN2S | STUB | 0.185 | 34 | 6.274 | 34 | 6.273 | Mass | 6.274 | 6.274 | 6.274 | 6.274 | 6.274 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| DN2T | S.S.T | 0.436 | 2 | 0.873 | 2 | 0.871 | Mass | 0.873 | 0.873 | 0.873 | 0.873 | 0.873 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| DN30 | NORMAL TOWER | 4.395 | 13 | 57.133 | 13 | 57.140 | Mass | 57.133 | 57.118 | 57.079 | 57.133 | 42.350 | 0.000 | 0.000 | 0.016 | 0.039 | -0.054 | 14.783
| DN30E | +3 MTR EXTN | 0.907 | 2 | 1.814 | 2 | 1.815 | Mass | 1.814 | 1.814 | 1.719 | 1.814 | 1.533 | 0.000 | 0.000 | 0.000 | 0.096 | -0.096 | 0.281
| DN30E. | +6 MTR EXTN | 1.670 | 6 | 10.021 | 6 | 10.021 | Mass | 10.021 | 10.021 | 10.021 | 10.021 | 8.632 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.389
| DN30E.. | +9 MTR EXTN | 2.503 | 1 | 2.503 | 1 | 2.506 | Mass | 2.503 | 2.503 | 2.451 | 2.503 | 1.779 | 0.000 | 0.000 | 0.000 | 0.051 | -0.051 | 0.724
| DN30S | STUB | 0.357 | 13 | 4.635 | 13 | 4.635 | Mass | 4.635 | 4.635 | 4.635 | 4.635 | 4.635 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| DN30T | S.S.T | 0.753 | 2 | 1.505 | 2 | 1.503 | Mass | 1.505 | 1.505 | 1.505 | 1.505 | 1.505 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| DN60 | NORMAL TOWER | 5.811 | 5 | 29.053 | 5 | 29.059 | Mass | 29.053 | 29.053 | 29.032 | 29.053 | 22.370 | 0.000 | 0.000 | 0.000 | 0.020 | -0.020 | 6.683
| DN60E | +6 MTR EXTN | 2.321 | 2 | 4.641 | 2 | 4.636 | Mass | 4.641 | 4.641 | 4.641 | 4.641 | 4.100 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.541
| DN60S | STUB | 0.421 | 5 | 2.103 | 5 | 2.103 | Mass | 2.103 | 2.103 | 2.103 | 2.103 | 2.103 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| DN60T | S.S.T | 1.348 | 2 | 2.696 | 2 | 2.694 | Mass | 2.696 | 2.696 | 2.696 | 2.696 | 2.696 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 27.460 | 168 | 240.478 | 168 | 240.489 |  | 240.477 | 237.365 | 236.291 | 233.457 | 200.495 | 0.000 | 0.000 | 3.112 | 1.074 | -0.230 | 32.962
| Project Code : 888 |  | Client : OM POWER TRANSMISSION PVT.LTD. - VT888 | [11 empty] | Order Dt. : 12/05/2025
| 1BC2 | BEAM | 0.381 | 3 | 1.143 | 3 | 1.143 | Mass | 1.143 | 1.143 | 1.143 | 1.143 | 1.143 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1CPC2 | COLUMN | 0.843 | 6 | 5.060 | 6 | 5.060 | Mass | 5.060 | 5.060 | 5.060 | 5.060 | 5.060 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2BL | BEAM | 2.204 | 24 | 52.901 | 24 | 52.903 | Mass | 52.901 | 52.901 | 52.901 | 52.901 | 52.901 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2BMB | BEAM | 1.977 | 14 | 27.681 | 14 | 27.682 | Mass | 27.681 | 27.681 | 27.681 | 27.681 | 27.681 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2BPI | EQUIPMENT | 0.154 | 111 | 17.114 | 111 | 17.113 | Mass | 17.114 | 17.114 | 17.114 | 17.114 | 17.067 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.046
| 2CMB | COLUMN | 2.395 | 14 | 33.524 | 14 | 33.521 | Mass | 33.524 | 33.524 | 33.524 | 33.524 | 33.524 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2CPL1 | COLUMN | 5.359 | 7 | 37.513 | 7 | 37.513 | Mass | 37.513 | 37.513 | 37.513 | 37.513 | 37.513 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2CPL2 | COLUMN | 5.837 | 19 | 110.909 | 19 | 110.911 | Mass | 110.909 | 110.909 | 110.909 | 110.909 | 110.909 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2CT | EQUIPMENT | 0.131 | 21 | 2.759 | 21 | 2.761 | Mass | 2.759 | 2.759 | 2.759 | 2.759 | 2.759 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2CVT | EQUIPMENT | 0.202 | 4 | 0.809 | 4 | 0.814 | Mass | 0.809 | 0.805 | 0.799 | 0.809 | 0.775 | 0.000 | 0.000 | 0.003 | 0.006 | -0.009 | 0.034
| 2HBPI | EQUIPMENT | 0.239 | 33 | 7.893 | 33 | 7.891 | Mass | 7.893 | 7.893 | 7.893 | 7.893 | 7.893 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2ISO | EQUIPMENT | 0.724 | 6 | 4.345 | 6 | 4.344 | Mass | 4.345 | 4.345 | 4.345 | 4.345 | 4.345 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2ISOW | EQUIPMENT | 0.715 | 16 | 11.436 | 16 | 11.433 | Mass | 11.436 | 11.436 | 11.436 | 11.436 | 11.436 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2LA | EQUIPMENT | 0.179 | 18 | 3.229 | 18 | 3.229 | Mass | 3.229 | 3.229 | 3.229 | 3.229 | 3.229 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2PT | EQUIPMENT | 0.131 | 6 | 0.788 | 6 | 0.788 | Mass | 0.788 | 0.788 | 0.788 | 0.788 | 0.788 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2TISO | EQUIPMENT | 0.715 | 6 | 4.289 | 6 | 4.288 | Mass | 4.289 | 4.289 | 4.289 | 4.289 | 4.289 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 6BA3A | BEAM | 0.503 | 42 | 21.124 | 42 | 21.125 | Mass | 21.124 | 21.124 | 21.124 | 21.124 | 21.124 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 6BPI | EQUIPMENT | 0.142 | 99 | 14.017 | 99 | 14.018 | Mass | 14.017 | 10.980 | 10.902 | 13.643 | 10.902 | 0.000 | 0.000 | 3.036 | 0.079 | -2.741 | 2.741
| 6CPA2A | COLUMN | 1.425 | 43 | 61.287 | 43 | 61.425 | Mass | 61.287 | 61.287 | 61.287 | 61.421 | 61.287 | -0.134 | 0.135 | 0.000 | 0.000 | -0.135 | 0.135
| 6CPB3A | COLUMN | 0.697 | 20 | 13.934 | 20 | 13.939 | Mass | 13.934 | 13.934 | 13.934 | 13.934 | 13.934 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 6CT | EQUIPMENT | 0.150 | 39 | 5.860 | 39 | 5.860 | Mass | 5.860 | 5.309 | 4.507 | 5.860 | 4.507 | 0.000 | 0.000 | 0.551 | 0.802 | -1.352 | 1.352
| 6HBPI | EQUIPMENT | 0.184 | 6 | 1.105 | 6 | 1.104 | Mass | 1.105 | 1.105 | 1.105 | 1.105 | 1.105 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 6ISO | EQUIPMENT | 0.293 | 9 | 2.635 | 9 | 2.632 | Mass | 2.635 | 2.233 | 1.757 | 2.418 | 1.757 | 0.000 | 0.000 | 0.402 | 0.476 | -0.662 | 0.662
| 6ISOW | EQUIPMENT | 0.290 | 39 | 11.309 | 39 | 11.311 | Mass | 11.309 | 9.270 | 6.669 | 10.153 | 6.669 | 0.000 | 0.000 | 2.039 | 2.600 | -3.484 | 3.484
| 6LA | EQUIPMENT | 0.137 | 36 | 4.938 | 36 | 4.937 | Mass | 4.938 | 4.387 | 3.703 | 4.260 | 3.703 | 0.000 | 0.000 | 0.551 | 0.683 | -0.557 | 0.557
| 6PT | EQUIPMENT | 0.150 | 6 | 0.901 | 6 | 0.900 | Mass | 0.901 | 0.901 | 0.901 | 0.901 | 0.901 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| IS | COLUMN | 0.034 | 1 | 0.034 | 1 | 0.033 | Mass | 0.034 | 0.034 | 0.010 |  |  | 0.000 | 0.000 | 0.000 | 0.024
|  |  |  | 1 | 0.039 | 1 | 0.039 | Mass | 0.039 | 0.039 | 0.039 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.018 | 1 | 0.018 | Mass | 0.018 | 0.018 | 0.018 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.263 | 1 | 0.263 | Mass | 0.263 | 0.196 | 0.196 |  |  | 0.000 | 0.000 | 0.067 | 0.000
|  |  |  | 1 | 0.084 | 1 | 0.084 | Mass | 0.084 | 0.037 | 0.037 |  |  | 0.000 | 0.000 | 0.046 | 0.000
| LM | NORMAL TOWER | 1.502 | 1 | 1.502 | 1 | 1.506 | Proto | 1.502 |  |  |  |  | 0.000 | 0.000 | 1.502
| SC | NORMAL TOWER | 0.022 | 1 | 0.022 | 1 | 0.022 | Mass | 0.022 |  |  |  |  | 0.000 | 0.000 | 0.022
|  | Sub Total | 28.121 | 654 | 460.465 | 654 | 460.610 |  | 460.462 | 452.242 | 447.572 | 456.212 | 447.201 | -0.134 | 0.135 | 8.220 | 4.670 | -8.940 | 9.011
| Project Code : 890 |  | Client : ASHOKA BUILDCON LIMITED - VT890 | [11 empty] | Order Dt. : 19/05/2025
| 2AB | BEAM | 0.880 | 12 | 10.560 | 12 | 10.562 | Mass | 10.560 | 10.560 | 10.532 | 10.560 | 10.529 | 0.000 | 0.000 | 0.000 | 0.028 | -0.028 | 0.031
| 2AG | COLUMN | 1.956 | 5 | 9.782 | 5 | 9.787 | Mass | 9.782 | 8.913 | 8.810 | 9.782 | 8.803 | 0.000 | 0.000 | 0.868 | 0.104 | -0.972 | 0.979
| 2AP | PEAK | 0.080 | 5 | 0.399 | 5 | 0.400 | Mass | 0.399 | 0.399 | 0.399 | 0.399 | 0.399 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2BB1 | BEAM | 1.456 | 16 | 23.293 | 16 | 23.290 | Mass | 23.293 | 23.293 | 23.293 | 23.293 | 23.293 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2BB2 | BEAM | 1.672 | 12 | 20.069 | 12 | 20.073 | Mass | 16.725 | 16.725 | 16.725 | 19.221 | 16.725 | 0.000 | 3.345 | 0.000 | 0.000 | -2.496 | 2.496
| 2BB3 | BEAM | 1.922 | 20 | 38.447 | 20 | 38.452 | Mass | 38.447 | 38.447 | 38.447 | 38.447 | 38.447 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2BPIB | EQUIPMENT | 0.154 | 53 | 8.171 | 53 | 8.171 | Mass | 8.171 | 8.171 | 8.171 | 8.171 | 8.171 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2CCB | EQUIPMENT | 0.118 | 16 | 1.882 | 16 | 1.882 | Mass | 1.882 | 1.882 | 1.882 | 1.882 | 1.880 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.002
| 2CTB | EQUIPMENT | 0.170 | 36 | 6.104 | 36 | 6.105 | Mass | 6.104 | 6.104 | 6.104 | 6.104 | 6.104 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2ISO | EQUIPMENT | 0.809 | 10 | 8.086 | 10 | 8.085 | Proto | 8.086 |  |  |  |  | 0.000 | 0.000 | 8.086
| 2ISO1 | EQUIPMENT | 0.309 | 6 | 1.851 | 6 | 1.849 | Proto | 1.851 | 0.174 | 0.174 |  |  | 0.000 | 0.000 | 1.678 | 0.000
| 2ISO1W | EQUIPMENT | 0.294 | 6 | 1.767 | 6 | 1.766 | Proto | 1.767 | 0.209 | 0.209 |  |  | 0.000 | 0.000 | 1.558 | 0.000
| 2ISO2 | EQUIPMENT | 0.323 | 1 | 0.323 | 1 | 0.321 | Proto | 0.323 |  |  |  |  | 0.000 | 0.000 | 0.323
| 2ISOW | EQUIPMENT | 0.794 | 35 | 27.807 | 35 | 27.811 | Proto | 27.807 | 3.428 | 3.428 |  |  | 0.000 | 0.000 | 24.379 | 0.000
| 2LAB | EQUIPMENT | 0.163 | 31 | 5.066 | 31 | 5.070 | Mass | 5.066 | 5.066 | 5.027 | 5.066 | 5.019 | 0.000 | 0.000 | 0.000 | 0.039 | -0.039 | 0.047
| 2PTB | EQUIPMENT | 0.148 | 6 | 0.890 | 6 | 0.889 | Mass | 0.890 | 0.890 | 0.887 | 0.890 | 0.885 | 0.000 | 0.000 | 0.000 | 0.003 | -0.003 | 0.005
| 2TA1 | COLUMN | 2.500 | 4 | 10.002 | 4 | 10.005 | Mass | 10.002 | 10.002 | 10.002 | 10.002 | 10.002 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2TA2 | COLUMN | 4.575 | 8 | 36.597 | 8 | 36.596 | Mass | 36.597 | 36.597 | 36.597 | 36.597 | 36.597 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2TA3 | COLUMN | 3.441 | 8 | 27.531 | 8 | 27.527 | Mass | 27.531 | 27.531 | 27.531 | 27.531 | 27.531 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2TA3P | COLUMN | 3.441 | 5 | 17.207 | 5 | 17.212 | Mass | 17.207 | 17.207 | 17.207 | 17.207 | 17.207 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2TA4 | COLUMN | 6.332 | 3 | 18.997 | 3 | 18.997 | Mass | 18.997 | 18.997 | 18.997 | 18.997 | 18.997 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2TA5 | COLUMN | 4.848 | 1 | 4.848 | 1 | 4.848 | Mass | 4.848 | 4.848 | 4.848 | 4.848 | 4.848 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2TA5P | COLUMN | 4.848 | 10 | 48.480 | 10 | 48.482 | Mass | 48.480 | 48.480 | 48.480 | 48.480 | 48.480 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2TA6 | COLUMN | 8.654 | 8 | 69.229 | 8 | 69.230 | Mass | 69.229 | 69.229 | 69.229 | 69.229 | 69.229 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2TP | COLUMN | 0.115 | 28 | 3.229 | 28 | 3.229 | Mass | 3.229 | 3.229 | 3.229 | 3.229 | 3.229 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2WTB | EQUIPMENT | 0.304 | 16 | 4.863 | 16 | 4.864 | Mass | 4.863 | 4.863 | 4.863 | 4.863 | 4.569 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.294
| 4B1MS | BEAM | 4.186 | 20 | 83.720 | 20 | 83.720 | Mass | 83.720 | 83.720 | 83.720 | 83.720 | 83.720 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4B2 | BEAM | 1.554 | 4 | 6.214 | 4 | 6.214 | Mass | 6.214 | 6.214 | 6.214 | 6.214 | 6.214 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4B3 | BEAM | 3.811 | 6 | 22.864 | 6 | 22.865 | Mass | 22.864 | 22.864 | 22.864 | 22.864 | 22.864 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4BPI | EQUIPMENT | 0.250 | 25 | 6.241 | 25 | 6.242 | Mass | 6.241 | 6.241 | 6.241 | 6.241 | 6.241 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4CT | EQUIPMENT | 0.212 | 25 | 5.297 | 25 | 5.297 | Proto | 5.297 | 3.028 | 1.150 |  |  | 0.000 | 0.000 | 2.270 | 1.877
| 4CVT | EQUIPMENT | 0.214 | 14 | 2.994 | 14 | 2.995 | Mass | 2.994 | 2.994 | 2.988 | 2.994 | 2.988 | 0.000 | 0.000 | 0.000 | 0.006 | -0.006 | 0.006
| 4ISO1L | EQUIPMENT | 0.496 | 8 | 3.966 | 8 | 3.970 | Proto | 3.966 | 0.095 | 0.031 |  |  | 0.000 | 0.000 | 3.871 | 0.064
| 4ISO1R | EQUIPMENT | 0.502 | 2 | 1.003 | 2 | 0.997 | Proto | 1.003 | 0.067 | 0.047 |  |  | 0.000 | 0.000 | 0.936 | 0.021
| 4ISO1W | EQUIPMENT | 0.486 | 6 | 2.914 | 6 | 2.914 | Proto | 2.914 | 0.398 | 0.347 |  |  | 0.000 | 0.000 | 2.516 | 0.050
| 4ISO2ES | EQUIPMENT | 0.512 | 5 | 2.559 | 5 | 2.554 | Proto | 2.559 | 0.419 | 0.368 |  |  | 0.000 | 0.000 | 2.140 | 0.050
| 4ISO3L | EQUIPMENT | 0.496 | 8 | 3.966 | 8 | 3.970 | Proto | 3.966 | 0.101 | 0.101 |  |  | 0.000 | 0.000 | 3.865 | 0.000
| 4ISO3R | EQUIPMENT | 0.502 | 8 | 4.013 | 8 | 4.017 | Proto | 4.013 | 0.700 | 0.635 |  |  | 0.000 | 0.000 | 3.314 | 0.065
| 4LA | EQUIPMENT | 0.213 | 17 | 3.614 | 17 | 3.614 | Proto | 3.614 | 3.339 | 3.327 |  |  | 0.000 | 0.000 | 0.276 | 0.012
| 4T1 | COLUMN | 3.844 | 8 | 30.751 | 8 | 30.747 | Mass | 30.751 | 30.751 | 30.751 | 30.751 | 30.751 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4T1P | COLUMN | 3.844 | 6 | 23.063 | 6 | 23.060 | Mass | 23.063 | 23.063 | 23.063 | 23.063 | 23.063 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4T3 | COLUMN | 5.867 | 1 | 5.867 | 1 | 5.866 | Mass | 5.867 | 5.867 | 5.867 | 5.867 | 5.867 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4T4 | COLUMN | 6.588 | 3 | 19.765 | 3 | 19.769 | Mass | 19.765 | 19.765 | 19.765 | 19.765 | 19.765 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4T5 | COLUMN | 8.554 | 18 | 153.969 | 18 | 153.967 | Mass | 153.969 | 153.969 | 153.969 | 153.969 | 153.969 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4TP | COLUMN | 0.301 | 30 | 9.032 | 30 | 9.034 | Mass | 9.032 | 9.032 | 9.032 | 9.032 | 9.032 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| IS | COLUMN | 0.803 | 1 | 0.803 | 1 | 0.808 | Mass | 0.803 | 0.803 | 0.803 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.530 | 1 | 0.532 | Mass | 0.530 | 0.281 |  |  |  | 0.000 | 0.000 | 0.249 | 0.281
| SC | NORMAL TOWER | 0.089 | 1 | 0.089 | 1 | 0.089 | Mass | 0.089 | 0.089 | 0.014 |  |  | 0.000 | 0.000 | 0.000 | 0.075
| SS | COLUMN | 1.708 | 1 | 1.708 | 1 | 1.709 | Mass | 1.708 | 1.630 | 1.015 |  |  | 0.000 | 0.000 | 0.078 | 0.615
|  | Sub Total | 95.866 | 579 | 800.422 | 579 | 800.453 |  | 797.077 | 740.671 | 737.381 | 729.276 | 725.415 | 0.000 | 3.345 | 56.406 | 3.290 | -3.545 | 3.861
| Project Code : 893 |  | Client : GE VERNOVA T&D INDIA LTD - VT893 | [11 empty] | Order Dt. : 12/06/2025
| 1BPI | EQUIPMENT | 0.243 | 24 | 5.826 | 24 | 5.832 | Mass | 5.826 | 5.826 | 5.826 | 5.826 | 4.377 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.449
| 1BPI2 | EQUIPMENT | 0.293 | 7 | 2.054 | 7 | 2.049 | Mass | 2.054 | 2.054 | 2.054 | 2.054 | 1.375 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.679
| 1BPI3 | EQUIPMENT | 0.275 | 2 | 0.550 | 2 | 0.548 | Proto | 0.550 | 0.359 | 0.307 |  |  | 0.000 | 0.000 | 0.191 | 0.052
| 1BPI4 | EQUIPMENT | 0.440 | 2 | 0.880 | 2 | 0.887 | Proto | 0.880 | 0.705 | 0.489 |  |  | 0.000 | 0.000 | 0.175 | 0.300
| 1NCT | EQUIPMENT | 0.200 | 1 | 0.200 | 1 | 0.203 | Mass | 0.200 | 0.200 | 0.200 | 0.200 | 0.104 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.096
| 1NCT2 | EQUIPMENT | 0.164 | 2 | 0.329 | 2 | 0.337 | Proto | 0.329 | 0.218 | 0.125 |  |  | 0.000 | 0.000 | 0.111 | 0.094
| 1TF | NORMAL TOWER | 2.351 | 4 | 9.402 | 4 | 9.401 | Proto | 9.496 | 5.969 | 4.175 |  |  | 0.000 | -0.093 | 3.526 | 1.794
| 3HBPI | EQUIPMENT | 0.299 | 27 | 8.071 | 27 | 8.069 | Mass | 8.071 | 8.071 | 8.071 | 8.071 | 7.019 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.052
| 3LBPI | EQUIPMENT | 0.218 | 13 | 2.833 | 13 | 2.833 | Mass | 2.833 | 2.833 | 2.833 | 2.833 | 1.771 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.063
| 3LBPI3 | EQUIPMENT | 0.188 | 9 | 1.690 | 9 | 1.695 | Mass | 1.690 | 1.690 | 1.690 | 1.690 | 0.955 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.735
| 3NCT | EQUIPMENT | 0.178 | 3 | 0.535 | 3 | 0.536 | Mass | 0.535 | 0.535 | 0.535 | 0.535 | 0.343 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.192
| 4CVT | EQUIPMENT | 0.186 | 6 | 1.117 | 6 | 1.113 | Mass | 1.117 | 1.117 | 1.117 | 1.117 | 1.117 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4G1 | BEAM | 3.012 | 2 | 6.024 | 2 | 6.025 | Mass | 6.024 | 6.024 | 6.024 | 6.024 | 6.024 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4G2A | BEAM | 3.591 | 9 | 32.318 | 9 | 32.324 | Proto | 32.318 | 32.318 | 32.318 | 32.318 | 32.318 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4HBPI | EQUIPMENT | 0.582 | 9 | 5.239 | 9 | 5.237 | Mass | 5.239 | 5.239 | 5.239 | 5.239 | 5.239 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4LBPI | EQUIPMENT | 0.234 | 12 | 2.806 | 12 | 2.805 | Mass | 2.806 | 2.806 | 2.806 | 2.806 | 2.800 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.007
| 4LLA | EQUIPMENT | 0.240 | 9 | 2.164 | 9 | 2.162 | Mass | 2.164 | 2.164 | 2.164 | 2.164 | 2.164 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4TAS | S.P.S | 0.018 | 2 | 0.035 | 2 | 0.036 | Mass | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4TB | NORMAL TOWER | 4.290 | 2 | 8.579 | 2 | 8.578 | Mass | 8.579 | 8.579 | 8.579 | 8.579 | 8.579 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4TC | NORMAL TOWER | 3.262 | 13 | 42.409 | 13 | 42.405 | Proto | 42.409 | 42.409 | 42.409 | 42.409 | 42.409 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4TD | NORMAL TOWER | 5.780 | 2 | 11.560 | 2 | 11.553 | Proto | 11.560 | 11.560 | 11.560 | 11.560 | 11.560 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4TE | NORMAL TOWER | 3.679 | 1 | 3.679 | 1 | 3.679 | Proto | 3.679 | 3.679 | 3.679 | 3.679 | 3.679 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4WT | EQUIPMENT | 0.499 | 4 | 1.997 | 4 | 1.993 | Mass | 1.997 | 1.997 | 1.997 | 1.997 | 1.934 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.063
| 6HBPI | EQUIPMENT | 0.318 | 27 | 8.595 | 27 | 8.593 | Mass | 8.595 | 8.595 | 8.595 | 8.595 | 7.633 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.962
| 6LBPI2 | EQUIPMENT | 0.284 | 18 | 5.117 | 18 | 5.119 | Mass | 5.117 | 5.117 | 5.117 | 5.117 | 4.297 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.820
| 6LBPI3 | EQUIPMENT | 0.210 | 15 | 3.150 | 15 | 3.150 | Mass | 3.150 | 3.150 | 3.150 | 3.150 | 2.467 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.683
| 7BPI | EQUIPMENT | 0.514 | 11 | 5.654 |  |  | Mass
| 7LA | EQUIPMENT | 0.496 | 3 | 1.488 |  |  | Mass
| IS | COLUMN | 0.070 | 1 | 0.070 | 1 | 0.070 | Mass | 0.070 |  |  |  |  | 0.000 | 0.000 | 0.070
| LM | COLUMN | 7.173 | 9 | 64.556 | 9 | 64.559 | Proto | 64.556 | 64.556 | 64.556 | 64.556 | 59.725 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 4.830
| S | COLUMN | 0.274 | 1 | 0.274 | 1 | 0.271 | Mass | 0.274 |  |  |  |  | 0.000 | 0.000 | 0.274
| SP | EQUIPMENT | 0.020 | 4 | 0.080 | 4 | 0.080 | Mass | 0.080 | 0.080 | 0.080 | 0.080 | 0.080 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| TCTD | S.P.S | 0.044 | 4 | 0.177 | 4 | 0.178 | Mass | 0.177 | 0.177 | 0.177 | 0.177 | 0.177 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 39.626 | 258 | 239.458 | 244 | 232.320 |  | 232.410 | 228.063 | 225.907 | 220.811 | 208.181 | 0.000 | -0.093 | 4.347 | 2.240 | 0.000 | 12.630
| Project Code : 894. |  | Client : ELEMECH ENGINEERING (K) LTD - VT894 | [11 empty] | Order Dt. : 12/10/2025
| HA | STUB | 26.532 | 1 | 26.532 | 1 | 26.534 | Mass | 26.532 | 26.532 | 26.532 | 26.532 | 26.532 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| IS | COLUMN | 0.013 | 1 | 0.013 | 1 | 0.013 | Mass | 0.013 |  |  |  |  | 0.000 | 0.000 | 0.013
|  | Sub Total | 26.545 | 2 | 26.545 | 2 | 26.547 |  | 26.545 | 26.532 | 26.532 | 26.532 | 26.532 | 0.000 | 0.000 | 0.013 | 0.000 | 0.000 | 0.000
| Project Code : 895 |  | Client : ASHOKA BUILDCON LIMITED - VT895 | [11 empty] | Order Dt. : 11/05/2026
| BB2 | BEAM | 1.672 | 2 | 3.345 |  |  | Mass
| BPID | EQUIPMENT | 0.211 | 14 | 2.951 |  |  | Mass
| BPID1 | EQUIPMENT | 0.156 | 13 | 2.022 |  |  | Proto
| CTD | EQUIPMENT | 0.237 | 2 | 0.474 |  |  | Mass
| HA | BEAM | 0.234 | 3 | 0.702 |  |  | Mass
| HGF | EQUIPMENT | 0.197 | 2 | 0.394 |  |  | Mass
| HH | COLUMN | 0.377 | 6 | 2.264 |  |  | Mass
| HP | PEAK | 0.036 | 6 | 0.217 |  |  | Mass
| ISOD | EQUIPMENT | 0.358 | 7 | 2.505 |  |  | Mass
| LAD | EQUIPMENT | 0.223 | 2 | 0.446 |  |  | Mass
| LAD1 | EQUIPMENT | 0.162 | 6 | 0.970 |  |  | Proto
| LCLM | COLUMN | 2.509 | 18 | 45.169 |  |  | Mass
| NCT | EQUIPMENT | 0.127 | 3 | 0.380 |  |  | Mass
| PTD | EQUIPMENT | 0.243 | 4 | 0.973 |  |  | Mass
|  | Sub Total | 6.742 | 88 | 62.812
| Project Code : 896 |  | Client : SRVS SOLARS PRIVATE LIMITED - VT896 | [11 empty] | Order Dt. : 27/06/2025
| 3HA | BEAM | 0.350 | 1 | 0.350 | 1 | 0.349 | Proto | 0.350 | 0.350 | 0.350 | 0.350 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.350
| 3HB | BEAM | 0.351 | 2 | 0.703 | 2 | 0.706 | Proto | 0.703 | 0.703 | 0.703 | 0.703 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.703
| 3HF | COLUMN | 0.918 | 4 | 3.672 | 4 | 3.582 | Proto | 3.580 | 3.580 | 3.580 | 3.580 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 3.580
| 3HH | COLUMN | 0.552 | 2 | 1.104 | 2 | 1.106 | Proto | 1.104 | 1.104 | 1.104 | 1.104 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.104
| 3PI | EQUIPMENT | 0.157 | 2 | 0.314 | 2 | 0.317 | Mass | 0.314 | 0.314 | 0.314 | 0.314 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.314
| CTD | EQUIPMENT | 0.209 | 2 | 0.418 | 2 | 0.419 | Mass | 0.418 | 0.418 | 0.418 | 0.418 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.418
| CTDT | S.S.T | 0.010 | 1 | 0.010 |  |  | Mass
| HGT | S.S.T | 0.034 | 1 | 0.034 |  |  | Mass
| ISODT | S.S.T | 0.026 | 1 | 0.026 |  |  | Mass
| ISODW | EQUIPMENT | 0.368 | 3 | 1.104 | 3 | 1.101 | Proto | 1.104 | 1.104 | 1.104 | 1.104 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.104
| PIT | S.S.T | 0.010 | 1 | 0.010 |  |  | Mass
| PTD | EQUIPMENT | 0.214 | 1 | 0.214 | 1 | 0.212 | Mass | 0.214 | 0.214 | 0.214 | 0.214 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.214
| PTT | S.S.T | 0.010 | 1 | 0.010 |  |  | Mass
|  | Sub Total | 3.210 | 22 | 7.969 | 17 | 7.792 |  | 7.788 | 7.788 | 7.788 | 7.788 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 7.788
| Project Code : 897 |  | Client : PRAKASH ELECTRICAL ENGINEERING CORPORATION. - VT897 | [11 empty] | Order Dt. : 27/06/2025
| BPIB | EQUIPMENT | 0.154 | 29 | 4.471 | 29 | 4.472 | Mass | 4.471 | 4.471 | 4.471 | 4.471 | 4.387 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.084
| BPIC | EQUIPMENT | 0.115 | 21 | 2.408 | 21 | 2.409 | Mass | 2.408 | 2.408 | 2.408 | 2.408 | 2.403 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.005
| BPID | EQUIPMENT | 0.211 | 14 | 2.951 | 14 | 2.953 | Mass | 2.951 | 2.951 | 2.951 | 2.951 | 2.951 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| CCB | EQUIPMENT | 0.118 | 4 | 0.471 | 4 | 0.470 | Mass | 0.471 | 0.471 | 0.471 | 0.471 | 0.456 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.014
| CCC | EQUIPMENT | 0.109 | 10 | 1.089 | 10 | 1.088 | Mass | 1.089 | 1.089 | 1.089 | 1.089 | 1.089 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| CTB | EQUIPMENT | 0.170 | 24 | 4.069 | 24 | 4.070 | Mass | 4.069 | 4.069 | 4.069 | 4.069 | 4.062 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.007
| CTC | EQUIPMENT | 0.122 | 27 | 3.281 | 27 | 3.283 | Mass | 3.281 | 3.281 | 3.281 | 3.281 | 3.281 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| CTD | EQUIPMENT | 0.237 | 13 | 3.078 | 13 | 3.078 | Mass | 3.078 | 3.078 | 3.078 | 3.078 | 3.064 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.014
| HGF | EQUIPMENT | 0.197 | 2 | 0.394 | 2 | 0.394 | Mass | 0.394 | 0.394 | 0.394 | 0.394 | 0.371 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.023
| IS | COLUMN | 0.007 | 1 | 0.007 | 1 | 0.006 | Mass | 0.007 | 0.007 | 0.001 |  |  | 0.000 | 0.000 | 0.000 | 0.006
| ISOB | EQUIPMENT | 0.843 | 2 | 1.686 | 2 | 1.685 | Mass | 1.686 | 1.686 | 1.686 | 1.686 | 1.681 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.005
| ISOBW | EQUIPMENT | 0.829 | 29 | 24.052 | 29 | 24.050 | Mass | 24.052 | 24.052 | 24.052 | 24.052 | 24.052 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| ISOC | EQUIPMENT | 0.594 | 5 | 2.971 | 5 | 2.971 | Mass | 2.971 | 2.971 | 2.971 | 2.971 | 2.928 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.043
| ISOCW | EQUIPMENT | 0.559 | 22 | 12.305 | 22 | 12.306 | Mass | 12.305 | 12.305 | 12.305 | 12.305 | 12.262 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.042
| ISOD | EQUIPMENT | 0.347 | 8 | 2.774 | 8 | 2.776 | Mass | 2.774 | 2.774 | 2.774 | 2.774 | 2.718 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.056
| ISODW | EQUIPMENT | 0.346 | 22 | 7.602 | 22 | 7.604 | Mass | 7.602 | 7.602 | 7.602 | 7.602 | 7.559 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.042
| LAB | EQUIPMENT | 0.163 | 18 | 2.942 | 18 | 2.941 | Mass | 2.942 | 2.942 | 2.942 | 2.942 | 2.942 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| LAC | EQUIPMENT | 0.117 | 21 | 2.448 | 21 | 2.449 | Mass | 2.448 | 2.448 | 2.448 | 2.448 | 2.448 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.001
| LM | COLUMN | 1.252 | 11 | 13.770 | 11 | 13.771 | Mass | 13.770 | 13.770 | 13.770 | 13.770 | 13.770 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| PTB | EQUIPMENT | 0.148 | 6 | 0.890 | 6 | 0.889 | Mass | 0.890 | 0.890 | 0.890 | 0.890 | 0.888 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.002
| PTC | EQUIPMENT | 0.117 | 6 | 0.702 | 6 | 0.703 | Mass | 0.702 | 0.702 | 0.702 | 0.702 | 0.696 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.005
| PTD | EQUIPMENT | 0.243 | 2 | 0.487 | 2 | 0.487 | Mass | 0.487 | 0.487 | 0.487 | 0.487 | 0.487 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| WTB | EQUIPMENT | 0.304 | 4 | 1.216 |  |  | Mass
| WTC | EQUIPMENT | 0.238 | 10 | 2.381 |  |  | Mass
|  | Sub Total | 7.539 | 311 | 98.445 | 297 | 94.855 |  | 94.847 | 94.847 | 94.841 | 94.840 | 94.497 | 0.000 | 0.000 | 0.000 | 0.006 | 0.000 | 0.343
| Project Code : 898. |  | Client : ASHOKA BUILDCON LIMITED - VT898 | [11 empty] | Order Dt. : 17/11/2025
| 2DA1 | S.S.T | 0.430 | 4 | 1.720 | 4 | 1.721 | Mass | 1.720 | 1.720 | 1.720 | 1.720 | 1.720 | 0.001 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DW3 | NORMAL TOWER | 8.078 | 14 | 113.098 | 14 | 113.099 | Mass | 113.098 | 113.098 | 113.098 | 113.098 | 113.098 | 0.214 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4DA3 | NORMAL TOWER | 10.468 | 6 | 62.807 | 6 | 62.810 | Mass | 62.807 | 0.692 | 0.692 |  |  | 0.085 | 0.000 | 62.115 | 0.000
| 4DA3M | +3 MTR EXTN | 1.422 | 2 | 2.844 | 2 | 2.844 | Mass | 2.844 |  |  |  |  | 0.001 | 0.000 | 2.844
| 4DA6M | +6 MTR EXTN | 2.316 | 1 | 2.316 | 1 | 2.321 | Mass | 2.316 |  |  |  |  | 0.001 | 0.000 | 2.316
| 4DC3 | NORMAL TOWER | 22.210 | 4 | 88.841 | 4 | 88.839 | Mass | 88.841 | 88.841 | 88.841 | 88.841 | 88.841 | 0.130 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4DD15M | +15 MTR EXTN | 15.368 | 2 | 30.736 | 2 | 30.741 | Mass | 30.736 | 0.860 | 0.860 |  |  | 0.050 | 0.000 | 29.877 | 0.000
| 4DD2 | STUB | 0.966 | 4 | 3.865 | 4 | 3.865 | Mass | 3.865 | 3.865 | 3.865 | 3.865 | 3.865 | 0.007 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4DD2A | STUB | 0.966 | 1 | 0.966 | 1 | 0.965 | Mass | 0.966 | 0.966 | 0.966 | 0.966 | 0.966 | 0.001 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4DD3 | NORMAL TOWER | 22.923 | 10 | 229.232 | 10 | 229.234 | Mass | 229.232 | 206.309 | 206.309 | 229.232 | 206.309 | 0.404 | 0.000 | 22.923 | 0.000 | -22.923 | 22.923
| 4DD3M | +3 MTR EXTN | 4.197 | 1 | 4.197 | 1 | 4.197 | Mass | 4.197 |  |  |  |  | 0.004 | 0.000 | 4.197
|  | Sub Total | 89.346 | 49 | 540.622 | 49 | 540.636 |  | 540.623 | 416.350 | 416.350 | 437.722 | 414.799 | 0.898 | 0.000 | 124.273 | 0.000 | -22.923 | 22.923
| Project Code : 899 |  | Client : IDEAS ELECTRICALS & ENGINEERS PVT. LTD. - VT899 | [11 empty] | Order Dt. : 01/08/2025
| AA | BEAM | 0.991 | 7 | 6.938 | 7 | 6.938 | Mass | 6.938 | 6.938 | 6.938 | 6.938 | 6.866 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.072
| AB | BEAM | 0.880 | 5 | 4.400 | 5 | 4.402 | Mass | 4.400 | 4.400 | 4.400 | 4.400 | 4.068 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.332
| AC | BEAM | 0.807 | 2 | 1.614 | 2 | 1.614 | Mass | 1.614 | 1.614 | 1.614 | 1.614 | 1.563 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.051
| AF | COLUMN | 2.235 | 6 | 13.408 | 6 | 13.409 | Mass | 13.408 | 13.408 | 13.408 | 13.408 | 13.311 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.096
| AG | COLUMN | 1.956 | 2 | 3.913 | 2 | 3.916 | Mass | 3.913 | 3.913 | 3.913 | 3.913 | 3.822 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.091
| AH | COLUMN | 0.930 | 13 | 12.094 | 13 | 12.096 | Mass | 12.094 | 12.094 | 12.094 | 12.094 | 11.961 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.133
| AP | PEAK | 0.080 | 21 | 1.676 | 21 | 1.676 | Mass | 1.676 | 1.676 | 1.676 | 1.676 | 1.621 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.056
| BPIB | EQUIPMENT | 0.154 | 12 | 1.850 | 12 | 1.850 | Mass | 1.850 | 1.850 | 1.850 | 1.850 | 1.850 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| BPIC | EQUIPMENT | 0.115 | 35 | 4.013 | 35 | 4.014 | Mass | 4.013 | 4.013 | 4.013 | 4.013 | 3.370 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.643
| BPID | EQUIPMENT | 0.211 | 24 | 5.059 | 24 | 5.060 | Mass | 5.059 | 5.059 | 5.059 | 5.059 | 4.690 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.369
| CCB | EQUIPMENT | 0.118 | 2 | 0.235 | 2 | 0.235 | Mass | 0.235 | 0.235 | 0.235 | 0.235 | 0.176 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.059
| CCC | EQUIPMENT | 0.109 | 8 | 0.871 | 8 | 0.870 | Mass | 0.871 | 0.871 | 0.871 | 0.871 | 0.506 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.365
| CTB | EQUIPMENT | 0.170 | 9 | 1.526 | 9 | 1.526 | Mass | 1.526 | 1.526 | 1.526 | 1.526 | 1.526 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| CTC | EQUIPMENT | 0.122 | 39 | 4.740 | 39 | 4.740 | Mass | 4.740 | 4.740 | 4.740 | 4.740 | 3.360 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.380
| CTD | EQUIPMENT | 0.237 | 36 | 8.525 | 36 | 8.523 | Mass | 8.525 | 8.525 | 8.525 | 8.525 | 7.525 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.000
| FC | BEAM | 0.407 | 4 | 1.627 | 4 | 1.626 | Mass | 1.627 | 1.627 | 1.627 | 1.627 | 1.178 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.449
| FD | BEAM | 0.502 | 16 | 8.038 | 16 | 8.035 | Mass | 8.038 | 8.038 | 8.038 | 8.038 | 7.211 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.827
| FE | BEAM | 0.465 | 18 | 8.370 | 18 | 8.375 | Mass | 8.370 | 8.370 | 8.370 | 8.370 | 6.797 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.573
| FF | NORMAL TOWER | 1.176 | 18 | 21.163 | 18 | 21.166 | Mass | 21.163 | 21.163 | 21.163 | 21.163 | 18.755 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 2.408
| FG | NORMAL TOWER | 1.060 | 28 | 29.675 | 28 | 29.676 | Mass | 29.675 | 29.675 | 29.675 | 29.675 | 28.243 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.432
| FH | NORMAL TOWER | 0.540 | 26 | 14.031 | 26 | 14.027 | Mass | 14.031 | 14.031 | 14.031 | 14.031 | 12.540 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.491
| FP | PEAK | 0.069 | 72 | 4.997 | 72 | 4.997 | Mass | 4.997 | 4.997 | 4.997 | 4.997 | 4.776 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.221
| HA | BEAM | 0.234 | 66 | 15.434 | 66 | 15.436 | Mass | 15.434 | 15.434 | 15.434 | 15.434 | 14.167 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.267
| HG | NORMAL TOWER | 0.425 | 62 | 26.374 | 62 | 26.372 | Mass | 26.374 | 26.374 | 26.374 | 26.374 | 25.008 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.366
| HGF | EQUIPMENT | 0.197 | 6 | 1.182 | 6 | 1.182 | Mass | 1.182 | 1.182 | 1.182 | 1.182 | 1.134 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.049
| HH | NORMAL TOWER | 0.377 | 28 | 10.566 | 28 | 10.563 | Mass | 10.566 | 10.566 | 10.566 | 10.566 | 10.159 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.407
| HP | PEAK | 0.036 | 90 | 3.254 | 90 | 3.255 | Mass | 3.254 | 3.254 | 3.254 | 3.254 | 1.775 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.479
| IS | COLUMN | 1.071 | 1 | 1.071 | 1 | 1.073 | Mass | 1.071 | 0.975 | 0.118 |  |  | 0.000 | 0.000 | 0.096 | 0.857
| ISOBW | EQUIPMENT | 0.829 | 14 | 11.611 | 14 | 11.611 | Mass | 11.611 | 11.611 | 11.611 | 11.611 | 11.602 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.010
| ISOC | EQUIPMENT | 0.594 | 5 | 2.971 | 5 | 2.971 | Mass | 2.971 | 2.971 | 2.971 | 2.971 | 2.625 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.346
| ISOCW | EQUIPMENT | 0.559 | 34 | 19.016 | 34 | 19.016 | Mass | 19.016 | 19.016 | 19.016 | 19.016 | 18.427 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.589
| ISOD | EQUIPMENT | 0.358 | 27 | 9.664 | 27 | 9.662 | Mass | 9.664 | 9.664 | 9.664 | 9.664 | 8.067 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.597
| ISODW | EQUIPMENT | 0.346 | 60 | 20.731 | 60 | 20.730 | Mass | 20.731 | 20.731 | 20.731 | 20.731 | 15.642 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 5.089
| LAB | EQUIPMENT | 0.163 | 9 | 1.471 | 9 | 1.470 | Mass | 1.471 | 1.471 | 1.471 | 1.471 | 1.471 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| LAC | EQUIPMENT | 0.117 | 27 | 3.148 | 27 | 3.150 | Mass | 3.148 | 3.148 | 3.148 | 3.148 | 2.520 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.628
| LM | COLUMN | 1.252 | 16 | 20.029 | 16 | 20.022 | Mass | 20.029 | 20.029 | 20.029 | 20.029 | 17.273 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 2.756
| PTC | EQUIPMENT | 0.117 | 12 | 1.403 | 12 | 1.403 | Mass | 1.403 | 1.403 | 1.403 | 1.403 | 1.083 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.321
| PTD | EQUIPMENT | 0.243 | 6 | 1.460 | 6 | 1.455 | Mass | 1.460 | 1.460 | 1.460 | 1.460 | 1.286 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.174
| SC | NORMAL TOWER | 0.006 | 1 | 0.006 | 1 | 0.006 | Mass | 0.006 | 0.006 | 0.006 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| WTB | EQUIPMENT | 0.304 | 2 | 0.608 | 2 | 0.607 | Mass | 0.608 | 0.608 | 0.608 | 0.608 | 0.588 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.020
| WTC | EQUIPMENT | 0.238 | 8 | 1.905 | 8 | 1.903 | Mass | 1.905 | 1.905 | 1.905 | 1.905 | 1.143 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.762
|  | Sub Total | 20.800 | 877 | 310.667 | 877 | 310.658 |  | 310.668 | 310.571 | 309.714 | 309.590 | 279.683 | 0.000 | 0.000 | 0.096 | 0.857 | 0.000 | 29.907
| Project Code : 900 |  | Client : STELMEC LIMITED - VT900 | [11 empty] | Order Dt. : 02/08/2025
| 4QDD2 | STUB | 1.814 | 3 | 5.442 | 3 | 5.441 | Proto | 5.442 | 5.442 | 5.442 | 5.442 | 5.442 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4QDD25M | +25.0 Mtr. Extn | 45.176 | 2 | 90.353 | 2 | 90.361 | Proto | 85.626 | 44.028 | 22.180 |  |  | 0.000 | 4.727 | 41.598 | 21.848
| 4QDD2A | STUB | 3.673 | 2 | 7.346 | 2 | 7.348 | Proto | 7.346 | 7.346 | 7.346 | 7.346 | 7.346 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4QDD3 | NORMAL TOWER | 42.811 | 5 | 214.055 | 4 | 171.239 | Proto | 9.629 |  |  |  |  | 0.000 | 161.615 | 9.629
| 4QDD3. | NORMAL TOWER | 42.811 | 5 | 214.055 | 5 | 214.063 | Proto | 212.883 | 45.641 | 24.600 |  |  | 0.000 | 1.172 | 167.242 | 21.041
| 4QDD3A | NORMAL TOWER | 3.686 | 3 | 11.059 | 3 | 11.063 | Proto | 9.609 |  |  |  |  | 0.000 | 1.449 | 9.609
| 4QMD2 | STUB | 7.749 | 5 | 38.743 | 4 | 30.996 | Proto | 30.995 | 30.995 | 30.995 | 30.995 | 30.995 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
[6 empty] | 1 | 7.747 | Mass | 7.749 | 7.749 | 7.749 | 7.749 | 7.749 | 23.249 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4QMD3 | NORMAL TOWER | 166.900 | 5 | 834.502 | 4 | 667.569 | Proto | 620.418 | 206.699 | 143.612 |  |  | 0.000 | 47.183 | 413.719 | 63.088
| 4QMD3. | NORMAL TOWER | 166.900 | 1 | 166.900 | 1 | 166.879 | Proto | 136.722 | 1.000 | 1.000 |  |  | 0.000 | 30.178 | 135.722 | 0.000
| 4QMD3M | +3 MTR EXTN | 27.559 | 2 | 55.118 | 2 | 55.126 | Proto | 50.828 | 30.084 | 17.266 |  |  | 0.000 | 4.290 | 20.745 | 12.818
|  | Sub Total | 516.829 | 33 | 1637.573 | 31 | 1427.832 |  | 1177.248 | 378.983 | 260.189 | 51.531 | 51.531 | 23.249 | 250.614 | 798.265 | 118.794 | 0.000 | 0.000
| Project Code : 901 |  | Client : IDEAS ELECTRICALS & ENGINEERS PVT. LTD. - VT901 | [11 empty] | Order Dt. : 02/08/2025
| 1DP3 | NORMAL TOWER | 2.507 | 26 | 65.180 |  |  | Mass
| 1DP3M | +3 MTR EXTN | 0.394 | 13 | 5.126 |  |  | Mass
| 1DP6M | +6 MTR EXTN | 0.822 | 3 | 2.465 |  |  | Mass
| 1DR3 | NORMAL TOWER | 3.501 | 5 | 17.507 |  |  | Mass
| 1DR3M | +3 MTR EXTN | 0.687 | 2 | 1.375 |  |  | Mass
| 1DS3 | NORMAL TOWER | 4.602 | 6 | 27.615 |  |  | Mass
| 1DS3M | +3 MTR EXTN | 1.243 | 3 | 3.730 | 3 | 3.728 | Mass | 3.730 | 3.730 | 3.730 | 3.730 | 2.920 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.810
| 1DS6M | +6 MTR EXTN | 2.047 | 3 | 6.141 |  |  | Mass
| 1MP3 | NORMAL TOWER | 7.019 | 2 | 14.038 | 2 | 14.032 | Mass | 14.038 | 14.038 | 14.038 | 14.038 | 9.366 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 4.671
| 1MP3M | +3 MTR EXTN | 1.066 | 2 | 2.133 | 2 | 2.130 | Mass | 2.133 | 2.133 | 2.133 | 2.133 | 1.674 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.459
| 1MR3 | NORMAL TOWER | 11.293 | 1 | 11.293 | 1 | 11.311 | Mass | 11.293 | 11.293 | 11.293 | 11.293 | 8.944 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 2.348
| 1MS3 | NORMAL TOWER | 14.642 | 2 | 29.285 | 2 | 29.152 | Mass | 21.052 | 21.052 | 21.052 | 29.146 | 23.829 | 0.000 | 8.093 | 0.000 | 0.000 | -8.093 | 5.317
| 1MS3M | +3 MTR EXTN | 2.615 | 1 | 2.615 |  |  | Mass
| 2DD3 | NORMAL TOWER | 7.508 | 2 | 15.016 |  |  | Mass
| 2MC3 | NORMAL TOWER | 19.203 | 1 | 19.203 |  |  | Mass
| 2MD3 | NORMAL TOWER | 25.556 | 5 | 127.778 |  |  | Mass
| 2MD3M | +3 MTR EXTN | 4.982 | 1 | 4.982 |  |  | Mass
| IS | COLUMN | 0.233 | 1 | 0.233 | 1 | 0.232 | Mass | 0.233 |  |  |  |  | 0.000 | 0.000 | 0.233
|  | Sub Total | 109.920 | 79 | 355.715 | 11 | 60.585 |  | 52.479 | 52.246 | 52.246 | 60.339 | 46.733 | 0.000 | 8.093 | 0.233 | 0.000 | -8.093 | 13.606
| Project Code : 902 |  | Client : LARSEN & TOUBRO LIMITED CONSTRUCTION - VT902 | [11 empty] | Order Dt. : 02/08/2025
| 1DPS | EQUIPMENT | 2.650 | 1 | 2.650 | 1 | 2.653 | Proto | 2.650 | 2.650 | 2.650 | 2.650 | 2.650 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DPS | EQUIPMENT | 4.280 | 1 | 4.280 | 1 | 4.271 | Proto | 4.280 | 4.280 | 4.280 | 4.280 | 4.280 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3HBPI | EQUIPMENT | 0.151 | 4 | 0.604 | 4 | 0.602 | Proto | 0.604 | 0.045 | 0.040 | 0.604 |  | 0.000 | 0.000 | 0.559 | 0.006 | -0.564 | 0.604
| 3HGF | EQUIPMENT | 0.200 | 1 | 0.200 | 1 | 0.199 | Proto | 0.200 | 0.200 | 0.200 | 0.200 | 0.200 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3ISO1 | EQUIPMENT | 0.052 | 2 | 0.104 | 2 | 0.103 | Mass | 0.104 | 0.104 | 0.104 | 0.104 | 0.104 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3ISOW | EQUIPMENT | 0.024 | 5 | 0.121 | 5 | 0.122 | Mass | 0.121 | 0.121 | 0.121 | 0.121 | 0.121 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3LA | EQUIPMENT | 0.168 | 3 | 0.503 | 3 | 0.167 | Proto | 0.168 | 0.242 | 0.207 | 0.503 | 0.001 | 0.000 | 0.000 | -0.074 | 0.035 | -0.296 | 0.503
| 3LBPI | EQUIPMENT | 0.117 | 2 | 0.234 | 2 | -0.477 | Proto | -0.476 | 0.030 | 0.023 | 0.234 |  | 0.000 | 0.000 | -0.506 | 0.007 | -0.211 | 0.234
| 3MBPI | EQUIPMENT | 0.148 | 3 | 0.444 | 3 | -0.275 | Proto | -0.271 | 0.087 | 0.081 | 0.444 |  | 0.000 | -0.006 | -0.357 | 0.006 | -0.364 | 0.444
| IS | COLUMN | 0.303 | 1 | 0.303 | 1 | 0.301 | Mass | 0.303 |  |  |  |  | 0.000 | 0.000 | 0.303
|  |  |  | 1 | 0.109 | 1 | 0.108 | Mass | [5 empty] | 0.000 | 0.109
| RB1 | BEAM | 0.830 | 2 | 1.660 | 2 | 1.665 | Mass | 1.660 | 1.660 | 1.528 | 1.660 | 0.994 | 0.000 | 0.000 | 0.000 | 0.132 | -0.132 | 0.666
| RBA | BEAM | 1.876 | 8 | 15.007 | 8 | 15.017 | Mass | 15.007 | 15.007 | 14.939 | 15.007 | 9.789 | 0.000 | 0.000 | 0.000 | 0.068 | -0.068 | 5.218
| RT2 | COLUMN | 1.711 | 3 | 5.134 | 3 | 5.131 | Mass | 5.134 | 5.134 | 5.082 | 5.134 | 2.238 | 0.000 | 0.000 | 0.000 | 0.053 | -0.053 | 2.896
| RTB | COLUMN | 7.763 | 8 | 62.102 | 8 | 62.098 | Mass | 62.102 | 62.102 | 58.767 | 62.102 | 47.251 | 0.000 | 0.000 | 0.000 | 3.335 | -3.335 | 14.851
| SC | NORMAL TOWER | 0.162 | 1 | 0.162 | 1 | 0.163 | Mass | 0.162 | 0.162 | 0.045 |  |  | 0.000 | 0.000 | 0.000 | 0.118
|  |  |  | 1 | 0.022 | 1 | 0.022 | Mass | 0.022 | 0.004 | 0.004 |  |  | 0.000 | 0.000 | 0.018 | 0.000
|  | Sub Total | 20.567 | 47 | 93.639 | 47 | 91.870 |  | 91.771 | 91.829 | 88.071 | 93.044 | 67.628 | 0.000 | 0.103 | -0.058 | 3.759 | -5.022 | 25.416
| Project Code : 903 |  | Client : BIHAR STATE POWER TRANSMISSION COMPANY LTD - VT903 | [11 empty] | Order Dt. : 11/08/2025
| 2DA2 | STUB | 0.210 | 25 | 5.245 | 25 | 5.244 | Proto | 5.245 | 5.245 | 4.555 | 5.245 | 1.260 | 0.000 | 0.000 | 0.000 | 0.691 | -0.691 | 3.985
| 2DA2R | STUB | 0.134 | 4 | 0.536 | 4 | 0.537 | Proto | 0.000 |  |  | 0.536 |  | 0.000 | 0.536 | 0.000 |  | -0.536 | 0.536
| 2DA3 | NORMAL TOWER | 4.098 | 15 | 61.464 | 15 | 61.464 | Proto | 61.464 | 59.654 | 59.327 | 61.464 | 8.860 | 0.000 | 0.000 | 1.809 | 0.327 | -2.136 | 52.604
| 2DA3M | +3 MTR EXTN | 0.654 | 10 | 6.537 | 10 | 6.536 | Proto | 6.537 | 6.516 | 6.483 | 6.537 | 0.158 | 0.000 | 0.000 | 0.020 | 0.033 | -0.053 | 6.378
| 2DB2 | STUB | 0.256 | 20 | 5.112 | 20 | 5.112 | Mass | 5.112 | 5.112 | 5.112 | 5.112 | 1.278 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 3.834
| 2DB2R | STUB | 0.183 | 4 | 0.730 | 4 | 0.730 | Proto | 0.730 |  |  | 0.730 |  | 0.000 | 0.000 | 0.730 |  | -0.730 | 0.730
| 2DB3 | NORMAL TOWER | 6.346 | 10 | 63.461 | 10 | 63.568 | Mass | 63.567 | 58.691 | 58.069 | 63.567 | 10.666 | -0.106 | 0.000 | 4.875 | 0.623 | -5.498 | 52.901
| 2DB3M | +3 MTR EXTN | 1.392 | 5 | 6.958 | 5 | 6.957 | Proto | 6.958 | 6.477 | 6.430 | 6.958 |  | 0.000 | 0.000 | 0.480 | 0.048 | -0.528 | 6.958
| 2DB6M | +6 MTR EXTN | 2.174 | 5 | 10.872 | 3 | 6.519 | Mass | 6.523 | 6.217 | 5.762 | 6.523 |  | 4.350 | 0.000 | 0.305 | 0.456 | -0.761 | 6.523
| 2DC2 | STUB | 0.314 | 10 | 3.138 | 10 | 3.137 | Mass | 3.138 | 3.138 | 3.138 | 3.138 | 1.569 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.569
| 2DC2R | STUB | 0.225 | 4 | 0.899 | 4 | 0.899 | Proto | 0.899 | 0.899 | 0.227 | 0.899 |  | 0.000 | 0.000 | 0.000 | 0.673 | -0.673 | 0.899
| 2DC3 | NORMAL TOWER | 6.782 | 10 | 67.820 | 8 | 54.249 | Mass | 54.256 | 52.744 | 52.004 | 54.256 | 14.054 | 13.567 | 0.000 | 1.512 | 0.740 | -2.252 | 40.202
| 2DD18M | +18 MTR EXTN | 9.865 | 5 | 49.327 | 5 | 49.331 | Mass | 49.327 | 48.890 | 48.758 | 49.327 | 12.256 | 0.000 | 0.000 | 0.437 | 0.132 | -0.569 | 37.072
| 2DD2 | STUB | 0.397 | 25 | 9.922 | 25 | 9.920 | Mass | 9.922 | 9.922 | 9.922 | 9.922 | 2.381 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 7.540
| 2DD2A | STUB | 0.462 | 5 | 2.309 | 5 | 2.309 | Mass | 2.309 | 2.309 | 2.309 | 2.309 | 1.386 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.924
| 2DD2B | STUB | 0.462 | 5 | 2.309 | 5 | 2.309 | Mass | 2.309 | 2.309 | 2.309 | 2.309 | 0.462 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.847
| 2DD2R | STUB | 0.251 | 8 | 2.005 | 8 | 2.005 | Proto | 2.005 |  |  | 2.005 |  | 0.000 | 0.000 | 2.005 |  | -2.005 | 2.005
| 2DD3 | NORMAL TOWER | 8.606 | 15 | 129.096 | 15 | 129.101 | Mass | 131.444 | 114.784 | 112.777 | 129.096 | 35.064 | 0.000 | -2.348 | 16.660 | 2.007 | -16.319 | 94.033
| 2DD3M | +3 MTR EXTN | 1.886 | 5 | 9.430 | 5 | 9.430 | Proto | 9.430 | 8.077 | 7.803 | 9.430 | 0.773 | 0.000 | 0.000 | 1.353 | 0.274 | -1.627 | 8.657
| 2DD6M | +6 MTR EXTN | 3.134 | 5 | 15.671 | 5 | 15.671 | Mass | 15.671 | 14.658 | 14.524 | 15.671 | 0.903 | 0.000 | 0.000 | 1.012 | 0.134 | -1.146 | 14.768
| 2DD9M | +9 MTR EXTN | 4.052 | 5 | 20.258 | 5 | 20.252 | Mass | 20.258 | 19.414 | 19.398 | 20.258 | 1.671 | 0.000 | 0.000 | 0.844 | 0.016 | -0.861 | 18.587
|  | Sub Total | 51.881 | 200 | 473.099 | 196 | 455.280 |  | 457.104 | 425.059 | 418.907 | 455.293 | 92.740 | 17.811 | -1.812 | 32.045 | 6.152 | -36.386 | 362.552
| Project Code : 904 |  | Client : BIHAR STATE POWER TRANSMISSION COMPANY LTD - VT903 | [11 empty] | Order Dt. : 11/08/2025
| 1DA2 | STUB | 0.142 | 25 | 3.555 | 25 | 3.554 | Mass | 3.555 | 3.555 | 3.555 | 3.555 | 0.149 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 3.405
| 1DA2R | STUB | 0.088 | 10 | 0.882 | 10 | 0.882 | Mass | 0.882 | 0.882 | 0.882 | 0.882 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.882
| 1DA3 | NORMAL TOWER | 2.878 | 15 | 43.167 | 15 | 43.173 | Mass | 43.167 | 43.155 | 43.007 | 43.167 | 2.359 | 0.000 | 0.000 | 0.012 | 0.147 | -0.159 | 40.808
| 1DA3M | +3 MTR EXTN | 0.614 | 5 | 3.070 | 5 | 3.075 | Mass | 3.070 | 3.028 | 2.515 | 3.070 |  | 0.000 | 0.000 | 0.042 | 0.513 | -0.555 | 3.070
| 1DA6M | +6 MTR EXTN | 0.991 | 5 | 4.957 | 5 | 4.957 | Mass | 4.957 | 4.890 | 4.774 | 4.957 |  | 0.000 | 0.000 | 0.067 | 0.116 | -0.183 | 4.957
| 1DB2 | STUB | 0.253 | 25 | 6.334 | 25 | 6.333 | Mass | 6.334 | 6.334 | 6.334 | 6.334 | 0.003 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 6.331
| 1DB2R | STUB | 0.150 | 6 | 0.901 | 6 | 0.901 | Mass | 0.901 | 0.901 | 0.901 | 0.901 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.901
| 1DB3 | NORMAL TOWER | 4.701 | 15 | 70.520 | 15 | 70.527 | Mass | 70.520 | 70.347 | 67.571 | 70.520 | 5.695 | 0.000 | 0.000 | 0.173 | 2.776 | -2.949 | 64.825
| 1DB3M | +3 MTR EXTN | 0.866 | 5 | 4.330 | 5 | 4.329 | Mass | 4.330 | 4.274 | 4.240 | 4.330 | 0.216 | 0.000 | 0.000 | 0.056 | 0.034 | -0.090 | 4.114
| 1DB6M | +6 MTR EXTN | 1.507 | 5 | 7.533 | 5 | 7.536 | Mass | 7.533 | 7.477 | 7.429 | 7.533 | 0.004 | 0.000 | 0.000 | 0.056 | 0.048 | -0.105 | 7.529
| 1DC2 | STUB | 0.282 | 25 | 7.059 | 25 | 7.061 | Mass | 7.059 | 7.059 | 7.059 | 7.059 | 0.282 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 6.777
| 1DC2R | STUB | 0.182 | 5 | 0.911 | 5 | 0.911 | Mass | 0.911 | 0.911 | 0.911 | 0.911 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.911
| 1DC3 | NORMAL TOWER | 4.832 | 15 | 72.476 | 15 | 72.475 | Mass | 72.476 | 71.898 | 71.789 | 72.476 | 10.941 | 0.000 | 0.000 | 0.578 | 0.109 | -0.687 | 61.535
| 1DC3M | +3 MTR EXTN | 1.026 | 5 | 5.131 | 5 | 5.131 | Mass | 5.131 | 5.131 | 5.126 | 5.131 | 0.007 | 0.000 | 0.000 | 0.000 | 0.005 | -0.005 | 5.124
| 1DC6M | +6 MTR EXTN | 1.828 | 5 | 9.141 | 5 | 9.092 | Mass | 9.092 | 9.042 | 8.996 | 9.092 | 0.005 | 0.000 | 0.000 | 0.049 | 0.046 | -0.095 | 9.087
| 1DD18M | +18 MTR EXTN | 7.036 | 10 | 70.359 | 6 | 42.129 | Mass | 42.215 | 42.115 | 41.934 | 42.127 | 5.974 | 28.229 | -0.088 | 0.101 | 0.181 | -0.193 | 36.153
| 1DD2 | STUB | 0.351 | 30 | 10.544 | 30 | 10.545 | Mass | 10.544 | 10.544 | 10.544 | 10.544 | 0.351 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 10.193
| 1DD25M | +25.0 Mtr. Extn | 11.807 | 1 | 11.807 | 1 | 11.789 | Mass | 11.807 | 11.796 | 11.654 | 11.785 |  | 0.022 | -0.022 | 0.012 | 0.142 | -0.131 | 11.785
| 1DD2A | STUB | 0.406 | 11 | 4.470 | 7 | 2.845 | Mass | 2.845 | 2.845 | 2.845 | 2.845 |  | 1.626 | 0.000 | 0.000 | 0.000 | 0.000 | 2.845
| 1DD2R | STUB | 0.211 | 9 | 1.900 | 9 | 1.899 | Mass | 1.900 | 1.900 | 1.900 | 1.900 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.900
| 1DD3 | NORMAL TOWER | 6.148 | 15 | 92.213 | 15 | 92.222 | Mass | 92.213 | 90.513 | 87.384 | 92.213 | 7.597 | 0.000 | 0.000 | 1.700 | 3.129 | -4.828 | 84.615
| 1DD3M | +3 MTR EXTN | 1.386 | 5 | 6.930 | 5 | 6.934 | Mass | 6.930 | 6.908 | 6.908 | 6.930 | 0.219 | 0.000 | 0.000 | 0.021 | 0.000 | -0.021 | 6.711
| 1DD6M | +6 MTR EXTN | 2.118 | 5 | 10.590 | 5 | 10.588 | Mass | 10.590 | 10.574 | 10.534 | 10.590 | 0.383 | 0.000 | 0.000 | 0.016 | 0.040 | -0.057 | 10.208
| 1DD9M | +9 MTR EXTN | 3.029 | 5 | 15.145 | 2 | 6.059 | Mass | 6.058 | 6.035 | 6.016 | 6.058 |  | 9.090 | 0.000 | 0.023 | 0.019 | -0.042 | 6.058
|  | Sub Total | 52.834 | 262 | 463.925 | 251 | 424.947 |  | 425.019 | 422.113 | 414.809 | 424.909 | 34.186 | 38.967 | -0.110 | 2.906 | 7.304 | -10.100 | 390.723
| Project Code : 905 |  | Client : SIEMENS ENERGY IN LTD - VT905 | [11 empty] | Order Dt. : 27/08/2025
| 2GB1 | BEAM | 2.080 | 6 | 12.479 |  |  | Mass
| 2GB2 | BEAM | 2.353 | 10 | 23.530 |  |  | Mass
| 2GT1 | COLUMN | 2.879 | 10 | 28.789 |  |  | Mass
| 2GT2 | NORMAL TOWER | 7.495 | 7 | 52.463 |  |  | Mass
| 4GB1 | BEAM | 4.233 | 6 | 25.401 |  |  | Mass
| 4GB2 | BEAM | 4.896 | 8 | 39.165 | 8 | 39.166 | Mass | 39.165 | 39.165 | 39.165 | 39.165 | 9.791 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 29.374
| 4GT1 | COLUMN | 4.765 | 8 | 38.119 |  |  | Mass
| 4GT2 | COLUMN | 12.309 | 4 | 49.234 |  |  | Mass
|  | Sub Total | 41.010 | 59 | 269.180 | 8 | 39.166 |  | 39.165 | 39.165 | 39.165 | 39.165 | 9.791 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 29.374
| Project Code : 906. |  | Client : BNC POWER PROJECTS LTD - VT906 | [11 empty] | Order Dt. : 27/09/2025
| 3HBPIDA | EQUIPMENT | 0.168 | 3 | 0.504 | 3 | 0.502 | Mass | [5 empty] | 0.000 | 0.504
| 3HBPIDB | EQUIPMENT | 0.204 | 5 | 1.020 | 5 | 1.019 | Mass | [5 empty] | 0.000 | 1.020
| 3HBPIDC | EQUIPMENT | 0.234 | 15 | 3.504 | 15 | 3.503 | Mass | [5 empty] | 0.000 | 3.504
| 3HNCTD | EQUIPMENT | 0.164 | 1 | 0.164 | 1 | 0.164 | Mass | [5 empty] | 0.000 | 0.164
| 3HPTDJ | EQUIPMENT | 0.274 | 1 | 0.274 | 1 | 0.272 | Mass | [5 empty] | 0.000 | 0.274
| 3LAD | EQUIPMENT | 0.223 | 2 | 0.446 | 2 | 0.444 | Mass | [5 empty] | 0.000 | 0.446
| 4BPI | EQUIPMENT | 0.250 | 12 | 2.996 | 12 | 2.996 | Mass | 2.996 | 1.743 | 0.982 |  |  | 0.000 | 0.000 | 1.253 | 0.760
| 4CT | EQUIPMENT | 0.225 | 6 | 1.349 | 6 | 1.348 | Mass | 1.349 | 1.117 | 0.849 |  |  | 0.000 | 0.000 | 0.232 | 0.268
| 4HBPI | EQUIPMENT | 0.497 | 9 | 4.475 |  |  | Mass
| 4ISO1 | EQUIPMENT | 0.484 | 3 | 1.451 |  |  | Proto
| 4ISO1ES | EQUIPMENT | 1.390 | 3 | 4.169 | 3 | 4.171 | Proto | 4.169 | 1.617 | 1.344 |  |  | 0.000 | 0.000 | 2.552 | 0.273
| 4ISOW | EQUIPMENT | 0.484 | 3 | 1.451 | 3 | 1.454 | Proto | 1.451 | 0.057 | 0.011 |  |  | 0.000 | 0.000 | 1.394 | 0.046
| 4LA | EQUIPMENT | 0.480 | 3 | 1.441 |  |  | Mass
| 6HBPIDD | EQUIPMENT | 0.226 | 9 | 2.035 | 9 | 2.033 | Mass | [5 empty] | 0.000 | 2.035
| 6HBPIDE | EQUIPMENT | 0.265 | 8 | 2.123 | 8 | 2.123 | Mass | [5 empty] | 0.000 | 2.123
| 6HBPIDF | EQUIPMENT | 0.200 | 8 | 1.600 | 8 | 1.603 | Mass | [5 empty] | 0.000 | 1.600
| 6HBPIDG | EQUIPMENT | 0.236 | 8 | 1.887 | 8 | 1.891 | Mass | [5 empty] | 0.000 | 1.887
| 7BPI | EQUIPMENT | 0.613 | 19 | 11.645 | 19 | 11.649 | Mass | 11.645 | 5.415 | 4.900 |  |  | 0.000 | 0.000 | 6.230 | 0.515
| 7CT | EQUIPMENT | 0.580 | 9 | 5.224 | 9 | 5.225 | Mass | 5.224 | 2.727 | 1.305 |  |  | 0.000 | 0.000 | 2.498 | 1.422
| 7CVT | EQUIPMENT | 0.384 | 1 | 0.384 | 1 | 0.380 | Mass | 0.384 | 0.274 | 0.121 |  |  | 0.000 | 0.000 | 0.109 | 0.154
| 7ISOB | EQUIPMENT | 1.367 | 5 | 6.834 | 5 | 6.830 | Mass | 6.834 | 4.376 | 2.627 |  |  | 0.000 | 0.000 | 2.458 | 1.749
| 7ISOC | EQUIPMENT | 1.367 | 1 | 1.367 |  |  | Mass
| 7ISOD | EQUIPMENT | 1.362 | 6 | 8.170 | 6 | 8.170 | Mass | 8.170 | 4.082 | 3.535 |  |  | 0.000 | 0.000 | 4.089 | 0.547
| 7LA | EQUIPMENT | 0.669 | 3 | 2.008 | 3 | 2.007 | Mass | 2.008 | 0.951 | 0.077 |  |  | 0.000 | 0.000 | 1.056 | 0.875
| 7T1 | COLUMN | 15.010 | 4 | 60.039 | 4 | 60.036 | Mass | 60.039 | 59.162 | 59.156 | 59.232 | 57.134 | 0.000 | 0.000 | 0.878 | 0.005 | -0.076 | 2.099
| 7T2 | COLUMN | 32.987 | 4 | 131.949 | 4 | 131.959 | Mass | 131.949 | 131.949 | 131.941 | 131.949 | 124.063 | 0.000 | 0.000 | 0.000 | 0.008 | -0.008 | 7.887
| 7T3 | COLUMN | 39.398 | 1 | 39.398 | 1 | 39.408 | Mass | 39.398 | 39.328 | 39.328 | 39.398 | 36.998 | 0.000 | 0.000 | 0.070 | 0.000 | -0.070 | 2.400
| IS | COLUMN | 0.085 | 1 | 0.085 | 1 | 0.085 | Mass | 0.085 | 0.085 | 0.085 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 99.825 | 153 | 297.992 | 137 | 289.272 |  | 275.702 | 252.882 | 246.260 | 230.580 | 218.194 | 0.000 | 13.556 | 22.820 | 6.622 | -0.154 | 12.386
| Project Code : 907 |  | Client : GEPDEC INFRATECH LTD. - VT907 | [11 empty] | Order Dt. : 24/09/2025
| 7ABA | BEAM | 2.596 | 4 | 10.385 |  |  | Pre
| 7ABB | BEAM | 1.901 | 8 | 15.208 |  |  | Pre
| 7ABD | BEAM | 3.565 | 10 | 35.650 |  |  | Pre
| 7ABE | BEAM | 2.584 | 20 | 51.676 |  |  | Pre
| 7ABF | BEAM | 4.918 | 4 | 19.674 |  |  | Pre
| 7ABG | BEAM | 4.298 | 8 | 34.384 |  |  | Pre
| 7ABPI | EQUIPMENT | 0.781 | 92 | 71.815 |  |  | Proto
| 7ACA | COLUMN | 8.157 | 8 | 65.256 |  |  | Pre
| 7ACB | COLUMN | 18.008 | 20 | 360.168 |  |  | Pre
| 7ACC | COLUMN | 20.074 | 8 | 160.588 |  |  | Pre
| 7ACT | EQUIPMENT | 0.646 | 30 | 19.393 |  |  | Proto
| 7ACVT | EQUIPMENT | 0.651 | 18 | 11.719 |  |  | Proto
| 7AGWCB | PEAK | 0.524 | 20 | 10.476 |  |  | Pre
| 7AGWCC | PEAK | 0.525 | 8 | 4.197 |  |  | Pre
| 7AISO1 | EQUIPMENT | 1.831 | 7 | 12.819 |  |  | Proto
| 7AISO2 | EQUIPMENT | 1.848 | 8 | 14.785 |  |  | Proto
| 7AISOW | EQUIPMENT | 1.815 | 11 | 19.965 |  |  | Proto
| 7ALA | EQUIPMENT | 0.663 | 31 | 20.555 |  |  | Proto
| 7AWT | EQUIPMENT | 0.633 | 12 | 7.596 |  |  | Proto
|  | Sub Total | 76.018 | 327 | 946.309
| Project Code : 907. |  | Client : SHARVARI ELECTRICALS - VT907. | [11 empty] | Order Dt. : 30/12/2025
| 2DA2 | STUB | 0.171 | 8 | 1.368 | 8 | 1.368 | Mass | 1.368 | 1.368 | 1.368 | 1.368 | 1.368 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DA2E | STUB | 0.181 | 10 | 1.810 | 10 | 1.810 | Mass | 1.810 | 1.810 | 1.810 | 1.810 | 1.810 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DA3 | NORMAL TOWER | 3.872 | 60 | 232.332 | 60 | 232.334 | Mass | 232.332 | 185.101 | 179.785 | 231.662 | 168.418 | 0.000 | 0.000 | 47.232 | 5.316 | -51.878 | 63.244
| 2DA3M | +3 MTR EXTN | 0.533 | 25 | 13.318 | 25 | 13.320 | Mass | 13.318 | 13.187 | 13.178 | 13.252 | 11.704 | 0.000 | 0.000 | 0.132 | 0.009 | -0.074 | 1.548
| 2DA6M | +6 MTR EXTN | 0.993 | 8 | 7.947 | 8 | 7.945 | Mass | 7.947 | 7.086 | 7.060 | 7.810 | 5.955 | 0.000 | 0.000 | 0.861 | 0.026 | -0.750 | 1.855
| 2DC2 | STUB | 0.306 | 6 | 1.833 | 6 | 1.833 | Mass | 1.833 | 1.833 | 1.833 | 1.833 | 1.833 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DC3 | NORMAL TOWER | 5.823 | 20 | 116.468 | 20 | 116.474 | Mass | 116.468 | 93.761 | 91.789 | 111.338 | 69.360 | 0.000 | 0.000 | 22.707 | 1.973 | -19.550 | 41.978
| 2DC3M | +3 MTR EXTN | 1.354 | 10 | 13.541 | 10 | 13.542 | Mass | 13.541 | 9.357 | 8.649 | 13.293 | 6.652 | 0.000 | 0.000 | 4.184 | 0.708 | -4.644 | 6.641
| 2DC6M | +6 MTR EXTN | 1.961 | 1 | 1.961 | 1 | 1.958 | Mass | 1.961 | 0.853 | 0.524 |  |  | 0.000 | 0.000 | 1.108 | 0.330
| 2DC9M | +9 MTR EXTN | 3.697 | 2 | 7.394 | 2 | 7.389 | Mass | 7.394 | 4.803 | 4.493 | 7.394 | 3.944 | 0.000 | 0.000 | 2.591 | 0.310 | -2.902 | 3.450
| 2DD2 | STUB | 0.419 | 6 | 2.515 | 6 | 2.516 | Mass | 2.515 | 2.515 | 2.515 | 2.515 | 2.515 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DD2A | STUB | 0.419 | 2 | 0.838 | 2 | 0.839 | Mass | 0.838 | 0.838 | 0.838 | 0.838 | 0.838 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DD3 | NORMAL TOWER | 7.508 | 16 | 120.125 | 16 | 120.132 | Mass | 120.125 | 100.335 | 97.258 | 116.011 | 81.663 | 0.000 | 0.000 | 19.791 | 3.076 | -18.753 | 34.349
| 2DD3M | +3 MTR EXTN | 1.673 | 4 | 6.691 | 4 | 6.691 | Mass | 6.691 | 4.918 | 4.681 | 6.606 | 3.546 | 0.000 | 0.000 | 1.773 | 0.236 | -1.924 | 3.059
| 2DD6M | +6 MTR EXTN | 2.657 | 2 | 5.315 | 2 | 5.310 | Mass | 5.315 | 3.815 | 3.715 | 5.315 | 3.078 | 0.000 | 0.000 | 1.500 | 0.100 | -1.600 | 2.237
| 2DD9M | +9 MTR EXTN | 3.723 | 1 | 3.723 | 1 | 3.725 | Mass | 3.723 | 2.335 | 2.244 | 3.723 | 2.174 | 0.000 | 0.000 | 1.388 | 0.092 | -1.479 | 1.549
| 2MA2 | STUB | 0.420 | 1 | 0.420 |  |  | Mass
| 2MA3 | NORMAL TOWER | 11.566 | 1 | 11.566 |  |  | Mass
| 2MC2 | STUB | 0.906 | 1 | 0.906 |  |  | Mass
| 2MC3 | NORMAL TOWER | 19.203 | 3 | 57.609 |  |  | Mass
| 2MD2 | STUB | 0.966 | 4 | 3.864 |  |  | Mass
| 2MD3 | NORMAL TOWER | 25.556 | 5 | 127.778 |  |  | Mass
| 2MD3M | +3 MTR EXTN | 4.982 | 1 | 4.982 |  |  | Mass
| 2MD6M | +6 MTR EXTN | 7.343 | 1 | 7.343 |  |  | Mass
| 2MDN2 | STUB | 3.014 | 3 | 9.042 |  |  | Mass
| 2MDN3 | NORMAL TOWER | 32.536 | 3 | 97.607 | 3 | 97.633 | Mass | 3.813 |  |  |  |  | 0.000 | 93.794 | 3.813
| 2MDN3M | +3 MTR EXTN | 3.625 | 2 | 7.250 |  |  | Mass
| 2SD2 | STUB | 0.211 | 2 | 0.423 |  |  | Mass
| 2SD3 | NORMAL TOWER | 2.449 | 2 | 4.898 | 2 | 4.894 | Mass | 4.898 | 1.683 | 1.628 |  |  | 0.000 | 0.000 | 3.215 | 0.055
|  | Sub Total | 148.067 | 210 | 870.867 | 186 | 639.713 |  | 545.891 | 435.597 | 423.368 | 524.770 | 364.860 | 0.000 | 93.794 | 110.294 | 12.229 | -103.553 | 159.910
| Project Code : 908. |  | Client : SKIPPER LIMITED - VT908 | [11 empty] | Order Dt. : 12/10/2025
| 1DD2 | STUB | 0.303 | 10 | 3.033 | 10 | 3.033 | Mass | 3.033 | 3.033 | 3.033 | 3.033 | 3.033 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DP2 | STUB | 0.134 | 34 | 4.558 | 34 | 4.559 | Mass | 4.558 | 4.558 | 4.558 | 4.558 | 4.558 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DP3 | NORMAL TOWER | 2.507 | 53 | 132.866 | 53 | 132.871 | Mass | 85.235 | 85.235 | 85.235 | 124.607 | 85.099 | 0.000 | 47.631 | 0.000 | 0.000 | -39.372 | 39.508
| 1DP3M | +3 MTR EXTN | 0.394 | 26 | 10.253 | 26 | 10.250 | Mass | 5.521 | 5.521 | 5.521 | 8.560 | 5.521 | 0.000 | 4.732 | 0.000 | 0.000 | -3.039 | 3.039
| 1DP6M | +6 MTR EXTN | 0.822 | 11 | 9.040 | 11 | 9.039 | Mass | 8.218 | 8.218 | 8.217 | 8.747 | 8.215 | 0.000 | 0.822 | 0.000 | 0.001 | -0.530 | 0.531
| 1DP9M | +9 MTR EXTN | 1.476 | 2 | 2.952 | 2 | 2.953 | Mass | 2.952 | 2.952 | 2.952 | 2.952 | 2.851 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.102
| 1DR2 | STUB | 0.232 | 11 | 2.548 | 11 | 2.547 | Mass | 2.548 | 2.548 | 2.548 | 2.548 | 2.548 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DR3 | NORMAL TOWER | 3.501 | 16 | 56.024 | 16 | 56.018 | Mass | 28.012 | 28.012 | 28.012 | 33.798 | 27.992 | 0.000 | 28.012 | 0.000 | 0.000 | -5.786 | 5.806
| 1DR3M | +3 MTR EXTN | 0.687 | 10 | 6.874 | 10 | 6.874 | Mass | 3.437 | 3.437 | 3.437 | 5.796 | 3.436 | 0.000 | 3.437 | 0.000 | 0.000 | -2.359 | 2.360
| 1DR6M | +6 MTR EXTN | 1.267 | 1 | 1.267 | 1 | 1.263 | Mass | [5 empty] | 0.000 | 1.267
| 1DS3 | NORMAL TOWER | 4.602 | 16 | 73.640 | 16 | 73.642 | Mass | 46.025 | 46.025 | 45.668 | 69.029 | 45.668 | 0.000 | 27.615 | 0.000 | 0.356 | -23.361 | 23.361
| 1DS3M | +3 MTR EXTN | 1.243 | 1 | 1.243 | 1 | 1.243 | Mass | [5 empty] | 0.000 | 1.243
| 1DS6M | +6 MTR EXTN | 2.047 | 4 | 8.188 | 4 | 8.189 | Mass | 8.188 | 8.188 | 8.188 | 8.188 | 8.188 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DS9M | +9 MTR EXTN | 3.641 | 3 | 10.923 | 3 | 10.924 | Mass | 10.923 | 10.923 | 10.923 | 10.923 | 10.923 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2SD2 | STUB | 0.211 | 4 | 0.845 | 4 | 0.846 | Mass | 0.845 | 0.845 | 0.845 | 0.845 | 0.845 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2SD3 | NORMAL TOWER | 2.449 | 4 | 9.796 | 4 | 9.797 | Mass | [5 empty] | 0.000 | 9.796
| 2SH2 | STUB | 0.080 | 2 | 0.159 | 2 | 0.158 | Mass | 0.159 | 0.159 | 0.159 | 0.159 | 0.159 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2SH3 | NORMAL TOWER | 1.518 | 2 | 3.035 | 2 | 3.033 | Mass | [5 empty] | 0.000 | 3.035
| BPIC | EQUIPMENT | 0.115 | 15 | 1.720 | 15 | 1.719 | Mass | 1.720 | 0.785 | 0.641 |  |  | 0.000 | 0.000 | 0.935 | 0.144
| BPID | EQUIPMENT | 0.211 | 6 | 1.265 | 6 | 1.263 | Mass | 1.265 | 0.908 | 0.710 |  |  | 0.000 | 0.000 | 0.357 | 0.198
| CCC | EQUIPMENT | 0.109 | 4 | 0.435 | 4 | 0.437 | Mass | 0.435 | 0.383 | 0.326 |  |  | 0.000 | 0.000 | 0.052 | 0.057
| CTC | EQUIPMENT | 0.122 | 18 | 2.188 | 18 | 2.187 | Mass | 2.188 | 0.954 | 0.721 |  |  | 0.000 | 0.000 | 1.233 | 0.233
| CTD | EQUIPMENT | 0.237 | 11 | 2.605 | 11 | 2.605 | Mass | 2.605 | 1.821 | 1.660 |  |  | 0.000 | 0.000 | 0.784 | 0.161
| FC | BEAM | 0.407 | 2 | 0.814 | 2 | 0.817 | Mass | 0.814 | 0.814 | 0.814 | 0.814 | 0.814 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| FD | BEAM | 0.502 | 8 | 4.019 | 8 | 4.021 | Mass | 4.019 | 4.019 | 4.018 | 4.019 | 4.016 | 0.000 | 0.000 | 0.000 | 0.001 | -0.001 | 0.003
| FE | BEAM | 0.465 | 8 | 3.720 | 8 | 3.723 | Mass | 3.720 | 3.464 | 3.324 | 3.434 | 3.231 | 0.000 | 0.000 | 0.256 | 0.141 | -0.111 | 0.203
| FF | NORMAL TOWER | 1.176 | 10 | 11.757 | 10 | 11.754 | Mass | 11.757 | 11.757 | 11.757 | 11.757 | 11.751 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.006
| FG | NORMAL TOWER | 1.060 | 13 | 13.778 | 13 | 13.782 | Mass | 13.778 | 13.235 | 13.199 | 12.988 | 12.718 | 0.000 | 0.000 | 0.543 | 0.036 | 0.211 | 0.270
| FH | NORMAL TOWER | 0.540 | 6 | 3.238 | 6 | 3.235 | Mass | 3.238 | 3.238 | 3.238 | 3.238 | 3.198 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.040
| FH3 | NORMAL TOWER | 0.539 | 4 | 2.156 | 4 | 2.157 | Proto | 2.156 | 0.745 | 0.687 |  |  | 0.000 | 0.000 | 1.411 | 0.057
| FP | PEAK | 0.069 | 33 | 2.290 | 33 | 2.288 | Mass | 2.290 | 2.237 | 2.215 | 2.246 | 1.943 | 0.000 | 0.000 | 0.054 | 0.022 | -0.031 | 0.302
| HA | BEAM | 0.234 | 10 | 2.338 | 10 | 2.340 | Mass | 2.338 | 0.482 | 0.425 |  |  | 0.000 | 0.000 | 1.856 | 0.058
| HAM | BEAM | 0.250 | 8 | 1.997 | 8 | 1.995 | Mass | 1.997 | 0.616 | 0.451 |  |  | 0.000 | 0.000 | 1.381 | 0.165
| HG | NORMAL TOWER | 0.425 | 16 | 6.806 | 16 | 6.808 | Mass | 6.806 | 6.480 | 4.665 |  |  | 0.000 | 0.000 | 0.326 | 1.815
| HGF | EQUIPMENT | 0.197 | 2 | 0.394 | 2 | 0.394 | Mass | 0.394 | 0.301 | 0.159 |  |  | 0.000 | 0.000 | 0.093 | 0.142
| HH | NORMAL TOWER | 0.377 | 8 | 3.019 | 8 | 3.020 | Mass | 3.019 | 2.873 | 2.783 |  |  | 0.000 | 0.000 | 0.145 | 0.091
| HP | PEAK | 0.036 | 24 | 0.868 | 24 | 0.868 | Mass | 0.868 | 0.350 | 0.318 |  |  | 0.000 | 0.000 | 0.518 | 0.032
| IS | NORMAL TOWER | 0.381 | 1 | 0.381 | 1 | 0.381 | Mass | 0.381 | 0.376 |  |  |  | 0.000 | 0.000 | 0.005 | 0.376
|  |  |  | 1 | 0.353 | 1 | 0.353 | Mass | 0.353 | 0.316 |  |  |  | 0.000 | 0.000 | 0.037 | 0.316
| ISOC | EQUIPMENT | 0.594 | 2 | 1.188 | 2 | 1.191 | Mass | 1.188 | 0.792 | 0.781 |  |  | 0.000 | 0.000 | 0.397 | 0.011
| ISOCW | EQUIPMENT | 0.559 | 16 | 8.949 | 16 | 8.948 | Mass | 8.949 | 7.458 | 7.400 |  |  | 0.000 | 0.000 | 1.491 | 0.057
| LAC | EQUIPMENT | 0.117 | 12 | 1.399 | 12 | 1.399 | Mass | 1.399 | 1.399 | 0.938 |  |  | 0.000 | 0.000 | 0.000 | 0.461
| LAD | EQUIPMENT | 0.223 | 10 | 2.228 | 10 | 2.232 | Mass | 2.228 | 1.062 | 0.389 |  |  | 0.000 | 0.000 | 1.167 | 0.673
| LM | NORMAL TOWER | 1.252 | 6 | 7.511 | 6 | 7.513 | Mass | 7.511 | 5.643 | 5.375 |  |  | 0.000 | 0.000 | 1.868 | 0.268
| PTC | EQUIPMENT | 0.117 | 6 | 0.702 | 6 | 0.703 | Mass | 0.702 | 0.262 | 0.184 |  |  | 0.000 | 0.000 | 0.439 | 0.078
| PTD | EQUIPMENT | 0.243 | 2 | 0.487 | 2 | 0.487 | Mass | 0.487 | 0.285 | 0.254 |  |  | 0.000 | 0.000 | 0.202 | 0.030
| SC | NORMAL TOWER | 0.005 | 1 | 0.005 | 1 | 0.005 | Mass | 0.005 |  |  |  |  | 0.000 | 0.000 | 0.005
| WTC | EQUIPMENT | 0.238 | 4 | 0.953 | 4 | 0.953 | Mass | 0.953 | 0.283 | 0.103 |  |  | 0.000 | 0.000 | 0.669 | 0.180
|  | Sub Total | 38.267 | 477 | 426.807 | 477 | 426.817 |  | 299.216 | 282.991 | 276.830 | 322.239 | 246.708 | 0.000 | 127.591 | 16.225 | 6.161 | -74.379 | 75.531
| Project Code : 909 |  | Client : SIGMA CON. -MSPL (JV) - VT909 | [11 empty] | Order Dt. : 19/10/2025
| 1AB | BEAM | 1.041 | 2 | 2.081 | 2 | 2.079 | Proto | 2.081 | 2.081 | 2.081 | 2.081 | 1.793 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.288
| 1AB1 | BEAM | 0.866 | 8 | 6.926 | 8 | 6.928 | Proto | 6.926 | 6.926 | 6.921 | 6.926 | 5.941 | 0.000 | 0.000 | 0.000 | 0.004 | -0.004 | 0.985
| 1BUS-I | EQUIPMENT | 0.966 | 12 | 11.594 | 12 | 11.594 | Proto | 11.594 | 2.567 | 1.501 |  |  | 0.000 | 0.000 | 9.028 | 1.065
| 1C1 | COLUMN | 1.751 | 5 | 8.757 | 3 | 5.256 | Proto | 5.254 | 5.231 | 5.212 | 5.254 | 4.415 | 0.000 | 0.000 | 0.024 | 0.019 | -0.042 | 0.840
[6 empty] | 2 | 3.503 | Mass | 3.503 | 0.558 | 0.132 | 3.503 |  | 3.503 | 0.000 | 2.945 | 0.426 | -3.370 | 3.503
| 1C2 | COLUMN | 1.468 | 12 | 17.622 | 12 | 17.626 | Proto | 17.622 | 17.622 | 17.622 | 17.622 | 14.424 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 3.198
| 1CD | BEAM | 1.038 | 2 | 2.077 | 2 | 2.078 | Proto | 2.077 | 2.077 | 2.077 | 2.077 | 1.680 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.397
| 1CT | EQUIPMENT | 0.156 | 15 | 2.335 | 15 | 2.337 | Proto | 2.335 | 2.335 | 2.335 | 2.335 | 1.277 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.058
| 1CVT | EQUIPMENT | 0.142 | 12 | 1.703 | 12 | 1.703 | Proto | 1.703 | 1.703 | 1.703 | 1.703 | 1.181 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.521
| 1DS | EQUIPMENT | 0.755 | 12 | 9.062 | 12 | 9.058 | Proto | 9.062 | 0.270 | 0.270 |  |  | 0.000 | 0.000 | 8.791 | 0.000
| 1DSE | EQUIPMENT | 0.762 | 2 | 1.524 | 2 | 1.531 | Proto | 1.524 |  |  |  |  | 0.000 | 0.000 | 1.524
| 1LA | EQUIPMENT | 0.176 | 6 | 1.058 | 6 | 1.059 | Proto | 1.058 | 1.058 | 1.058 | 1.058 | 0.562 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.496
| 1LAT | EQUIPMENT | 0.221 | 6 | 1.323 | 6 | 1.322 | Proto | 1.323 | 1.323 | 1.323 | 1.323 | 0.765 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.558
| 1PI | EQUIPMENT | 0.182 | 15 | 2.724 | 15 | 2.727 | Proto | 2.724 | 2.724 | 2.720 | 2.724 | 1.808 | 0.000 | 0.000 | 0.000 | 0.004 | -0.004 | 0.916
| 3AB | BEAM | 0.485 | 2 | 0.971 | 2 | 0.970 | Proto | 0.971 | 0.971 | 0.971 | 0.971 | 0.561 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.410
| 3AB1 | BEAM | 0.485 | 8 | 3.884 | 8 | 3.886 | Proto | 3.884 | 3.884 | 3.861 | 3.884 | 3.153 | 0.000 | 0.000 | 0.000 | 0.023 | -0.023 | 0.731
| 3BUS | EQUIPMENT | 0.399 | 11 | 4.388 | 11 | 4.390 | Proto | 4.388 | 4.388 | 4.360 | 4.388 | 2.922 | 0.000 | 0.000 | 0.000 | 0.028 | -0.028 | 1.466
| 3C1 | COLUMN | 0.905 | 7 | 6.336 | 4 | 3.628 | Proto | 3.621 | 3.621 | 3.621 | 3.621 | 2.606 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.015
[6 empty] | 3 | 2.717 | Mass | 2.715 | 0.517 | 0.309 | 2.715 |  | 2.717 | 0.000 | 2.199 | 0.208 | -2.406 | 2.715
| 3C2 | COLUMN | 0.905 | 10 | 9.051 | 10 | 9.052 | Proto | 9.051 | 9.051 | 9.038 | 9.051 | 6.427 | 0.000 | 0.000 | 0.000 | 0.013 | -0.013 | 2.624
| 3CT | EQUIPMENT | 0.143 | 33 | 4.731 | 33 | 4.732 | Proto | 4.731 | 4.731 | 4.731 | 4.731 | 4.206 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.525
| 3DS | EQUIPMENT | 0.296 | 11 | 3.258 | 11 | 3.260 | Proto | 3.258 | 0.273 | 0.252 |  |  | 0.000 | 0.000 | 2.985 | 0.021
| 3DSE | EQUIPMENT | 0.314 | 10 | 3.135 | 10 | 3.132 | Proto | 3.135 | 0.257 | 0.238 |  |  | 0.000 | 0.000 | 2.879 | 0.019
| 3LA | EQUIPMENT | 0.166 | 27 | 4.474 | 27 | 4.476 | Proto | 4.474 | 4.474 | 4.419 | 4.474 | 3.517 | 0.000 | 0.000 | 0.000 | 0.054 | -0.054 | 0.957
| 3LAT | EQUIPMENT | 0.193 | 3 | 0.578 | 3 | 0.580 | Proto | 0.578 | 0.578 | 0.578 | 0.578 | 0.404 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.175
| 3PI | EQUIPMENT | 0.170 | 13 | 2.214 | 13 | 2.213 | Proto | 2.214 | 2.105 | 2.104 | 2.214 | 1.372 | 0.000 | 0.000 | 0.109 | 0.001 | -0.110 | 0.842
| 3PT | EQUIPMENT | 0.143 | 6 | 0.860 | 6 | 0.859 | Proto | 0.860 | 0.860 | 0.724 | 0.860 | 0.359 | 0.000 | 0.000 | 0.000 | 0.136 | -0.136 | 0.501
| IS | COLUMN | 5.107 | 1 | 5.107 | 1 | 5.108 | Mass | 5.107 |  |  |  |  | 0.000 | 0.000 | 5.107
|  |  |  | 1 | 0.384 | 1 | 0.385 | Mass | [5 empty] | 0.000 | 0.384
|  | Sub Total | 22.277 | 252 | 118.157 | 252 | 118.189 |  | 117.772 | 82.182 | 80.162 | 84.091 | 59.371 | 6.220 | 0.384 | 35.590 | 2.021 | -6.192 | 24.721
| Project Code : 910. |  | Client : MEGHA ENGINEERING & INFRASTRUCTURES LTD - VT910 | [11 empty] | Order Dt. : 03/05/2026
| 1DB3 | NORMAL TOWER | 4.701 | 6 | 28.208 | 6 | 28.208 | Mass | 2.598 |  |  |  |  | 0.000 | 25.610 | 2.598
| 1DB3M | +3 MTR EXTN | 0.866 | 2 | 1.732 | 2 | 1.733 | Mass | 1.111 |  |  |  |  | 0.000 | 0.621 | 1.111
| 1DB6M | +6 MTR EXTN | 1.507 | 1 | 1.507 | 1 | 1.506 | Mass | 0.678 |  |  |  |  | 0.000 | 0.829 | 0.678
| 1DD18M | +18 MTR EXTN | 7.021 | 1 | 7.021 | 1 | 7.025 | Mass | 2.116 |  |  |  |  | 0.000 | 4.905 | 2.116
| 1DD3 | NORMAL TOWER | 6.160 | 9 | 55.441 | 9 | 55.448 | Mass | 8.581 | 0.716 |  |  |  | 0.000 | 46.860 | 7.865 | 0.716
| 1DD6M | +6 MTR EXTN | 2.118 | 3 | 6.354 | 3 | 6.355 | Mass | 1.228 |  |  |  |  | 0.000 | 5.126 | 1.228
| 1DD9M | +9 MTR EXTN | 3.029 | 5 | 15.145 | 5 | 15.142 | Mass | 3.957 |  |  |  |  | 0.000 | 11.187 | 3.957
| 2DB3 | NORMAL TOWER | 6.346 | 1 | 6.346 | 1 | 6.345 | Mass | 1.144 |  |  |  |  | 0.000 | 5.202 | 1.144
| 2DD3 | NORMAL TOWER | 8.588 | 3 | 25.763 | 3 | 25.770 | Mass | 4.088 |  |  |  |  | 0.000 | 21.675 | 4.088
| 2DD6M | +6 MTR EXTN | 3.127 | 3 | 9.381 | 3 | 9.382 | Mass | 2.477 |  |  |  |  | 0.000 | 6.904 | 2.477
|  | Sub Total | 43.463 | 34 | 156.898 | 34 | 156.914 |  | 27.978 | 0.716 |  |  |  | 0.000 | 128.920 | 27.262 | 0.716
| Project Code : 910A |  | Client : ASHOKA BUILDCON LIMITED - VT910A | [11 empty] | Order Dt. : 29/06/2026
| 1DR3M | +3 MTR EXTN | 0.687 | 1 | 0.687 |  |  | Mass
| 2DC2 | STUB | 0.306 | 1 | 0.306 |  |  | Mass
| 2DC3 | NORMAL TOWER | 5.823 | 1 | 5.823 |  |  | Mass
| 2DC3M | +3 MTR EXTN | 1.354 | 1 | 1.354 |  |  | Mass
| 2DD2 | STUB | 0.419 | 1 | 0.419 |  |  | Mass
| 2MA9M | +9 MTR EXTN | 3.642 | 1 | 3.642 |  |  | Mass
| 2MD3 | NORMAL TOWER | 25.556 | 1 | 25.556 |  |  | Mass
| 2MD6M | +6 MTR EXTN | 7.343 | 1 | 7.343 |  |  | Mass
| 2SD3 | NORMAL TOWER | 2.449 | 4 | 9.796 |  |  | Mass
| 2SH3 | NORMAL TOWER | 1.536 | 2 | 3.072 |  |  | Mass
| 4DD3 | NORMAL TOWER | 22.923 | 1 | 22.923 |  |  | Pre
| FCB | BEAM | 0.449 | 2 | 0.898 |  |  | Mass
|  | Sub Total | 72.487 | 17 | 81.819
| Project Code : 911 |  | Client : SHYAM INDUS POWER SOLUTIONS PRIVATE LIMITED - VT911 | [11 empty] | Order Dt. : 19/10/2025
| 4DD | +0. MTR EXTN. | 7.786 | 5 | 38.930 | 2 | 15.576 | Proto | 14.473 | 8.687 | 3.878 |  |  | 0.000 | 1.100 | 5.785 | 4.809
| 4DD1 | S.S.T | 2.370 | 1 | 2.370 | 1 | 2.368 | Proto | 2.370 | 2.263 | 1.057 |  |  | 0.000 | 0.000 | 0.107 | 1.206
| 4DD18M | +18 MTR EXTN | 27.618 | 2 | 55.236 | 2 | 55.239 | Proto | 55.236 | 33.354 | 21.563 |  |  | 0.000 | 0.000 | 21.881 | 11.792
| 4DD1A | S.S.T | 3.021 | 1 | 3.021 | 1 | 3.021 | Proto | 2.980 | 2.614 | 0.613 |  |  | 0.000 | 0.042 | 0.366 | 2.001
| 4DD2 | STUB | 1.792 | 2 | 3.584 |  |  | Pre
| 4DD25M | +25.0 Mtr. Extn | 35.062 | 1 | 35.062 | 1 | 35.068 | Proto | 35.062 | 0.850 | 0.018 |  |  | 0.000 | 0.000 | 34.213 | 0.831
| 4DD2A | STUB | 2.184 | 3 | 6.552 |  |  | Pre
| 4DD3 | NORMAL TOWER | 32.951 | 5 | 164.755 | 5 | 164.759 | Proto | 164.492 | 129.197 | 88.123 |  |  | 0.000 | 0.263 | 35.294 | 41.075
| 4DD3M | +3 MTR EXTN | 10.201 | 1 | 10.201 |  |  | Proto
|  | Sub Total | 122.986 | 21 | 319.711 | 12 | 276.031 |  | 274.612 | 176.965 | 115.252 |  |  | 0.000 | 1.405 | 97.647 | 61.714
| Project Code : 912 |  | Client : SKIPPER LIMITED - VT912 | [11 empty] | Order Dt. : 29/10/2025
| 3B03 | EQUIPMENT | 0.977 | 2 | 1.955 | 2 | 1.954 | Mass | [5 empty] | 0.000 | 1.955
| 3B04 | COLUMN | 1.526 | 2 | 3.052 | 2 | 3.052 | Mass | [5 empty] | 0.000 | 3.052
| 3C05 | EQUIPMENT | 0.218 | 10 | 2.183 | 10 | 2.184 | Mass | [5 empty] | 0.000 | 2.183
| 3D02 | EQUIPMENT | 0.690 | 6 | 4.139 | 6 | 4.139 | Mass | [5 empty] | 0.000 | 4.139
| 3G02 | COLUMN | 1.997 | 4 | 7.987 | 4 | 7.992 | Mass | [5 empty] | 0.000 | 7.987
| 3G02B | BEAM | 1.129 | 4 | 4.514 | 4 | 4.513 | Mass | [5 empty] | 0.000 | 4.514
| 3L04 | EQUIPMENT | 0.130 | 6 | 0.781 | 6 | 0.784 | Mass | [5 empty] | 0.000 | 0.781
| 3P02 | EQUIPMENT | 0.194 | 3 | 0.582 | 3 | 0.582 | Mass | [5 empty] | 0.000 | 0.582
| E010M | +10M Body Extn | 2.745 | 2 | 5.491 | 2 | 5.487 | Proto | [5 empty] | 0.000 | 5.491
| E02 | STUB | 0.225 | 17 | 3.827 | 17 | 3.826 | Mass | 3.827 | 3.827 | 3.827 | 3.827 | 3.827 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| E03 | NORMAL TOWER | 3.371 | 17 | 57.304 | 13 | 43.822 | Proto | [5 empty] | 0.000 | 43.821
| E03M | +3 MTR EXTN | 0.737 | 9 | 6.634 | 4 | 2.950 | Proto | [5 empty] | 0.000 | 2.948
| E06M | +6 MTR EXTN | 1.628 | 7 | 11.393 | 7 | 11.392 | Proto | [5 empty] | 0.000 | 11.393
| E3010M | +10M Body Extn | 3.853 | 1 | 3.853 |  |  | Pre
| E302 | STUB | 0.371 | 6 | 2.225 | 6 | 2.225 | Mass | 2.225 | 2.225 | 2.225 | 2.225 | 2.225 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| E303 | NORMAL TOWER | 5.021 | 6 | 30.125 | 5 | 25.102 | Proto | [5 empty] | 0.000 | 25.104
| E303M | +3 MTR EXTN | 1.053 | 1 | 1.053 | 1 | 1.052 | Proto | [5 empty] | 0.000 | 1.053
| E306M | +6 MTR EXTN | 2.261 | 4 | 9.046 | 4 | 9.046 | Proto | [5 empty] | 0.000 | 9.046
| E602 | STUB | 0.554 | 7 | 3.881 | 6 | 3.327 | Mass | 3.326 | 3.326 | 3.326 | 3.326 | 3.326 | 0.553 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| E603 | NORMAL TOWER | 6.234 | 6 | 37.403 |  |  | Pre
| E603M | +3 MTR EXTN | 1.314 | 1 | 1.314 |  |  | Pre
| E606M | +6 MTR EXTN | 2.813 | 4 | 11.251 |  |  | Pre
| MC602 | STUB | 1.464 | 1 | 1.464 |  |  | Mass
| MC603 | NORMAL TOWER | 22.792 | 2 | 45.584 |  |  | Pre
| MC603M | +3 MTR EXTN | 3.308 | 1 | 3.308 | 1 | 3.307 | Proto | [5 empty] | 0.000 | 3.308
| MD6010M | +10M Body Extn | 6.393 | 2 | 12.786 | 1 | 6.397 | Proto | [5 empty] | 0.000 | 6.393
| MD603 | NORMAL TOWER | 13.371 | 3 | 40.112 | 2 | 26.753 | Proto | [5 empty] | 0.000 | 26.741
| MD605M | +5.0 Mtr. Extn. | 3.056 | 1 | 3.056 | 1 | 3.060 | Proto | [5 empty] | 0.000 | 3.056
| NBE3010M | +10M Body Extn | 4.675 | 1 | 4.675 |  |  | Pre
| NBE303 | NORMAL TOWER | 4.854 | 2 | 9.709 |  |  | Pre
| NBE306M | +6 MTR EXTN | 2.674 | 1 | 2.674 |  |  | Pre
| NBE60 | NORMAL TOWER | 6.974 | 5 | 34.872 |  |  | Pre
|  |  |  | 1 | 6.901 |  |  | Pre
| NBE6010M | +10M Body Extn | 7.916 | 4 | 31.664 |  |  | Pre
| NBE602A | STUB | 3.660 | 2 | 7.321 |  |  | Proto
| NBE603 | NORMAL TOWER | 2.816 | 2 | 5.633 |  |  | Pre
| NBE902 | STUB | 2.521 | 1 | 2.521 |  |  | Proto
| NBE902A | STUB | 2.887 | 1 | 2.887 |  |  | Proto
| NBE903 | NORMAL TOWER | 7.229 | 1 | 7.229 |  |  | Pre
| NBE906M | +6 MTR EXTN | 4.408 | 1 | 4.408 |  |  | Pre
|  | Sub Total | 146.941 | 157 | 436.797 | 107 | 172.946 |  | 9.379 | 9.379 | 9.379 | 9.379 | 9.379 | 0.553 | 163.548 | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : 912. |  | Client : SKIPPER LIMITED - VT912 | [11 empty] | Order Dt. : 22/05/2026
| E010M | +10M Body Extn | 2.745 | 2 | 5.491 | 2 | 5.487 | Proto | 3.982 |  |  |  |  | 0.000 | 1.509 | 3.982
| E03 | NORMAL TOWER | 3.371 | 17 | 57.304 | 11 | 37.079 | Proto | 23.284 | 2.948 | 0.660 |  |  | 0.000 | 13.796 | 20.335 | 2.288
| E03M | +3 MTR EXTN | 0.737 | 9 | 6.634 | 7 | 5.160 | Proto | 3.593 |  |  |  |  | 0.000 | 1.567 | 3.593
| E3010M | +10M Body Extn | 3.873 | 1 | 3.873 | 1 | 3.873 | Proto | [5 empty] | 0.000 | 3.873
| E303 | NORMAL TOWER | 5.021 | 6 | 30.125 | 6 | 30.132 | Proto | 15.683 |  |  |  |  | 0.000 | 14.442 | 15.683
| E306M | +6 MTR EXTN | 2.261 | 3 | 6.784 | 2 | 4.522 | Proto | 3.047 |  |  |  |  | 0.000 | 1.476 | 3.047
| E6010M | +10M Body Extn | 4.855 | 1 | 4.855 | 1 | 4.850 | Mass | 3.257 |  |  |  |  | 0.000 | 1.597 | 3.257
| E603 | NORMAL TOWER | 6.234 | 6 | 37.403 | 6 | 37.393 | Mass | 21.571 |  |  |  |  | 0.000 | 15.832 | 21.571
| E606M | +6 MTR EXTN | 2.813 | 4 | 11.251 | 4 | 11.255 | Mass | 7.417 |  |  |  |  | 0.000 | 3.834 | 7.417
| MC602 | STUB | 1.464 | 1 | 1.464 | 1 | 1.464 | Mass | 0.273 |  |  |  |  | 0.000 | 1.191 | 0.273
| MC603 | NORMAL TOWER | 22.792 | 1 | 22.792 | 1 | 22.810 | Mass | 11.440 |  |  |  |  | 0.000 | 11.352 | 11.440
| MC603M | +3 MTR EXTN | 3.308 | 1 | 3.308 | 1 | 3.307 | Proto | 1.290 |  |  |  |  | 0.000 | 2.018 | 1.290
| MD6010M | +10M Body Extn | 6.393 | 2 | 12.786 | 2 | 12.785 | Proto | 5.252 |  |  |  |  | 0.000 | 7.534 | 5.252
| MD602 | STUB | 1.411 | 3 | 4.234 | 3 | 4.234 | Mass | 0.574 |  |  |  |  | 0.000 | 3.660 | 0.574
| MD603 | NORMAL TOWER | 13.371 | 3 | 40.112 | 3 | 40.112 | Proto | 14.047 |  |  |  |  | 0.000 | 26.065 | 14.047
| MD605M | +5.0 Mtr. Extn. | 3.056 | 1 | 3.056 | 1 | 3.060 | Proto | 1.207 |  |  |  |  | 0.000 | 1.850 | 1.207
| NBE6010M | +10M Body Extn | 7.916 | 2 | 15.832 | 2 | 15.830 | Proto | [5 empty] | 0.000 | 15.832
| NBE602A | STUB | 3.660 | 2 | 7.321 | 2 | 7.322 | Proto | [5 empty] | 0.000 | 7.321
| NBE603 | NORMAL TOWER | 9.723 | 2 | 19.445 | 2 | 19.440 | Proto | 1.644 |  |  |  |  | 0.000 | 17.801 | 1.644
| NBE9010M | +10M Body Extn | 7.366 | 1 | 7.366 | 1 | 7.365 | Proto | [5 empty] | 0.000 | 7.366
| NBE902 | STUB | 2.521 | 1 | 2.521 | 1 | 2.521 | Proto | 2.521 | 1.179 | 1.179 |  |  | 0.000 | 0.000 | 1.342 | 0.000
| NBE902A | STUB | 2.887 | 1 | 2.887 | 1 | 2.887 | Proto | 1.362 |  |  |  |  | 0.000 | 1.525 | 1.362
| NBE903 | NORMAL TOWER | 9.842 | 2 | 19.683 | 2 | 19.673 | Proto | 1.969 |  |  |  |  | 0.000 | 17.714 | 1.969
|  | Sub Total | 127.622 | 72 | 326.527 | 63 | 302.561 |  | 123.412 | 4.128 | 1.839 |  |  | 0.000 | 179.157 | 119.284 | 2.288
| Project Code : 914 |  | Client : BALAJI ELECTRICALS - VT914 | [11 empty] | Order Dt. : 10/11/2025
| 1DB2 | STUB | 0.199 | 1 | 0.199 | 1 | 0.199 | Mass | 0.199 | 0.199 | 0.199 | 0.199 | 0.199 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DB3 | NORMAL TOWER | 3.663 | 1 | 3.663 | 1 | 3.664 | Mass | 3.663 | 3.663 | 3.627 | 3.663 | 3.061 | 0.000 | 0.000 | 0.000 | 0.036 | -0.036 | 0.602
| 1DB3E | NORMAL TOWER | 0.163 | 1 | 0.163 | 1 | 0.163 | Mass | 0.163 | 0.163 | 0.161 | 0.163 | 0.083 | 0.000 | 0.000 | 0.000 | 0.001 | -0.001 | 0.079
| 1DB3M | +3 MTR EXTN | 0.623 | 1 | 0.623 | 1 | 0.625 | Mass | 0.623 | 0.623 | 0.577 | 0.623 | 0.570 | 0.000 | 0.000 | 0.000 | 0.046 | -0.046 | 0.053
| 1DB6M | +6 MTR EXTN | 1.199 | 1 | 1.199 | 1 | 1.195 | Mass | 1.199 | 0.887 | 0.754 | 1.199 |  | 0.000 | 0.000 | 0.313 | 0.133 | -0.445 | 1.199
| 1DD18M | +18 MTR EXTN | 6.285 | 1 | 6.285 | 1 | 6.283 | Mass | 6.285 | 6.261 | 6.224 | 6.285 | 5.676 | 0.000 | 0.000 | 0.024 | 0.037 | -0.061 | 0.609
| 1DD2 | STUB | 0.305 | 2 | 0.609 | 2 | 0.611 | Mass | 0.609 | 0.609 | 0.609 | 0.609 | 0.609 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DD2A | STUB | 0.332 | 1 | 0.332 | 1 | 0.331 | Mass | 0.332 | 0.332 | 0.332 | 0.332 | 0.332 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DD3 | NORMAL TOWER | 4.876 | 3 | 14.628 | 3 | 14.638 | Mass | 14.628 | 14.618 | 14.584 | 14.628 | 11.092 | 0.000 | 0.000 | 0.010 | 0.034 | -0.043 | 3.536
| 1DD3E | NORMAL TOWER | 0.386 | 3 | 1.159 | 3 | 1.160 | Mass | 1.159 | 1.159 | 1.159 | 1.159 | 1.097 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.061
| 1DD3M | +3 MTR EXTN | 0.949 | 1 | 0.949 | 1 | 0.946 | Mass | 0.949 | 0.949 | 0.861 | 0.949 |  | 0.000 | 0.000 | 0.000 | 0.087 | -0.087 | 0.949
| 1DD9M | +9 MTR EXTN | 2.740 | 1 | 2.740 | 1 | 2.738 | Mass | 2.740 | 2.740 | 2.740 | 2.740 | 2.419 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.321
| IS | COLUMN | 0.298 | 1 | 0.298 | 1 | 0.298 | Mass | [5 empty] | 0.000 | 0.298
|  |  |  | 1 | 1.032 |  |  | Mass
|  |  |  | 1 | 1.061 | 1 | 1.059 | Mass | 1.061 |  |  |  |  | 0.000 | 0.000 | 1.061
| SC | NORMAL TOWER | 0.017 | 1 | 0.017 | 1 | 0.017 | Mass | 0.017 | 0.017 | 0.004 |  |  | 0.000 | 0.000 | 0.000 | 0.013
|  | Sub Total | 24.127 | 21 | 34.957 | 20 | 33.927 |  | 33.625 | 32.219 | 31.832 | 32.548 | 25.139 | 0.000 | 0.298 | 1.406 | 0.388 | -0.721 | 7.409
| Project Code : 915 |  | Client : THE TATA POWER COMPANY LTD. -VT915 | [11 empty] | Order Dt. : 19/11/2025
| 2DF2 | STUB | 1.924 | 15 | 28.864 | 15 | 28.864 | Mass | 28.864 | 28.864 | 28.864 | 28.864 | 28.864 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 1.924 | 15 | 28.864 | 15 | 28.864 |  | 28.864 | 28.864 | 28.864 | 28.864 | 28.864 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : 916 |  | Client : ODISHA POWER TRANSMISSION CORPORATION LTD -VT916 | [11 empty] | Order Dt. : 19/11/2025
| 1PA2 | STUB | 0.252 | 20 | 5.031 | 20 | 5.031 | Mass | 5.031 | 5.031 | 5.031 | 5.031 | 5.031 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1PB2 | STUB | 0.434 | 8 | 3.471 | 8 | 3.471 | Mass | 3.471 | 3.471 | 3.471 | 3.471 | 3.471 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1PC2 | STUB | 0.610 | 12 | 7.314 | 12 | 7.315 | Mass | 7.314 | 7.314 | 7.314 | 7.314 | 7.314 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2OA2 | STUB | 0.232 | 20 | 4.635 | 20 | 4.636 | Mass | 4.635 | 4.635 | 4.635 | 4.635 | 4.635 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2OB2 | STUB | 0.438 | 8 | 3.501 | 8 | 3.501 | Mass | 3.501 | 3.501 | 3.501 | 3.501 | 3.501 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2OC2 | STUB | 0.777 | 12 | 9.321 | 12 | 9.321 | Mass | 9.321 | 9.321 | 9.321 | 9.321 | 9.321 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2OC2A | STUB | 1.067 | 3 | 3.202 | 3 | 3.202 | Mass | 3.202 | 3.202 | 3.202 | 3.202 | 3.202 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2OC2B | STUB | 1.067 | 3 | 3.202 | 3 | 3.202 | Mass | 3.202 | 3.202 | 3.202 | 3.202 | 3.202 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2UR2 | STUB | 0.692 | 4 | 2.770 | 4 | 2.770 | Mass | 2.770 | 2.770 | 2.770 | 2.770 | 2.770 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 5.568 | 90 | 42.447 | 90 | 42.449 |  | 42.447 | 42.447 | 42.447 | 42.447 | 42.447 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : 916F |  | Client : ODISHA POWER TRANSMISSION CORPORATION LTD -VT916 | [11 empty] | Order Dt. : 19/11/2025
| F24 | FOUNDATION BOLTS | 0.005 | 19253 | 94.686 | 1003658 | 4935.990 | Mass | 4935.990 | 4935.990 | 4935.990 |  |  | 0.004 | 0.000 | 0.000 | 0.000
|  | Sub Total | 0.005 | 19253 | 94.686 | 1003658 | 4935.990 |  | 4935.990 | 4935.990 | 4935.990 |  |  | 0.004 | 0.000 | 0.000 | 0.000
| Project Code : 917 |  | Client : SAFETY CONTROLS & DEVICES LIMITED - VT917 | [11 empty] | Order Dt. : 27/11/2025
| 2CT | EQUIPMENT | 0.134 | 9 | 1.209 |  |  | Proto
| 2ISO1 | EQUIPMENT | 0.827 | 3 | 2.482 |  |  | Proto
| 2SA | EQUIPMENT | 0.152 | 6 | 0.913 |  |  | Proto
| 2TISO | EQUIPMENT | 0.865 | 5 | 4.326 |  |  | Proto
| 4BPI | EQUIPMENT | 0.420 | 64 | 26.883 |  |  | Proto
| 4CT | EQUIPMENT | 0.318 | 3 | 0.953 |  |  | Proto
| 4G1 | BEAM | 4.913 | 1 | 4.913 | 1 | 4.913 | Proto | 2.715 | 0.116 |  |  |  | 0.000 | 2.198 | 2.599 | 0.116
| 4G2 | BEAM | 4.115 | 5 | 20.574 | 3 | 12.345 | Proto | 12.344 | 5.670 | 1.428 |  |  | 0.000 | 0.000 | 6.674 | 4.242
| 4HBPI | EQUIPMENT | 0.529 | 10 | 5.286 |  |  | Proto
| 4HLA | EQUIPMENT | 0.441 | 3 | 1.322 |  |  | Proto
| 4ISO1 | EQUIPMENT | 0.342 | 6 | 2.054 |  |  | Proto
| 4ISO3 | EQUIPMENT | 0.996 | 2 | 1.993 |  |  | Proto
| 4ISOW | EQUIPMENT | 0.669 | 3 | 2.008 |  |  | Proto
| 4TG | NORMAL TOWER | 6.063 | 2 | 12.127 | 2 | 12.125 | Proto | 12.127 | 1.956 |  |  |  | 0.000 | 0.000 | 10.171 | 1.956
| 4TI | NORMAL TOWER | 5.269 | 4 | 21.077 | 4 | 21.070 | Proto | 21.077 | 6.701 | 0.736 |  |  | 0.000 | 0.000 | 14.376 | 5.966
| 4TM | NORMAL TOWER | 7.160 | 2 | 14.321 | 2 | 14.323 | Proto | 14.321 | 0.649 | 0.069 |  |  | 0.000 | 0.000 | 13.672 | 0.580
| 7BGE | BEAM | 2.410 | 1 | 2.410 | 1 | 2.407 | Proto | 2.410 |  |  |  |  | 0.000 | 0.000 | 2.410
| 7BGF | BEAM | 1.085 | 2 | 2.169 | 2 | 2.164 | Proto | 2.169 | 0.341 |  |  |  | 0.000 | 0.000 | 1.829 | 0.341
| 7BPI | EQUIPMENT | 0.781 | 9 | 7.029 |  |  | Proto
| 7BTC | NORMAL TOWER | 10.821 | 2 | 21.643 | 2 | 21.642 | Proto | 21.121 | 2.910 | 1.088 |  |  | 0.000 | 0.522 | 18.211 | 1.822
| 7CT | EQUIPMENT | 0.943 | 3 | 2.828 |  |  | Proto
| 7ISO1 | EQUIPMENT | 0.995 | 6 | 5.970 |  |  | Proto
| 7ISO3 | EQUIPMENT | 5.703 | 2 | 11.406 |  |  | Proto
| 7ISOW | EQUIPMENT | 1.923 | 6 | 11.540 |  |  | Proto
| 7SA | EQUIPMENT | 0.818 | 3 | 2.455 |  |  | Proto
| 7TCGW | PEAK | 0.300 | 2 | 0.599 | 2 | 0.599 | Proto | 0.599 | 0.060 |  |  |  | 0.000 | 0.000 | 0.539 | 0.060
|  | Sub Total | 58.993 | 164 | 190.490 | 19 | 91.588 |  | 88.883 | 18.403 | 3.321 |  |  | 0.000 | 2.720 | 70.481 | 15.082
| Project Code : 918 |  | Client : KANTI PRASAD MITTAL INFRA PRIVATE LIMITED - VT918 | [11 empty] | Order Dt. : 29/11/2025
| 1DA1 | S.S.T | 0.406 | 3 | 1.219 | 3 | 1.219 | Mass | 1.219 | 1.219 | 1.219 | 1.219 | 1.219 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DA2 | STUB | 0.159 | 172 | 27.392 | 172 | 27.393 | Mass | 27.392 | 27.392 | 27.392 | 27.392 | 27.392 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DA3 | NORMAL TOWER | 3.120 | 91 | 283.924 | 91 | 283.925 | Mass | 283.924 | 283.924 | 283.821 | 283.924 | 267.415 | 0.000 | 0.000 | 0.000 | 0.103 | -0.103 | 16.509
| 1DA3M | +3 MTR EXTN | 0.541 | 50 | 27.071 | 50 | 27.071 | Mass | 27.071 | 27.071 | 27.071 | 27.071 | 25.952 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.119
| 1DA6M | +6 MTR EXTN | 1.064 | 20 | 21.279 | 20 | 21.276 | Mass | 21.279 | 21.279 | 21.151 | 21.279 | 19.496 | 0.000 | 0.000 | 0.000 | 0.129 | -0.129 | 1.783
| 1DA9M | +9 MTR EXTN | 1.829 | 1 | 1.829 | 1 | 1.826 | Mass | 1.829 | 1.829 | 1.752 | 1.829 | 1.248 | 0.000 | 0.000 | 0.000 | 0.078 | -0.078 | 0.581
| 1DAE | NORMAL TOWER | 0.147 | 71 | 10.469 | 71 | 10.470 | Mass | 10.469 | 10.469 | 10.469 | 10.469 | 10.467 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.001
| 1DB1 | S.S.T | 0.465 | 1 | 0.465 |  |  | Mass
| 1DB2 | STUB | 0.199 | 33 | 6.568 | 33 | 6.568 | Mass | 6.568 | 6.568 | 6.568 | 6.480 | 6.170 | 0.000 | 0.000 | 0.000 | 0.000 | 0.087 | 0.311
| 1DB3 | NORMAL TOWER | 3.659 | 11 | 40.247 | 11 | 40.294 | Mass | 40.291 | 40.291 | 40.155 | 40.291 | 37.509 | -0.093 | 0.000 | 0.000 | 0.136 | -0.136 | 2.783
| 1DB3M | +3 MTR EXTN | 0.623 | 4 | 2.492 | 4 | 2.416 | Mass | 2.415 | 2.415 | 2.415 | 2.415 | 2.286 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.129
| 1DB9M | +9 MTR EXTN | 2.158 | 3 | 6.475 | 3 | 6.478 | Mass | 6.475 |  |  |  |  | 0.000 | 0.000 | 6.475
| 1DBE | NORMAL TOWER | 0.163 | 7 | 1.138 | 7 | 1.138 | Mass | 1.138 | 1.138 | 1.138 | 1.138 | 1.138 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DC1 | S.S.T | 0.534 | 1 | 0.534 |  |  | Mass
| 1DC2 | STUB | 0.273 | 9 | 2.454 | 9 | 2.456 | Mass | 2.454 | 2.454 | 2.454 | 2.454 | 2.454 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DC3 | NORMAL TOWER | 4.061 | 4 | 16.244 | 4 | 16.247 | Mass | 16.244 | 16.244 | 16.206 | 16.244 | 15.002 | 0.000 | 0.000 | 0.000 | 0.037 | -0.037 | 1.241
| 1DC3M | +3 MTR EXTN | 0.700 | 2 | 1.400 | 2 | 1.399 | Mass | 1.400 | 1.400 | 1.373 | 1.400 | 1.213 | 0.000 | 0.000 | 0.000 | 0.027 | -0.027 | 0.187
| 1DCE | NORMAL TOWER | 0.202 | 2 | 0.405 | 2 | 0.404 | Mass | 0.405 | 0.405 | 0.405 | 0.405 | 0.405 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DD2 | STUB | 0.305 | 36 | 10.970 | 36 | 10.969 | Mass | 10.970 | 10.970 | 10.970 | 10.970 | 10.970 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DD3 | NORMAL TOWER | 4.876 | 14 | 68.262 | 14 | 68.263 | Mass | 68.262 | 68.249 | 68.161 | 68.262 | 66.672 | 0.000 | 0.000 | 0.013 | 0.089 | -0.101 | 1.590
| 1DD3M | +3 MTR EXTN | 0.949 | 3 | 2.846 | 3 | 2.844 | Mass | 2.846 | 2.789 | 2.789 | 2.846 | 2.523 | 0.000 | 0.000 | 0.057 | 0.000 | -0.057 | 0.322
| 1DD6M | +6 MTR EXTN | 1.589 | 1 | 1.589 | 1 | 1.591 | Mass | 1.589 | 1.589 | 1.589 | 1.589 | 1.495 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.094
| 1DD9M | +9 MTR EXTN | 2.354 | 2 | 4.708 | 2 | 4.707 | Mass | 4.708 | 4.708 | 4.691 | 4.708 | 4.620 | 0.000 | 0.000 | 0.000 | 0.018 | -0.018 | 0.088
| 1DDE | NORMAL TOWER | 0.386 | 6 | 2.317 | 6 | 2.318 | Mass | 2.317 | 2.317 | 2.317 | 2.317 | 2.314 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.004
| IS | NORMAL TOWER | 0.009 | 1 | 0.009 | 1 | 0.009 | Mass | 0.009 | 0.009 |  |  |  | 0.000 | 0.000 | 0.000 | 0.009
|  | Sub Total | 30.772 | 548 | 542.306 | 546 | 541.281 |  | 541.274 | 534.729 | 534.104 | 534.703 | 507.961 | -0.093 | 0.000 | 6.545 | 0.625 | -0.599 | 26.742
| Project Code : 919 |  | Client : KERALA STATE ELECTRICITY BOARD LTD - VT919 | [11 empty] | Order Dt. : 04/12/2025
| 13M | COLUMN | 1.338 | 2 | 2.677 | 2 | 2.680 | Mass | 2.677 | 2.677 | 2.677 | 2.677 | 2.677 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1C2 | COLUMN | 1.296 | 29 | 37.583 | 29 | 37.585 | Mass | 37.583 | 37.583 | 37.583 | 37.583 | 37.583 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1C3 | COLUMN | 1.071 | 2 | 2.142 | 2 | 2.144 | Mass | 2.142 | 2.142 | 2.142 | 2.142 | 2.142 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| IS | NORMAL TOWER | 0.118 | 1 | 0.118 | 1 | 0.118 | Mass | 0.118 | 0.118 | 0.118 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| N | BEAM | 0.390 | 18 | 7.025 | 18 | 7.025 | Mass | 7.025 | 7.025 | 7.025 | 7.025 | 7.025 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| P1 | COLUMN | 2.498 | 4 | 9.994 | 4 | 9.989 | Mass | 9.994 | 9.994 | 9.994 | 9.994 | 9.994 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| P4 | COLUMN | 2.195 | 8 | 17.561 | 8 | 17.562 | Mass | 17.561 | 17.561 | 17.561 | 17.561 | 17.561 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| Q1 | BEAM | 0.935 | 26 | 24.303 | 26 | 24.308 | Mass | 24.303 | 24.303 | 24.303 | 24.303 | 24.303 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| Q2 | BEAM | 0.719 | 28 | 20.129 | 28 | 20.131 | Mass | 20.129 | 20.129 | 20.129 | 20.129 | 20.129 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| SC | NORMAL TOWER | 0.064 | 1 | 0.064 | 1 | 0.064 | Mass | 0.064 | 0.014 | 0.014 |  |  | 0.000 | 0.000 | 0.050 | 0.000
|  | Sub Total | 10.626 | 119 | 121.596 | 119 | 121.606 |  | 121.596 | 121.546 | 121.546 | 121.414 | 121.414 | 0.000 | 0.000 | 0.050 | 0.000 | 0.000 | 0.000
| Project Code : 920 |  | Client : GE VERNOVA T&D INDIA LTD - VT920 | [11 empty] | Order Dt. : 05/12/2025
| 2BA | BEAM | 2.083 | 14 | 29.159 | 14 | 29.156 | Proto | 29.159 | 29.159 | 29.158 | 29.159 | 28.989 | 0.000 | 0.000 | 0.000 | 0.001 | -0.001 | 0.171
| 2BB | BEAM | 2.083 | 3 | 6.248 | 3 | 6.248 | Proto | 6.248 | 6.248 | 6.144 | 6.248 | 6.121 | 0.000 | 0.000 | 0.000 | 0.104 | -0.104 | 0.127
| 2BC | BEAM | 2.083 | 4 | 8.331 | 4 | 8.330 | Proto | 8.331 | 8.331 | 8.213 | 8.331 | 7.941 | 0.000 | 0.000 | 0.000 | 0.118 | -0.118 | 0.390
| 2BD | BEAM | 2.255 | 2 | 4.510 | 2 | 4.509 | Proto | 4.510 | 4.447 | 4.396 | 4.510 | 4.122 | 0.000 | 0.000 | 0.063 | 0.051 | -0.114 | 0.388
| 2CA | COLUMN | 2.429 | 10 | 24.295 | 10 | 24.293 | Proto | 24.295 | 24.295 | 24.260 | 24.295 | 24.215 | 0.000 | 0.000 | 0.000 | 0.034 | -0.034 | 0.080
| 2CB | COLUMN | 1.960 | 7 | 13.721 | 7 | 13.718 | Proto | 13.721 | 13.713 | 13.522 | 13.721 | 13.005 | 0.000 | 0.000 | 0.008 | 0.191 | -0.199 | 0.716
| 2CC | COLUMN | 4.380 | 3 | 13.139 | 3 | 13.140 | Proto | 13.139 | 13.139 | 13.114 | 13.139 | 13.082 | 0.000 | 0.000 | 0.000 | 0.025 | -0.025 | 0.057
| 2CD | COLUMN | 4.380 | 1 | 4.380 | 1 | 4.370 | Proto | 4.380 | 4.290 | 4.290 | 4.380 | 4.246 | 0.000 | 0.000 | 0.090 | 0.000 | -0.090 | 0.133
| 2CE | COLUMN | 3.304 | 1 | 3.304 | 1 | 3.304 | Proto | 3.304 | 3.296 | 3.296 | 3.299 | 3.279 | 0.000 | 0.000 | 0.008 | 0.000 | -0.008 | 0.021
| 2CF | COLUMN | 3.304 | 9 | 29.735 | 9 | 29.734 | Proto | 29.735 | 29.735 | 29.730 | 29.735 | 29.194 | 0.000 | 0.000 | 0.000 | 0.006 | -0.006 | 0.541
| 2CVT1 | EQUIPMENT | 0.143 | 7 | 1.004 | 1 | 0.146 | Proto | 0.115 | 0.076 | 0.076 |  |  | 0.000 | 0.029 | 0.038 | 0.000
[6 empty] | 6 | 0.858 | Mass | 0.085 |  |  |  |  | 0.000 | 0.775 | 0.085
| 2CVT2 | EQUIPMENT | 0.134 | 14 | 1.877 | 1 | 0.135 | Proto | 0.134 |  |  |  |  | 0.000 | 0.000 | 0.134
[6 empty] | 13 | 1.743 | Mass | 0.185 |  |  |  |  | 0.000 | 1.558 | 0.185
| 2HBPI | EQUIPMENT | 0.253 | 12 | 3.034 | 1 | 0.253 | Proto | 0.253 | 0.253 | 0.088 |  |  | 0.000 | 0.000 | 0.000 | 0.165
[6 empty] | 11 | 2.783 | Mass | 0.083 |  |  |  |  | 0.000 | 2.698 | 0.083
| 2HCT-1 | EQUIPMENT | 0.212 | 4 | 0.849 | 1 | 0.216 | Proto | 0.202 | 0.160 | 0.113 |  |  | 0.000 | 0.011 | 0.042 | 0.047
[6 empty] | 3 | 0.639 | Mass | 0.055 |  |  |  |  | 0.000 | 0.582 | 0.055
| 2HCT-2 | EQUIPMENT | 0.204 | 8 | 1.629 | 1 | 0.202 | Proto | 0.191 | 0.191 |  |  |  | 0.000 | 0.012 | 0.000 | 0.191
[6 empty] | 7 | 1.425 | Mass | 0.121 |  |  |  |  | 0.000 | 1.305 | 0.121
| 2HISO1 | EQUIPMENT | 0.253 | 4 | 1.011 | 1 | 0.257 | Proto | 0.253 | 0.253 | 0.019 |  |  | 0.000 | 0.000 | 0.000 | 0.234
[6 empty] | 3 | 0.763 | Mass | 0.093 |  |  |  |  | 0.000 | 0.665 | 0.093
| 2HISO2 | EQUIPMENT | 0.241 | 4 | 0.965 | 1 | 0.245 | Proto | 0.241 | 0.241 | 0.019 |  |  | 0.000 | 0.000 | 0.000 | 0.222
[6 empty] | 3 | 0.728 | Mass | 0.059 |  |  |  |  | 0.000 | 0.665 | 0.059
| 2HISO3 | EQUIPMENT | 0.233 | 16 | 3.729 | 1 | 0.233 | Proto | 0.233 | 0.233 | 0.060 |  |  | 0.000 | 0.000 | 0.000 | 0.173
[6 empty] | 15 | 3.496 | Mass | 0.621 |  |  |  |  | 0.000 | 2.875 | 0.621
| 2HLA1 | EQUIPMENT | 0.252 | 4 | 1.008 | 1 | 0.252 | Proto | 0.252 | 0.223 | 0.118 |  |  | 0.000 | 0.000 | 0.029 | 0.104
[6 empty] | 3 | 0.757 | Mass | 0.023 |  |  |  |  | 0.000 | 0.733 | 0.023
| 2HLA2 | EQUIPMENT | 0.246 | 8 | 1.965 | 1 | 0.247 | Proto | 0.246 | 0.246 | 0.148 |  |  | 0.000 | 0.000 | 0.000 | 0.098
[6 empty] | 7 | 1.719 | Mass | 0.053 |  |  |  |  | 0.000 | 1.666 | 0.053
| 2ISO1 | EQUIPMENT | 0.185 | 45 | 8.310 | 1 | 0.188 | Proto | 0.185 | 0.066 |  |  |  | 0.000 | 0.000 | 0.118 | 0.066
[6 empty] | 44 | 8.121 | Mass | 2.688 |  |  |  |  | 0.000 | 5.438 | 2.688
| 2ISO2 | EQUIPMENT | 0.173 | 18 | 3.118 | 1 | 0.176 | Proto | 0.173 | 0.106 | 0.106 |  |  | 0.000 | 0.000 | 0.068 | 0.000
[6 empty] | 17 | 2.941 | Mass | 0.335 |  |  |  |  | 0.000 | 2.610 | 0.335
| 2ISO3 | EQUIPMENT | 0.165 | 99 | 16.334 | 1 | 0.165 | Proto | 0.165 | 0.106 | 0.106 |  |  | 0.000 | 0.000 | 0.059 | 0.000
[6 empty] | 98 | 16.168 | Mass | 4.057 |  |  |  |  | 0.000 | 12.111 | 4.057
| 2LA1-1 | EQUIPMENT | 0.173 | 3 | 0.520 | 1 | 0.175 | Proto | 0.173 | 0.173 | 0.062 |  |  | 0.000 | 0.000 | 0.000 | 0.111
[6 empty] | 2 | 0.346 | Mass | 0.015 |  |  |  |  | 0.000 | 0.332 | 0.015
| 2LA1-2 | EQUIPMENT | 0.167 | 6 | 1.003 | 1 | 0.169 | Proto | 0.167 | 0.167 | 0.065 |  |  | 0.000 | 0.000 | 0.000 | 0.102
[6 empty] | 5 | 0.838 | Mass | 0.038 |  |  |  |  | 0.000 | 0.798 | 0.038
| 2LA2-1 | EQUIPMENT | 0.176 | 2 | 0.352 | 2 | 0.353 | Proto | 0.352 | 0.309 | 0.182 |  |  | 0.000 | 0.000 | 0.043 | 0.127
| 2LA2-2 | EQUIPMENT | 0.169 | 4 | 0.678 | 4 | 0.678 | Proto | 0.678 | 0.656 | 0.305 |  |  | 0.000 | 0.000 | 0.022 | 0.351
| 2LBPI | EQUIPMENT | 0.177 | 37 | 6.567 | 1 | 0.177 | Proto | 0.177 | 0.022 | 0.022 |  |  | 0.000 | 0.000 | 0.156 | 0.000
[6 empty] | 36 | 6.389 | Mass | 1.446 |  |  |  |  | 0.000 | 4.944 | 1.446
| 2LCT1 | EQUIPMENT | 0.145 | 7 | 1.015 | 1 | 0.150 | Proto | 0.137 | 0.110 | 0.075 |  |  | 0.000 | 0.008 | 0.027 | 0.034
[6 empty] | 6 | 0.871 | Mass | 0.103 |  |  |  |  | 0.000 | 0.767 | 0.103
| 2LCT2 | EQUIPMENT | 0.137 | 14 | 1.924 | 1 | 0.139 | Proto | 0.137 | 0.037 |  |  |  | 0.000 | 0.000 | 0.100 | 0.037
[6 empty] | 13 | 1.788 | Mass | 0.224 |  |  |  |  | 0.000 | 1.563 | 0.224
| 2WT | EQUIPMENT | 0.472 | 6 | 2.835 | 1 | 0.473 | Proto | 0.472 | 0.472 | 0.310 |  |  | 0.000 | 0.000 | 0.000 | 0.162
[6 empty] | 5 | 2.362 | Mass | 1.272 |  |  |  |  | 0.000 | 1.090 | 1.272
| 3B1 | BEAM | 0.579 | 28 | 16.224 | 1 | 0.583 | Proto | 0.579 | 0.467 | 0.357 |  |  | 0.000 | 0.000 | 0.113 | 0.109
[6 empty] | 27 | 15.644 | Mass | 6.837 |  |  |  |  | 0.000 | 8.807 | 6.837
| 3BPI1 | EQUIPMENT | 0.266 | 11 | 2.930 | 1 | 0.268 | Proto | 0.266 | 0.266 | 0.106 |  |  | 0.000 | 0.000 | 0.000 | 0.160
[6 empty] | 10 | 2.664 | Mass | 2.663 | 0.085 |  |  |  | 0.000 | 0.000 | 2.579 | 0.085
| 3BPI2 | EQUIPMENT | 0.223 | 11 | 2.448 | 1 | 0.223 | Proto | 0.223 | 0.223 | 0.021 |  |  | 0.000 | 0.000 | 0.000 | 0.201
[6 empty] | 10 | 2.224 | Mass | 2.226 |  |  |  |  | 0.000 | 0.000 | 2.226
| 3BPI3 | EQUIPMENT | 0.135 | 42 | 5.649 | 1 | 0.136 | Proto | 0.135 | 0.082 | 0.082 |  |  | 0.000 | 0.000 | 0.053 | 0.000
[6 empty] | 41 | 5.513 | Mass | 5.515 |  |  |  |  | 0.000 | 0.000 | 5.515
| 3CT1 | EQUIPMENT | 0.241 | 16 | 3.850 | 1 | 0.240 | Proto | 0.226 | 0.071 | 0.042 |  |  | 0.000 | 0.015 | 0.155 | 0.028
[6 empty] | 15 | 3.613 | Mass | 3.610 | 0.035 |  |  |  | 0.000 | 0.000 | 3.575 | 0.035
| 3CT2 | EQUIPMENT | 0.242 | 36 | 8.709 | 1 | 0.242 | Proto | 0.227 | 0.219 | 0.122 |  |  | 0.000 | 0.015 | 0.008 | 0.097
[6 empty] | 35 | 8.471 | Mass | 8.468 | 0.080 |  |  |  | 0.000 | 0.000 | 8.388 | 0.080
| 3CT3 | EQUIPMENT | 0.234 | 4 | 0.936 | 1 | 0.234 | Proto | 0.220 | 0.212 | 0.118 |  |  | 0.000 | 0.014 | 0.008 | 0.093
[6 empty] | 3 | 0.701 | Mass | 0.702 |  |  |  |  | 0.000 | 0.000 | 0.702
| 3HBPI | EQUIPMENT | 0.358 | 28 | 10.023 | 1 | 0.355 | Proto | 0.358 | 0.358 | 0.150 |  |  | 0.000 | 0.000 | 0.000 | 0.208
[6 empty] | 27 | 9.666 | Mass | 9.665 | 0.129 |  |  |  | 0.000 | 0.000 | 9.537 | 0.129
| 3HCT | EQUIPMENT | 0.321 | 4 | 1.285 | 1 | 0.320 | Proto | 0.306 | 0.297 | 0.042 |  |  | 0.000 | 0.015 | 0.009 | 0.255
[6 empty] | 3 | 0.964 | Mass | 0.964 |  |  |  |  | 0.000 | 0.000 | 0.964
| 3HISO | EQUIPMENT | 0.349 | 8 | 2.794 | 1 | 0.350 | Proto | 0.349 |  |  |  |  | 0.000 | 0.000 | 0.349
| 3HLA | EQUIPMENT | 0.396 | 8 | 3.170 | 1 | 0.400 | Proto | 0.388 | 0.031 | 0.031 |  |  | 0.000 | 0.009 | 0.356 | 0.000
[6 empty] | 7 | 2.774 | Mass | 2.774 |  |  |  |  | 0.000 | 0.000 | 2.774
| 3LA | EQUIPMENT | 0.333 | 20 | 6.667 | 1 | 0.334 | Proto | 0.294 | 0.206 | 0.101 |  |  | 0.000 | 0.040 | 0.087 | 0.106
[6 empty] | 19 | 6.335 | Mass | 6.334 | 0.048 |  |  |  | 0.000 | 0.000 | 6.286 | 0.048
| 3LISO | EQUIPMENT | 0.280 | 8 | 2.240 | 1 | 0.282 | Proto | 0.280 | 0.280 | 0.083 |  |  | 0.000 | 0.000 | 0.000 | 0.197
[6 empty] | 7 | 1.960 | Mass | 1.960 | 0.091 |  |  |  | 0.000 | 0.000 | 1.870 | 0.091
| 3MISO1 | EQUIPMENT | 0.282 | 96 | 27.068 | 1 | 0.284 | Proto | 0.282 | 0.252 | 0.084 |  |  | 0.000 | 0.000 | 0.030 | 0.168
[6 empty] | 95 | 26.785 | Mass | 26.786 | 0.095 |  |  |  | 0.000 | 0.000 | 26.691 | 0.095
| 3MISO2 | EQUIPMENT | 0.285 | 16 | 4.561 | 1 | 0.288 | Proto | 0.285 | 0.233 | 0.063 |  |  | 0.000 | 0.000 | 0.052 | 0.171
[6 empty] | 15 | 4.280 | Mass | 4.276 |  |  |  |  | 0.000 | 0.000 | 4.276
| 3T1 | NORMAL TOWER | 0.797 | 36 | 28.686 | 1 | 0.794 | Proto | 0.772 | 0.735 | 0.688 |  |  | 0.000 | 0.025 | 0.037 | 0.047
[6 empty] | 35 | 27.891 | Mass | 11.029 |  |  |  |  | 0.000 | 16.860 | 11.029
| 3VT | EQUIPMENT | 0.264 | 8 | 2.113 | 1 | 0.265 | Proto | 0.250 | 0.116 | 0.042 |  |  | 0.000 | 0.014 | 0.135 | 0.073
[6 empty] | 7 | 1.849 | Mass | 1.849 |  |  |  |  | 0.000 | 0.000 | 1.849
| 4BPI | EQUIPMENT | 0.216 | 8 | 1.728 | 1 | 0.215 | Proto | 0.216 | 0.165 | 0.085 |  |  | 0.000 | 0.000 | 0.051 | 0.080
[6 empty] | 7 | 1.512 | Mass | 1.009 | 0.040 |  |  |  | 0.000 | 0.503 | 0.969 | 0.040
| 4CT1 | EQUIPMENT | 0.206 | 5 | 1.028 | 5 | 1.029 | Proto | 1.028 | 1.028 | 0.436 |  |  | 0.000 | 0.000 | 0.000 | 0.591
| 4CT2 | EQUIPMENT | 0.190 | 10 | 1.897 | 1 | 0.191 | Proto | 0.190 | 0.088 | 0.050 |  |  | 0.000 | 0.000 | 0.102 | 0.038
[6 empty] | 9 | 1.708 | Mass | 1.048 | 0.086 |  |  |  | 0.000 | 0.659 | 0.962 | 0.086
| 4CVT1 | EQUIPMENT | 0.151 | 3 | 0.454 | 3 | 0.450 | Proto | 0.454 | 0.442 | 0.215 |  |  | 0.000 | -0.001 | 0.012 | 0.228
| 4CVT2 | EQUIPMENT | 0.142 | 6 | 0.852 | 6 | 0.852 | Proto | 0.852 | 0.842 | 0.555 |  |  | 0.000 | 0.000 | 0.010 | 0.288
| 4GA | BEAM | 3.575 | 2 | 7.149 | 2 | 7.150 | Proto | 7.149 | 7.149 | 7.149 | 7.149 | 6.943 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.206
| 4GB | BEAM | 3.132 | 2 | 6.263 | 2 | 6.268 | Proto | 6.263 | 6.263 | 6.263 | 6.263 | 5.549 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.714
| 4GC | BEAM | 2.945 | 4 | 11.780 | 4 | 11.778 | Proto | 11.780 | 11.780 | 11.780 | 11.780 | 10.861 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.919
| 4GD | BEAM | 3.575 | 2 | 7.149 | 2 | 7.150 | Mass | 7.149 | 7.149 | 7.149 | 7.149 | 6.480 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.670
| 4HCVT1 | EQUIPMENT | 0.158 | 1 | 0.158 | 1 | 0.161 | Proto | 0.158 | 0.098 | 0.043 |  |  | 0.000 | 0.000 | 0.059 | 0.056
| 4HCVT2 | EQUIPMENT | 0.148 | 2 | 0.297 | 2 | 0.298 | Proto | 0.297 | 0.286 | 0.179 |  |  | 0.000 | 0.000 | 0.010 | 0.107
| 4HLA1 | EQUIPMENT | 0.220 | 1 | 0.220 | 1 | 0.223 | Proto | 0.220 | 0.212 | 0.138 |  |  | 0.000 | 0.003 | 0.009 | 0.074
| 4HLA2 | EQUIPMENT | 0.214 | 2 | 0.428 | 2 | 0.432 | Proto | 0.428 | 0.428 | 0.226 |  |  | 0.000 | 0.005 | 0.000 | 0.202
| 4ISO1 | EQUIPMENT | 0.219 | 48 | 10.497 | 1 | 0.222 | Proto | 0.194 | 0.051 | 0.019 |  |  | 0.000 | 0.025 | 0.143 | 0.032
[6 empty] | 47 | 10.281 | Mass | 7.159 | 0.053 |  |  |  | 0.000 | 3.120 | 7.105 | 0.053
| 4ISO2 | EQUIPMENT | 0.213 | 48 | 10.204 | 1 | 0.215 | Proto | 0.188 | 0.052 | 0.013 |  |  | 0.000 | 0.025 | 0.136 | 0.039
[6 empty] | 47 | 9.994 | Mass | 6.871 | 0.129 | 0.078 |  |  | 0.000 | 3.120 | 6.742 | 0.051
| 4LA1 | EQUIPMENT | 0.217 | 2 | 0.435 | 2 | 0.434 | Proto | 0.435 | 0.385 | 0.151 |  |  | 0.000 | 0.001 | 0.050 | 0.234
| 4LA2 | EQUIPMENT | 0.211 | 4 | 0.844 | 4 | 0.846 | Proto | 0.844 | 0.819 | 0.404 |  |  | 0.000 | 0.002 | 0.024 | 0.415
| 4MCT1 | EQUIPMENT | 0.206 | 1 | 0.206 | 1 | 0.207 | Mass | 0.206 | 0.170 | 0.102 |  |  | 0.000 | 0.000 | 0.035 | 0.068
| 4MCT2 | EQUIPMENT | 0.190 | 2 | 0.379 | 2 | 0.378 | Mass | 0.379 | 0.277 | 0.076 |  |  | 0.000 | 0.000 | 0.102 | 0.201
| 4TA | NORMAL TOWER | 6.486 | 2 | 12.971 | 2 | 12.974 | Proto | 12.971 | 12.971 | 12.971 | 12.971 | 11.847 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.125
| 4TB | NORMAL TOWER | 5.780 | 1 | 5.780 | 1 | 5.773 | Proto | 5.780 | 5.780 | 5.780 | 5.780 | 5.033 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.747
| 4TC | NORMAL TOWER | 2.052 | 4 | 8.209 | 4 | 8.210 | Proto | 8.209 | 8.209 | 8.209 | 8.209 | 7.030 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.179
| 4TD | NORMAL TOWER | 5.164 | 3 | 15.493 | 3 | 15.491 | Proto | 15.493 | 15.493 | 15.493 | 15.493 | 14.095 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.398
| 4TE | NORMAL TOWER | 5.734 | 1 | 5.734 | 1 | 5.728 | Mass | 5.734 | 5.734 | 5.734 | 5.734 | 4.952 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.781
| 4TF | NORMAL TOWER | 6.430 | 2 | 12.859 | 2 | 12.862 | Mass | 12.859 | 12.859 | 12.859 | 12.859 | 11.327 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.532
| 4WT | EQUIPMENT | 0.610 | 2 | 1.220 | 2 | 1.218 | Proto | 1.220 | 1.220 | 0.591 |  |  | 0.000 | 0.000 | 0.000 | 0.629
| CBOM | COLUMN | 0.005 | 1 | 0.005 | 1 | 0.005 | Mass | 0.005 |  |  | 0.005 |  | 0.000 | 0.000 | 0.005 |  | -0.005 | 0.005
| IS | COLUMN | 0.236 | 1 | 0.236 | 1 | 0.237 | Mass | 0.236 | 0.236 | 0.226 |  |  | 0.000 | 0.000 | 0.000 | 0.011
|  |  |  | 1 | 0.141 | 1 | 0.141 | Mass | 0.141 | 0.141 | 0.141 | 0.141 | 0.141 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| SC | NORMAL TOWER | 0.054 | 1 | 0.054 | 1 | 0.054 | Mass | 0.054 | 0.008 |  |  |  | 0.000 | 0.000 | 0.046 | 0.008
|  | Sub Total | 97.015 | 928 | 450.572 | 921 | 448.185 |  | 371.632 | 246.010 | 237.248 | 230.352 | 218.452 | 0.000 | 76.509 | 125.623 | 8.762 | -0.704 | 11.900
| Project Code : 921 |  | Client : SHARVARI ELECTRICALS - VT921 | [11 empty] | Order Dt. : 06/12/2025
| 2DA2 | STUB | 0.171 | 31 | 5.301 | 31 | 5.301 | Mass | 5.301 | 5.301 | 5.301 | 5.301 | 5.301 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DA2E | STUB | 0.181 | 38 | 6.877 | 38 | 6.877 | Mass | 6.877 | 6.877 | 6.877 | 6.877 | 6.877 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DA3 | NORMAL TOWER | 3.872 | 50 | 193.610 | 49 | 189.739 | Mass | 189.738 | 189.034 | 188.852 | 189.738 | 187.980 | 3.872 | 0.000 | 0.704 | 0.182 | -0.886 | 1.758
| 2DA3M | +3 MTR EXTN | 0.533 | 15 | 7.991 | 15 | 7.988 | Mass | 7.991 | 7.991 | 7.991 | 7.991 | 7.991 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DA6M | +6 MTR EXTN | 0.993 | 18 | 17.880 | 18 | 17.879 | Mass | 17.880 | 17.347 | 17.014 | 17.880 | 16.761 | 0.000 | 0.000 | 0.533 | 0.333 | -0.866 | 1.119
| 2DA9M | +9 MTR EXTN | 1.785 | 1 | 1.785 | 1 | 1.784 | Mass | 1.785 | 1.785 | 1.400 | 1.785 | 1.291 | 0.000 | 0.000 | 0.000 | 0.385 | -0.385 | 0.493
| 2DC2 | STUB | 0.306 | 14 | 4.277 | 14 | 4.277 | Mass | 4.277 | 4.277 | 4.277 | 4.277 | 4.277 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DC3 | NORMAL TOWER | 5.823 | 22 | 128.115 | 22 | 128.115 | Mass | 128.115 | 127.813 | 126.927 | 128.115 | 126.269 | 0.000 | 0.000 | 0.301 | 0.886 | -1.188 | 1.846
| 2DC3M | +3 MTR EXTN | 1.354 | 6 | 8.124 | 6 | 8.125 | Mass | 8.124 | 8.101 | 8.101 | 8.124 | 8.101 | 0.000 | 0.000 | 0.023 | 0.000 | -0.023 | 0.023
| 2DC6M | +6 MTR EXTN | 1.961 | 2 | 3.922 | 2 | 3.923 | Mass | 3.922 | 3.922 | 3.878 | 3.922 | 3.846 | 0.000 | 0.000 | 0.000 | 0.044 | -0.044 | 0.076
| 2DC9M | +9 MTR EXTN | 3.697 | 1 | 3.697 | 1 | 3.694 | Mass | 3.697 | 3.285 | 3.124 | 3.697 | 2.738 | 0.000 | 0.000 | 0.412 | 0.161 | -0.573 | 0.959
| 2DD12M | +12 MTR EXTN | 5.828 | 6 | 34.966 | 6 | 34.968 | Mass | 34.966 | 34.534 | 34.185 | 34.966 | 34.155 | 0.000 | 0.000 | 0.433 | 0.349 | -0.781 | 0.812
| 2DD18M | +18 MTR EXTN | 9.922 | 2 | 19.843 | 2 | 19.839 | Mass | 19.843 | 19.832 | 19.528 | 19.843 | 19.394 | 0.000 | 0.000 | 0.011 | 0.304 | -0.315 | 0.449
| 2DD2 | STUB | 0.419 | 7 | 2.935 | 7 | 2.935 | Mass | 2.935 | 2.935 | 2.935 | 2.935 | 2.935 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DD3 | NORMAL TOWER | 7.508 | 34 | 255.266 | 34 | 255.264 | Mass | 255.266 | 251.371 | 250.448 | 255.266 | 249.814 | 0.000 | 0.000 | 3.896 | 0.922 | -4.818 | 5.453
| 2DD3M | +3 MTR EXTN | 1.673 | 6 | 10.036 | 6 | 10.038 | Mass | 10.036 | 9.946 | 9.796 | 10.036 | 9.708 | 0.000 | 0.000 | 0.090 | 0.150 | -0.240 | 0.328
| 2DD6M | +6 MTR EXTN | 2.657 | 4 | 10.630 | 4 | 10.630 | Mass | 10.630 | 10.605 | 10.526 | 10.630 | 10.488 | 0.000 | 0.000 | 0.025 | 0.078 | -0.104 | 0.142
| 2DD9M | +9 MTR EXTN | 3.723 | 1 | 3.723 |  |  | Mass
| 2MA2 | STUB | 0.420 | 1 | 0.420 | 1 | 0.420 | Mass | 0.420 | 0.420 | 0.420 | 0.420 | 0.420 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2MA3 | NORMAL TOWER | 11.566 | 4 | 46.265 | 3 | 34.691 | Mass | 34.699 | 33.504 | 32.791 | 34.699 | 32.497 | 11.564 | 0.000 | 1.196 | 0.712 | -1.908 | 2.202
| 2MA6M | +6 MTR EXTN | 2.893 | 2 | 5.785 | 2 | 5.784 | Mass | 5.785 | 5.760 | 5.691 | 5.785 | 5.672 | 0.000 | 0.000 | 0.025 | 0.069 | -0.094 | 0.113
| 2MC2 | STUB | 0.906 | 4 | 3.624 | 4 | 3.624 | Mass | 3.624 | 3.624 | 3.624 | 3.624 | 3.624 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2MC3 | NORMAL TOWER | 19.203 | 7 | 134.421 | 5 | 96.015 | Mass | 96.015 | 94.938 | 93.382 | 96.015 | 93.173 | 38.410 | 0.000 | 1.077 | 1.556 | -2.633 | 2.842
| 2MD18M | +18 MTR EXTN | 25.361 | 2 | 50.722 | 2 | 50.715 | Mass | 50.722 | 50.502 | 50.187 | 50.722 | 50.008 | 0.000 | 0.000 | 0.219 | 0.316 | -0.535 | 0.714
| 2MD2 | STUB | 0.966 | 4 | 3.864 | 4 | 3.864 | Mass | 3.864 | 3.864 | 3.864 | 3.864 | 3.864 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2MD2A | STUB | 0.986 | 1 | 0.986 | 1 | 0.986 | Mass | 0.986 | 0.986 | 0.986 | 0.986 | 0.986 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2MD3 | NORMAL TOWER | 25.556 | 11 | 281.111 | 7 | 178.896 | Mass | 178.889 | 175.838 | 174.719 | 178.889 | 171.997 | 102.221 | 0.000 | 3.051 | 1.119 | -4.170 | 6.892
| 2MD3M | +3 MTR EXTN | 4.982 | 2 | 9.963 |  |  | Mass
| 2MD6M | +6 MTR EXTN | 7.343 | 3 | 22.030 | 2 | 14.689 | Mass | 14.687 | 14.668 | 14.619 | 14.687 | 14.457 | 7.345 | 0.000 | 0.019 | 0.049 | -0.068 | 0.230
| 2MDB21M | +21.0 Mtr. Extn. | 21.749 | 1 | 21.749 | 1 | 21.750 | Mass | 21.749 | 21.532 | 21.386 | 21.749 | 21.209 | 0.000 | 0.000 | 0.217 | 0.145 | -0.363 | 0.540
| 2MDB25M | +25.0 Mtr. Extn | 27.131 | 2 | 54.263 |  |  | Proto
| 2MDB2A | STUB | 2.175 | 3 | 6.525 | 3 | 6.525 | Mass | 6.525 | 6.525 | 6.525 | 6.525 | 6.525 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2MDB3 | NORMAL TOWER | 26.246 | 3 | 78.737 | 3 | 78.730 | Mass | 78.737 | 77.592 | 74.970 | 78.737 | 74.465 | 0.000 | 0.000 | 1.145 | 2.623 | -3.767 | 4.272
| 2ND3 | NORMAL TOWER | 6.301 | 1 | 6.301 |  |  | Mass
| 2ND6M | +6 MTR EXTN | 2.549 | 1 | 2.549 |  |  | Mass
| 2SD2 | STUB | 0.211 | 2 | 0.423 | 2 | 0.422 | Mass | 0.423 | 0.423 | 0.423 | 0.423 | 0.423 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2SD3 | NORMAL TOWER | 2.449 | 2 | 4.898 |  |  | Mass
|  | Sub Total | 241.398 | 314 | 1453.614 | 296 | 1208.487 |  | 1208.509 | 1195.131 | 1184.748 | 1208.509 | 1177.247 | 163.412 | 0.000 | 13.378 | 10.383 | -23.761 | 31.262
| Project Code : 922 |  | Client : SHARVARI ELECTRICALS - VT922 | [11 empty] | Order Dt. : 13/12/2025
| 2DD12M | +12 MTR EXTN | 5.828 | 2 | 11.655 | 2 | 11.654 | Mass | 11.655 | 2.389 | 0.683 |  |  | 0.000 | 0.000 | 9.266 | 1.707
| 2DD21M | +21.0 Mtr. Extn. | 10.210 | 2 | 20.420 | 2 | 20.418 | Mass | 20.420 | 1.052 | 1.052 |  |  | 0.000 | 0.000 | 19.368 | 0.000
| 2MA3 | NORMAL TOWER | 11.566 | 1 | 11.566 | 1 | 11.564 | Mass | 11.566 | 6.773 | 5.357 | 11.566 |  | 0.000 | 0.000 | 4.793 | 1.417 | -6.210 | 11.566
| 2MA9M | +9 MTR EXTN | 3.274 | 1 | 3.274 | 1 | 3.277 | Mass | [5 empty] | 0.000 | 3.274
| 2MAN2 | STUB | 0.739 | 1 | 0.739 | 1 | 0.739 | Mass | 0.739 | 0.739 | 0.739 | 0.739 | 0.739 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2MAN3 | NORMAL TOWER | 10.542 | 1 | 10.542 | 1 | 10.549 | Mass | 10.542 | 5.461 | 3.443 | 10.542 |  | 0.000 | 0.000 | 5.081 | 2.018 | -7.099 | 10.542
| 2MAN3M | +3 MTR EXTN | 1.014 | 1 | 1.014 | 1 | 0.655 | Mass | 0.654 | 0.131 | 0.027 | 0.774 |  | 0.000 | 0.000 | 0.522 | 0.104 | -0.747 | 0.774
| 2MC3 | NORMAL TOWER | 19.203 | 3 | 57.609 | 3 | 57.609 | Mass | 57.609 | 37.973 | 34.197 | 57.609 |  | 0.000 | 0.000 | 19.636 | 3.776 | -23.412 | 57.609
| 2MC3M | +3 MTR EXTN | 3.145 | 3 | 9.436 | 3 | 9.436 | Mass | 9.436 | 3.694 | 3.055 |  |  | 0.000 | 0.000 | 5.741 | 0.639
| 2MC6M | +6 MTR EXTN | 4.777 | 2 | 9.555 | 2 | 9.550 | Mass | 9.555 | 3.073 | 2.951 |  |  | 0.000 | 0.000 | 6.482 | 0.122
| 2MCN2 | STUB | 2.379 | 1 | 2.379 | 1 | 2.376 | Mass | 2.379 | 2.379 | 2.379 | 2.379 | 2.379 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2MCN3 | NORMAL TOWER | 25.679 | 1 | 25.679 | 1 | 25.665 | Mass | 25.679 | 16.698 | 15.341 | 25.679 |  | 0.000 | 0.000 | 8.981 | 1.357 | -10.338 | 25.679
| 2MD3 | NORMAL TOWER | 25.556 | 5 | 127.778 | 5 | 127.781 | Mass | 127.778 | 101.481 | 84.471 | 127.778 |  | 0.000 | 0.000 | 26.297 | 17.010 | -43.306 | 127.778
| 2MD3M | +3 MTR EXTN | 4.982 | 1 | 4.982 | 1 | 4.986 | Mass | 4.982 | 1.975 | 1.786 | 4.982 |  | 0.000 | 0.000 | 3.007 | 0.189 | -3.196 | 4.982
| 2MDB25M | +25.0 Mtr. Extn | 27.131 | 2 | 54.263 | 2 | 54.249 | Proto | 54.263 | 29.001 | 14.040 |  |  | 0.000 | 0.000 | 25.262 | 14.960
| 2MDN2 | STUB | 3.014 | 3 | 9.042 | 3 | 9.042 | Mass | 9.042 | 9.042 | 9.042 | 9.042 | 9.042 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2MDN3 | NORMAL TOWER | 32.536 | 3 | 97.607 | 3 | 97.633 | Mass | 97.607 | 79.675 | 75.548 | 97.607 |  | 0.000 | 0.000 | 17.932 | 4.127 | -22.059 | 97.607
| 2MDN6M | +6 MTR EXTN | 7.247 | 2 | 14.493 | 2 | 14.486 | Mass | 14.493 | 12.810 | 12.508 | 14.493 |  | 0.000 | 0.000 | 1.684 | 0.302 | -1.986 | 14.493
| 2ND3 | NORMAL TOWER | 6.301 | 1 | 6.301 | 1 | 6.300 | Mass | 6.301 | 0.083 |  |  |  | 0.000 | 0.000 | 6.218 | 0.083
| 2ND6M | +6 MTR EXTN | 2.549 | 1 | 2.549 | 1 | 2.549 | Mass | 2.549 | 0.089 |  |  |  | 0.000 | 0.000 | 2.460 | 0.089
| SC | NORMAL TOWER | 0.134 | 1 | 0.134 | 1 | 0.135 | Mass | 0.134 |  |  |  |  | 0.000 | 0.000 | 0.134
|  | Sub Total | 207.805 | 38 | 481.017 | 38 | 480.653 |  | 477.383 | 314.518 | 266.618 | 363.189 | 12.159 | 0.000 | 3.274 | 162.865 | 47.900 | -118.353 | 351.030
| Project Code : 923 |  | Client : SIDDHARTHA ENGINEERING LIMITED - VT923 | [11 empty] | Order Dt. : 13/12/2025
| 1BPI | EQUIPMENT | 0.230 | 4 | 0.922 | 4 | 0.922 | Mass | 0.922 | 0.319 | 0.064 |  |  | 0.000 | 0.000 | 0.603 | 0.255
| 1CTS | EQUIPMENT | 0.227 | 6 | 1.361 | 6 | 1.361 | Mass | 1.361 | 0.571 | 0.571 |  |  | 0.000 | 0.000 | 0.791 | 0.000
| 1CVTS | EQUIPMENT | 0.200 | 6 | 1.202 | 6 | 1.205 | Proto | 1.202 | 0.498 | 0.299 |  |  | 0.000 | 0.000 | 0.704 | 0.199
| 1G1 | BEAM | 0.577 | 4 | 2.309 | 4 | 2.311 | Mass | 2.309 | 1.382 | 1.266 |  |  | 0.000 | 0.000 | 0.926 | 0.116
| 1G2 | BEAM | 0.857 | 2 | 1.715 | 2 | 1.710 | Mass | 1.715 | 1.334 | 1.308 |  |  | 0.000 | 0.000 | 0.380 | 0.026
| 1PA1 | S.S.T | 0.495 | 2 | 0.990 | 2 | 0.989 | Mass | 0.990 | 0.990 | 0.990 | 0.990 | 0.495 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.495
| 1PA2 | STUB | 0.252 | 20 | 5.031 | 20 | 5.031 | Mass | 5.031 | 5.031 | 5.031 | 5.031 | 5.031 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1PA3 | NORMAL TOWER | 3.237 | 20 | 64.748 | 20 | 64.741 | Mass | 64.748 | 52.222 | 47.481 |  |  | 0.000 | 0.000 | 12.526 | 4.741
| 1PA3M | +3 MTR EXTN | 0.641 | 7 | 4.486 | 7 | 4.485 | Mass | 4.486 | 2.193 | 1.925 |  |  | 0.000 | 0.000 | 2.294 | 0.267
| 1PA6M | +6 MTR EXTN | 1.356 | 4 | 5.425 | 4 | 5.427 | Mass | 5.425 | 2.674 | 2.228 |  |  | 0.000 | 0.000 | 2.751 | 0.446
| 1PB1 | S.S.T | 0.631 | 1 | 0.631 | 1 | 0.632 | Mass | 0.631 | 0.631 | 0.631 | 0.631 | 0.631 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1PB2 | STUB | 0.434 | 8 | 3.471 | 8 | 3.471 | Mass | 3.471 | 3.471 | 3.471 | 3.471 | 3.471 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1PB3 | NORMAL TOWER | 4.662 | 8 | 37.295 | 8 | 37.301 | Mass | 37.295 | 29.367 | 26.294 |  |  | 0.000 | 0.000 | 7.927 | 3.074
| 1PB3M | +3 MTR EXTN | 1.043 | 2 | 2.086 | 2 | 2.084 | Mass | 2.086 | 1.536 | 1.427 |  |  | 0.000 | 0.000 | 0.550 | 0.109
| 1PB6M | +6 MTR EXTN | 2.165 | 2 | 4.329 | 2 | 4.328 | Mass | 4.329 | 4.077 | 4.023 |  |  | 0.000 | 0.000 | 0.253 | 0.054
| 1PC1 | S.S.T | 0.819 | 1 | 0.819 | 1 | 0.817 | Mass | 0.819 | 0.819 | 0.819 | 0.819 | 0.819 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1PC2 | STUB | 0.610 | 8 | 4.876 | 8 | 4.876 | Mass | 4.876 | 4.876 | 4.876 | 4.876 | 4.876 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1PC3 | NORMAL TOWER | 5.585 | 8 | 44.677 | 8 | 44.680 | Mass | 44.677 | 34.108 | 33.274 |  |  | 0.000 | 0.000 | 10.569 | 0.834
| 1S2 | EQUIPMENT | 1.111 | 2 | 2.223 | 2 | 2.221 | Mass | 2.223 | 0.088 |  |  |  | 0.000 | 0.000 | 2.135 | 0.088
| 1S4 | EQUIPMENT | 0.646 | 2 | 1.292 | 2 | 1.296 | Mass | 1.292 | 0.807 | 0.609 |  |  | 0.000 | 0.000 | 0.486 | 0.198
| 1SA | EQUIPMENT | 0.189 | 6 | 1.136 | 6 | 1.137 | Mass | 1.136 | 0.925 | 0.638 |  |  | 0.000 | 0.000 | 0.211 | 0.287
| 1T1S | NORMAL TOWER | 1.093 | 4 | 4.372 | 4 | 4.375 | Mass | 4.372 | 3.676 | 3.641 |  |  | 0.000 | 0.000 | 0.696 | 0.035
| 1T4S | NORMAL TOWER | 0.852 | 1 | 0.852 | 1 | 0.851 | Mass | 0.852 | 0.463 | 0.428 |  |  | 0.000 | 0.000 | 0.389 | 0.035
| 2UR1 | S.S.T | 1.563 | 1 | 1.563 |  |  | Mass
| 2UR2 | STUB | 0.692 | 6 | 4.155 |  |  | Mass
| 2UR3 | NORMAL TOWER | 12.725 | 6 | 76.351 |  |  | Mass
| 2UR6M | +6 MTR EXTN | 4.214 | 6 | 25.285 |  |  | Mass
|  | Sub Total | 47.107 | 147 | 303.602 | 128 | 196.251 |  | 196.248 | 152.057 | 141.293 | 15.817 | 15.322 | 0.000 | 0.000 | 44.192 | 10.764 | 0.000 | 0.495
| Project Code : 924 |  | Client : SIEMENS ENERGY IN LTD - VT924 | [11 empty] | Order Dt. : 06/12/2025
| 2B1 | BEAM | 2.019 | 1 | 2.019 | 1 | 2.022 | Mass | 2.019 | 2.019 | 2.019 | 2.019 | 1.015 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.004
| 2B2 | BEAM | 1.618 | 1 | 1.618 | 1 | 1.616 | Mass | 1.618 | 1.618 | 1.618 | 1.618 | 1.060 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.558
| 2BPI | EQUIPMENT | 0.184 | 6 | 1.104 | 6 | 1.102 | Mass | 1.104 | 1.104 | 1.104 | 1.104 | 0.174 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.930
| 2CVT | EQUIPMENT | 0.163 | 6 | 0.975 | 6 | 0.975 | Mass | 0.975 | 0.975 | 0.975 | 0.975 | 0.162 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.813
| 2HBPI | EQUIPMENT | 0.302 | 7 | 2.117 | 7 | 2.122 | Mass | 2.117 | 2.117 | 2.117 | 2.117 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 2.117
| 2LA | EQUIPMENT | 0.169 | 6 | 1.011 | 6 | 1.010 | Mass | 1.011 | 1.011 | 1.011 | 1.011 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.011
| 2T1 | COLUMN | 3.485 | 1 | 3.485 | 1 | 3.485 | Mass | 3.485 | 3.485 | 3.485 | 3.485 | 3.180 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.305
| 2T2 | COLUMN | 4.855 | 1 | 4.855 | 1 | 4.848 | Mass | 4.855 | 4.855 | 4.855 | 4.855 | 4.364 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.491
| 2WT | EQUIPMENT | 0.481 | 4 | 1.925 | 4 | 1.920 | Mass | 1.925 | 1.925 | 1.925 | 1.925 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.925
| IS | COLUMN | 0.019 | 1 | 0.019 | 1 | 0.019 | Mass | 0.019 | 0.012 |  |  |  | 0.000 | 0.000 | 0.007 | 0.012
| SC | NORMAL TOWER | 0.016 | 1 | 0.016 | 1 | 0.015 | Mass | 0.016 |  |  |  |  | 0.000 | 0.000 | 0.016
|  | Sub Total | 13.311 | 35 | 19.144 | 35 | 19.134 |  | 19.144 | 19.121 | 19.110 | 19.110 | 9.955 | 0.000 | 0.000 | 0.023 | 0.012 | 0.000 | 9.154
| Project Code : 926 |  | Client : HARTEK POWER PRIVATE LIMITED - VT925 | [11 empty] | Order Dt. : 29/12/2025
| 2BPI | EQUIPMENT | 0.179 | 58 | 10.395 |  |  | Proto
| 2CT | EQUIPMENT | 0.149 | 36 | 5.362 |  |  | Proto
| 2CVT | EQUIPMENT | 0.153 | 24 | 3.668 |  |  | Proto
| 2G1 | BEAM | 1.545 | 21 | 32.447 | 21 | 32.444 | Proto | 32.447 | 25.506 | 8.126 |  |  | 0.000 | 0.000 | 6.941 | 17.380
| 2G3 | BEAM | 1.717 | 10 | 17.174 | 10 | 17.172 | Proto | 17.174 | 9.714 | 2.490 |  |  | 0.000 | 0.000 | 7.460 | 7.225
| 2HBPI | EQUIPMENT | 0.277 | 58 | 16.047 |  |  | Proto
| 2ISO1L | EQUIPMENT | 1.002 | 6 | 6.014 |  |  | Proto
| 2ISO1R | EQUIPMENT | 1.008 | 5 | 5.039 |  |  | Proto
| 2ISO2 | EQUIPMENT | 1.008 | 13 | 13.101 |  |  | Proto
| 2LA | EQUIPMENT | 0.179 | 15 | 2.683 |  |  | Proto
| 2TA1 | COLUMN | 2.548 | 4 | 10.194 | 4 | 10.184 | Proto | 9.833 | 1.145 | 0.693 |  |  | 0.000 | 0.361 | 8.687 | 0.453
| 2TA2 | COLUMN | 3.574 | 8 | 28.589 | 8 | 28.588 | Proto | 28.041 | 5.107 | 1.802 |  |  | 0.000 | 0.548 | 22.934 | 3.305
| 2TD2 | COLUMN | 2.342 | 6 | 14.051 | 6 | 14.058 | Proto | 14.051 | 1.397 | 0.477 |  |  | 0.000 | 0.000 | 12.654 | 0.920
| 2TF1 | COLUMN | 1.798 | 8 | 14.384 | 8 | 14.388 | Proto | 13.466 | 2.253 |  |  |  | 0.000 | 0.917 | 11.214 | 2.253
| 2TI3 | COLUMN | 3.708 | 2 | 7.415 | 2 | 7.411 | Proto | 7.415 | 1.652 | 0.541 |  |  | 0.000 | 0.000 | 5.763 | 1.112
| 2TISO | EQUIPMENT | 1.029 | 21 | 21.600 |  |  | Proto
| 2TJ2 | COLUMN | 2.999 | 8 | 23.994 | 8 | 23.988 | Proto | 23.446 | 7.996 | 3.438 |  |  | 0.000 | 0.548 | 15.450 | 4.558
| 2WT | EQUIPMENT | 0.179 | 12 | 2.149 |  |  | Proto
| 4BPI | EQUIPMENT | 0.229 | 42 | 9.633 |  |  | Proto
| 4CT | EQUIPMENT | 0.225 | 36 | 8.112 |  |  | Proto
| 4CVT | EQUIPMENT | 0.258 | 12 | 3.096 |  |  | Proto
| 4G1 | BEAM | 2.577 | 6 | 15.459 | 6 | 15.460 | Proto | 15.459 | 9.072 | 5.242 |  |  | 0.000 | 0.000 | 6.387 | 3.831
| 4G2 | BEAM | 2.785 | 6 | 16.709 | 6 | 16.710 | Proto | 16.370 | 9.546 | 7.499 |  |  | 0.000 | 0.339 | 6.824 | 2.047
| 4G3 | BEAM | 2.382 | 6 | 14.292 | 6 | 14.297 | Proto | 14.141 | 7.152 | 4.453 |  |  | 0.000 | 0.152 | 6.988 | 2.700
| 4ISO1L | EQUIPMENT | 1.612 | 15 | 24.181 |  |  | Proto
| 4ISO1R | EQUIPMENT | 1.600 | 15 | 24.003 |  |  | Proto
| 4ISO2 | EQUIPMENT | 1.644 | 2 | 3.288 |  |  | Proto
| 4LA | EQUIPMENT | 0.211 | 24 | 5.063 |  |  | Proto
| 4TC | NORMAL TOWER | 2.566 | 6 | 15.394 | 6 | 15.402 | Proto | 13.740 | 1.868 | 1.160 |  |  | 0.000 | 1.654 | 11.872 | 0.707
| 4TH | COLUMN | 5.366 | 6 | 32.196 | 6 | 32.192 | Proto | 22.451 | 2.982 | 1.693 |  |  | 0.000 | 9.744 | 19.469 | 1.289
| 4TJ | COLUMN | 4.675 | 5 | 23.375 | 5 | 23.370 | Proto | 22.389 | 5.300 | 2.199 |  |  | 0.000 | 0.986 | 17.089 | 3.101
| 4TK | NORMAL TOWER | 5.704 | 4 | 22.817 | 4 | 22.824 | Proto | 16.884 | 1.211 | 1.211 |  |  | 0.000 | 5.933 | 15.673 | 0.000
| 4WT | EQUIPMENT | 0.240 | 4 | 0.959 |  |  | Proto
|  | Sub Total | 57.468 | 504 | 452.883 | 106 | 288.488 |  | 267.309 | 91.901 | 41.022 |  |  | 0.000 | 21.183 | 175.407 | 50.879
| Project Code : 927 |  | Client : BANSAL CONSTRUCTION & ENGINEERING - VT927 | [11 empty] | Order Dt. : 30/12/2025
| B01 | S.S.T | 0.862 | 1 | 0.862 | 1 | 0.861 | Proto | 0.862 | 0.862 | 0.862 | 0.862 | 0.862 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| B02 | STUB | 0.269 | 1 | 0.269 | 1 | 0.269 | Mass | 0.269 | 0.269 | 0.269 | 0.269 | 0.269 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| B03 | NORMAL TOWER | 4.500 | 1 | 4.500 | 1 | 4.496 | Mass | 4.500 | 4.500 | 4.500 | 4.500 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 4.500
| B03M | +3 MTR EXTN | 0.936 | 1 | 0.936 | 1 | 0.937 | Mass | 0.936 | 0.936 | 0.936 | 0.936 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.936
| B301 | S.S.T | 1.331 | 1 | 1.331 | 1 | 1.331 | Mass | 1.331 | 1.331 | 1.331 | 1.331 | 1.331 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| B3010M | +10M Body Extn | 3.203 | 1 | 3.203 | 1 | 3.206 | Proto | 3.203 | 3.203 | 3.203 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| B302 | STUB | 0.440 | 1 | 0.440 | 1 | 0.440 | Mass | 0.440 | 0.440 | 0.440 | 0.440 | 0.440 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| B303 | NORMAL TOWER | 7.304 | 1 | 7.304 | 1 | 7.303 | Mass | 7.304 | 7.304 |  |  |  | 0.000 | 0.000 | 0.000 | 7.304
| B601 | S.S.T | 1.888 | 2 | 3.775 | 2 | 3.775 | Proto | 3.775 | 3.775 | 3.775 | 3.775 | 3.775 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| B6010M | +10M Body Extn | 7.993 | 3 | 23.979 | 3 | 23.966 | Proto | 23.979 | 23.979 | 23.979 | 23.979 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 23.979
| B602 | STUB | 0.582 | 8 | 4.659 | 8 | 4.657 | Mass | 4.659 | 4.659 | 4.659 | 4.659 | 4.659 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| B603 | NORMAL TOWER | 8.963 | 8 | 71.701 | 8 | 71.707 | Mass | 71.701 | 71.701 | 69.861 | 71.701 | 0.243 | 0.000 | 0.000 | 0.000 | 1.840 | -1.840 | 71.458
| B606M | +6 MTR EXTN | 4.804 | 5 | 24.019 | 5 | 24.024 | Mass | 24.019 | 24.019 | 0.047 | 24.019 | 0.005 | 0.000 | 0.000 | 0.000 | 23.972 | -23.972 | 24.014
| E01 | S.S.T | 0.514 | 1 | 0.514 | 1 | 0.513 | Proto | 0.514 | 0.514 | 0.514 | 0.514 | 0.514 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| E02 | STUB | 0.225 | 1 | 0.225 | 1 | 0.227 | Mass | 0.225 | 0.225 | 0.225 | 0.225 | 0.225 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| E03 | NORMAL TOWER | 3.371 | 1 | 3.371 | 1 | 3.378 | Proto | 3.371 | 3.371 | 3.371 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| E06M | +6 MTR EXTN | 1.628 | 1 | 1.628 | 1 | 1.630 | Proto | 1.628 | 1.628 | 1.628 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| E601 | S.S.T | 1.175 | 1 | 1.175 | 1 | 1.172 | Proto | 1.175 | 1.175 | 1.175 | 1.175 | 1.175 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| E6010M | +10M Body Extn | 4.855 | 1 | 4.855 | 1 | 4.850 | Proto | 4.855 | 4.855 | 4.855 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| E602 | STUB | 0.554 | 1 | 0.554 | 1 | 0.553 | Mass | 0.554 | 0.554 | 0.554 | 0.554 | 0.554 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| E603 | NORMAL TOWER | 6.234 | 1 | 6.234 | 1 | 6.229 | Mass | 6.234 | 6.234 | 6.234 | 6.234 |  | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 6.234
| SC | NORMAL TOWER | 0.060 | 1 | 0.060 | 1 | 0.060 | Mass | 0.060 | 0.060 | 0.060 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  |  |  | 1 | 0.060 | 1 | 0.060 | Mass | 0.060 | 0.060 | 0.060 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 61.750 | 44 | 165.654 | 44 | 165.644 |  | 165.654 | 165.654 | 132.537 | 145.173 | 14.052 | 0.000 | 0.000 | 0.000 | 33.116 | -25.813 | 131.121
| Project Code : 928 |  | Client : SIDDHARTHA ENGINEERING LIMITED - VT923 | [11 empty] | Order Dt. : 01/01/2026
| 1G1 | BEAM | 0.577 | 4 | 2.309 |  |  | Mass
| 1T1S | NORMAL TOWER | 1.101 | 4 | 4.404 |  |  | Mass
| 2P1S | COLUMN | 4.158 | 7 | 29.103 | 7 | 29.102 | Mass | 29.103 | 18.665 | 11.993 |  |  | 0.000 | 0.000 | 10.438 | 6.672
| 2Q1 | BEAM | 1.601 | 6 | 9.608 | 6 | 9.611 | Mass | 9.608 | 8.183 | 5.234 |  |  | 0.000 | 0.000 | 1.425 | 2.949
| 2UR1 | S.S.T | 1.563 | 2 | 3.125 | 2 | 3.128 | Mass | 3.125 | 2.718 | 2.183 | 3.125 | 1.563 | 0.000 | 0.000 | 0.408 | 0.535 | -0.943 | 1.563
| 2UR2 | STUB | 0.692 | 8 | 5.540 | 8 | 5.540 | Mass | 5.540 | 5.540 | 5.540 | 5.540 | 4.155 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.385
| 2UR3 | NORMAL TOWER | 12.725 | 8 | 101.802 | 8 | 101.802 | Mass | 101.802 | 82.063 | 76.138 | 101.802 |  | 0.000 | 0.000 | 19.739 | 5.925 | -25.664 | 101.802
| 2UR6M | +6 MTR EXTN | 4.214 | 8 | 33.713 | 8 | 33.727 | Mass | 33.713 | 30.115 | 24.627 | 33.727 |  | -0.014 | 0.013 | 3.599 | 5.488 | -9.100 | 33.727
| 3G4 | BEAM | 0.287 | 8 | 2.297 | 8 | 2.295 | Mass | 2.297 | 1.488 | 0.834 |  |  | 0.000 | 0.000 | 0.809 | 0.654
| 3G4X | BEAM | 0.287 | 4 | 1.148 | 4 | 1.148 | Mass | 1.148 | 0.835 |  |  |  | 0.000 | 0.000 | 0.314 | 0.835
| 3G6 | BEAM | 0.361 | 4 | 1.442 | 4 | 1.444 | Mass | 1.442 | 1.175 | 0.670 |  |  | 0.000 | 0.000 | 0.268 | 0.504
| 3T8S | NORMAL TOWER | 0.677 | 10 | 6.767 | 10 | 6.769 | Mass | 6.767 | 2.610 | 0.146 |  |  | 0.000 | 0.000 | 4.157 | 2.464
| 3T9S | NORMAL TOWER | 0.506 | 12 | 6.077 | 12 | 6.077 | Mass | 6.077 | 1.865 |  |  |  | 0.000 | 0.000 | 4.212 | 1.865
| OA1 | S.S.T | 0.648 | 1 | 0.648 | 1 | 0.648 | Mass | 0.648 | 0.648 | 0.648 | 0.648 | 0.648 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| OA2 | STUB | 0.232 | 28 | 6.490 | 28 | 6.490 | Mass | 6.490 | 6.490 | 6.490 | 6.490 | 6.026 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.464
| OA3 | NORMAL TOWER | 4.348 | 20 | 86.962 | 20 | 86.956 | Mass | 86.962 | 72.605 | 64.072 | 86.962 |  | 0.000 | 0.000 | 14.357 | 8.532 | -22.889 | 86.962
| OA3M | +3 MTR EXTN | 0.763 | 10 | 7.633 | 10 | 7.636 | Mass | 7.633 | 7.359 | 6.986 | 7.633 |  | 0.000 | 0.000 | 0.274 | 0.372 | -0.647 | 7.633
| OA6M | +6 MTR EXTN | 1.515 | 7 | 10.604 | 5 | 7.576 | Mass | 7.574 | 6.421 | 6.202 | 7.574 |  | 3.031 | 0.000 | 1.153 | 0.219 | -1.372 | 7.574
| OB1 | S.S.T | 0.896 | 1 | 0.896 | 1 | 0.897 | Mass | 0.896 | 0.896 | 0.896 | 0.896 | 0.896 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| OB2 | STUB | 0.438 | 9 | 3.939 | 9 | 3.939 | Mass | 3.939 | 3.939 | 3.939 | 3.939 | 3.939 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| OB3 | NORMAL TOWER | 6.512 | 9 | 58.606 | 9 | 58.613 | Mass | 58.606 | 50.345 | 47.060 | 58.606 |  | 0.000 | 0.000 | 8.261 | 3.286 | -11.547 | 58.606
| OB3M | +3 MTR EXTN | 1.358 | 7 | 9.507 | 7 | 9.508 | Mass | 9.507 | 8.533 | 8.097 | 9.507 |  | 0.000 | 0.000 | 0.974 | 0.437 | -1.411 | 9.507
| OB6M | +6 MTR EXTN | 2.346 | 5 | 11.730 | 5 | 11.731 | Mass | 11.730 | 10.614 | 10.242 | 11.730 |  | 0.000 | 0.000 | 1.116 | 0.371 | -1.487 | 11.730
| OC1 | S.S.T | 1.016 | 1 | 1.016 | 1 | 1.015 | Mass | 1.016 | 1.016 | 1.016 | 1.016 | 1.016 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| OC15M | +15 MTR EXTN | 8.696 | 2 | 17.393 | 2 | 17.388 | Mass | 17.393 | 13.163 | 10.835 | 17.393 |  | 0.000 | 0.000 | 4.230 | 2.328 | -6.557 | 17.393
| OC1A | S.S.T | 2.095 | 1 | 2.095 | 1 | 2.096 | Mass | 2.095 | 1.693 |  |  |  | 0.000 | 0.000 | 0.402 | 1.693
| OC2 | STUB | 0.777 | 20 | 15.535 | 20 | 15.535 | Mass | 15.535 | 15.535 | 15.535 | 15.535 | 15.535 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| OC2A | STUB | 1.067 | 2 | 2.134 | 2 | 2.134 | Mass | 2.134 | 2.134 | 2.134 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| OC3 | NORMAL TOWER | 9.237 | 21 | 193.984 | 21 | 193.974 | Mass | 193.984 | 170.171 | 161.911 | 193.984 |  | 0.000 | 0.000 | 23.813 | 8.259 | -32.072 | 193.984
| OC3M | +3 MTR EXTN | 1.488 | 12 | 17.853 | 12 | 17.853 | Mass | 17.853 | 13.707 | 13.583 | 17.853 |  | 0.000 | 0.000 | 4.147 | 0.123 | -4.270 | 17.853
| OC6M | +6 MTR EXTN | 2.741 | 8 | 21.928 | 8 | 21.931 | Mass | 21.928 | 17.224 | 13.197 | 21.928 |  | 0.000 | 0.000 | 4.705 | 4.027 | -8.732 | 21.928
|  | Sub Total | 74.922 | 249 | 676.288 | 239 | 666.563 |  | 666.546 | 557.748 | 500.209 | 605.887 | 33.777 | 3.017 | 0.013 | 108.798 | 57.538 | -126.691 | 572.110
| Project Code : 929 |  | Client : BHARAT HEAVY ELECTRICALS LIMITED (PGCIL KHAVDA) - VT929 | [11 empty] | Order Dt. : 01/01/2026
| 4B1 | BEAM | 4.015 | 23 | 92.347 | 23 | 92.346 | Proto | 92.155 | 71.250 | 39.549 |  |  | 0.000 | 0.191 | 20.906 | 31.700
| 4B2 | BEAM | 4.026 | 21 | 84.539 |  |  | Pre
| 4B3 | BEAM | 5.650 | 4 | 22.600 | 4 | 22.600 | Proto | 22.262 | 10.125 | 4.259 |  |  | 0.000 | 0.337 | 12.137 | 5.866
| 4TA | NORMAL TOWER | 5.015 | 27 | 135.393 | 27 | 135.391 | Proto | 133.205 | 87.207 | 53.988 |  |  | 0.000 | 2.188 | 45.998 | 33.219
| 4TC | NORMAL TOWER | 5.015 | 11 | 55.160 | 11 | 55.160 | Proto | 41.255 | 21.730 | 16.126 |  |  | 0.000 | 13.905 | 19.525 | 5.604
| 4TE | NORMAL TOWER | 6.218 | 1 | 6.218 | 1 | 6.215 | Proto | 3.076 |  |  |  |  | 0.000 | 3.141 | 3.076
| 4TF | NORMAL TOWER | 8.839 | 4 | 35.357 | 4 | 35.347 | Proto | 13.982 | 1.967 |  |  |  | 0.000 | 21.376 | 12.015 | 1.967
| 4TG | NORMAL TOWER | 12.617 | 2 | 25.233 | 2 | 25.232 | Proto | 19.525 | 0.207 |  |  |  | 0.000 | 5.708 | 19.318 | 0.207
|  | Sub Total | 51.394 | 93 | 456.847 | 72 | 372.291 |  | 325.461 | 192.486 | 113.922 |  |  | 0.000 | 46.846 | 132.975 | 78.564
| Project Code : 931 |  | Client : FLOWMORE LIMITED - VT931 | [11 empty] | Order Dt. : 01/01/2026
| OA3M | +3 MTR EXTN | 0.763 | 1 | 0.763 | 1 | 0.762 | Mass | 0.763 | 0.672 | 0.493 | 0.763 | 0.371 | 0.000 | 0.000 | 0.091 | 0.179 | -0.270 | 0.392
| OA6M | +6 MTR EXTN | 1.515 | 5 | 7.574 | 5 | 7.576 | Mass | 7.574 | 6.625 | 6.571 | 7.574 | 6.571 | 0.000 | 0.000 | 0.949 | 0.055 | -1.004 | 1.004
| OB2 | STUB | 0.438 | 3 | 1.313 | 3 | 1.313 | Mass | 1.313 | 1.297 | 1.297 | 1.313 | 1.297 | 0.000 | 0.000 | 0.016 | 0.000 | -0.016 | 0.016
| OB3 | NORMAL TOWER | 6.518 | 2 | 13.036 | 2 | 13.032 | Mass | 13.036 | 9.188 | 8.499 | 13.036 | 7.789 | 0.000 | 0.000 | 3.848 | 0.688 | -4.537 | 5.247
| OB3M | +3 MTR EXTN | 1.361 | 8 | 10.885 | 8 | 10.885 | Mass | 10.885 | 10.885 | 10.436 | 10.885 | 9.791 | 0.000 | 0.000 | 0.000 | 0.449 | -0.449 | 1.094
| OB6M | +6 MTR EXTN | 2.346 | 4 | 9.384 | 4 | 9.386 | Mass | 9.384 | 8.685 | 8.397 | 9.384 | 7.810 | 0.000 | 0.000 | 0.699 | 0.287 | -0.986 | 1.574
| OC15M | +15 MTR EXTN | 8.696 | 12 | 104.356 | 12 | 104.357 | Mass | 104.356 | 101.567 | 101.102 | 104.356 | 99.198 | 0.000 | 0.000 | 2.790 | 0.465 | -3.254 | 5.158
| OC1A | S.S.T | 2.095 | 2 | 4.190 | 2 | 4.189 | Mass | 4.190 | 4.190 | 2.452 | 4.190 | 2.452 | 0.000 | 0.000 | 0.000 | 1.738 | -1.738 | 1.738
| OC2 | STUB | 0.777 | 16 | 12.428 | 16 | 12.427 | Mass | 12.428 | 12.428 | 12.425 | 12.428 | 12.133 | 0.000 | 0.000 | 0.000 | 0.003 | -0.003 | 0.295
| OC2A | STUB | 1.067 | 12 | 12.807 | 12 | 12.807 | Mass | 12.807 | 12.807 | 12.807 | 12.807 | 12.807 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| OC3 | NORMAL TOWER | 9.238 | 27 | 249.418 | 27 | 249.402 | Mass | 249.418 | 234.901 | 230.155 | 249.418 | 226.413 | 0.010 | -0.010 | 14.517 | 4.746 | -19.263 | 23.005
| OC3M | +3 MTR EXTN | 1.488 | 7 | 10.414 | 7 | 10.415 | Mass | 10.414 | 10.222 | 10.127 | 10.414 | 9.473 | 0.000 | 0.000 | 0.192 | 0.095 | -0.287 | 0.942
| OC6M | +6 MTR EXTN | 2.741 | 15 | 41.116 | 15 | 41.118 | Mass | 41.116 | 39.286 | 37.451 | 41.116 | 36.621 | 0.000 | 0.000 | 1.830 | 1.835 | -3.665 | 4.495
| SR | EQUIPMENT | 1.289 | 1 | 1.289 | 1 | 1.289 | Mass | 1.289 |  |  |  |  | 0.000 | 0.000 | 1.289
| UR2 | STUB | 0.692 | 2 | 1.385 | 2 | 1.384 | Mass | 1.385 | 1.385 | 1.385 | 1.385 | 1.328 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.057
| UR6M | +6 MTR EXTN | 4.216 | 1 | 4.216 | 1 | 4.216 | Mass | 4.216 | 4.216 | 4.216 | 4.216 | 4.216 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 45.239 | 118 | 484.574 | 118 | 484.558 |  | 484.574 | 458.354 | 447.812 | 483.286 | 438.268 | 0.010 | -0.010 | 26.221 | 10.542 | -35.474 | 45.018
| Project Code : 932. |  | Client : KALPATARU PROJECTS INTERNATIONAL LTD-VT932 | [11 empty] | Order Dt. : 15/02/2026
| 2BPIH | EQUIPMENT | 0.290 | 3 | 0.871 | 3 | 0.869 | Mass | 0.871 |  |  |  |  | 0.000 | 0.000 | 0.871
| 2CT | EQUIPMENT | 0.201 | 3 | 0.603 | 3 | 0.602 | Mass | 0.603 |  |  |  |  | 0.000 | 0.000 | 0.603
| 2CVT | EQUIPMENT | 0.202 | 3 | 0.607 | 3 | 0.606 | Mass | 0.607 |  |  |  |  | 0.000 | 0.000 | 0.607
| 2ISO1 | EQUIPMENT | 0.416 | 3 | 1.249 | 3 | 1.248 | Mass | 1.249 |  |  |  |  | 0.000 | 0.000 | 1.249
| 2ISO2 | EQUIPMENT | 0.363 | 3 | 1.089 | 3 | 1.091 | Mass | 1.089 |  |  |  |  | 0.000 | 0.000 | 1.089
| 2ISO3 | EQUIPMENT | 0.414 | 3 | 1.241 | 3 | 1.243 | Mass | 1.241 |  |  |  |  | 0.000 | 0.000 | 1.241
| 2LA | EQUIPMENT | 0.168 | 3 | 0.505 | 3 | 0.503 | Mass | 0.505 |  |  |  |  | 0.000 | 0.000 | 0.505
| 2SA1 | BEAM | 2.309 | 1 | 2.309 | 1 | 2.300 | Mass | 2.309 |  |  |  |  | 0.000 | 0.000 | 2.309
| 2SA2 | BEAM | 2.614 | 1 | 2.614 | 1 | 2.610 | Mass | 2.614 |  |  |  |  | 0.000 | 0.000 | 2.614
| 2SA3 | BEAM | 1.962 | 1 | 1.962 | 1 | 1.962 | Mass | 1.962 |  |  |  |  | 0.000 | 0.000 | 1.962
| 2TA1 | COLUMN | 3.140 | 1 | 3.140 | 1 | 3.142 | Mass | 3.140 |  |  |  |  | 0.000 | 0.000 | 3.140
| 2TB1 | COLUMN | 6.790 | 1 | 6.790 | 1 | 6.794 | Mass | 6.790 |  |  |  |  | 0.000 | 0.000 | 6.790
|  | Sub Total | 18.869 | 26 | 22.980 | 26 | 22.970 |  | 22.978 |  |  |  |  | 0.000 | 0.000 | 22.978
| Project Code : 933 |  | Client : THE TATA POWER COMPANY LIMITED. -VT933 | [11 empty] | Order Dt. : 15/02/2026
| 2AF1 | S.S.T | 0.774 | 7 | 5.420 | 7 | 4.961 | Proto | 4.961 | 4.961 | 4.961 | 4.961 | 4.961 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2AF10M | +10M Body Extn | 4.580 | 1 | 4.580 | 1 | 4.579 | Proto | 4.580 | 0.455 | 0.217 |  |  | 0.000 | 0.000 | 4.125 | 0.238
| 2AF2 | STUB | 0.833 | 15 | 12.496 | 15 | 12.496 | Proto | 12.496 | 12.496 | 12.496 | 12.496 | 12.496 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2AF3 | NORMAL TOWER | 19.767 | 21 | 415.102 | 11 | 217.431 | Mass | 217.434 | 198.841 | 132.015 | 217.434 |  | 197.673 | 0.000 | 18.594 | 66.826 | -85.419 | 217.434
| 2AF5M | +5.0 Mtr. Extn. | 2.240 | 3 | 6.719 | 3 | 6.721 | Proto | 6.719 | 3.749 | 2.525 |  |  | 0.000 | 0.000 | 2.970 | 1.224
| 2DF1 | S.S.T | 1.313 | 5 | 6.567 | 5 | 6.566 | Mass | 6.567 | 6.567 | 6.567 | 6.567 | 6.567 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DF1A | S.S.T | 0.795 | 1 | 0.795 | 1 | 0.795 | Mass | 0.795 | 0.795 | 0.795 | 0.795 | 0.795 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DF2 | STUB | 1.924 | 16 | 30.788 | 16 | 30.788 | Mass | 30.788 | 30.788 | 30.788 | 30.788 | 30.788 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DF2A | STUB | 1.924 | 4 | 7.697 | 4 | 7.699 | Mass | 7.697 | 7.697 | 7.697 | 7.697 | 7.697 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 2DF3 | NORMAL TOWER | 45.062 | 27 | 1216.679 | 11 | 495.444 | Mass | 485.660 | 451.121 | 378.684 | 495.442 |  | 721.242 | 9.782 | 34.539 | 72.437 | -116.759 | 495.442
| 2DF-5 | NORMAL TOWER | 40.422 | 4 | 161.688 | 4 | 161.689 | Mass | 161.688 | 137.596 | 110.975 | 161.688 |  | 0.000 | 0.000 | 24.092 | 26.621 | -50.713 | 161.688
| 2DF5M | +5.0 Mtr. Extn. | 4.980 | 1 | 4.980 | 1 | 4.983 | Mass | 4.980 | 4.126 | 3.690 | 4.980 |  | 0.000 | 0.000 | 0.854 | 0.436 | -1.289 | 4.980
| IS | COLUMN | 0.018 | 1 | 0.018 | 1 | 0.018 | Mass | 0.018 | 0.018 |  |  |  | 0.000 | 0.000 | 0.000 | 0.018
|  | Sub Total | 124.633 | 106 | 1873.529 | 80 | 954.170 |  | 944.384 | 859.209 | 691.410 | 942.849 | 63.304 | 918.915 | 9.782 | 85.174 | 167.799 | -254.181 | 879.545
| Project Code : 934 |  | Client : SHYAM INDUS POWER SOLUTIONS PRIVATE LIMITED - VT934 | [11 empty] | Order Dt. : 15/02/2026
| 3DA2 | STUB | 0.131 | 14 | 1.840 | 14 | 1.840 | Proto | 1.840 | 1.840 | 1.840 | 1.840 | 1.840 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3DA3 | NORMAL TOWER | 1.623 | 14 | 22.721 | 14 | 22.716 | Proto | 22.721 | 9.488 | 3.774 |  |  | 0.000 | 0.000 | 13.232 | 5.714
| 3DA3M | +3 MTR EXTN | 0.343 | 7 | 2.399 | 7 | 2.398 | Proto | 2.399 |  |  |  |  | 0.000 | 0.000 | 2.399
| 3DA6M | +6 MTR EXTN | 0.688 | 4 | 2.752 | 4 | 2.753 | Proto | 2.752 | 0.024 |  |  |  | 0.000 | 0.000 | 2.727 | 0.024
| 3DA9M | +9 MTR EXTN | 1.062 | 3 | 3.186 | 3 | 3.183 | Proto | 2.718 | 0.019 |  |  |  | 0.000 | 0.468 | 2.700 | 0.019
| 3DB2 | STUB | 0.183 | 39 | 7.125 | 39 | 7.126 | Proto | 7.125 | 7.125 | 7.125 | 7.125 | 7.125 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3DB3 | NORMAL TOWER | 1.968 | 39 | 76.752 | 39 | 76.759 | Proto | 70.666 | 11.722 | 8.374 |  |  | 0.000 | 6.087 | 58.944 | 3.348
| 3DB3M | +3 MTR EXTN | 0.585 | 8 | 4.680 | 8 | 4.677 | Proto | 4.640 | 0.440 | 0.386 |  |  | 0.000 | 0.040 | 4.200 | 0.054
| 3DB6M | +6 MTR EXTN | 1.247 | 15 | 18.707 | 15 | 18.707 | Proto | 16.506 | 2.248 | 1.931 |  |  | 0.000 | 2.201 | 14.257 | 0.317
| 3DB9M | +9 MTR EXTN | 1.987 | 12 | 23.850 | 12 | 23.845 | Proto | 19.342 | 4.285 | 2.735 |  |  | 0.000 | 4.508 | 15.057 | 1.550
| 3DC2 | STUB | 0.223 | 12 | 2.679 | 12 | 2.679 | Proto | 2.679 | 2.679 | 2.679 | 2.679 | 2.456 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.223
| 3DC3 | NORMAL TOWER | 2.182 | 12 | 26.181 | 12 | 26.183 | Proto | 26.181 | 1.804 | 1.339 |  |  | 0.000 | 0.000 | 24.376 | 0.466
| 3DC3M | +3 MTR EXTN | 0.629 | 4 | 2.515 | 4 | 2.513 | Proto | 2.141 | 0.069 | 0.069 |  |  | 0.000 | 0.374 | 2.072 | 0.000
| 3DC6M | +6 MTR EXTN | 1.321 | 7 | 9.245 | 7 | 9.250 | Proto | 9.245 | 1.172 | 0.954 |  |  | 0.000 | 0.000 | 8.073 | 0.217
| 3DC9M | +6 MTR EXTN | 2.095 | 1 | 2.095 | 1 | 2.100 | Proto | 1.797 |  |  |  |  | 0.000 | 0.298 | 1.797
| 3DD2 | STUB | 0.334 | 14 | 4.679 | 14 | 4.680 | Proto | 4.679 | 4.679 | 4.679 | 4.679 | 1.671 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 3.008
| 3DD3 | NORMAL TOWER | 2.482 | 14 | 34.744 | 14 | 34.741 | Proto | 34.564 | 1.238 | 0.636 |  |  | 0.000 | 0.180 | 33.325 | 0.602
| 3DD3M | +3 MTR EXTN | 0.833 | 4 | 3.333 | 4 | 3.330 | Proto | 3.333 | 0.520 |  |  |  | 0.000 | 0.000 | 2.813 | 0.520
| 3DD6M | +6 MTR EXTN | 1.755 | 6 | 10.529 | 6 | 10.523 | Proto | 10.529 | 2.168 | 0.075 |  |  | 0.000 | 0.000 | 8.360 | 2.094
| 3DD9M | +9 MTR EXTN | 2.827 | 3 | 8.482 | 3 | 8.487 | Proto | 8.482 | 0.790 |  |  |  | 0.000 | 0.000 | 7.692 | 0.790
| DD | COLUMN | 0.036 | 1 | 0.036 | 1 | 0.036 | Mass | 0.036 |  |  |  |  | 0.000 | 0.000 | 0.036
|  | Sub Total | 24.535 | 233 | 268.530 | 233 | 268.526 |  | 254.372 | 52.311 | 36.595 | 16.324 | 13.092 | 0.000 | 14.157 | 202.062 | 15.715 | 0.000 | 3.231
| Project Code : 935 |  | Client : PRAKASH ELECTRICAL ENGINEERING CORPORATION. - VT935 | [11 empty] | Order Dt. : 15/02/2026
| 2BB1 | BEAM | 1.456 | 53 | 77.157 | 53 | 77.160 | Mass | 56.331 | 9.064 | 9.064 | 77.157 |  | 0.000 | 20.826 | 47.267 | 0.000 | -68.094 | 77.157
| 2BB2 | BEAM | 1.672 | 35 | 58.536 | 35 | 58.535 | Mass | 33.946 |  |  | 58.536 |  | 0.000 | 24.590 | 33.946 |  | -58.536 | 58.536
| 2BB3 | BEAM | 1.922 | 22 | 42.292 | 22 | 42.287 | Mass | 27.107 | 16.821 | 14.450 | 42.292 |  | 0.000 | 15.185 | 10.286 | 2.371 | -27.842 | 42.292
| 2TA2 | NORMAL TOWER | 4.575 | 30 | 137.238 | 30 | 137.240 | Mass | 123.825 | 51.820 | 41.028 | 137.238 |  | 0.000 | 13.413 | 72.006 | 10.792 | -96.210 | 137.238
| 2TA3 | NORMAL TOWER | 3.441 | 27 | 92.916 | 27 | 92.916 | Mass | 67.155 | 43.186 | 33.662 | 92.916 |  | 0.000 | 25.761 | 23.969 | 9.524 | -59.254 | 92.916
| 2TA3-P | NORMAL TOWER | 3.441 | 1 | 3.441 | 1 | 3.442 | Mass | 2.512 |  |  | 3.441 |  | 0.000 | 0.930 | 2.512 |  | -3.441 | 3.441
| 2TA4 | NORMAL TOWER | 6.332 | 13 | 82.319 | 13 | 82.317 | Mass | 67.428 | 15.866 | 15.866 | 82.319 |  | 0.000 | 14.891 | 51.562 | 0.000 | -66.453 | 82.319
| 2TA5 | NORMAL TOWER | 4.848 | 22 | 106.655 | 22 | 106.658 | Mass | 91.379 | 45.516 | 36.032 | 106.655 |  | 0.000 | 15.277 | 45.862 | 9.484 | -70.623 | 106.655
| 2TA5-P | NORMAL TOWER | 4.848 | 13 | 63.024 | 13 | 63.026 | Mass | 53.027 | 18.181 | 7.152 | 63.024 |  | 0.000 | 9.997 | 34.846 | 11.029 | -55.872 | 63.024
| 2TA6 | NORMAL TOWER | 8.654 | 17 | 147.111 | 10 | 86.542 | Mass | 69.629 | 12.431 | 8.433 | 86.536 |  | 60.572 | 16.907 | 57.198 | 3.998 | -78.103 | 86.536
| 2TP | PEAK | 0.115 | 102 | 11.763 | 102 | 11.762 | Mass | 10.874 | 2.384 | 1.788 | 11.763 |  | 0.000 | 0.889 | 8.489 | 0.596 | -9.975 | 11.763
| 4B1MS | BEAM | 4.186 | 35 | 146.509 | 35 | 146.499 | Mass | 120.874 | 48.159 | 41.647 | 146.509 |  | 0.000 | 25.635 | 72.715 | 6.512 | -104.862 | 146.509
| 4B3 | BEAM | 3.811 | 12 | 45.728 | 12 | 45.722 | Mass | 37.346 | 15.834 | 6.581 | 45.728 |  | 0.000 | 8.382 | 21.512 | 9.253 | -39.146 | 45.728
| 4T1 | NORMAL TOWER | 3.844 | 7 | 26.907 | 7 | 26.915 | Mass | 24.881 | 7.172 | 5.406 | 26.907 |  | 0.000 | 2.026 | 17.709 | 1.766 | -21.501 | 26.907
| 4T1-P | NORMAL TOWER | 3.844 | 10 | 38.439 | 10 | 38.440 | Mass | 31.195 | 10.690 | 6.768 | 38.439 |  | 0.000 | 7.244 | 20.505 | 3.921 | -31.671 | 38.439
| 4T3 | NORMAL TOWER | 5.867 | 2 | 11.734 | 2 | 11.732 | Mass | 7.083 |  |  | 11.734 |  | 0.000 | 4.651 | 7.083 |  | -11.734 | 11.734
| 4T4 | NORMAL TOWER | 6.588 | 2 | 13.176 | 2 | 13.174 | Mass | 10.409 | 0.069 |  | 13.176 |  | 0.000 | 2.767 | 10.340 | 0.069 | -13.176 | 13.176
| 4T5 | NORMAL TOWER | 8.554 | 28 | 239.507 | 10 | 85.541 | Mass | 68.601 | 6.651 | 5.829 | 85.538 |  | 153.967 | 16.937 | 61.950 | 0.822 | -79.709 | 85.538
| 4TP | PEAK | 0.301 | 39 | 11.741 | 21 | 6.323 | Mass | 4.606 | 2.693 | 1.039 | 6.322 |  | 5.419 | 1.716 | 1.913 | 1.654 | -5.283 | 6.322
| AA | BEAM | 0.991 | 12 | 11.894 | 12 | 11.893 | Mass | 7.305 |  |  | 11.894 |  | 0.000 | 4.589 | 7.305 |  | -11.894 | 11.894
| AB | BEAM | 0.880 | 15 | 13.200 | 15 | 13.201 | Mass | 10.417 |  |  | 13.200 |  | 0.000 | 2.783 | 10.417 |  | -13.200 | 13.200
| AC | BEAM | 0.807 | 2 | 1.614 | 2 | 1.614 | Mass | 0.776 |  |  | 1.614 |  | 0.000 | 0.838 | 0.776 |  | -1.614 | 1.614
| AF | COLUMN | 2.235 | 15 | 33.519 | 15 | 33.525 | Mass | 31.595 | 2.537 | 2.537 | 33.519 |  | 0.000 | 1.924 | 29.058 | 0.000 | -30.983 | 33.519
| AG | COLUMN | 1.956 | 11 | 21.520 | 11 | 21.513 | Mass | 19.973 | 5.544 | 3.550 | 21.520 |  | 0.000 | 1.547 | 14.429 | 1.994 | -17.970 | 21.520
| AH | COLUMN | 0.930 | 13 | 12.094 | 13 | 12.096 | Mass | 8.129 |  |  | 12.094 |  | 0.000 | 3.964 | 8.129 |  | -12.094 | 12.094
| AP | PEAK | 0.080 | 39 | 3.113 | 39 | 3.114 | Mass | 1.120 |  |  | 3.113 |  | 0.000 | 1.993 | 1.120 |  | -3.113 | 3.113
| FD | BEAM | 0.502 | 8 | 4.019 | 8 | 4.021 | Mass | 2.015 |  |  | 4.019 |  | 0.000 | 2.004 | 2.015 |  | -4.019 | 4.019
| FE | BEAM | 0.465 | 7 | 3.255 | 7 | 3.258 | Mass | 1.274 |  |  | 3.255 |  | 0.000 | 1.981 | 1.274 |  | -3.255 | 3.255
| FF | COLUMN | 1.176 | 6 | 7.054 | 6 | 7.056 | Mass | 4.563 |  |  | 7.054 |  | 0.000 | 2.491 | 4.563 |  | -7.054 | 7.054
| FG | COLUMN | 1.060 | 8 | 8.479 | 8 | 8.478 | Mass | 8.166 | 1.385 | 1.196 | 8.479 |  | 0.000 | 0.312 | 6.781 | 0.189 | -7.282 | 8.479
| FH | COLUMN | 0.540 | 10 | 5.396 | 10 | 5.394 | Mass | 2.406 |  |  | 5.396 |  | 0.000 | 2.991 | 2.406 |  | -5.396 | 5.396
| FP | PEAK | 0.069 | 24 | 1.666 | 24 | 1.665 | Mass | 1.573 |  |  | 1.666 |  | 0.000 | 0.092 | 1.573 |  | -1.666 | 1.666
|  | Sub Total | 89.991 | 640 | 1483.016 | 597 | 1263.059 |  | 1007.519 | 316.002 | 242.028 | 1263.055 |  | 219.958 | 255.536 | 691.517 | 73.974 | -1021.027 | 1263.055
| Project Code : 936 |  | Client : KSHEMA POWER INDIA PVT. LTD - VT936 | [11 empty] | Order Dt. : 18/03/2026
| 2B1 | BEAM | 1.526 | 6 | 9.159 | 6 | 9.163 | Mass | 9.159 |  |  |  |  | 0.000 | 0.000 | 9.159
| 2B2 | BEAM | 1.526 | 8 | 12.212 | 8 | 12.213 | Mass | 12.212 |  |  |  |  | 0.000 | 0.000 | 12.212
| 2B3 | BEAM | 1.526 | 2 | 3.053 | 2 | 3.052 | Mass | 3.053 |  |  |  |  | 0.000 | 0.000 | 3.053
| 2T1 | COLUMN | 1.921 | 4 | 7.685 | 4 | 7.695 | Mass | 7.685 |  |  |  |  | 0.000 | 0.000 | 7.685
| 2T2 | COLUMN | 2.471 | 2 | 4.942 | 2 | 4.946 | Mass | 4.942 |  |  |  |  | 0.000 | 0.000 | 4.942
| 2T3 | COLUMN | 2.630 | 2 | 5.260 | 2 | 5.263 | Mass | 5.260 |  |  |  |  | 0.000 | 0.000 | 5.260
| 2T4 | COLUMN | 2.982 | 1 | 2.982 | 1 | 2.989 | Mass | 2.982 |  |  |  |  | 0.000 | 0.000 | 2.982
| 2T5 | COLUMN | 2.377 | 5 | 11.886 | 5 | 11.883 | Mass | 11.886 |  |  |  |  | 0.000 | 0.000 | 11.886
| 2T6 | COLUMN | 2.718 | 2 | 5.436 | 2 | 5.440 | Mass | 5.436 |  |  |  |  | 0.000 | 0.000 | 5.436
| 2T7 | COLUMN | 2.639 | 3 | 7.918 | 3 | 7.924 | Mass | 7.918 |  |  |  |  | 0.000 | 0.000 | 7.918
|  | Sub Total | 22.318 | 35 | 70.533 | 35 | 70.568 |  | 70.533 |  |  |  |  | 0.000 | 0.000 | 70.533
| Project Code : 937 |  | Client : SHYAM INDUS POWER SOLUTIONS PRIVATE LIMITED - VT937 | [11 empty] | Order Dt. : 15/02/2026
| 4BPI | EQUIPMENT | 0.240 | 3 | 0.719 | 3 | 0.716 | Proto | [5 empty] | 0.000 | 0.719
| 4CT | EQUIPMENT | 0.195 | 3 | 0.584 | 3 | 0.583 | Proto | [5 empty] | 0.000 | 0.584
| 4ISO1 | EQUIPMENT | 1.608 | 2 | 3.215 | 2 | 3.211 | Proto | [5 empty] | 0.000 | 3.215
| 4LA | EQUIPMENT | 0.205 | 3 | 0.614 | 3 | 0.611 | Proto | [5 empty] | 0.000 | 0.614
| 7BA | BEAM | 2.020 | 2 | 4.040 |  |  | Mass
| 7BB | BEAM | 2.503 | 4 | 10.014 |  |  | Mass
| 7BC | BEAM | 5.174 | 2 | 10.347 |  |  | Mass
| 7BD | BEAM | 4.394 | 4 | 17.577 |  |  | Mass
| 7BE | BEAM | 6.428 | 3 | 19.283 |  |  | Mass
| 7BF | BEAM | 5.317 | 6 | 31.903 |  |  | Mass
| 7BGC | BEAM | 1.823 | 1 | 1.823 | 1 | 1.827 | Proto | [5 empty] | 0.000 | 1.823
| 7BGD | BEAM | 0.995 | 2 | 1.989 | 2 | 1.986 | Proto | [5 empty] | 0.000 | 1.989
| 7BPI | EQUIPMENT | 0.517 | 14 | 7.244 | 14 | 7.245 | Proto | [5 empty] | 0.000 | 7.244
| 7BTB | NORMAL TOWER | 9.188 | 2 | 18.377 | 2 | 18.381 | Proto | [5 empty] | 0.000 | 18.377
| 7CA | NORMAL TOWER | 8.935 | 4 | 35.741 |  |  | Mass
| 7CB | NORMAL TOWER | 24.737 | 4 | 98.947 |  |  | Mass
| 7CC | NORMAL TOWER | 29.437 | 4 | 117.748 |  |  | Mass
| 7CT | EQUIPMENT | 0.432 | 3 | 1.295 | 3 | 1.293 | Proto | [5 empty] | 0.000 | 1.295
| 7GWCB | PEAK | 0.686 | 4 | 2.743 |  |  | Mass
| 7GWCC | PEAK | 0.714 | 6 | 4.287 |  |  | Mass
| 7ISO1 | EQUIPMENT | 3.669 | 4 | 14.677 | 4 | 14.679 | Proto | [5 empty] | 0.000 | 14.677
| 7ISO2 | EQUIPMENT | 3.719 | 1 | 3.719 | 1 | 3.717 | Proto | [5 empty] | 0.000 | 3.719
| 7ISOW | EQUIPMENT | 3.669 | 5 | 18.347 | 5 | 18.346 | Proto | [5 empty] | 0.000 | 18.347
| 7LA | EQUIPMENT | 0.426 | 3 | 1.277 | 3 | 1.275 | Proto | [5 empty] | 0.000 | 1.277
| 7TBGW | PEAK | 0.300 | 2 | 0.599 | 2 | 0.599 | Proto | [5 empty] | 0.000 | 0.599
|  | Sub Total | 117.330 | 91 | 427.109 | 48 | 74.469 | [6 empty] | 0.000 | 74.481
| Project Code : 938 |  | Client : TOSHIBA TRANSMISSION & DISTRIBUTION SYSTEMS (INDIA) PVT LTD -VT938 | [11 empty] | Order Dt. : 18/03/2026
| 4BPI | EQUIPMENT | 0.438 | 10 | 4.376 | 10 | 4.377 | Proto | 4.187 |  |  |  |  | 0.000 | 0.189 | 4.187
| 4CVT | EQUIPMENT | 0.355 | 6 | 2.133 | 6 | 2.134 | Proto | 2.056 |  |  |  |  | 0.000 | 0.077 | 2.056
| 4G1 | BEAM | 4.026 | 4 | 16.104 | 4 | 16.104 | Proto | 1.756 |  |  |  |  | 0.000 | 14.348 | 1.756
| 4HBPI | EQUIPMENT | 0.511 | 6 | 3.066 | 6 | 3.064 | Proto | 2.939 |  |  |  |  | 0.000 | 0.127 | 2.939
| 4LA | EQUIPMENT | 0.375 | 12 | 4.504 | 12 | 4.505 | Proto | 4.243 |  |  |  |  | 0.000 | 0.261 | 4.243
| 4TB | COLUMN | 7.639 | 6 | 45.833 | 6 | 45.843 | Proto | 10.488 |  |  |  |  | 0.000 | 35.345 | 10.488
| 4WT | EQUIPMENT | 1.282 | 4 | 5.129 | 4 | 5.129 | Proto | 4.889 |  |  |  |  | 0.000 | 0.240 | 4.889
|  | Sub Total | 14.626 | 48 | 81.145 | 48 | 81.156 |  | 30.557 |  |  |  |  | 0.000 | 50.587 | 30.557
| Project Code : 939 |  | Client : FLOWMORE LIMITED - VT939 | [11 empty] | Order Dt. : 18/03/2026
| 2OA3 | NORMAL TOWER | 36.558 | 1 | 36.558 | 1 | 36.560 | Mass | 33.481 |  |  |  |  | 0.000 | 3.077 | 33.481
| 2OA3M | +3 MTR EXTN | 2.029 | 1 | 2.029 | 1 | 2.029 | Mass | 2.029 |  |  |  |  | 0.000 | 0.000 | 2.029
| 2OB3 | NORMAL TOWER | 84.133 | 1 | 84.133 | 1 | 84.135 | Mass | 77.481 | 5.749 | 3.711 |  |  | 0.000 | 6.652 | 71.732 | 2.038
| 2OB3M | +3 MTR EXTN | 0.005 | 1 | 0.005 | 1 | 0.005 | Mass | 0.005 |  |  |  |  | 0.000 | 0.000 | 0.005
| 2OB6M | +6 MTR EXTN | 11.372 | 1 | 11.372 | 1 | 11.372 | Mass | 10.689 | 2.661 | 1.177 |  |  | 0.000 | 0.683 | 8.028 | 1.484
| 2OC3 | NORMAL TOWER | 87.206 | 1 | 87.206 | 1 | 87.207 | Mass | 77.168 | 28.970 | 17.014 |  |  | 0.000 | 10.038 | 48.198 | 11.956
| 2OC3M | +3 MTR EXTN | 0.954 | 1 | 0.954 | 1 | 0.955 | Mass | 0.892 | 0.014 |  |  |  | 0.000 | 0.062 | 0.878 | 0.014
| 2UR3 | NORMAL TOWER | 28.941 | 1 | 28.941 | 1 | 28.944 | Mass | 25.754 | 4.238 | 2.654 |  |  | 0.000 | 3.188 | 21.516 | 1.584
| 2UR6M | +6 MTR EXTN | 17.285 | 1 | 17.285 | 1 | 17.289 | Mass | 6.690 | 0.423 |  |  |  | 0.000 | 10.595 | 6.267 | 0.423
|  | Sub Total | 268.483 | 9 | 268.483 | 9 | 268.496 |  | 234.188 | 42.056 | 24.557 |  |  | 0.000 | 34.294 | 192.133 | 17.499
| Project Code : 940 |  | Client : SHARVARI ELECTRICALS - VT940 | [11 empty] | Order Dt. : 19/03/2026
| 1DP2 | STUB | 0.125 | 19 | 2.376 | 19 | 2.376 | Mass | 2.376 | 2.376 | 2.376 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| 1DP2E | STUB | 0.134 | 26 | 3.486 | 26 | 3.486 | Mass | 3.486 | 3.486 | 3.486 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| 1DR2 | STUB | 0.232 | 11 | 2.548 | 11 | 2.547 | Mass | 2.548 | 2.548 | 2.548 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| 1DS2 | STUB | 0.303 | 15 | 4.550 | 15 | 4.550 | Mass | 4.550 | 4.550 | 4.550 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| 4DA2 | STUB | 0.359 | 18 | 6.454 | 18 | 6.455 | Mass | 6.454 | 6.454 | 6.454 | 6.454 | 6.454 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4DA3 | NORMAL TOWER | 10.468 | 18 | 188.420 | 18 | 188.424 | Mass | 23.606 |  |  |  |  | 0.000 | 164.815 | 23.606
| 4DA3M | +3 MTR EXTN | 1.422 | 2 | 2.844 | 2 | 2.844 | Mass | 0.370 |  |  |  |  | 0.000 | 2.474 | 0.370
| 4DC2 | STUB | 0.966 | 2 | 1.932 | 2 | 1.933 | Mass | 1.932 | 1.932 | 1.932 | 1.932 | 1.932 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4DC3 | NORMAL TOWER | 22.210 | 2 | 44.421 | 2 | 44.420 | Mass | 7.895 | 1.433 | 0.243 |  |  | 0.000 | 36.525 | 6.462 | 1.191
| 4DD15M | +15 MTR EXTN | 15.376 | 1 | 15.376 | 1 | 15.366 | Mass | 1.618 |  |  |  |  | 0.000 | 13.758 | 1.618
| 4DD2 | STUB | 0.966 | 8 | 7.730 | 8 | 7.729 | Mass | 7.730 | 7.730 | 7.730 | 7.730 | 7.730 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4DD2A | STUB | 0.966 | 5 | 4.831 | 5 | 4.832 | Mass | 4.831 | 4.831 | 4.831 | 4.831 | 4.831 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 4DD3 | NORMAL TOWER | 22.260 | 14 | 311.637 | 14 | 311.629 | Mass | 76.135 | 10.033 | 0.850 |  |  | 0.000 | 235.502 | 66.102 | 9.184
| 4DD6M | +6 MTR EXTN | 5.756 | 1 | 5.756 |  |  | Mass
| CMP | STUB | 0.376 | 1 | 0.376 | 1 | 0.376 | Mass | 0.376 | 0.376 | 0.376 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| CMR | STUB | 1.255 | 1 | 1.255 | 1 | 1.256 | Mass | 1.255 | 1.255 | 1.255 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| CMS | STUB | 1.655 | 8 | 13.240 | 8 | 13.241 | Mass | 13.240 | 12.875 | 12.875 |  |  | 0.000 | 0.000 | 0.365 | 0.000
|  | Sub Total | 84.829 | 152 | 617.232 | 151 | 611.464 |  | 158.402 | 59.880 | 49.505 | 20.948 | 20.948 | 0.000 | 453.074 | 98.523 | 10.374 | 0.000 | 0.000
| Project Code : 941 |  | Client : LC INFRA PROJECTS PRIVATE LIMITED - VT941 | [11 empty] | Order Dt. : 18/03/2026
| 1DP2 | STUB | 0.125 | 5 | 0.625 | 5 | 0.625 | Mass | 0.625 | 0.625 | 0.625 | 0.625 | 0.625 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DP2E | STUB | 0.134 | 29 | 3.888 | 29 | 3.887 | Mass | 3.888 | 3.888 | 3.888 | 3.888 | 3.888 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DP3 | NORMAL TOWER | 2.507 | 53 | 132.866 | 53 | 132.871 | Mass | 132.866 | 50.835 | 38.363 | 132.866 |  | 0.000 | 0.000 | 82.032 | 12.472 | -94.504 | 132.866
| 1DP3M | +3 MTR EXTN | 0.394 | 34 | 13.407 | 34 | 13.406 | Mass | 13.407 | 6.113 | 0.333 | 13.407 |  | 0.000 | 0.000 | 7.295 | 5.779 | -13.074 | 13.407
| 1DP6M | +6 MTR EXTN | 0.822 | 8 | 6.574 | 8 | 6.574 | Mass | 6.574 | 2.987 | 1.627 | 6.574 |  | 0.000 | 0.000 | 3.587 | 1.360 | -4.947 | 6.574
| 1DR2 | STUB | 0.232 | 12 | 2.779 | 12 | 2.780 | Mass | 2.779 | 2.779 | 2.779 | 2.779 | 2.779 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DR3 | NORMAL TOWER | 3.501 | 20 | 70.030 | 20 | 70.029 | Mass | 70.030 | 31.704 | 22.007 | 70.030 |  | 0.000 | 0.000 | 38.326 | 9.697 | -48.023 | 70.030
| 1DR3M | +3 MTR EXTN | 0.687 | 8 | 5.499 | 8 | 5.496 | Mass | 5.499 | 0.345 | 0.345 | 5.499 |  | 0.000 | 0.000 | 5.155 | 0.000 | -5.155 | 5.499
| 1DR6M | +6 MTR EXTN | 1.267 | 4 | 5.070 | 4 | 5.070 | Mass | 5.070 | 0.605 | 0.324 | 5.070 |  | 0.000 | 0.000 | 4.464 | 0.282 | -4.746 | 5.070
| 1DS2 | STUB | 0.303 | 13 | 3.943 | 13 | 3.943 | Mass | 3.943 | 3.943 | 3.943 | 3.943 | 3.943 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1DS3 | NORMAL TOWER | 4.602 | 24 | 110.459 | 24 | 110.458 | Mass | 109.750 | 38.589 | 16.923 | 110.459 |  | 0.000 | 0.709 | 71.161 | 21.667 | -93.537 | 110.459
| 1DS3M | +3 MTR EXTN | 1.243 | 6 | 7.460 | 6 | 7.463 | Mass | 7.460 | 0.662 |  | 7.460 |  | 0.000 | 0.000 | 6.798 | 0.662 | -7.460 | 7.460
| 1DS6M | +6 MTR EXTN | 2.047 | 1 | 2.047 | 1 | 2.049 | Mass | 2.047 | 0.069 |  | 2.047 |  | 0.000 | 0.000 | 1.978 | 0.069 | -2.047 | 2.047
| 1DS9M | +9 MTR EXTN | 3.641 | 2 | 7.282 | 2 | 7.285 | Mass | 7.282 | 0.350 |  | 7.282 |  | 0.000 | 0.000 | 6.932 | 0.350 | -7.282 | 7.282
| IS | COLUMN | 0.006 | 1 | 0.006 | 1 | 0.006 | Mass | 0.006 |  |  |  |  | 0.000 | 0.000 | 0.006
|  | Sub Total | 21.513 | 220 | 371.935 | 220 | 371.942 |  | 371.227 | 143.493 | 91.157 | 371.930 | 11.236 | 0.000 | 0.709 | 227.734 | 52.337 | -280.774 | 360.695
| Project Code : 942 |  | Client : THE TATA POWER COMPANY LIMITED. -VT942 | [11 empty] | Order Dt. : 30/03/2026
| 2AF3 | NORMAL TOWER | 19.767 | 10 | 197.668 | 10 | 197.673 | Mass | 183.469 | 57.456 | 24.403 |  |  | 0.000 | 14.199 | 126.013 | 33.052
| 2DF3 | NORMAL TOWER | 45.062 | 16 | 720.995 | 16 | 721.000 | Mass | 694.527 | 311.538 | 184.816 |  |  | 0.000 | 26.468 | 382.988 | 126.723
|  | Sub Total | 64.829 | 26 | 918.663 | 26 | 918.673 |  | 877.995 | 368.994 | 209.219 |  |  | 0.000 | 40.667 | 509.001 | 159.775
| Project Code : 944 |  | Client : THE TATA POWER COMPANY LIMITED. -VT944 | [11 empty] | Order Dt. : 31/03/2026
| 2DF | NORMAL TOWER | 1.497 | 5 | 7.486 |  |  | Mass
| 2DF10M | +10M Body Extn | 10.275 | 3 | 30.824 | 3 | 30.823 | Mass | 23.002 | 1.269 |  |  |  | 0.000 | 7.823 | 21.733 | 1.269
| 2DF15M | +15 MTR EXTN | 15.679 | 2 | 31.357 | 2 | 31.356 | Mass | 23.270 | 4.151 |  |  |  | 0.000 | 8.087 | 19.120 | 4.151
| 2DF2 | STUB | 1.924 | 15 | 28.864 | 15 | 28.864 | Mass | 28.864 | 28.825 | 26.553 |  |  | 0.000 | 0.000 | 0.039 | 2.271
| 2DF3 | NORMAL TOWER | 45.062 | 15 | 675.933 | 15 | 675.937 | Mass | 359.485 | 110.448 | 20.973 |  |  | 0.000 | 316.447 | 249.037 | 89.475
| 2DF5M | +5.0 Mtr. Extn. | 4.980 | 3 | 14.939 | 3 | 14.942 | Mass | 11.399 | 2.959 |  |  |  | 0.000 | 3.540 | 8.440 | 2.959
| 2DNEH2 | STUB | 0.557 | 4 | 2.229 | 4 | 2.230 | Mass | 2.229 | 0.117 |  |  |  | 0.000 | 0.000 | 2.113 | 0.117
| 2DNEH-5 | NORMAL TOWER | 8.435 | 4 | 33.739 | 4 | 33.739 | Mass | 10.151 |  |  |  |  | 0.000 | 23.588 | 10.151
|  | Sub Total | 88.409 | 51 | 825.371 | 46 | 817.891 |  | 458.401 | 147.768 | 47.526 |  |  | 0.000 | 359.485 | 310.632 | 100.242
| Project Code : 945. |  | Client : ORIANA POWER LIMITED - VT945 | [11 empty] | Order Dt. : 11/05/2026
| D30 | NORMAL TOWER | 3.499 | 1 | 3.499 | 1 | 3.495 | Proto | 3.499 |  |  |  |  | 0.000 | 0.000 | 3.499
| D302 | STUB | 0.350 | 1 | 0.350 | 1 | 0.349 | Proto | 0.350 | 0.300 | 0.300 |  |  | 0.000 | 0.000 | 0.050 | 0.000
| D30E | +4.5 MTR EXTN | 1.152 | 1 | 1.152 | 1 | 1.151 | Proto | 1.152 |  |  |  |  | 0.000 | 0.000 | 1.152
| D60 | NORMAL TOWER | 4.903 | 1 | 4.903 | 1 | 4.913 | Proto | 4.903 |  |  |  |  | 0.000 | 0.000 | 4.903
| D602 | STUB | 0.615 | 1 | 0.615 | 1 | 0.615 | Proto | 0.615 | 0.615 | 0.548 |  |  | 0.000 | 0.000 | 0.000 | 0.067
| D60E | +4.5 MTR EXTN | 1.500 | 1 | 1.500 | 1 | 1.498 | Proto | 1.500 |  |  |  |  | 0.000 | 0.000 | 1.500
| NB30 | NORMAL TOWER | 2.852 | 4 | 11.407 | 4 | 11.404 | Mass | 11.407 |  |  |  |  | 0.000 | 0.000 | 11.407
| NB302 | STUB | 0.248 | 4 | 0.992 | 4 | 0.993 | Mass | 0.992 | 0.992 | 0.853 |  |  | 0.000 | 0.000 | 0.000 | 0.140
| NB30E | +6 MTR EXTN | 1.409 | 2 | 2.818 | 2 | 2.820 | Mass | 2.818 |  |  |  |  | 0.000 | 0.000 | 2.818
| NB30EE | +9 MTR EXTN | 2.151 | 2 | 4.302 | 2 | 4.305 | Mass | 4.302 |  |  |  |  | 0.000 | 0.000 | 4.302
| NB60 | NORMAL TOWER | 3.853 | 1 | 3.853 | 1 | 3.848 | Mass | 3.853 |  |  |  |  | 0.000 | 0.000 | 3.853
| NB602 | STUB | 0.443 | 1 | 0.443 | 1 | 0.444 | Mass | 0.443 | 0.443 | 0.443 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| NB60E | +9 MTR EXTN | 2.995 | 1 | 2.995 | 1 | 2.989 | Mass | 2.995 |  |  |  |  | 0.000 | 0.000 | 2.995
|  | Sub Total | 25.970 | 21 | 38.829 | 21 | 38.824 |  | 38.829 | 2.350 | 2.144 |  |  | 0.000 | 0.000 | 36.479 | 0.207
| Project Code : 946 |  | Client : GUJARAT ENERGY TRANSMISSION CORPORATION LIMITED - VT946 | [11 empty] | Order Dt. : 18/04/2026
| -069-2NBA1 | S.S.T | 0.294 | 1 | 0.294 | 1 | 0.293 | Proto | 0.294 |  |  |  |  | 0.000 | 0.000 | 0.294
| -069-2NBA2 | STUB | 0.248 | 2 | 0.497 | 2 | 0.497 | Proto | 0.497 |  |  |  |  | 0.000 | 0.000 | 0.497
| -069-2NBA3 | NORMAL TOWER | 3.247 | 2 | 6.494 | 2 | 6.490 | Proto | 6.494 |  |  |  |  | 0.000 | 0.000 | 6.494
| -069-2NBA3M | +3 MTR EXTN | 0.476 | 2 | 0.952 | 2 | 0.951 | Proto | 0.952 |  |  |  |  | 0.000 | 0.000 | 0.952
| -069-2NBC1 | S.S.T | 0.452 | 1 | 0.452 | 1 | 0.451 | Proto | 0.452 | 0.211 |  |  |  | 0.000 | 0.000 | 0.241 | 0.211
| -069-2NBC2 | STUB | 0.369 | 3 | 1.106 | 3 | 1.106 | Proto | 1.106 |  |  |  |  | 0.000 | 0.000 | 1.106
| -069-2NBC3 | NORMAL TOWER | 5.023 | 3 | 15.070 | 3 | 15.067 | Proto | 15.070 |  |  |  |  | 0.000 | 0.000 | 15.070
| -069-2NBC3M | +3 MTR EXTN | 0.896 | 2 | 1.791 | 2 | 1.787 | Proto | 1.791 |  |  |  |  | 0.000 | 0.000 | 1.791
| -069-2NBC6M | +6 MTR EXTN | 1.838 | 2 | 3.676 | 2 | 3.672 | Proto | 3.676 |  |  |  |  | 0.000 | 0.000 | 3.676
| -069-2NBD1 | S.S.T | 0.536 | 1 | 0.536 | 1 | 0.538 | Proto | 0.536 | 0.233 |  |  |  | 0.000 | 0.000 | 0.303 | 0.233
| -069-2NBD2 | STUB | 0.497 | 6 | 2.982 | 6 | 2.983 | Proto | 0.200 |  |  |  |  | 0.000 | 2.783 | 0.200
| -069-2NBD3 | NORMAL TOWER | 6.301 | 6 | 37.806 | 6 | 37.810 | Proto | 37.806 |  |  |  |  | 0.000 | 0.000 | 37.806
| -069-2NBD3M | +3 MTR EXTN | 1.223 | 2 | 2.445 | 2 | 2.445 | Proto | 2.445 |  |  |  |  | 0.000 | 0.000 | 2.445
| -069-2NBD6M | +6 MTR EXTN | 2.549 | 1 | 2.549 | 1 | 2.549 | Proto | 2.549 |  |  |  |  | 0.000 | 0.000 | 2.549
| -069-2NBE1 | S.S.T | 0.561 | 1 | 0.561 | 1 | 0.561 | Proto | 0.561 |  |  |  |  | 0.000 | 0.000 | 0.561
| -069-2NBE2 | STUB | 0.575 | 2 | 1.150 | 2 | 1.151 | Proto | 1.150 | 1.066 | 0.800 |  |  | 0.000 | 0.000 | 0.084 | 0.267
| -069-2NBE3 | NORMAL TOWER | 8.171 | 2 | 16.342 | 2 | 16.343 | Proto | 16.342 |  |  |  |  | 0.000 | 0.000 | 16.342
| -069-2NBE3M | +3 MTR EXTN | 1.402 | 2 | 2.805 | 2 | 2.803 | Proto | 2.805 |  |  |  |  | 0.000 | 0.000 | 2.805
| -069-2NBE6M | +6 MTR EXTN | 2.884 | 2 | 5.768 | 2 | 5.765 | Proto | 5.768 |  |  |  |  | 0.000 | 0.000 | 5.768
|  | Sub Total | 37.542 | 43 | 103.276 | 43 | 103.262 |  | 100.493 | 1.510 | 0.800 |  |  | 0.000 | 2.783 | 98.983 | 0.711
| Project Code : 947 |  | Client : ODISHA POWER TRANSMISSION CORPORATION LTD -VT947 | [11 empty] | Order Dt. : 18/04/2026
| 1PB3 | NORMAL TOWER | 4.673 | 7 | 32.709 | 7 | 32.706 | Mass | 32.709 |  |  |  |  | 0.000 | 0.000 | 32.709
| 1PB6M | +6 MTR EXTN | 2.165 | 4 | 8.659 | 4 | 8.658 | Mass | 8.659 |  |  |  |  | 0.000 | 0.000 | 8.659
|  | Sub Total | 6.837 | 11 | 41.368 | 11 | 41.364 |  | 41.368 |  |  |  |  | 0.000 | 0.000 | 41.368
| Project Code : 948 |  | Client : SIKHA ELECTRIC STORES - VT948 | [11 empty] | Order Dt. : 22/05/2026
| 1DA | +0. MTR EXTN. | 0.701 | 20 | 14.020 | 20 | 14.018 | Mass | [5 empty] | 0.000 | 14.020
| 1DA3 | NORMAL TOWER | 2.224 | 20 | 44.477 | 20 | 44.479 | Mass | [5 empty] | 0.000 | 44.477
| 1DA3M | +3 MTR EXTN | 0.625 | 10 | 6.254 | 10 | 6.255 | Mass | [5 empty] | 0.000 | 6.254
| 1DA6M | +6 MTR EXTN | 1.012 | 2 | 2.023 | 2 | 2.017 | Mass | [5 empty] | 0.000 | 2.023
| 1DB | +0. MTR EXTN. | 0.862 | 20 | 17.246 | 20 | 17.247 | Mass | [5 empty] | 0.000 | 17.246
| 1DB3 | NORMAL TOWER | 3.839 | 20 | 76.780 | 20 | 76.782 | Mass | [5 empty] | 0.000 | 76.780
| 1DB3M | +3 MTR EXTN | 0.866 | 14 | 12.125 | 14 | 12.127 | Mass | [5 empty] | 0.000 | 12.125
| 1DB6M | +6 MTR EXTN | 1.507 | 3 | 4.520 | 3 | 4.519 | Mass | [5 empty] | 0.000 | 4.520
| 1DC | +0. MTR EXTN. | 0.937 | 9 | 8.437 | 9 | 8.436 | Mass | [5 empty] | 0.000 | 8.437
| 1DC3 | NORMAL TOWER | 3.899 | 9 | 35.092 | 9 | 35.090 | Mass | [5 empty] | 0.000 | 35.092
| 1DC3M | +3 MTR EXTN | 1.026 | 5 | 5.131 | 5 | 5.131 | Mass | [5 empty] | 0.000 | 5.131
| 1DC6M | +6 MTR EXTN | 1.828 | 5 | 9.141 | 5 | 9.142 | Mass | [5 empty] | 0.000 | 9.141
| 1DD | +0. MTR EXTN. | 1.083 | 15 | 16.240 | 15 | 16.238 | Mass | [5 empty] | 0.000 | 16.240
| 1DD3 | NORMAL TOWER | 5.077 | 3 | 15.232 | 3 | 15.245 | Mass | [5 empty] | 0.000 | 15.232
| 1DD3M | +3 MTR EXTN | 1.386 | 8 | 11.088 | 8 | 11.088 | Mass | [5 empty] | 0.000 | 11.088
| 1DD6M | +6 MTR EXTN | 2.118 | 1 | 2.118 | 1 | 2.118 | Mass | [5 empty] | 0.000 | 2.118
|  | Sub Total | 28.991 | 164 | 279.924 | 164 | 279.932 | [6 empty] | 0.000 | 279.925
| Project Code : 949 |  | Client : HARTEK POWER PRIVATE LIMITED - VT949 | [11 empty] | Order Dt. : 22/05/2026
| 2B1 | BEAM | 1.660 | 9 | 14.937 |  |  | Proto
| 2T1 | COLUMN | 1.906 | 6 | 11.436 |  |  | Proto
| 2T2 | COLUMN | 2.849 | 2 | 5.698 |  |  | Proto
| 2T4 | COLUMN | 2.914 | 6 | 17.486 |  |  | Proto
|  | Sub Total | 9.329 | 23 | 49.557
| Project Code : 951 |  | Client : MAHADEV PRESTRESSED PRODUCTS PRIVATE LIMITED - VT951 | [11 empty] | Order Dt. : 22/05/2026
| AA | BEAM | 0.991 | 18 | 17.841 |  |  | Mass
| AB | BEAM | 0.880 | 35 | 30.800 |  |  | Mass
| AC | BEAM | 0.807 | 4 | 3.228 |  |  | Mass
| AF | COLUMN | 2.235 | 20 | 44.693 |  |  | Mass
| AG | COLUMN | 1.956 | 16 | 31.302 |  |  | Mass
| AH | COLUMN | 0.930 | 10 | 9.303 |  |  | Mass
| AK | COLUMN | 5.118 | 3 | 15.354 |  |  | Mass
| AL | COLUMN | 3.906 | 3 | 11.717 |  |  | Mass
| AM | COLUMN | 3.866 | 6 | 23.194 |  |  | Mass
| AP | PEAK | 0.080 | 58 | 4.629 |  |  | Mass
| FD | BEAM | 0.502 | 12 | 6.029 |  |  | Mass
| FE | BEAM | 0.465 | 12 | 5.580 |  |  | Mass
| FF | COLUMN | 1.176 | 7 | 8.230 |  |  | Mass
| FG | COLUMN | 1.060 | 12 | 12.718 |  |  | Mass
| FH | COLUMN | 0.540 | 13 | 7.015 |  |  | Mass
| FP | PEAK | 0.069 | 32 | 2.221 |  |  | Mass
| HA | BEAM | 0.234 | 16 | 3.741 |  |  | Mass
| HG | COLUMN | 0.425 | 16 | 6.806 |  |  | Mass
| HH | COLUMN | 0.377 | 8 | 3.019 |  |  | Mass
| HP | PEAK | 0.036 | 24 | 0.868 |  |  | Mass
| LM | NORMAL TOWER | 1.252 | 9 | 11.266 |  |  | Mass
|  | Sub Total | 26.905 | 334 | 259.554
| Project Code : 952. |  | Client : SKY ENGINEERING AND CONTRACTORS - VT952 | [11 empty] | Order Dt. : 22/05/2026
| TB | MAST | 1.535 | 9 | 13.814 | 9 | 13.816 | Mass | 13.814 |  |  |  |  | 0.000 | 0.000 | 13.814
| TC | MAST | 1.211 | 4 | 4.843 | 4 | 4.845 | Mass | 4.843 |  |  |  |  | 0.000 | 0.000 | 4.843
|  | Sub Total | 2.746 | 13 | 18.657 | 13 | 18.661 |  | 18.657 |  |  |  |  | 0.000 | 0.000 | 18.657
| Project Code : 957 |  | Client : TEXMACO RAIL & ENGINERING LTD - VT957 | [11 empty] | Order Dt. : 14/06/2026
| AGT | COLUMN | 2.987 | 1 | 2.987 | 1 | 2.992 | Mass | 0.123 |  |  |  |  | 0.000 | 2.865 | 0.123
|  | Sub Total | 2.987 | 1 | 2.987 | 1 | 2.992 |  | 0.123 |  |  |  |  | 0.000 | 2.865 | 0.123
| Project Code : 958 |  | Client : GROMA INFRASTRUCTURE LIMITED - VT958 | [11 empty] | Order Dt. : 08/06/2026
| E02 | STUB | 0.225 | 39 | 8.780 | 20 | 4.503 | Mass | [5 empty] | 4.276 | 4.502
| E302 | STUB | 0.371 | 18 | 6.676 | 9 | 3.338 | Mass | [5 empty] | 3.338 | 3.338
| E602 | STUB | 0.554 | 38 | 21.066 | 19 | 10.533 | Mass | [5 empty] | 10.533 | 10.533
|  | Sub Total | 1.150 | 95 | 36.522 | 48 | 18.374 | [6 empty] | 18.147 | 18.374
| Project Code : 960 |  | Client : MEGHA ENGINEERING & INFRASTRUCTURES LTD - VT862 | [11 empty] | Order Dt. : 04/06/2026
| B02 | STUB | 0.269 | 3 | 0.808 |  |  | Pre
| B03 | NORMAL TOWER | 4.500 | 3 | 13.499 |  |  | Pre
| B03M | +3 MTR EXTN | 0.936 | 1 | 0.936 |  |  | Pre
| B06M | +6 MTR EXTN | 1.649 | 1 | 1.649 |  |  | Pre
| B302 | STUB | 0.440 | 2 | 0.880 |  |  | Pre
| B303 | NORMAL TOWER | 7.304 | 2 | 14.608 |  |  | Pre
| B6010M | +10M Body Extn | 7.993 | 3 | 23.979 |  |  | Pre
| B602 | STUB | 0.582 | 6 | 3.494 |  |  | Pre
| B603 | NORMAL TOWER | 8.963 | 6 | 53.776 |  |  | Pre
| B606M | +6 MTR EXTN | 4.804 | 1 | 4.804 |  |  | Pre
| E602 | STUB | 0.554 | 6 | 3.326 |  |  | Pre
| E603 | NORMAL TOWER | 6.234 | 6 | 37.403 |  |  | Pre
| E603M | +3 MTR EXTN | 1.314 | 2 | 2.627 |  |  | Pre
| E606M | +6 MTR EXTN | 2.813 | 4 | 11.251 |  |  | Pre
| MC602 | STUB | 1.464 | 1 | 1.464 |  |  | Pre
| MC603 | NORMAL TOWER | 22.792 | 1 | 22.792 |  |  | Pre
| NBB9010M | +10M Body Extn | 10.317 | 1 | 10.317 |  |  | Pre
| NBB902 | STUB | 3.871 | 2 | 7.741 |  |  | Pre
| NBB902A | STUB | 3.873 | 1 | 3.873 |  |  | Pre
| NBB902B | STUB | 3.281 | 1 | 3.281 |  |  | Pre
| NBB903 | NORMAL TOWER | 15.778 | 3 | 47.334 |  |  | Pre
| NBB904 | NORMAL TOWER | 11.767 | 1 | 11.767 |  |  | Pre
| NBB906M | +6 MTR EXTN | 6.449 | 2 | 12.897 |  |  | Pre
|  | Sub Total | 127.947 | 59 | 294.506
| Project Code : 962 |  | Client : BKS ENTERPRISES - VT962 | [11 empty] | Order Dt. : 24/06/2026
| 3DA2 | STUB | 0.131 | 20 | 2.629 |  |  | Pre
| 3DA3 | NORMAL TOWER | 1.623 | 20 | 32.458 |  |  | Pre
| 3DA3M | +3 MTR EXTN | 0.343 | 9 | 3.084 |  |  | Pre
| 3DA6M | +6 MTR EXTN | 0.688 | 11 | 7.567 |  |  | Pre
| 3DB2 | STUB | 0.183 | 6 | 1.096 |  |  | Pre
| 3DB3 | NORMAL TOWER | 1.968 | 6 | 11.808 |  |  | Pre
| 3DB3M | +3 MTR EXTN | 0.585 | 2 | 1.170 |  |  | Pre
| 3DB6M | +6 MTR EXTN | 1.247 | 4 | 4.988 |  |  | Pre
| 3DC2 | STUB | 0.223 | 4 | 0.893 |  |  | Pre
| 3DC3 | NORMAL TOWER | 2.182 | 4 | 8.727 |  |  | Pre
| 3DC3M | +3 MTR EXTN | 0.629 | 2 | 1.257 |  |  | Pre
| 3DC6M | +6 MTR EXTN | 1.321 | 2 | 2.641 |  |  | Pre
| 3DD2 | STUB | 0.334 | 10 | 3.342 |  |  | Pre
| 3DD3 | NORMAL TOWER | 2.482 | 10 | 24.817 |  |  | Pre
| 3DD3M | +3 MTR EXTN | 0.833 | 2 | 1.666 |  |  | Pre
| 3DD6M | +6 MTR EXTN | 1.755 | 7 | 12.283 |  |  | Pre
| 3DE3 | NORMAL TOWER | 3.068 | 2 | 6.136 |  |  | Pre
| 3DE3M | +3 MTR EXTN | 0.987 | 2 | 1.975 |  |  | Pre
|  | Sub Total | 20.582 | 123 | 128.537
| Project Code : 963 |  | Client : PRAKASH ELECTRICAL ENGINEERING CORPORATION. - VT963 | [11 empty] | Order Dt. : 21/06/2026
| 4QMA2 | STUB | 2.458 | 5 | 12.292 |  |  | Mass
| 4QMA3 | NORMAL TOWER | 57.035 | 5 | 285.174 |  |  | Pre
| 4QMA3M | +3 MTR EXTN | 9.801 | 1 | 9.801 |  |  | Pre
| 4QMD2 | STUB | 7.749 | 8 | 61.989 |  |  | Mass
| 4QMD3 | NORMAL TOWER | 166.900 | 8 | 1335.203 |  |  | Pre
|  | Sub Total | 243.943 | 27 | 1704.459
| Project Code : BPTCL |  | Client : BIHAR STATE POWER TRANSMISSION COMPANY LTD ( ARARIA) | [11 empty] | Order Dt. : 11/12/2017
| 2DD3 | NORMAL TOWER | 8.595 | 1 | 8.595 |  |  | Pre
|  | Sub Total | 8.595 | 1 | 8.595
| Project Code : GETCO |  | Client : GETCO (VT245) | [11 empty] | Order Dt. : 11/12/2017
| 2BA2 | BEAM | 0.561 | 1 | 0.561 |  |  | Pre
| 2BB1 | BEAM | 0.575 | 1 | 0.575 |  |  | Pre
| 2BB-1 | BEAM | 2.884 | 1 | 2.884 |  |  | Pre
| 2BB2 | BEAM | 8.171 | 1 | 8.171 |  |  | Pre
| 2BB-2 | BEAM | 1.402 | 1 | 1.402 |  |  | Pre
| DD3 | NORMAL TOWER | 1.402 | 1 | 1.402 |  |  | Pre
|  | Sub Total | 14.995 | 6 | 14.995
| Project Code : PG |  | Client : PGCIL (FARAKKA - DURGAPUR) VT292 | [11 empty] | Order Dt. : 11/12/2017
| 4G1 | BEAM | 3.968 | 1 | 3.968 |  |  | Mass
| 4P1 | COLUMN | 0.389 | 1 | 0.389 |  |  | Mass
| 4P2 | COLUMN | 0.413 | 1 | 0.413 |  |  | Mass
| 4TA | COLUMN | 3.017 | 1 | 3.017 |  |  | Mass
| 4TH | COLUMN | 7.998 | 1 | 7.998 |  |  | Mass
| 7BA | BEAM | 2.010 | 1 | 2.010 |  |  | Mass
| 7BB | BEAM | 2.499 | 1 | 2.499 |  |  | Mass
| 7BC | BEAM | 5.160 | 1 | 5.160 |  |  | Mass
| 7BD | BEAM | 4.354 | 1 | 4.354 |  |  | Mass
| 7BE | BEAM | 6.418 | 1 | 6.418 |  |  | Mass
| 7BF | BEAM | 5.285 | 1 | 5.285 |  |  | Mass
| 7CA | COLUMN | 8.917 | 1 | 8.917 |  |  | Mass
| 7CB | COLUMN | 24.706 | 1 | 24.706 |  |  | Mass
| 7CC | COLUMN | 29.425 | 1 | 29.425 |  |  | Mass
| 7GWCB | COLUMN | 0.681 | 1 | 0.681 |  |  | Mass
| 7GWCC | COLUMN | 0.711 | 1 | 0.711 |  |  | Mass
| B1 | BEAM | 1.627 | 1 | 1.627 |  |  | Pre
| LM | COLUMN | 13.011 | 1 | 13.011 |  |  | Mass
|  | Sub Total | 120.589 | 18 | 120.589
| Project Code : RAILWAY BATCH 10 |  | Client : VIJAY TRANSMISSION PVT LTD (RAILWAY) | [11 empty] | Order Dt. : 15/05/2022
| 0076-1 | S.P.S | 0.125 | 10 | 1.248 | 10 | 1.249 | Mass | 1.248 | 1.248 | 1.248 | 1.248 | 1.248 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 0076-2 | S.P.S | 0.007 | 20 | 0.131 | 20 | 0.132 | Mass | 0.131 | 0.131 | 0.131 | 0.131 | 0.131 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 0076-3 | S.P.S | 0.002 | 20 | 0.038 | 20 | 0.038 | Mass | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 0076-4 | S.P.S | 0.015 | 20 | 0.309 | 20 | 0.309 | Mass | 0.309 | 0.309 | 0.309 | 0.309 | 0.309 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3051 | S.P.S | 0.033 | 88 | 2.898 | 88 | 2.898 | Mass | 2.898 | 2.898 | 2.898 | 2.898 | 2.898 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3076-1 | S.P.S | 0.001 | 270 | 0.279 | 270 | 0.279 | Mass | 0.279 | 0.279 | 0.279 | 0.279 | 0.279 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3076-2 | S.P.S | 0.001 | 610 | 0.769 | 610 | 0.769 | Mass | 0.769 | 0.769 | 0.769 | 0.769 | 0.769 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3076-3 | S.P.S | 0.001 | 20 | 0.030 |  |  | Mass
| 3076-4 | S.P.S | 0.002 | 44 | 0.074 | 44 | 0.074 | Mass | 0.074 | 0.074 | 0.074 | 0.074 | 0.074 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3121 | S.P.S | 0.021 | 230 | 4.830 |  |  | Mass
| 3122 | S.P.S | 0.002 | 460 | 1.118 | 280 | 0.680 | Mass | 0.680 | 0.680 | 0.680 | 0.680 | 0.680 | 0.437 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3131-1 | S.P.S | 0.004 | 40 | 0.167 | 40 | 0.167 | Mass | 0.167 | 0.167 | 0.167 | 0.167 | 0.167 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3131-2 | S.P.S | 0.005 | 10 | 0.046 |  |  | Mass
| 3241 | S.P.S | 0.009 | 106 | 1.002 | 106 | 1.002 | Mass | 1.002 | 1.002 | 1.002 | 1.002 | 1.002 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3242 | S.P.S | 0.011 | 80 | 0.897 | 80 | 0.897 | Mass | 0.897 | 0.897 | 0.897 | 0.897 | 0.897 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3243 | S.P.S | 0.007 | 25 | 0.179 |  |  | Mass
| 5062-4 | S.P.S | 0.005 | 44 | 0.200 |  |  | Mass
| 5513-01 | S.P.S | 0.005 | 12 | 0.063 | 12 | 0.063 | Mass | 0.063 | 0.063 | 0.063 | 0.063 | 0.063 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 5513-02 | S.P.S | 0.007 | 6 | 0.045 | 6 | 0.045 | Mass | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 5513-03 | S.P.S | 0.024 | 6 | 0.144 | 6 | 0.144 | Mass | 0.144 | 0.144 | 0.144 | 0.144 | 0.144 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 5513-03A | S.P.S | 0.024 | 18 | 0.432 | 18 | 0.431 | Mass | 0.432 | 0.432 | 0.432 | 0.432 | 0.432 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 5513-04 | S.P.S | 0.001 | 12 | 0.016 | 12 | 0.016 | Mass | 0.016 | 0.016 | 0.016 | 0.016 | 0.016 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 5513-05 | S.P.S | 0.001 | 12 | 0.015 | 12 | 0.015 | Mass | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 5513-06 | S.P.S | 0.001 | 15 | 0.017 |  |  | Mass
| 5513-08 | S.P.S | 0.002 | 12 | 0.029 |  |  | Mass
| 5513-09 | S.P.S | 0.003 | 3 | 0.009 | 3 | 0.009 | Mass | 0.009 | 0.009 | 0.009 | 0.009 | 0.009 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 9031-3 | S.P.S | 0.001 | 50 | 0.058 | 50 | 0.058 | Mass | 0.058 | 0.058 | 0.058 | 0.058 | 0.058 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 9032-3 | S.P.S | 0.003 | 30 | 0.078 | 30 | 0.078 | Mass | 0.078 | 0.078 | 0.078 | 0.078 | 0.078 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 9032-6 | S.P.S | 0.001 | 30 | 0.035 | 30 | 0.035 | Mass | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 9036 | S.P.S | 0.020 | 10 | 0.196 | 10 | 0.196 | Mass | 0.196 | 0.196 | 0.196 | 0.196 | 0.196 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 9037 | S.P.S | 0.006 | 10 | 0.055 | 10 | 0.055 | Mass | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 9039 | S.P.S | 0.010 | 10 | 0.104 | 10 | 0.104 | Mass | 0.104 | 0.104 | 0.104 | 0.104 | 0.104 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 9039A | S.P.S | 0.010 | 10 | 0.104 | 10 | 0.104 | Mass | 0.104 | 0.104 | 0.104 | 0.104 | 0.104 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| B150 | MAST | 0.370 | 634 | 234.383 | 634 | 234.384 | Mass | 234.383 | 234.383 | 234.383 | 234.383 | 234.383 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| B175 | MAST | 0.423 | 250 | 105.723 | 250 | 105.723 | Mass | 105.723 | 105.723 | 105.723 | 105.723 | 105.723 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| B200 | MAST | 0.474 | 70 | 33.193 | 70 | 33.194 | Mass | 33.193 | 33.193 | 33.193 | 33.193 | 33.193 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| BFB - 8x6 (9.50 | RSJ | 0.494 | 7 | 3.458 | 7 | 3.458 | Mass | 3.458 | 3.458 | 3.458 | 3.458 | 3.458 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| DM 4.35 | S.P.S | 0.223 | 20 | 4.457 | 20 | 4.457 | Mass | 4.457 | 4.457 | 4.457 | 4.457 | 4.457 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| DMA4.35 | MAST | 0.226 | 43 | 9.730 | 43 | 9.730 | Mass | 9.730 | 9.730 | 9.730 | 9.730 | 9.730 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| DMA-6 | S.P.S | 0.006 | 43 | 0.241 | 43 | 0.241 | Mass | 0.241 | 0.241 | 0.241 | 0.241 | 0.241 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| P 9061 | S.P.S | 0.009 | 3 | 0.026 | 3 | 0.026 | Mass | 0.026 | 0.026 | 0.026 | 0.026 | 0.026 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| P 9062 | S.P.S | 0.012 | 6 | 0.073 | 6 | 0.073 | Mass | 0.073 | 0.073 | 0.073 | 0.073 | 0.073 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| P 9063 | S.P.S | 0.007 | 6 | 0.045 | 6 | 0.045 | Mass | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| S-1 | MAST | 0.593 | 8 | 4.742 | 8 | 4.742 | Mass | 4.742 | 4.742 | 4.742 | 4.742 | 4.742 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| S6 | MAST | 0.645 | 2 | 1.290 | 2 | 1.290 | Mass | 1.290 | 1.290 | 1.290 | 1.290 | 1.290 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| S8 | MAST | 1.347 | 1 | 1.347 | 1 | 1.348 | Mass | 1.347 | 1.347 | 1.347 | 1.347 | 1.347 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| TTB 10 MTRTTB 1 | MAST | 0.571 | 1 | 0.571 | 1 | 0.571 | Mass | 0.571 | 0.571 | 0.571 | 0.571 | 0.571 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| TTB8 | MAST | 0.383 | 9 | 3.445 | 9 | 3.445 | Mass | 3.445 | 3.445 | 3.445 | 3.445 | 3.445 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| TTK 3 & 4 | PORTAL | 0.109 | 2 | 0.219 | 2 | 0.218 | Mass | 0.219 | 0.219 | 0.219 | 0.219 | 0.219 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| TTK1 & 2 | MAST | 0.094 | 13 | 1.220 | 13 | 1.220 | Mass | 1.220 | 1.220 | 1.220 | 1.220 | 1.220 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| TTU | MAST | 0.811 | 6 | 4.865 | 6 | 4.866 | Mass | 4.865 | 4.865 | 4.865 | 4.865 | 4.865 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| TTU- | MAST | 0.734 | 3 | 2.202 | 3 | 2.202 | Mass | 2.202 |  |  |  |  | 0.000 | 0.000 | 2.202
| TTU-300 | MAST | 0.977 | 2 | 1.954 | 2 | 1.953 | Mass | 1.954 | 1.954 | 1.954 | 1.954 | 1.954 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 8.879 | 3472 | 428.799 | 2936 | 423.033 |  | 423.030 | 420.829 | 420.829 | 420.829 | 420.829 | 0.437 | 0.000 | 2.202 | 0.000 | 0.000 | 0.000
| Project Code : RAILWAY BATCH 11 |  | Client : VIJAY TRANSMISSION PVT LTD (RAILWAY) | [11 empty] | Order Dt. : 26/07/2022
| 0076-2A | S.P.S | 0.008 | 70 | 0.552 | 70 | 0.551 | Mass | 0.552 | 0.552 | 0.552 | 0.552 | 0.552 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 0076-4 | S.P.S | 0.015 | 85 | 1.314 | 85 | 1.314 | Mass | 1.314 | 1.314 | 1.314 | 1.314 | 1.314 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3051 | S.P.S | 0.033 | 88 | 2.898 | 88 | 2.898 | Mass | 2.898 | 2.898 | 2.898 | 2.898 | 2.898 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 3076-1 | S.P.S | 0.001 | 200 | 0.207 | 200 | 0.207 | Mass | 0.207 | 0.207 | 0.207 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| 3111 | S.P.S | 0.061 | 10 | 0.609 | 10 | 0.609 | Mass | 0.609 | 0.609 | 0.609 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| 3121 | S.P.S | 0.021 | 40 | 0.840 | 40 | 0.840 | Mass | 0.840 | 0.840 | 0.840 | 0.840 | 0.630 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.210
| 3122 | S.P.S | 0.002 | 80 | 0.194 | 80 | 0.194 | Mass | 0.194 | 0.194 | 0.194 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| 3131-1 | S.P.S | 0.004 | 420 | 1.756 | 420 | 1.756 | Mass | 1.756 | 1.756 | 1.756 | 1.756 | 1.756 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 8054-2 | S.P.S | 0.003 | 50 | 0.165 | 50 | 0.165 | Mass | 0.165 | 0.165 | 0.165 | 0.165 | 0.165 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| B150 | MAST | 0.370 | 179 | 66.175 | 179 | 66.174 | Mass | 66.175 | 66.175 | 66.175 | 66.175 | 66.175 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| B175 | MAST | 0.423 | 30 | 12.687 | 30 | 12.687 | Mass | 12.687 | 12.687 | 12.687 | 12.687 | 12.687 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| B200 | MAST | 0.474 | 45 | 21.339 | 45 | 21.339 | Mass | 21.339 | 21.339 | 21.339 | 21.339 | 21.339 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| DA1 | PORTAL | 0.125 | 30 | 3.745 | 30 | 3.745 | Mass | 3.745 | 3.745 | 3.745 | 3.745 | 3.745 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| DA1A | PORTAL | 0.168 | 10 | 1.681 | 10 | 1.681 | Mass | 1.681 | 1.681 | 1.681 | 1.681 | 1.681 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| DA2 | PORTAL | 0.089 | 3 | 0.266 | 3 | 0.266 | Mass | 0.266 | 0.266 | 0.266 | 0.266 | 0.266 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| DM4.35 | S.P.S | 0.226 | 8 | 1.810 | 8 | 1.811 | Mass | 1.810 | 1.810 | 1.810 | 1.810 | 1.810 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| OB1 | PORTAL | 0.118 | 4 | 0.473 | 4 | 0.473 | Mass | 0.473 | 0.473 | 0.473 | 0.473 | 0.473 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| OB3 | PORTAL | 0.185 | 1 | 0.185 | 1 | 0.185 | Mass | 0.185 | 0.185 | 0.185 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| OB4 | PORTAL | 0.264 | 4 | 1.054 | 4 | 1.054 | Mass | 1.054 | 1.054 | 1.054 | 1.054 | 1.054 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| OB6 | PORTAL | 0.344 | 2 | 0.688 | 2 | 0.688 | Mass | 0.688 | 0.688 | 0.688 | 0.684 | 0.344 | 0.000 | 0.000 | 0.000 | 0.000 | 0.004 | 0.340
| OC | PORTAL | 0.009 | 78 | 0.719 | 78 | 0.719 | Mass | 0.719 | 0.719 | 0.719 | 0.719 | 0.719 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| OE1 | PORTAL | 0.551 | 12 | 6.612 | 12 | 6.613 | Mass | 6.612 | 6.612 | 6.612 | 6.612 | 6.612 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| OE2 | PORTAL | 0.576 | 11 | 6.339 | 11 | 6.338 | Mass | 6.339 | 6.339 | 6.339 | 6.339 | 6.339 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| OK | PORTAL | 0.022 | 22 | 0.480 | 22 | 0.481 | Mass | 0.480 | 0.480 | 0.480 | 0.480 | 0.480 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| OU | PORTAL | 0.587 | 22 | 12.906 | 22 | 12.906 | Mass | 12.906 | 12.906 | 12.906 | 12.906 | 12.906 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| RB7.5 | PORTAL | 0.433 | 1 | 0.433 | 1 | 0.433 | Mass | 0.433 | 0.433 | 0.433 | 0.433 | 0.433 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| RE1 | PORTAL | 0.636 | 3 | 1.907 | 1 | 0.638 | Mass | 0.636 | 0.636 | 0.636 | 0.636 |  | 1.271 | 0.000 | 0.000 | 0.000 | 0.000 | 0.636
| RE2 | PORTAL | 0.662 | 4 | 2.648 | 3 | 1.986 | Mass | 1.986 | 1.986 | 1.986 | 1.986 |  | 0.663 | 0.000 | 0.000 | 0.000 | 0.000 | 1.986
| RU | PORTAL | 0.629 | 6 | 3.776 | 6 | 3.776 | Mass | 3.776 | 3.776 | 3.776 | 3.776 | 3.776 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| TTB5.5 | MAST | 0.281 | 1 | 0.281 | 1 | 0.281 | Mass | 0.281 | 0.281 | 0.281 | 0.281 | 0.281 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| TTK1&2 | MAST | 0.094 | 1 | 0.094 | 1 | 0.094 | Mass | 0.094 | 0.094 | 0.094 | 0.094 | 0.094 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| TTU | MAST | 0.811 | 1 | 0.811 | 1 | 0.811 | Mass | 0.811 | 0.811 | 0.811 | 0.811 | 0.811 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 8.225 | 1521 | 155.644 | 1518 | 153.713 |  | 153.711 | 153.711 | 153.711 | 152.512 | 149.340 | 1.934 | 0.000 | 0.000 | 0.000 | 0.004 | 3.172
| Project Code : VR067 |  | Client : SOUTHERN RAILWAY TAMILNADU-VR067 | [11 empty] | Order Dt. : 26/11/2022
| B200 | MAST | 0.474 | 105 | 49.790 | 105 | 49.790 | Mass | 49.790 | 49.790 | 49.790 | 49.790 | 49.790 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| B225 | MAST | 0.570 | 40 | 22.799 | 40 | 22.800 | Mass | 22.799 | 22.799 | 22.799 | 22.799 | 22.799 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 1.044 | 145 | 72.589 | 145 | 72.590 |  | 72.589 | 72.589 | 72.589 | 72.589 | 72.589 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : VR068 |  | Client : ALSTOM TRANSPORT INDIA LIMITED - VR068 | [11 empty] | Order Dt. : 20/12/2022
| 1620-001 | S.P.S | 0.026 | 33 | 0.850 | 33 | 0.851 | Mass | 0.850 | 0.850 | 0.850 | 0.850 | 0.850 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1621-016 | S.P.S | 0.053 | 9 | 0.476 | 9 | 0.477 | Mass | 0.476 | 0.476 | 0.476 | 0.476 | 0.476 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1621-017 | S.P.S | 0.055 | 70 | 3.824 | 70 | 3.824 | Mass | 3.824 | 3.824 | 3.824 | 3.824 | 3.824 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1621-18 | S.P.S | 0.066 | 2 | 0.131 | 2 | 0.132 | Mass | 0.131 | 0.131 | 0.131 | 0.131 | 0.131 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-08 | S.P.S | 0.056 | 2 | 0.112 | 2 | 0.113 | Mass | 0.112 | 0.112 | 0.112 | 0.112 | 0.112 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-09 | S.P.S | 0.069 | 1 | 0.069 | 1 | 0.069 | Mass | 0.069 | 0.069 | 0.069 | 0.069 | 0.069 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-10 | S.P.S | 0.047 | 2 | 0.093 | 2 | 0.094 | Mass | 0.093 | 0.093 | 0.093 | 0.093 | 0.093 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-11 | S.P.S | 0.073 | 2 | 0.146 | 2 | 0.147 | Mass | 0.146 | 0.146 | 0.146 | 0.146 | 0.146 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-12 | S.P.S | 0.076 | 2 | 0.151 | 2 | 0.152 | Mass | 0.151 | 0.151 | 0.151 | 0.151 | 0.151 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-13 | S.P.S | 0.067 | 4 | 0.268 | 4 | 0.268 | Mass | 0.268 | 0.268 | 0.268 | 0.268 | 0.268 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-14 | S.P.S | 0.066 | 1 | 0.066 | 1 | 0.066 | Mass | 0.066 | 0.066 | 0.066 | 0.066 | 0.066 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-15 | S.P.S | 0.067 | 1 | 0.067 | 1 | 0.067 | Mass | 0.067 | 0.067 | 0.067 | 0.067 | 0.067 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-16 | S.P.S | 0.032 | 4 | 0.129 | 4 | 0.129 | Mass | 0.129 | 0.129 | 0.129 | 0.129 | 0.129 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-17 | S.P.S | 0.048 | 2 | 0.095 | 2 | 0.096 | Mass | 0.095 | 0.095 | 0.095 | 0.095 | 0.095 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-18 | S.P.S | 0.064 | 2 | 0.129 | 2 | 0.130 | Mass | 0.129 | 0.129 | 0.129 | 0.129 | 0.129 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-19 | S.P.S | 0.031 | 4 | 0.126 | 4 | 0.126 | Mass | 0.126 | 0.126 | 0.126 | 0.126 | 0.126 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-20 | S.P.S | 0.064 | 2 | 0.127 | 2 | 0.128 | Mass | 0.127 | 0.127 | 0.127 | 0.127 | 0.127 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-21 | S.P.S | 0.030 | 4 | 0.119 | 4 | 0.119 | Mass | 0.119 | 0.119 | 0.119 | 0.119 | 0.119 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-22 | S.P.S | 0.043 | 2 | 0.087 | 2 | 0.087 | Mass | 0.087 | 0.087 | 0.087 | 0.087 | 0.087 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-23 | S.P.S | 0.051 | 1 | 0.051 | 1 | 0.051 | Mass | 0.051 | 0.051 | 0.051 | 0.051 | 0.051 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-24 | S.P.S | 0.059 | 2 | 0.119 | 2 | 0.119 | Mass | 0.119 | 0.119 | 0.119 | 0.119 | 0.119 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-25 | S.P.S | 0.055 | 1 | 0.055 | 1 | 0.055 | Mass | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-26 | S.P.S | 0.025 | 3 | 0.076 | 3 | 0.076 | Mass | 0.076 | 0.076 | 0.076 | 0.076 | 0.076 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-27 | S.P.S | 0.037 | 2 | 0.075 | 2 | 0.075 | Mass | 0.075 | 0.075 | 0.075 | 0.075 | 0.075 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-28 | S.P.S | 0.045 | 2 | 0.090 | 2 | 0.090 | Mass | 0.090 | 0.090 | 0.090 | 0.090 | 0.090 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-29 | S.P.S | 0.053 | 2 | 0.105 | 2 | 0.106 | Mass | 0.105 | 0.105 | 0.105 | 0.105 | 0.105 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-30 | S.P.S | 0.025 | 12 | 0.305 | 12 | 0.306 | Mass | 0.305 | 0.305 | 0.305 | 0.305 | 0.305 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-31 | S.P.S | 0.047 | 2 | 0.093 | 2 | 0.094 | Mass | 0.093 | 0.093 | 0.093 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| 1622-32 | S.P.S | 0.055 | 2 | 0.110 | 2 | 0.111 | Mass | 0.110 | 0.110 | 0.110 | 0.110 | 0.110 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-33 | S.P.S | 0.051 | 3 | 0.153 | 3 | 0.152 | Mass | 0.153 | 0.153 | 0.153 | 0.153 | 0.153 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-34 | S.P.S | 0.029 | 1 | 0.029 | 1 | 0.029 | Mass | 0.029 | 0.029 | 0.029 | 0.029 | 0.029 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-36 | S.P.S | 0.046 | 2 | 0.092 | 2 | 0.092 | Mass | 0.092 | 0.092 | 0.092 | 0.092 | 0.092 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-37 | S.P.S | 0.028 | 6 | 0.168 | 6 | 0.168 | Mass | 0.168 | 0.168 | 0.168 | 0.168 | 0.168 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-38 | S.P.S | 0.029 | 3 | 0.086 | 3 | 0.086 | Mass | 0.086 | 0.086 | 0.086 | 0.086 | 0.086 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-55 | S.P.S | 0.036 | 1 | 0.036 | 1 | 0.036 | Mass | 0.036 | 0.036 | 0.036 | 0.036 | 0.036 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-57 | S.P.S | 0.036 | 1 | 0.036 | 1 | 0.035 | Mass | 0.036 | 0.036 | 0.036 | 0.036 | 0.036 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-58 | S.P.S | 0.031 | 10 | 0.305 | 10 | 0.307 | Mass | 0.305 | 0.305 | 0.305 | 0.305 | 0.305 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-59 | S.P.S | 0.037 | 1 | 0.037 | 1 | 0.037 | Mass | 0.037 | 0.037 | 0.037 | 0.037 | 0.037 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-60 | S.P.S | 0.032 | 2 | 0.064 | 2 | 0.065 | Mass | 0.064 | 0.064 | 0.064 | 0.064 | 0.064 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-61 | S.P.S | 0.066 | 2 | 0.132 | 2 | 0.133 | Mass | 0.132 | 0.132 | 0.132 | 0.132 | 0.132 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-71 | S.P.S | 0.040 | 2 | 0.080 | 2 | 0.080 | Mass | 0.080 | 0.080 | 0.080 | 0.080 | 0.080 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 1.945 | 212 | 9.362 | 212 | 9.378 |  | 9.363 | 9.363 | 9.363 | 9.270 | 9.270 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : VR069 |  | Client : ALSTOM TRANSPORT INDIA LIMITED - VR069 | [11 empty] | Order Dt. : 25/03/2023
| 1618-001 | S.P.S | 0.024 | 60 | 1.462 | 60 | 1.462 | Mass | 1.462 | 1.462 | 1.462 | 1.462 | 1.462 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1620-002 | S.P.S | 0.027 | 150 | 4.118 | 150 | 4.119 | Mass | 4.118 | 4.118 | 4.118 | 4.118 | 4.118 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1621-016 | S.P.S | 0.053 | 50 | 2.646 | 50 | 2.646 | Mass | 2.646 | 2.646 | 2.646 | 2.646 | 2.646 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1621-02 | S.P.S | 0.029 | 6 | 0.175 | 6 | 0.174 | Mass | 0.175 | 0.175 | 0.175 | 0.175 | 0.175 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-40 | S.P.S | 0.042 | 2 | 0.085 | 2 | 0.085 | Mass | 0.085 | 0.085 | 0.085 | 0.085 | 0.085 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-41 | S.P.S | 0.045 | 4 | 0.179 | 4 | 0.179 | Mass | 0.179 | 0.179 | 0.179 | 0.179 | 0.179 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-42 | S.P.S | 0.047 | 4 | 0.189 | 4 | 0.189 | Mass | 0.189 | 0.189 | 0.189 | 0.189 | 0.189 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-43 | S.P.S | 0.048 | 4 | 0.193 | 4 | 0.193 | Mass | 0.193 | 0.193 | 0.193 | 0.193 | 0.193 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-44 | S.P.S | 0.050 | 4 | 0.199 | 4 | 0.200 | Mass | 0.199 | 0.199 | 0.199 | 0.199 | 0.199 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-45 | S.P.S | 0.052 | 4 | 0.209 | 4 | 0.210 | Mass | 0.209 | 0.209 | 0.209 | 0.209 | 0.209 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-46 | S.P.S | 0.055 | 4 | 0.219 | 4 | 0.220 | Mass | 0.219 | 0.219 | 0.219 | 0.219 | 0.219 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-47 | S.P.S | 0.056 | 4 | 0.223 | 4 | 0.223 | Mass | 0.223 | 0.223 | 0.223 | 0.223 | 0.223 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-48 | S.P.S | 0.056 | 4 | 0.226 | 4 | 0.226 | Mass | 0.226 | 0.226 | 0.226 | 0.226 | 0.226 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-49 | S.P.S | 0.056 | 4 | 0.223 | 4 | 0.223 | Mass | 0.223 | 0.223 | 0.223 | 0.223 | 0.223 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-50 | S.P.S | 0.052 | 4 | 0.206 | 4 | 0.206 | Mass | 0.206 | 0.206 | 0.206 | 0.206 | 0.206 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-51 | S.P.S | 0.050 | 4 | 0.199 | 4 | 0.199 | Mass | 0.199 | 0.199 | 0.199 | 0.199 | 0.199 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-52 | S.P.S | 0.048 | 4 | 0.193 | 4 | 0.193 | Mass | 0.193 | 0.193 | 0.193 | 0.193 | 0.193 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-53 | S.P.S | 0.052 | 1 | 0.052 | 1 | 0.052 | Mass | 0.052 | 0.052 | 0.052 | 0.052 | 0.052 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-54 | S.P.S | 0.026 | 30 | 0.794 | 30 | 0.794 | Mass | 0.794 | 0.794 | 0.794 | 0.794 | 0.794 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-56 | S.P.S | 0.054 | 4 | 0.217 | 4 | 0.217 | Mass | 0.217 | 0.217 | 0.217 | 0.217 | 0.217 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 0.923 | 351 | 12.007 | 351 | 12.010 |  | 12.007 | 12.007 | 12.007 | 12.007 | 12.007 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : VR070 |  | Client : SREELAKSHMI CONSTRUCTIONS -VR070 | [11 empty] | Order Dt. : 31/03/2023
| 3241 | S.P.S | 0.009 | 1 | 0.009 |  |  | Pre
| 3242 | S.P.S | 0.011 | 1 | 0.011 |  |  | Pre
| 9201-3 | S.P.S | 0.125 | 5 | 0.624 |  |  | Pre
| 9201-4 | S.P.S | 0.015 | 10 | 0.155 |  |  | Pre
| 9201-5 | S.P.S | 0.007 | 10 | 0.067 |  |  | Pre
| B150 | MAST | 0.370 | 1 | 0.370 |  |  | Pre
| B175 | MAST | 0.423 | 1 | 0.423 |  |  | Pre
| DA1 | PORTAL | 0.161 | 2 | 0.322 |  |  | Pre
| DMA | S.P.S | 0.006 | 2 | 0.011 |  |  | Pre
| TTB1 | MAST | 0.281 | 5 | 1.407 |  |  | Pre
| TTK1&2 | MAST | 0.094 | 5 | 0.469 |  |  | Pre
| TTU | MAST | 0.811 | 5 | 4.054 |  |  | Pre
|  | Sub Total | 2.313 | 48 | 7.922
| Project Code : VR073 |  | Client : SARDAR ENGINEERS & ASSOCIATES (VR073) | [11 empty] | Order Dt. : 29/06/2023
| 3050 | S.P.S | 0.033 | 20 | 0.659 |  |  | Mass
| 3076-1 | S.P.S | 0.001 | 20 | 0.021 |  |  | Mass
| 3076-2 | S.P.S | 0.001 | 36 | 0.045 |  |  | Mass
| 3121 | S.P.S | 0.021 | 8 | 0.168 |  |  | Mass
| 3122 | S.P.S | 0.002 | 16 | 0.039 |  |  | Mass
| 3131-1 | S.P.S | 0.004 | 75 | 0.314 |  |  | Mass
| 3131-2 | S.P.S | 0.005 | 10 | 0.046 |  |  | Mass
| 3241 | S.P.S | 0.009 | 16 | 0.151 |  |  | Mass
| 3242 | S.P.S | 0.011 | 16 | 0.179 |  |  | Mass
| 3243 | S.P.S | 0.007 | 16 | 0.114 |  |  | Mass
| 9031-3 | S.P.S | 0.001 | 5 | 0.006 |  |  | Mass
| 9032-6 | S.P.S | 0.001 | 3 | 0.003 |  |  | Mass
| 9034-3 | S.P.S | 0.004 | 1 | 0.004 |  |  | Mass
| 9036 | S.P.S | 0.020 | 1 | 0.020 |  |  | Pre
| 9037 | S.P.S | 0.006 | 1 | 0.006 |  |  | Mass
| 9039 | S.P.S | 0.010 | 1 | 0.010 |  |  | Mass
| 9039A | S.P.S | 0.010 | 1 | 0.010 |  |  | Mass
| B150 | MAST | 0.370 | 5 | 1.848 |  |  | Mass
| B175 | MAST | 0.423 | 4 | 1.692 |  |  | Mass
| B200 | MAST | 0.474 | 9 | 4.268 |  |  | Mass
| DMA | S.P.S | 0.006 | 6 | 0.034 |  |  | Mass
| T150 | MAST | 0.362 | 2 | 0.724 |  |  | Mass
|  | Sub Total | 1.781 | 272 | 10.361
| Project Code : VR074 |  | Client : SOUTHERN RAILWAY TAMILNADU-VR074 | [11 empty] | Order Dt. : 29/06/2023
|  |  |  | 92 | 33.299 | 92 | 33.299 | Mass | 33.299 | 33.299 | 33.299 | 33.299 | 33.299 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 0.362 | 92 | 33.299 | 92 | 33.299 |  | 33.299 | 33.299 | 33.299 | 33.299 | 33.299 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : VR075. |  | Client : SUNCITY URJA PRIVATE LIMITED VR075 | [11 empty] | Order Dt. : 29/08/2023
| DS0 | S.P.S | 0.151 | 77 | 11.657 | 77 | 11.657 | Mass | 11.657 | 11.657 | 11.657 | 11.657 | 11.657 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| DT | S.P.S | 0.225 | 16 | 3.603 | 16 | 3.602 | Mass | 3.603 | 3.603 | 3.603 | 3.603 | 3.603 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| DT0 | S.P.S | 0.771 | 19 | 14.642 | 19 | 14.642 | Mass | 14.642 | 14.642 | 14.642 | 14.642 | 14.642 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| IS | COLUMN | 0.011 | 1 | 0.011 | 1 | 0.010 | Mass | 0.011 | 0.011 | 0.011 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 1.158 | 113 | 29.913 | 113 | 29.911 |  | 29.913 | 29.913 | 29.913 | 29.902 | 29.902 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : VR077 |  | Client : TELEGENCE POWERCOMM PVT.LTD.-VR077 | [11 empty] | Order Dt. : 12/07/2023
| RF | EQUIPMENT | 4.160 | 1 | 4.160 | 1 | 4.159 | Proto | 4.160 | 4.160 | 4.160 | 4.160 | 4.160 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 4.160 | 1 | 4.160 | 1 | 4.159 |  | 4.160 | 4.160 | 4.160 | 4.160 | 4.160 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : VR078 |  | Client : SIDDHARTHA ENGINEERING LIMITED - VR078 | [11 empty] | Order Dt. : 04/10/2023
| 11D | S.P.S | 7.175 | 1 | 7.175 | 1 | 7.175 | Mass | 7.175 | 7.175 | 7.175 | 7.175 | 7.175 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 11S | S.P.S | 3.106 | 1 | 3.106 | 1 | 3.106 | Mass | 3.106 | 3.106 | 3.106 | 1.964 | 1.964 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 13D | S.P.S | 19.601 | 1 | 19.601 | 1 | 19.601 | Mass | 19.601 | 19.601 | 19.601 | 19.601 | 19.601 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 13S | S.P.S | 11.961 | 1 | 11.961 | 1 | 11.962 | Mass | 11.961 | 11.961 | 11.961 | 10.436 | 10.436 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 41.842 | 4 | 41.843 | 4 | 41.844 |  | 41.842 | 41.842 | 41.842 | 39.175 | 39.175 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : VR081 |  | Client : TP CENTRAL ODISHA DISTRIBUTION LIMITED (VR081) | [11 empty] | Order Dt. : 26/12/2023
| CA1 | S.P.S | 0.011 | 4341 | 48.854 | 4341 | 48.854 | Mass | 48.854 | 48.854 | 48.854 | 48.854 | 48.854 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| CA2 | S.P.S | 0.022 | 3112 | 69.030 | 3112 | 69.030 | Mass | 69.030 | 69.030 | 69.030 | 69.030 | 69.030 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 0.033 | 7453 | 117.884 | 7453 | 117.884 |  | 117.884 | 117.884 | 117.884 | 117.884 | 117.884 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : VR082. |  | Client : SIDDHARTHA ENGINEERING LIMITED - VR082 | [11 empty] | Order Dt. : 30/12/2023
| - | S.P.S | 0.001 | 200 | 0.229 | 200 | 0.229 | Mass | 0.229 | 0.229 | 0.229 | 0.229 | 0.229 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| -- | S.P.S | 0.010 | 200 | 1.952 | 200 | 1.952 | Mass | 1.952 | 1.952 | 1.952 | 1.952 | 1.952 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| --- | S.P.S | 0.001 | 700 | 0.803 | 700 | 0.803 | Mass | 0.803 | 0.803 | 0.803 | 0.803 | 0.803 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| ---- | S.P.S | 0.021 | 700 | 14.417 | 700 | 14.416 | Mass | 14.417 | 14.417 | 14.417 | 14.417 | 14.417 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 0.033 | 1800 | 17.401 | 1800 | 17.400 |  | 17.401 | 17.401 | 17.401 | 17.401 | 17.401 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : VR087 |  | Client : SIDDHARTHA ENGINEERING LIMITED - VR087 | [11 empty] | Order Dt. : 02/06/2024
| 01 | S.P.S | 13.776 | 1 | 13.776 | 1 | 13.776 | Mass | 13.776 | 13.776 | 13.776 | 13.776 | 13.776 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 02 | S.P.S | 50.570 | 1 | 50.570 | 1 | 50.569 | Mass | 50.570 | 50.570 | 50.570 | 50.570 | 50.570 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 03 | S.P.S | 10.697 | 1 | 10.697 | 1 | 10.697 | Mass | 10.697 | 10.697 | 10.697 | 10.697 | 10.697 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 04 | S.P.S | 11.705 | 1 | 11.705 | 1 | 11.706 | Mass | 11.705 | 11.617 | 11.617 | 11.705 | 11.705 | 0.000 | 0.000 | 0.088 | 0.000 | -0.088 | 0.000
| 05 | S.P.S | 15.045 | 1 | 15.045 | 1 | 15.046 | Mass | 15.045 | 15.045 | 15.045 | 15.045 | 15.045 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 06 | S.P.S | 1.695 | 1 | 1.695 | 1 | 1.695 | Mass | 1.695 | 1.695 | 1.695 | 1.695 | 1.695 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 07 | S.P.S | 1.773 | 1 | 1.773 | 1 | 1.773 | Mass | 1.773 | 1.773 | 1.773 | 1.773 | 1.773 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| SC | NORMAL TOWER | 0.041 | 1 | 0.041 | 1 | 0.040 | Mass | 0.041 | 0.041 | 0.041 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 105.302 | 8 | 105.302 | 8 | 105.302 |  | 105.302 | 105.214 | 105.214 | 105.261 | 105.261 | 0.000 | 0.000 | 0.088 | 0.000 | -0.088 | 0.000
| Project Code : VR088. |  | Client : ALSTOM TRANSPORT INDIA LIMITED - VR088 | [11 empty] | Order Dt. : 02/09/2024
| 1613-001 | S.P.S | 0.024 | 263 | 6.409 | 237 | 5.775 | Mass | 5.775 | 5.775 | 5.775 | 5.775 | 5.775 | 0.634 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1618-001 | S.P.S | 0.024 | 237 | 5.775 |  |  | Mass
| 1620-001 | S.P.S | 0.026 | 24 | 0.618 | 2 | 0.052 | Mass | 0.052 | 0.052 | 0.052 | 0.052 | 0.052 | 0.567 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1620-002 | S.P.S | 0.027 | 49 | 1.345 | 21 | 0.577 | Mass | 0.577 | 0.577 | 0.577 | 0.577 | 0.577 | 0.768 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1620-05 | S.P.S | 0.034 | 86 | 2.945 | 86 | 2.945 | Mass | 2.945 | 2.945 | 2.945 | 2.945 | 2.945 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1621-015 | S.P.S | 0.051 | 4 | 0.205 |  |  | Mass
| 1621-016 | S.P.S | 0.053 | 5 | 0.265 | 5 | 0.265 | Mass | 0.265 | 0.265 | 0.265 | 0.265 | 0.265 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1621-017 | S.P.S | 0.055 | 7 | 0.382 | 1 | 0.054 | Mass | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.327 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1621-02 | S.P.S | 0.029 | 88 | 2.565 | 88 | 2.566 | Mass | 2.565 | 2.565 | 2.565 | 2.565 | 2.565 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-007 | S.P.S | 0.041 | 29 | 1.183 | 29 | 1.184 | Mass | 1.183 | 1.183 | 1.183 | 1.183 | 1.183 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-19 | S.P.S | 0.031 | 4 | 0.126 | 4 | 0.126 | Mass | 0.126 | 0.126 | 0.126 | 0.126 | 0.126 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-30 | S.P.S | 0.025 | 2 | 0.051 | 1 | 0.025 | Mass | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-31 | S.P.S | 0.047 | 2 | 0.093 | 2 | 0.094 | Mass | 0.093 | 0.093 | 0.093 | 0.093 | 0.093 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-39 | S.P.S | 0.029 | 3 | 0.086 | 2 | 0.058 | Mass | 0.058 | 0.058 | 0.058 | 0.058 | 0.058 | 0.029 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-54 | S.P.S | 0.026 | 1 | 0.026 | 1 | 0.026 | Mass | 0.026 | 0.026 | 0.026 | 0.026 | 0.026 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-64 | S.P.S | 0.042 | 3 | 0.125 |  |  | Mass
| 1622-66 | S.P.S | 0.032 | 2 | 0.065 |  |  | Mass
| 1622-72 | S.P.S | 0.039 | 7 | 0.275 | 7 | 0.275 | Mass | 0.275 | 0.275 | 0.275 | 0.275 | 0.275 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-73 | S.P.S | 0.037 | 1 | 0.037 | 1 | 0.036 | Mass | 0.037 | 0.037 | 0.037 | 0.037 | 0.037 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-74 | S.P.S | 0.041 | 3 | 0.123 | 3 | 0.122 | Mass | 0.123 | 0.123 | 0.123 | 0.123 | 0.123 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| 1622-75 | S.P.S | 0.028 | 1 | 0.028 |  |  | Mass
| 1622-76 | S.P.S | 0.027 | 1 | 0.027 |  |  | Mass
| 1622-77 | S.P.S | 0.027 | 1 | 0.027 |  |  | Mass
| 1622-78 | S.P.S | 0.027 | 1 | 0.027 |  |  | Mass
| 1622-79 | S.P.S | 0.050 | 1 | 0.050 |  |  | Mass
| 1622-80 | S.P.S | 0.024 | 2 | 0.047 |  |  | Mass
| 1622-81 | S.P.S | 0.024 | 2 | 0.048 |  |  | Mass
| CP | S.P.S | 0.110 | 2 | 0.220 | 2 | 0.220 | Mass | 0.220 | 0.220 | 0.220 | 0.220 | 0.220 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| RA1 | S.P.S | 0.350 | 1 | 0.350 | 1 | 0.349 | Mass | 0.350 | 0.350 | 0.350 | 0.350 | 0.350 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| RA2 | S.P.S | 0.248 | 1 | 0.248 | 1 | 0.248 | Mass | 0.248 | 0.248 | 0.248 | 0.248 | 0.248 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 1.629 | 833 | 23.771 | 494 | 14.997 |  | 14.997 | 14.997 | 14.997 | 14.997 | 14.997 | 2.350 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : VR089 |  | Client : SIDDHARTHA ENGINEERING LIMITED - VR089 | [11 empty] | Order Dt. : 17/11/2024
| B/PHASE-IV-A | S.P.S | 0.201 | 13 | 2.610 | 13 | 2.610 | Mass | 2.610 | 2.610 | 2.610 | 2.610 | 2.610 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| B/PHASE-IV-B | S.P.S | 0.025 | 13 | 0.322 | 13 | 0.322 | Mass | 0.322 | 0.322 | 0.322 | 0.322 | 0.322 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| B/PHASE-IV-C | S.P.S | 0.061 | 13 | 0.795 | 13 | 0.795 | Mass | 0.795 | 0.795 | 0.795 | 0.795 | 0.795 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| B/PHASE-IV-D | S.P.S | 0.154 | 13 | 2.005 | 13 | 2.005 | Mass | 2.005 | 2.005 | 2.005 | 2.005 | 2.005 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| B/PHASE-IV-E | S.P.S | 0.300 | 13 | 3.898 | 13 | 3.898 | Mass | 3.898 | 3.898 | 3.898 | 3.898 | 3.898 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| B/PHASE-IV-F | S.P.S | 0.089 | 13 | 1.160 | 13 | 1.160 | Mass | 1.160 | 1.160 | 1.160 | 1.160 | 1.160 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| B/PHASE-IV-G | S.P.S | 0.013 | 13 | 0.167 | 13 | 0.167 | Mass | 0.167 | 0.167 | 0.167 | 0.167 | 0.167 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| B/PHASE-IV-H | S.P.S | 0.006 | 13 | 0.078 | 13 | 0.078 | Mass | 0.078 | 0.078 | 0.078 | 0.078 | 0.078 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| SC | NORMAL TOWER | 0.046 | 1 | 0.046 | 1 | 0.046 | Mass | 0.046 | 0.046 | 0.046 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 0.895 | 105 | 11.081 | 105 | 11.081 |  | 11.082 | 11.082 | 11.082 | 11.036 | 11.036 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : VR091 |  | Client : GODREJ & BOYCE MANUFACTURING COMPANY LIMITED - VR091 | [11 empty] | Order Dt. : 03/12/2024
| CTS-1 | S.P.S | 0.002 | 515 | 0.782 | 515 | 0.782 | Mass | 0.782 | 0.782 | 0.782 | 0.618 | 0.619 | 0.125 | 0.000 | 0.000 | 0.000 | 0.164 | -0.002
| CTS-2 | S.P.S | 0.003 | 4141 | 11.578 | 4141 | 11.578 | Mass | 11.578 | 11.578 | 11.578 | 10.995 | 9.881 | 1.862 | 0.000 | 0.000 | 0.000 | 0.584 | 1.113
| CTS-3 | S.P.S | 0.005 | 6265 | 31.068 | 6265 | 31.069 | Mass | 31.068 | 31.068 | 31.068 | 30.724 | 29.888 | 4.997 | 0.000 | 0.000 | 0.000 | 0.344 | 0.836
| CTS-4 | S.P.S | 0.007 | 696 | 4.602 | 696 | 4.602 | Mass | 4.602 | 4.602 | 4.602 | 4.600 | 4.602 | 0.734 | 0.000 | 0.000 | 0.000 | 0.002 | -0.002
| CTS-5 | S.P.S | 0.008 | 1006 | 8.315 | 1006 | 8.315 | Proto | 8.315 | 8.315 | 8.315 | 8.315 | 8.315 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 0.024 | 12623 | 56.345 | 12623 | 56.346 |  | 56.345 | 56.345 | 56.345 | 55.251 | 53.305 | 7.718 | 0.000 | 0.000 | 0.000 | 1.094 | 1.946
| Project Code : VS-100 |  | Client : CREDA VS-100 | [11 empty] | Order Dt. : 23/07/2023
| SS... | COLUMN | 0.114 | 1 | 0.114 |  |  | Mass
|  | Sub Total | 0.114 | 1 | 0.114
| Project Code : VS-102 |  | Client : CREDA VS-102 | [11 empty] | Order Dt. : 07/08/2023
| S2 | EQUIPMENT | 0.273 | 1000 | 273.352 | 1000 | 273.352 | Mass | 273.352 | 273.352 | 273.352 | 273.352 | 273.279 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.073
|  | Sub Total | 0.273 | 1000 | 273.352 | 1000 | 273.352 |  | 273.352 | 273.352 | 273.352 | 273.352 | 273.279 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.073
| Project Code : VS-112 |  | Client : A POLE-VS-02 | [11 empty] | Order Dt. : 29/08/2023
| A14 | EQUIPMENT | 0.441 | 1000 | 440.721 |  |  | Mass
|  | Sub Total | 0.441 | 1000 | 440.721
| Project Code : VS-124 |  | Client : TP CENTRAL ODISHA DISTRIBUTION LIMITED (VS-124) | [11 empty] | Order Dt. : 26/10/2023
| H14 | NORMAL TOWER | 0.738 | 161 | 118.797 | 161 | 118.798 | Mass | 118.797 | 118.797 | 118.797 | 118.797 | 116.989 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.808
|  | Sub Total | 0.738 | 161 | 118.797 | 161 | 118.798 |  | 118.797 | 118.797 | 118.797 | 118.797 | 116.989 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 1.808
| Project Code : VS-153 |  | Client : BAJEL PROJECTS LIMITED (VS-153 ) | [11 empty] | Order Dt. : 15/05/2024
| H13DP | MAST | 0.723 | 8 | 5.783 | 8 | 5.783 | Mass | 5.783 | 5.783 | 5.783 |  |  | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 0.723 | 8 | 5.783 | 8 | 5.783 |  | 5.783 | 5.783 | 5.783 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : VS-157 |  | Client : SIDDHARTHA ENGINEERING LIMITED - VR087 | [11 empty] | Order Dt. : 19/06/2024
| H13M | MAST | 0.700 | 52 | 36.384 | 52 | 36.385 | Mass | 36.384 | 36.384 | 36.384 | 36.384 | 36.384 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 0.700 | 52 | 36.384 | 52 | 36.385 |  | 36.384 | 36.384 | 36.384 | 36.384 | 36.384 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : VS-170 |  | Client : HANSCOM K. INC. - VS-170 | [11 empty] | Order Dt. : 24/08/2024
| HELIX | S.P.S | 0.089 | 130 | 11.507 | 130 | 11.507 | Mass | 11.507 | 11.507 | 11.507 | 11.507 | 11.507 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 0.089 | 130 | 11.507 | 130 | 11.507 |  | 11.507 | 11.507 | 11.507 | 11.507 | 11.507 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : VS-181 |  | Client : S K MOHAPATRA (VS-181) | [11 empty] | Order Dt. : 05/12/2024
| H13 | MAST | 0.723 | 4 | 2.892 | 4 | 2.891 | Mass | 2.892 | 2.892 | 2.892 | 2.892 | 2.892 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 0.723 | 4 | 2.892 | 4 | 2.891 |  | 2.892 | 2.892 | 2.892 | 2.892 | 2.892 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : VS-183. |  | Client : SWITCHSOL SYSTEMS & SERVICES (OPC) PVT LTD - VS-183 | [11 empty] | Order Dt. : 19/12/2024
| VS-183 | EQUIPMENT | 0.181 | 37 | 6.684 | 37 | 6.684 | Mass | 6.684 | 6.684 | 6.684 | 6.684 | 6.684 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 0.181 | 37 | 6.684 | 37 | 6.684 |  | 6.684 | 6.684 | 6.684 | 6.684 | 6.684 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : VS-189 |  | Client : VINDHYA TELELINKS LTD (VS- 189) | [11 empty] | Order Dt. : 14/01/2025
| A11 | EQUIPMENT | 0.267 | 500 | 133.691 | 500 | 133.696 | Mass | 133.691 | 133.691 | 133.691 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| A12 | EQUIPMENT | 0.296 | 100 | 29.624 |  |  | Mass
| A13 | EQUIPMENT | 0.321 | 10 | 3.208 |  |  | Mass
|  | Sub Total | 0.884 | 610 | 166.523 | 500 | 133.696 |  | 133.691 | 133.691 | 133.691 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : VS-29 |  | Client : CREDA VS-29 | [11 empty] | Order Dt. : 23/08/2022
| S1 | EQUIPMENT | 0.177 | 351 | 62.115 | 1 | 5.161 | Proto | 5.161 | 5.175 | 5.175 | 5.161 | 5.022 | 0.000 | 0.000 | -0.014 | 0.000 | 0.014 | 0.138
[6 empty] | 350 | 56.940 | Mass | 58.368 | 56.940 | 56.940 | 56.888 | 56.915 | 4.998 | -1.428 | 1.428 | 0.000 | 0.052 | -0.028
| S2 | EQUIPMENT | 0.273 | 600 | 164.011 | 600 | 164.012 | Mass | 164.011 | 164.011 | 164.011 | 164.011 | 164.011 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| T6 | S.S.T | 0.010 | 80 | 0.763 | 80 | 0.763 | Mass | 0.763 | 0.763 | 0.763 | 0.763 | 0.763 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| T9 | S.S.T | 0.012 | 135 | 1.590 | 135 | 1.590 | Mass | 1.590 | 1.590 | 1.590 | 1.590 | 1.590 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 0.649 | 1166 | 228.479 | 1166 | 228.466 |  | 229.892 | 228.479 | 228.479 | 228.412 | 228.302 | 4.998 | -1.428 | 1.414 | 0.000 | 0.066 | 0.111
| Project Code : VS-33 |  | Client : A POLE-VS-02 | [11 empty] | Order Dt. : 15/09/2022
| A11 | EQUIPMENT | 0.267 | 12000 | 3208.572 | 11140 | 2978.622 | Mass | 2978.624 | 2978.624 | 2978.624 | 2978.624 | 2965.523 | 1834.237 | 0.000 | 0.000 | 0.000 | 0.000 | 13.102
| A12 | EQUIPMENT | 0.297 | 4000 | 1186.652 | 3501 | 1038.617 | Mass | 1032.684 | 1024.377 | 1009.544 | 1038.617 | 966.528 | 741.361 | 5.933 | 8.307 | 14.833 | -29.073 | 72.089
| A13 | EQUIPMENT | 0.320 | 1500 | 480.531 | 1275 | 408.452 | Mass | 408.451 | 402.365 | 402.365 | 408.451 | 299.851 | 312.345 | 0.000 | 6.087 | 0.000 | -6.087 | 108.600
| A14 | EQUIPMENT | 0.441 | 1521 | 670.337 | 1521 | 670.338 | Mass | 626.265 | 568.530 | 568.530 | 648.505 | 560.597 | 335.165 | 44.072 | 57.734 | 0.000 | -79.975 | 87.908
|  | Sub Total | 1.325 | 19021 | 5546.092 | 17437 | 5096.029 |  | 5046.024 | 4973.896 | 4959.063 | 5074.198 | 4792.499 | 3223.108 | 50.005 | 72.128 | 14.833 | -115.134 | 281.698
| Project Code : VS-34 |  | Client : SUYOG TELEMATICS LIMITED -VS-34 | [11 empty] | Order Dt. : 21/09/2022
| 3T | NORMAL TOWER | 2.334 | 10 | 23.340 | 10 | 23.333 | Proto | 23.340 | 23.340 | 23.340 | 23.340 | 23.340 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 2.334 | 10 | 23.340 | 10 | 23.333 |  | 23.340 | 23.340 | 23.340 | 23.340 | 23.340 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| Project Code : VS-36 |  | Client : CREDA VS-36 | [11 empty] | Order Dt. : 21/10/2022
| S1 | EQUIPMENT | 0.179 | 250 | 44.752 | 250 | 44.755 | Mass | 44.752 | 44.752 | 44.752 | 44.752 | 44.752 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| S2 | EQUIPMENT | 0.271 | 500 | 135.532 | 500 | 135.533 | Mass | 156.450 | 135.532 | 135.532 | 135.532 | 130.111 | 0.000 | -20.918 | 20.918 | 0.000 | 0.000 | 5.421
|  | Sub Total | 0.450 | 750 | 180.284 | 750 | 180.288 |  | 201.202 | 180.284 | 180.284 | 180.284 | 174.862 | 0.000 | -20.918 | 20.918 | 0.000 | 0.000 | 5.421
| Project Code : VS-42 |  | Client : CREDA VS-42 | [11 empty] | Order Dt. : 11/11/2022
| S1 | EQUIPMENT | 0.177 | 250 | 44.209 | 250 | 44.212 | Mass | 44.209 | 44.209 | 44.209 | 44.209 | 44.209 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| S2 | EQUIPMENT | 0.273 | 500 | 136.676 | 500 | 136.655 | Mass | 152.564 | 136.676 | 136.676 | 136.654 | 136.676 | 0.022 | -15.910 | 15.888 | 0.000 | 0.022 | -0.022
|  | Sub Total | 0.450 | 750 | 180.885 | 750 | 180.867 |  | 196.773 | 180.885 | 180.885 | 180.863 | 180.885 | 0.022 | -15.910 | 15.888 | 0.000 | 0.022 | -0.022
| Project Code : VS-68 |  | Client : CREDA VS-68 | [11 empty] | Order Dt. : 20/02/2023
| WT9 | EQUIPMENT | 3.224 | 300 | 967.135 | 300 | 967.131 | Mass | 967.135 | 967.135 | 967.135 | 967.135 | 966.931 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.204
|  | Sub Total | 3.224 | 300 | 967.135 | 300 | 967.131 |  | 967.135 | 967.135 | 967.135 | 967.135 | 966.931 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.204
| Project Code : VS-70 |  | Client : CREDA VS-70 | [11 empty] | Order Dt. : 20/02/2023
| S2 | EQUIPMENT | 0.273 | 1000 | 273.352 | 1000 | 273.352 | Mass | 273.352 | 273.352 | 273.352 | 273.352 | 254.217 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 19.135
|  | Sub Total | 0.273 | 1000 | 273.352 | 1000 | 273.352 |  | 273.352 | 273.352 | 273.352 | 273.352 | 254.217 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 19.135
| Project Code : VS-91 |  | Client : CREDA VS-91 | [11 empty] | Order Dt. : 19/05/2023
| OFS | NORMAL TOWER | 10.596 | 1 | 10.596 | 1 | 10.597 | Mass | 10.596 | 10.596 | 10.596 |  |  | 0.000 | 0.000 | 0.000 | 0.000
| WT9 | EQUIPMENT | 3.227 | 301 | 971.428 | 300 | 968.021 | Mass | 968.023 | 968.023 | 967.846 | 968.023 | 457.445 | 3.407 | 0.000 | 0.000 | 0.177 | -0.177 | 510.578
|  | Sub Total | 13.824 | 302 | 982.024 | 301 | 978.618 |  | 978.620 | 978.620 | 978.442 | 968.023 | 457.445 | 3.407 | 0.000 | 0.000 | 0.177 | -0.177 | 510.578
| Project Code : VS-94. |  | Client : TP CENTRAL ODISHA DISTRIBUTION LIMITED (VS-94) | [11 empty] | Order Dt. : 15/07/2023
| CA2 | S.P.S | 0.022 | 1500 | 33.273 | 1500 | 33.273 | Mass | 33.273 | 33.273 | 33.273 | 33.273 | 33.273 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
|  | Sub Total | 0.022 | 1500 | 33.273 | 1500 | 33.273 |  | 33.273 | 33.273 | 33.273 | 33.273 | 33.273 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000
| Grand Total |  | 7103.685 | 95888 | 50984.736 | 1070954 | 41810.444 |  | 38997.515 | 33768.449 | 32516.027 | 28166.037 | 21549.750 | 7301.940 | 2812.683 | 5229.066 | 1252.506 | -2250.207 | 6616.288