## Combined
IN-HOUSE
A - Project to Start |  | B - Raw Material Incomplete | [5 empty] | C - RM Complete | [6 empty] | D - Dispatch Clearance | [6 empty] | E - Ready Not Dispatched
Project | WO Qty (MT) | Project | MFC Batch | Rel. Bal. | Fab+Galva | Yard | Structures | Project | MFC Batch | Rel. Bal. | Fab | Galva | Yard | Structures | Project | MFC Batch | Rel. Bal. | Fab | Galva | Yard | Structures | Project | MFC Batch | Release Bal. (MT) | Fab+Galva (MT) | Yard (MT) | Structures
|  | 824 | B | 0.014 | 0.58 | 0 | 2 | 821 | Z | 0 | 10.29 | 0 | 193.914 | 4 | 821 | Z | 0 | 10.29 | 0 | 193.914 | 4 | 941 | B | 0 | 251.795 | 108.901 | 10
|  | 885 | Z | 0.089 | 0.066 | 6.691 | 1 | 824 | A | 0 | 5.72 | 18.417 | 53.469 | 9 | 824 | A | 0 | 5.72 | 18.417 | 53.469 | 9
|  | 888 | Z | 0.135 | 0 | 61.287 | 1 | 824 | B | 0 | 1.564 | 0 | 0 | 6 | 824 | Z | 0 | 4 | 0.246 | 86.269 | 3
|  | 890 | Z | 3.345 | 0 | 16.725 | 1 | 824 | Z | 0 | 4.752 | 0.637 | 86.467 | 8 | 848 | Z | 0 | 0 | 0 | 141.041 | 5
|  | 900 | B | 7.348 | 260.45 | 47.668 | 3 | 839 | B | 0 | 1.274 | 0 | 0.023 | 1 | 866 | Z | 0 | 2.046 | 0.678 | 50.536 | 12
|  | 900 | C | 81.651 | 636.004 | 171.965 | 3 | 848 | A | 0 | 47.531 | 5.41 | 1.004 | 7 | 870 | Z | 0 | 0 | 0 | 33.488 | 1
|  | 900 | Z | 161.615 | 9.629 | 0 | 1 | 848 | Z | 0 | 0 | 0 | 141.041 | 5 | 884 | Z | 0 | 0.369 | 1.298 | 255.009 | 7
|  | 908 | Z | 127.59 | 0.356 | 176.091 | 10 | 862 | Z | 0 | 39.995 | 47.115 | 182.528 | 15 | 885 | Z | 0.089 | 3.698 | 3.007 | 486.621 | 19
|  | 911 | A | 0.042 | 2.367 | 0.613 | 1 | 866 | Z | 0 | 5.983 | 0.678 | 50.536 | 13 | 886 | B | 0 | 0.016 | 0.156 | 210.56 | 8
|  | 911 | B | 1.363 | 86.576 | 92.389 | 2 | 870 | Z | 0 | 8.021 | 6.108 | 39.434 | 2 | 888 | Z | 0.135 | 0.003 | 0.006 | 181.838 | 7
|  | 912 | C | 57.368 | 21.528 | 2.004 | 1 | 884 | Z | 0 | 0.369 | 1.298 | 255.009 | 7 | 890 | Z | 3.345 | 0 | 0 | 19.719 | 2
|  | 912 | Z | 37.321 | 8.257 | 0 | 12 | 885 | Z | 0 | 3.698 | 2.941 | 479.93 | 18 | 893 | A | 0 | 0.702 | 0 | 2.806 | 1
|  | 917 | B | 0.522 | 19.941 | 1.18 | 1 | 886 | A | 0 | 0 | 0 | 0.573 | 2 | 893 | Z | 0 | 28.691 | 0 | 102.57 | 11
|  | 917 | Z | 2.198 | 2.715 | 0 | 1 | 886 | B | 0 | 0.016 | 0.156 | 210.56 | 8 | 899 | Z | 0 | 0 | 0 | 148.075 | 12
|  | 920 | C | 7.701 | 42.634 | 1.746 | 15 | 886 | C | 0 | 1.944 | 1.49 | 3.014 | 3 | 901 | Z | 0 | 0 | 0 | 56.61 | 4
|  | 920 | D | 61.784 | 37.469 | 2.725 | 20 | 888 | Z | 0 | 0.003 | 0.006 | 120.551 | 6 | 903 | A | 0 | 26.249 | 4.075 | 327.644 | 10
|  | 926 | A | 7.587 | 27.561 | 3.064 | 2 | 890 | Z | 0 | 37.983 | 0.865 | 9.883 | 9 | 903 | Z | 0 | 4.283 | 1.724 | 70.874 | 6
|  | 926 | B | 13.595 | 124.859 | 25.277 | 8 | 893 | A | 0 | 0.702 | 0 | 2.806 | 1 | 904 | A | 0 | 2.895 | 7.014 | 380.182 | 15
|  | 928 | B | 0.013 | 8.835 | 24.879 | 1 | 893 | Z | 0 | 32.689 | 1.643 | 108.267 | 15 | 907 | Z | 0 | 98.224 | 18.485 | 417.007 | 12
|  | 929 | A | 0.528 | 60.764 | 53.655 | 2 | 899 | Z | 0 | 0 | 0 | 148.075 | 12 | 908 | A | 0 | 0.052 | 0.015 | 6.243 | 2
|  | 929 | B | 46.318 | 130.044 | 80.999 | 5 | 901 | Z | 0 | 0 | 0 | 56.61 | 4 | 908 | Z | 112.249 | 0.128 | 0.624 | 179.415 | 7
|  | 933 | B | 9.782 | 70.831 | 414.83 | 1 | 903 | A | 0 | 26.249 | 4.075 | 327.644 | 10 | 909 | A | 0 | 5.007 | 0.392 | 9.695 | 2
|  | 934 | B | 11.345 | 133.453 | 21.731 | 8 | 903 | Z | 0 | 4.283 | 1.724 | 70.874 | 6 | 909 | Z | 0 | 0 | 0.052 | 56.753 | 13
|  | 935 | A | 220.449 | 657.132 | 258.646 | 19 | 904 | A | 0 | 2.895 | 7.014 | 380.182 | 15 | 914 | Z | 0 | 0.326 | 0.216 | 29.706 | 8
|  | 935 | B | 12.385 | 68.377 | 7.303 | 6 | 906 | A | 0 | 1.224 | 1.257 | 1.864 | 2 | 918 | B | 0 | 0.07 | 0.431 | 494.037 | 14
|  | 935 | C | 11.251 | 22.731 | 0 | 5 | 906 | B | 0 | 3.752 | 0.466 | 1.403 | 2 | 920 | B | 0 | 0.146 | 0.402 | 136.274 | 10
|  | 937 | Z | 71.29 | 3.19 | 0 | 14 | 906 | Z | 0 | 13.561 | 0 | 0.085 | 12 | 920 | Z | 0 | 0 | 0 | 73.309 | 7
|  | 938 | A | 0.556 | 12.015 | 0 | 3 | 907 | Z | 0 | 98.224 | 18.485 | 417.007 | 12 | 921 | Z | 0 | 2.782 | 18.47 | 1144.031 | 20
|  | 938 | Z | 50.031 | 18.543 | 0 | 4 | 908 | A | 0 | 6.55 | 9.825 | 34.796 | 20 | 922 | B | 0 | 86.592 | 24.524 | 239.794 | 9
|  | 939 | A | 34.295 | 201.907 | 30.248 | 7 | 908 | Z | 0 | 1.295 | 1.303 | 4.011 | 3 | 924 | Z | 0 | 0 | 0 | 7.448 | 3
|  | 940 | C | 425.877 | 135.729 | 1.093 | 5 | 909 | A | 0 | 17.626 | 2.968 | 12.488 | 5 | 928 | A | 0 | 0.408 | 0.535 | 2.183 | 1
|  | 942 | A | 40.667 | 635.98 | 242.015 | 2 | 909 | Z | 0 | 10.315 | 0.052 | 57.023 | 15 | 928 | B | 0.013 | 80.999 | 41.613 | 446.075 | 12
|  | 944 | B | 341.434 | 420.667 | 24.691 | 5 | 911 | A | 0 | 0.107 | 1.206 | 1.057 | 1 | 931 | A | 0 | 0.016 | 1.741 | 16.174 | 3
|  | 944 | Z | 5.349 | 2.138 | 0 | 1 | 911 | C | 0 | 55.652 | 11.238 | 23.408 | 2 | 931 | B | 0 | 9.096 | 8.721 | 429.131 | 9
|  | 946 | Z | 2.783 | 0.2 | 0 | 1 | 912 | A | 0 | 1.342 | 0 | 1.179 | 1 | 933 | B | 9.782 | 67.335 | 85.949 | 716.479 | 4
|  | 948 | Z | 273.899 | 6.028 | 0 | 16 | 912 | Z | 0 | 2.887 | 0 | 0 | 1 | 933 | Z | 0 | 0 | 0 | 4.961 | 1
|  | 958 | Z | 18.373 | 0 | 0 | 3 | 914 | Z | 0 | 0.326 | 0.216 | 29.706 | 8 | 935 | A | 220.449 | 570.427 | 86.705 | 258.646 | 19
[8 empty] | 917 | A | 0 | 0.539 | 0.06 | 0 | 1 | 935 | B | 12.385 | 53.444 | 14.933 | 7.303 | 6
[8 empty] | 917 | B | 0 | 47.164 | 14.581 | 2.704 | 6 | 935 | C | 11.251 | 18.107 | 4.624 | 0 | 5
[8 empty] | 918 | B | 0 | 0.07 | 0.431 | 494.037 | 14 | 941 | Z | 0 | 0 | 0 | 3.943 | 1
[8 empty] | 918 | Z | 0 | 6.475 | 0 | 0 | 1
[8 empty] | 920 | B | 0 | 0.146 | 0.402 | 136.274 | 10
[8 empty] | 920 | C | 0 | 32.53 | 18.992 | 3.303 | 13
[8 empty] | 920 | D | 0 | 1.22 | 1.475 | 0.575 | 3
[8 empty] | 920 | Z | 0 | 0 | 0 | 73.309 | 7
[8 empty] | 921 | Z | 0 | 2.782 | 18.47 | 1144.031 | 20
[8 empty] | 922 | B | 0 | 86.592 | 24.524 | 239.794 | 9
[8 empty] | 922 | C | 0 | 73.448 | 18.492 | 22.239 | 7
[8 empty] | 923 | B | 0 | 37.79 | 10.853 | 129.586 | 16
[8 empty] | 924 | Z | 0 | 0 | 0 | 7.448 | 3
[8 empty] | 926 | B | 0 | 34.02 | 34.311 | 18.216 | 5
[8 empty] | 928 | A | 0 | 0.81 | 2.228 | 2.183 | 2
[8 empty] | 928 | B | 0 | 94.067 | 49.018 | 441.104 | 16
[8 empty] | 931 | A | 0 | 0.016 | 1.741 | 16.174 | 3
[8 empty] | 931 | B | 0 | 9.096 | 8.721 | 429.131 | 9
[8 empty] | 931 | Z | 0 | 1.289 | 0 | 0 | 1
[8 empty] | 933 | B | 0 | 36.742 | 45.711 | 301.649 | 3
[8 empty] | 933 | C | 0 | 6.836 | 1.203 | 3.261 | 2
[8 empty] | 933 | Z | 0 | 0 | 0 | 4.961 | 1
[8 empty] | 934 | B | 0 | 63.068 | 8.964 | 11.208 | 7
[8 empty] | 934 | Z | 0 | 2.435 | 0 | 0 | 2
[8 empty] | 939 | A | 0 | 2.029 | 0 | 0 | 1
[8 empty] | 939 | Z | 0 | 0.005 | 0 | 0 | 1
[8 empty] | 940 | A | 0 | 0 | 0 | 12.96 | 4
[8 empty] | 940 | B | 0 | 0.365 | 0 | 14.506 | 3
[8 empty] | 941 | Z | 0 | 0 | 0 | 3.943 | 1
[8 empty] | 944 | A | 0 | 2.152 | 0.369 | 28.572 | 2
[8 empty] | 945 | A | 0 | 0.05 | 0.207 | 2.144 | 4
[8 empty] | 945 | B | 0 | 25.375 | 0 | 0 | 5
[8 empty] | 945 | C | 0 | 11.054 | 0 | 0 | 4
[8 empty] | 946 | A | 0 | 1.399 | 0.444 | 0 | 4
[8 empty] | 946 | B | 0 | 0.084 | 0.267 | 0.8 | 1
[8 empty] | 946 | Z | 0 | 97.301 | 0 | 0 | 13
[8 empty] | 957 | Z | 0 | 2.987 | 0 | 0 | 1
|  | In-House SUMMARY | [5 empty] | In-House SUMMARY | [6 empty] | In-House SUMMARY
|  | Total Release Balance |  | 2147.893 |  |  |  | Total Release Balance |  | 0 | 0 |  |  |  | Total Release Balance |  | 369.698 | 369.698
|  | Under Production |  |  | 3869.556 |  |  | Under Production |  |  | 1536.815 |  |  |  | Under Production |  |  | 1427.174
|  | Total Yard |  |  |  | 1769.515 |  | Total Yard |  |  |  |  | 7050.533 |  | Total Yard |  |  |  |  | 7479.832
|  | Operation Weight |  |  | 5639.071 |  |  | Operation Weight |  |  | 8587.348 |  |  |  | Operation Weight |  |  | 8907.006
|  | Grand Total Weight |  |  | 7786.964 |  |  | Grand Total Weight |  |  | 8587.348 |  |  |  | Grand Total Weight |  |  | 9276.704
TOTAL | 0 | TOTAL |  | 2147.893 | 3869.556 | 1769.515 |  | TOTAL |  | 0 | 1128.758 | 408.057 | 7050.533 |  | TOTAL |  | 369.698 | 1082.121 | 345.053 | 7479.832 |  | TOTAL |  | 0 | 251.795 | 108.901
OUT-VENDOR
A - Project to Start |  | B - Raw Material Incomplete | [5 empty] | C - RM Complete | [6 empty] | D - Dispatch Clearance | [6 empty] | E - Ready Not Dispatched
Project | WO Qty (MT) | Project | MFC Batch | Rel. Bal. | Fab+Galva | Yard | Structures | Project | MFC Batch | Rel. Bal. | Fab | Galva | Yard | Structures | Project | MFC Batch | Rel. Bal. | Fab | Galva | Yard | Structures | Project | MFC Batch | Release Bal. (MT) | Fab+Galva (MT) | Yard (MT) | Structures
|  | 900 | B | 5.899 | 250.841 | 47.668 | 2 | 821 | Z | 0 | 7.449 | 0 | 77.442 | 1 | 821 | Z | 0 | 7.449 | 0 | 77.442 | 1
|  | 900 | C | 81.651 | 636.004 | 171.965 | 3 | 824 | A | 0 | 5.72 | 18.417 | 53.469 | 9 | 824 | A | 0 | 5.72 | 18.417 | 53.469 | 9
|  | 911 | B | 1.363 | 86.576 | 92.389 | 2 | 824 | Z | 0 | 0.24 | 0.512 | 55.021 | 3 | 824 | Z | 0 | 0.091 | 0.121 | 54.823 | 1
|  | 912 | B | 1.365 | 3.49 | 0 | 1 | 839 | B | 0 | 5.461 | 0 | 0.023 | 3 | 866 | Z | 0 | 2.873 | 0.607 | 43.415 | 6
|  | 912 | C | 219.594 | 117.397 | 2.004 | 12 | 848 | A | 0 | 35.76 | 2.305 | 0.011 | 2 | 885 | Z | 0 | 3.184 | 2.108 | 46.803 | 1
|  | 912 | Z | 53.186 | 20.295 | 0 | 5 | 862 | Z | 0 | 17.19 | 12.412 | 42.783 | 4 | 886 | B | 0 | 0 | 0.005 | 10.92 | 1
|  | 917 | B | 0.522 | 19.941 | 1.18 | 1 | 866 | Z | 0 | 2.873 | 0.607 | 43.415 | 6 | 888 | A | 0 | 6.579 | 2.858 | 29.321 | 5
|  | 920 | C | 7.585 | 43.623 | 1.788 | 15 | 870 | Z | 0 | 8.021 | 6.108 | 5.946 | 1 | 888 | Z | 0 | 0.003 | 0.006 | 0.799 | 1
|  | 920 | D | 35.137 | 21.471 | 1.876 | 15 | 885 | Z | 0 | 5.452 | 3.212 | 47.206 | 4 | 890 | Z | 0 | 0 | 0 | 311.741 | 8
|  | 926 | A | 7.587 | 27.561 | 3.064 | 2 | 886 | B | 0 | 0 | 0.005 | 10.92 | 1 | 893 | A | 0 | 0.702 | 0 | 2.806 | 1
|  | 926 | B | 13.595 | 124.859 | 25.277 | 8 | 886 | C | 0 | 1.944 | 1.49 | 3.014 | 3 | 893 | Z | 0 | 30.134 | 0 | 66.72 | 2
|  | 928 | B | 0.013 | 8.835 | 24.879 | 1 | 888 | A | 0 | 6.579 | 2.858 | 29.321 | 5 | 899 | Z | 0 | 0 | 0 | 254.817 | 27
|  | 929 | A | 0.528 | 60.764 | 53.655 | 2 | 888 | Z | 0 | 1.505 | 0.006 | 0.799 | 2 | 901 | Z | 0 | 0 | 0 | 11.293 | 1
|  | 929 | B | 43.177 | 126.968 | 80.999 | 4 | 890 | Z | 0 | 54.337 | 2.128 | 322.442 | 21 | 903 | A | 0 | 24.088 | 3.618 | 287.275 | 6
|  | 933 | B | 9.782 | 70.831 | 414.83 | 1 | 893 | A | 0 | 0.702 | 0 | 2.806 | 1 | 904 | A | 0 | 0.844 | 0.828 | 115.49 | 8
|  | 934 | B | 11.345 | 133.453 | 21.731 | 8 | 893 | Z | 0 | 37.573 | 0.034 | 67.268 | 6 | 905 | Z | 0 | 0 | 0 | 39.165 | 1
|  | 935 | A | 220.449 | 657.132 | 258.646 | 19 | 899 | Z | 0 | 0 | 0 | 254.817 | 27 | 907 | Z | 0 | 96.875 | 18.355 | 414.763 | 11
|  | 935 | B | 14.219 | 69.656 | 7.303 | 7 | 901 | Z | 0 | 0 | 0 | 11.293 | 1 | 908 | A | 0 | 0.052 | 0.014 | 2.225 | 1
|  | 935 | C | 11.251 | 22.731 | 0 | 5 | 903 | A | 0 | 24.088 | 3.618 | 287.275 | 6 | 908 | Z | 0 | 0.483 | 0.476 | 16.539 | 2
|  | 939 | A | 34.295 | 201.907 | 30.248 | 7 | 904 | A | 0 | 0.844 | 0.828 | 115.49 | 8 | 909 | A | 0 | 5.007 | 0.392 | 9.695 | 2
|  | 940 | C | 425.877 | 135.729 | 1.093 | 5 | 905 | Z | 0 | 0 | 0 | 39.165 | 1 | 914 | Z | 0 | 0.326 | 0.148 | 22.586 | 4
|  | 942 | A | 40.667 | 635.98 | 242.015 | 2 | 906 | A | 0 | 16.325 | 6.801 | 15.482 | 8 | 918 | B | 0 | 0.013 | 0.353 | 429.636 | 5
|  | 944 | B | 341.434 | 420.667 | 24.691 | 5 | 906 | B | 0 | 3.752 | 0.466 | 1.403 | 2 | 920 | B | 0 | 0.051 | 0.402 | 69.791 | 6
[8 empty] | 907 | Z | 0 | 96.875 | 18.355 | 414.763 | 11 | 920 | Z | 0 | 0 | 0 | 7.149 | 1
[8 empty] | 908 | A | 0 | 7.783 | 6.601 | 22.467 | 16 | 921 | Z | 0 | 1.727 | 11.77 | 745.848 | 6
[8 empty] | 908 | Z | 0 | 1.65 | 1.511 | 17.226 | 4 | 922 | B | 0 | 86.592 | 24.524 | 239.794 | 9
[8 empty] | 909 | A | 0 | 17.626 | 2.968 | 12.488 | 5 | 924 | Z | 0 | 0 | 0 | 4.648 | 3
[8 empty] | 909 | Z | 0 | 10.315 | 0 | 0.27 | 2 | 928 | B | 0.013 | 80.999 | 41.613 | 446.075 | 12
[8 empty] | 911 | C | 0 | 55.652 | 11.238 | 23.408 | 2 | 931 | B | 0 | 7.94 | 7.923 | 392.063 | 4
[8 empty] | 914 | Z | 0 | 0.326 | 0.148 | 22.586 | 4 | 933 | B | 9.782 | 67.335 | 85.949 | 716.479 | 4
[8 empty] | 917 | A | 0 | 0.539 | 0.06 | 0 | 1 | 933 | Z | 0 | 0 | 0 | 14.264 | 2
[8 empty] | 917 | B | 0 | 44.754 | 14.581 | 2.704 | 5 | 935 | A | 220.449 | 570.427 | 86.705 | 258.646 | 19
[8 empty] | 918 | B | 0 | 0.013 | 0.353 | 429.636 | 5 | 935 | B | 14.219 | 56.389 | 14.933 | 7.303 | 8
[8 empty] | 920 | B | 0 | 0.051 | 0.402 | 69.791 | 6 | 935 | C | 11.251 | 18.107 | 4.624 | 0 | 5
[8 empty] | 920 | C | 0 | 34.569 | 19.379 | 3.324 | 14
[8 empty] | 920 | D | 0 | 1.22 | 1.475 | 0.575 | 3
[8 empty] | 920 | Z | 0 | 0 | 0 | 7.149 | 1
[8 empty] | 921 | Z | 0 | 1.727 | 11.77 | 745.848 | 6
[8 empty] | 922 | B | 0 | 86.592 | 24.524 | 239.794 | 9
[8 empty] | 922 | C | 0 | 54.08 | 18.492 | 21.187 | 6
[8 empty] | 923 | B | 0 | 39.925 | 10.941 | 129.586 | 17
[8 empty] | 924 | Z | 0 | 0 | 0 | 4.648 | 3
[8 empty] | 926 | B | 0 | 34.02 | 34.311 | 18.216 | 5
[8 empty] | 928 | B | 0 | 98.593 | 51.718 | 441.104 | 18
[8 empty] | 931 | B | 0 | 7.94 | 7.923 | 392.063 | 4
[8 empty] | 932 | A | 0 | 22.98 | 0 | 0 | 12
[8 empty] | 933 | B | 0 | 36.742 | 45.711 | 301.649 | 3
[8 empty] | 933 | C | 0 | 6.836 | 1.203 | 3.261 | 2
[8 empty] | 933 | Z | 0 | 0 | 0 | 14.264 | 2
[8 empty] | 934 | B | 0 | 63.068 | 8.964 | 11.208 | 7
[8 empty] | 934 | Z | 0 | 2.399 | 0 | 0 | 1
[8 empty] | 935 | B | 0 | 1.666 | 0 | 0 | 1
[8 empty] | 936 | A | 0 | 70.533 | 0 | 0 | 10
[8 empty] | 939 | A | 0 | 2.029 | 0 | 0 | 1
[8 empty] | 944 | A | 0 | 0.039 | 0.369 | 28.455 | 1
[8 empty] | 945 | A | 0 | 0 | 0.207 | 1.401 | 2
[8 empty] | 947 | A | 0 | 41.368 | 0 | 0 | 2
[8 empty] | 952 | A | 0 | 18.657 | 0 | 0 | 2
|  | Out-Vendor SUMMARY | [5 empty] | Out-Vendor SUMMARY | [6 empty] | Out-Vendor SUMMARY
|  | Total Release Balance |  | 1580.521 |  |  |  | Total Release Balance |  | 0 | 0 |  |  |  | Total Release Balance |  | 255.714 | 255.714
|  | Under Production |  |  | 3896.711 |  |  | Under Production |  |  | 1451.393 |  |  |  | Under Production |  |  | 1400.739
|  | Total Yard |  |  |  | 1507.301 |  | Total Yard |  |  |  |  | 4865.882 |  | Total Yard |  |  |  |  | 5203.803
|  | Operation Weight |  |  | 5404.012 |  |  | Operation Weight |  |  | 6317.275 |  |  |  | Operation Weight |  |  | 6604.542
|  | Grand Total Weight |  |  | 6984.533 |  |  | Grand Total Weight |  |  | 6317.275 |  |  |  | Grand Total Weight |  |  | 6860.256
TOTAL | 0 | TOTAL |  | 1580.521 | 3896.711 | 1507.301 |  | TOTAL |  | 0 | 1096.382 | 355.011 | 4865.882 |  | TOTAL |  | 255.714 | 1073.99 | 326.749 | 5203.803 |  | TOTAL |  | 0 | 0 | 0

## A - Project to Start
Side | Project | WO Qty (MT) | Note

## B - Raw Material Incomplete
Side | MFC Batch | Project | Rel. Bal. | Fab+Galva | Yard | Structures
In-House | A | 911 | 0.042 | 2.367 | 0.613 | 1
In-House | A | 926 | 7.587 | 27.561 | 3.064 | 2
In-House | A | 929 | 0.528 | 60.764 | 53.655 | 2
In-House | A | 935 | 220.449 | 657.132 | 258.646 | 19
In-House | A | 938 | 0.556 | 12.015 | 0 | 3
In-House | A | 939 | 34.295 | 201.907 | 30.248 | 7
In-House | A | 942 | 40.667 | 635.98 | 242.015 | 2
In-House | B | 824 | 0.014 | 0.58 | 0 | 2
In-House | B | 900 | 7.348 | 260.45 | 47.668 | 3
In-House | B | 911 | 1.363 | 86.576 | 92.389 | 2
In-House | B | 917 | 0.522 | 19.941 | 1.18 | 1
In-House | B | 926 | 13.595 | 124.859 | 25.277 | 8
In-House | B | 928 | 0.013 | 8.835 | 24.879 | 1
In-House | B | 929 | 46.318 | 130.044 | 80.999 | 5
In-House | B | 933 | 9.782 | 70.831 | 414.83 | 1
In-House | B | 934 | 11.345 | 133.453 | 21.731 | 8
In-House | B | 935 | 12.385 | 68.377 | 7.303 | 6
In-House | B | 944 | 341.434 | 420.667 | 24.691 | 5
In-House | C | 900 | 81.651 | 636.004 | 171.965 | 3
In-House | C | 912 | 57.368 | 21.528 | 2.004 | 1
In-House | C | 920 | 7.701 | 42.634 | 1.746 | 15
In-House | C | 935 | 11.251 | 22.731 | 0 | 5
In-House | C | 940 | 425.877 | 135.729 | 1.093 | 5
In-House | D | 920 | 61.784 | 37.469 | 2.725 | 20
In-House | Z | 885 | 0.089 | 0.066 | 6.691 | 1
In-House | Z | 888 | 0.135 | 0 | 61.287 | 1
In-House | Z | 890 | 3.345 | 0 | 16.725 | 1
In-House | Z | 900 | 161.615 | 9.629 | 0 | 1
In-House | Z | 908 | 127.59 | 0.356 | 176.091 | 10
In-House | Z | 912 | 37.321 | 8.257 | 0 | 12
In-House | Z | 917 | 2.198 | 2.715 | 0 | 1
In-House | Z | 937 | 71.29 | 3.19 | 0 | 14
In-House | Z | 938 | 50.031 | 18.543 | 0 | 4
In-House | Z | 944 | 5.349 | 2.138 | 0 | 1
In-House | Z | 946 | 2.783 | 0.2 | 0 | 1
In-House | Z | 948 | 273.899 | 6.028 | 0 | 16
In-House | Z | 958 | 18.373 | 0 | 0 | 3
In-House SUMMARY
Total Release Balance |  |  | 2147.893
Under Production |  |  |  | 3869.556
Total Yard |  |  |  |  | 1769.515
Operation Weight |  |  |  | 5639.071
Grand Total Weight |  |  |  | 7786.964
Out-Vendor | A | 926 | 7.587 | 27.561 | 3.064 | 2
Out-Vendor | A | 929 | 0.528 | 60.764 | 53.655 | 2
Out-Vendor | A | 935 | 220.449 | 657.132 | 258.646 | 19
Out-Vendor | A | 939 | 34.295 | 201.907 | 30.248 | 7
Out-Vendor | A | 942 | 40.667 | 635.98 | 242.015 | 2
Out-Vendor | B | 900 | 5.899 | 250.841 | 47.668 | 2
Out-Vendor | B | 911 | 1.363 | 86.576 | 92.389 | 2
Out-Vendor | B | 912 | 1.365 | 3.49 | 0 | 1
Out-Vendor | B | 917 | 0.522 | 19.941 | 1.18 | 1
Out-Vendor | B | 926 | 13.595 | 124.859 | 25.277 | 8
Out-Vendor | B | 928 | 0.013 | 8.835 | 24.879 | 1
Out-Vendor | B | 929 | 43.177 | 126.968 | 80.999 | 4
Out-Vendor | B | 933 | 9.782 | 70.831 | 414.83 | 1
Out-Vendor | B | 934 | 11.345 | 133.453 | 21.731 | 8
Out-Vendor | B | 935 | 14.219 | 69.656 | 7.303 | 7
Out-Vendor | B | 944 | 341.434 | 420.667 | 24.691 | 5
Out-Vendor | C | 900 | 81.651 | 636.004 | 171.965 | 3
Out-Vendor | C | 912 | 219.594 | 117.397 | 2.004 | 12
Out-Vendor | C | 920 | 7.585 | 43.623 | 1.788 | 15
Out-Vendor | C | 935 | 11.251 | 22.731 | 0 | 5
Out-Vendor | C | 940 | 425.877 | 135.729 | 1.093 | 5
Out-Vendor | D | 920 | 35.137 | 21.471 | 1.876 | 15
Out-Vendor | Z | 912 | 53.186 | 20.295 | 0 | 5
Out-Vendor SUMMARY
Total Release Balance |  |  | 1580.521
Under Production |  |  |  | 3896.711
Total Yard |  |  |  |  | 1507.301
Operation Weight |  |  |  | 5404.012
Grand Total Weight |  |  |  | 6984.533
TOTAL |  |  | 3728.414 | 7766.267 | 3276.816

## C - RM Complete
Side | MFC Batch | Project | Rel. Bal. | Fab | Galva | Yard | Structures
In-House | A | 824 | 0 | 5.72 | 18.417 | 53.469 | 9
In-House | A | 848 | 0 | 47.531 | 5.41 | 1.004 | 7
In-House | A | 886 | 0 | 0 | 0 | 0.573 | 2
In-House | A | 893 | 0 | 0.702 | 0 | 2.806 | 1
In-House | A | 903 | 0 | 26.249 | 4.075 | 327.644 | 10
In-House | A | 904 | 0 | 2.895 | 7.014 | 380.182 | 15
In-House | A | 906 | 0 | 1.224 | 1.257 | 1.864 | 2
In-House | A | 908 | 0 | 6.55 | 9.825 | 34.796 | 20
In-House | A | 909 | 0 | 17.626 | 2.968 | 12.488 | 5
In-House | A | 911 | 0 | 0.107 | 1.206 | 1.057 | 1
In-House | A | 912 | 0 | 1.342 | 0 | 1.179 | 1
In-House | A | 917 | 0 | 0.539 | 0.06 | 0 | 1
In-House | A | 928 | 0 | 0.81 | 2.228 | 2.183 | 2
In-House | A | 931 | 0 | 0.016 | 1.741 | 16.174 | 3
In-House | A | 939 | 0 | 2.029 | 0 | 0 | 1
In-House | A | 940 | 0 | 0 | 0 | 12.96 | 4
In-House | A | 944 | 0 | 2.152 | 0.369 | 28.572 | 2
In-House | A | 945 | 0 | 0.05 | 0.207 | 2.144 | 4
In-House | A | 946 | 0 | 1.399 | 0.444 | 0 | 4
In-House | B | 824 | 0 | 1.564 | 0 | 0 | 6
In-House | B | 839 | 0 | 1.274 | 0 | 0.023 | 1
In-House | B | 886 | 0 | 0.016 | 0.156 | 210.56 | 8
In-House | B | 906 | 0 | 3.752 | 0.466 | 1.403 | 2
In-House | B | 917 | 0 | 47.164 | 14.581 | 2.704 | 6
In-House | B | 918 | 0 | 0.07 | 0.431 | 494.037 | 14
In-House | B | 920 | 0 | 0.146 | 0.402 | 136.274 | 10
In-House | B | 922 | 0 | 86.592 | 24.524 | 239.794 | 9
In-House | B | 923 | 0 | 37.79 | 10.853 | 129.586 | 16
In-House | B | 926 | 0 | 34.02 | 34.311 | 18.216 | 5
In-House | B | 928 | 0 | 94.067 | 49.018 | 441.104 | 16
In-House | B | 931 | 0 | 9.096 | 8.721 | 429.131 | 9
In-House | B | 933 | 0 | 36.742 | 45.711 | 301.649 | 3
In-House | B | 934 | 0 | 63.068 | 8.964 | 11.208 | 7
In-House | B | 940 | 0 | 0.365 | 0 | 14.506 | 3
In-House | B | 945 | 0 | 25.375 | 0 | 0 | 5
In-House | B | 946 | 0 | 0.084 | 0.267 | 0.8 | 1
In-House | C | 886 | 0 | 1.944 | 1.49 | 3.014 | 3
In-House | C | 911 | 0 | 55.652 | 11.238 | 23.408 | 2
In-House | C | 920 | 0 | 32.53 | 18.992 | 3.303 | 13
In-House | C | 922 | 0 | 73.448 | 18.492 | 22.239 | 7
In-House | C | 933 | 0 | 6.836 | 1.203 | 3.261 | 2
In-House | C | 945 | 0 | 11.054 | 0 | 0 | 4
In-House | D | 920 | 0 | 1.22 | 1.475 | 0.575 | 3
In-House | Z | 821 | 0 | 10.29 | 0 | 193.914 | 4
In-House | Z | 824 | 0 | 4.752 | 0.637 | 86.467 | 8
In-House | Z | 848 | 0 | 0 | 0 | 141.041 | 5
In-House | Z | 862 | 0 | 39.995 | 47.115 | 182.528 | 15
In-House | Z | 866 | 0 | 5.983 | 0.678 | 50.536 | 13
In-House | Z | 870 | 0 | 8.021 | 6.108 | 39.434 | 2
In-House | Z | 884 | 0 | 0.369 | 1.298 | 255.009 | 7
In-House | Z | 885 | 0 | 3.698 | 2.941 | 479.93 | 18
In-House | Z | 888 | 0 | 0.003 | 0.006 | 120.551 | 6
In-House | Z | 890 | 0 | 37.983 | 0.865 | 9.883 | 9
In-House | Z | 893 | 0 | 32.689 | 1.643 | 108.267 | 15
In-House | Z | 899 | 0 | 0 | 0 | 148.075 | 12
In-House | Z | 901 | 0 | 0 | 0 | 56.61 | 4
In-House | Z | 903 | 0 | 4.283 | 1.724 | 70.874 | 6
In-House | Z | 906 | 0 | 13.561 | 0 | 0.085 | 12
In-House | Z | 907 | 0 | 98.224 | 18.485 | 417.007 | 12
In-House | Z | 908 | 0 | 1.295 | 1.303 | 4.011 | 3
In-House | Z | 909 | 0 | 10.315 | 0.052 | 57.023 | 15
In-House | Z | 912 | 0 | 2.887 | 0 | 0 | 1
In-House | Z | 914 | 0 | 0.326 | 0.216 | 29.706 | 8
In-House | Z | 918 | 0 | 6.475 | 0 | 0 | 1
In-House | Z | 920 | 0 | 0 | 0 | 73.309 | 7
In-House | Z | 921 | 0 | 2.782 | 18.47 | 1144.031 | 20
In-House | Z | 924 | 0 | 0 | 0 | 7.448 | 3
In-House | Z | 931 | 0 | 1.289 | 0 | 0 | 1
In-House | Z | 933 | 0 | 0 | 0 | 4.961 | 1
In-House | Z | 934 | 0 | 2.435 | 0 | 0 | 2
In-House | Z | 939 | 0 | 0.005 | 0 | 0 | 1
In-House | Z | 941 | 0 | 0 | 0 | 3.943 | 1
In-House | Z | 946 | 0 | 97.301 | 0 | 0 | 13
In-House | Z | 957 | 0 | 2.987 | 0 | 0 | 1
In-House SUMMARY
Total Release Balance |  |  | 0 | 0
Under Production |  |  |  | 1536.815
Total Yard | [5 empty] | 7050.533
Operation Weight |  |  |  | 8587.348
Grand Total Weight |  |  |  | 8587.348
Out-Vendor | A | 824 | 0 | 5.72 | 18.417 | 53.469 | 9
Out-Vendor | A | 848 | 0 | 35.76 | 2.305 | 0.011 | 2
Out-Vendor | A | 888 | 0 | 6.579 | 2.858 | 29.321 | 5
Out-Vendor | A | 893 | 0 | 0.702 | 0 | 2.806 | 1
Out-Vendor | A | 903 | 0 | 24.088 | 3.618 | 287.275 | 6
Out-Vendor | A | 904 | 0 | 0.844 | 0.828 | 115.49 | 8
Out-Vendor | A | 906 | 0 | 16.325 | 6.801 | 15.482 | 8
Out-Vendor | A | 908 | 0 | 7.783 | 6.601 | 22.467 | 16
Out-Vendor | A | 909 | 0 | 17.626 | 2.968 | 12.488 | 5
Out-Vendor | A | 917 | 0 | 0.539 | 0.06 | 0 | 1
Out-Vendor | A | 932 | 0 | 22.98 | 0 | 0 | 12
Out-Vendor | A | 936 | 0 | 70.533 | 0 | 0 | 10
Out-Vendor | A | 939 | 0 | 2.029 | 0 | 0 | 1
Out-Vendor | A | 944 | 0 | 0.039 | 0.369 | 28.455 | 1
Out-Vendor | A | 945 | 0 | 0 | 0.207 | 1.401 | 2
Out-Vendor | A | 947 | 0 | 41.368 | 0 | 0 | 2
Out-Vendor | A | 952 | 0 | 18.657 | 0 | 0 | 2
Out-Vendor | B | 839 | 0 | 5.461 | 0 | 0.023 | 3
Out-Vendor | B | 886 | 0 | 0 | 0.005 | 10.92 | 1
Out-Vendor | B | 906 | 0 | 3.752 | 0.466 | 1.403 | 2
Out-Vendor | B | 917 | 0 | 44.754 | 14.581 | 2.704 | 5
Out-Vendor | B | 918 | 0 | 0.013 | 0.353 | 429.636 | 5
Out-Vendor | B | 920 | 0 | 0.051 | 0.402 | 69.791 | 6
Out-Vendor | B | 922 | 0 | 86.592 | 24.524 | 239.794 | 9
Out-Vendor | B | 923 | 0 | 39.925 | 10.941 | 129.586 | 17
Out-Vendor | B | 926 | 0 | 34.02 | 34.311 | 18.216 | 5
Out-Vendor | B | 928 | 0 | 98.593 | 51.718 | 441.104 | 18
Out-Vendor | B | 931 | 0 | 7.94 | 7.923 | 392.063 | 4
Out-Vendor | B | 933 | 0 | 36.742 | 45.711 | 301.649 | 3
Out-Vendor | B | 934 | 0 | 63.068 | 8.964 | 11.208 | 7
Out-Vendor | B | 935 | 0 | 1.666 | 0 | 0 | 1
Out-Vendor | C | 886 | 0 | 1.944 | 1.49 | 3.014 | 3
Out-Vendor | C | 911 | 0 | 55.652 | 11.238 | 23.408 | 2
Out-Vendor | C | 920 | 0 | 34.569 | 19.379 | 3.324 | 14
Out-Vendor | C | 922 | 0 | 54.08 | 18.492 | 21.187 | 6
Out-Vendor | C | 933 | 0 | 6.836 | 1.203 | 3.261 | 2
Out-Vendor | D | 920 | 0 | 1.22 | 1.475 | 0.575 | 3
Out-Vendor | Z | 821 | 0 | 7.449 | 0 | 77.442 | 1
Out-Vendor | Z | 824 | 0 | 0.24 | 0.512 | 55.021 | 3
Out-Vendor | Z | 862 | 0 | 17.19 | 12.412 | 42.783 | 4
Out-Vendor | Z | 866 | 0 | 2.873 | 0.607 | 43.415 | 6
Out-Vendor | Z | 870 | 0 | 8.021 | 6.108 | 5.946 | 1
Out-Vendor | Z | 885 | 0 | 5.452 | 3.212 | 47.206 | 4
Out-Vendor | Z | 888 | 0 | 1.505 | 0.006 | 0.799 | 2
Out-Vendor | Z | 890 | 0 | 54.337 | 2.128 | 322.442 | 21
Out-Vendor | Z | 893 | 0 | 37.573 | 0.034 | 67.268 | 6
Out-Vendor | Z | 899 | 0 | 0 | 0 | 254.817 | 27
Out-Vendor | Z | 901 | 0 | 0 | 0 | 11.293 | 1
Out-Vendor | Z | 905 | 0 | 0 | 0 | 39.165 | 1
Out-Vendor | Z | 907 | 0 | 96.875 | 18.355 | 414.763 | 11
Out-Vendor | Z | 908 | 0 | 1.65 | 1.511 | 17.226 | 4
Out-Vendor | Z | 909 | 0 | 10.315 | 0 | 0.27 | 2
Out-Vendor | Z | 914 | 0 | 0.326 | 0.148 | 22.586 | 4
Out-Vendor | Z | 920 | 0 | 0 | 0 | 7.149 | 1
Out-Vendor | Z | 921 | 0 | 1.727 | 11.77 | 745.848 | 6
Out-Vendor | Z | 924 | 0 | 0 | 0 | 4.648 | 3
Out-Vendor | Z | 933 | 0 | 0 | 0 | 14.264 | 2
Out-Vendor | Z | 934 | 0 | 2.399 | 0 | 0 | 1
Out-Vendor SUMMARY
Total Release Balance |  |  | 0 | 0
Under Production |  |  |  | 1451.393
Total Yard | [5 empty] | 4865.882
Operation Weight |  |  |  | 6317.275
Grand Total Weight |  |  |  | 6317.275
TOTAL |  |  | 0 | 2225.14 | 763.068 | 11916.415

## D - Dispatch Clearance
Side | MFC Batch | Project | Rel. Bal. | Fab | Galva | Yard | Structures
In-House | A | 824 | 0 | 5.72 | 18.417 | 53.469 | 9
In-House | A | 893 | 0 | 0.702 | 0 | 2.806 | 1
In-House | A | 903 | 0 | 26.249 | 4.075 | 327.644 | 10
In-House | A | 904 | 0 | 2.895 | 7.014 | 380.182 | 15
In-House | A | 908 | 0 | 0.052 | 0.015 | 6.243 | 2
In-House | A | 909 | 0 | 5.007 | 0.392 | 9.695 | 2
In-House | A | 928 | 0 | 0.408 | 0.535 | 2.183 | 1
In-House | A | 931 | 0 | 0.016 | 1.741 | 16.174 | 3
In-House | A | 935 | 220.449 | 570.427 | 86.705 | 258.646 | 19
In-House | B | 886 | 0 | 0.016 | 0.156 | 210.56 | 8
In-House | B | 918 | 0 | 0.07 | 0.431 | 494.037 | 14
In-House | B | 920 | 0 | 0.146 | 0.402 | 136.274 | 10
In-House | B | 922 | 0 | 86.592 | 24.524 | 239.794 | 9
In-House | B | 928 | 0.013 | 80.999 | 41.613 | 446.075 | 12
In-House | B | 931 | 0 | 9.096 | 8.721 | 429.131 | 9
In-House | B | 933 | 9.782 | 67.335 | 85.949 | 716.479 | 4
In-House | B | 935 | 12.385 | 53.444 | 14.933 | 7.303 | 6
In-House | C | 935 | 11.251 | 18.107 | 4.624 | 0 | 5
In-House | Z | 821 | 0 | 10.29 | 0 | 193.914 | 4
In-House | Z | 824 | 0 | 4 | 0.246 | 86.269 | 3
In-House | Z | 848 | 0 | 0 | 0 | 141.041 | 5
In-House | Z | 866 | 0 | 2.046 | 0.678 | 50.536 | 12
In-House | Z | 870 | 0 | 0 | 0 | 33.488 | 1
In-House | Z | 884 | 0 | 0.369 | 1.298 | 255.009 | 7
In-House | Z | 885 | 0.089 | 3.698 | 3.007 | 486.621 | 19
In-House | Z | 888 | 0.135 | 0.003 | 0.006 | 181.838 | 7
In-House | Z | 890 | 3.345 | 0 | 0 | 19.719 | 2
In-House | Z | 893 | 0 | 28.691 | 0 | 102.57 | 11
In-House | Z | 899 | 0 | 0 | 0 | 148.075 | 12
In-House | Z | 901 | 0 | 0 | 0 | 56.61 | 4
In-House | Z | 903 | 0 | 4.283 | 1.724 | 70.874 | 6
In-House | Z | 907 | 0 | 98.224 | 18.485 | 417.007 | 12
In-House | Z | 908 | 112.249 | 0.128 | 0.624 | 179.415 | 7
In-House | Z | 909 | 0 | 0 | 0.052 | 56.753 | 13
In-House | Z | 914 | 0 | 0.326 | 0.216 | 29.706 | 8
In-House | Z | 920 | 0 | 0 | 0 | 73.309 | 7
In-House | Z | 921 | 0 | 2.782 | 18.47 | 1144.031 | 20
In-House | Z | 924 | 0 | 0 | 0 | 7.448 | 3
In-House | Z | 933 | 0 | 0 | 0 | 4.961 | 1
In-House | Z | 941 | 0 | 0 | 0 | 3.943 | 1
In-House SUMMARY
Total Release Balance |  |  | 369.698 | 369.698
Under Production |  |  |  | 1427.174
Total Yard | [5 empty] | 7479.832
Operation Weight |  |  |  | 8907.006
Grand Total Weight |  |  |  | 9276.704
Out-Vendor | A | 824 | 0 | 5.72 | 18.417 | 53.469 | 9
Out-Vendor | A | 888 | 0 | 6.579 | 2.858 | 29.321 | 5
Out-Vendor | A | 893 | 0 | 0.702 | 0 | 2.806 | 1
Out-Vendor | A | 903 | 0 | 24.088 | 3.618 | 287.275 | 6
Out-Vendor | A | 904 | 0 | 0.844 | 0.828 | 115.49 | 8
Out-Vendor | A | 908 | 0 | 0.052 | 0.014 | 2.225 | 1
Out-Vendor | A | 909 | 0 | 5.007 | 0.392 | 9.695 | 2
Out-Vendor | A | 935 | 220.449 | 570.427 | 86.705 | 258.646 | 19
Out-Vendor | B | 886 | 0 | 0 | 0.005 | 10.92 | 1
Out-Vendor | B | 918 | 0 | 0.013 | 0.353 | 429.636 | 5
Out-Vendor | B | 920 | 0 | 0.051 | 0.402 | 69.791 | 6
Out-Vendor | B | 922 | 0 | 86.592 | 24.524 | 239.794 | 9
Out-Vendor | B | 928 | 0.013 | 80.999 | 41.613 | 446.075 | 12
Out-Vendor | B | 931 | 0 | 7.94 | 7.923 | 392.063 | 4
Out-Vendor | B | 933 | 9.782 | 67.335 | 85.949 | 716.479 | 4
Out-Vendor | B | 935 | 14.219 | 56.389 | 14.933 | 7.303 | 8
Out-Vendor | C | 935 | 11.251 | 18.107 | 4.624 | 0 | 5
Out-Vendor | Z | 821 | 0 | 7.449 | 0 | 77.442 | 1
Out-Vendor | Z | 824 | 0 | 0.091 | 0.121 | 54.823 | 1
Out-Vendor | Z | 866 | 0 | 2.873 | 0.607 | 43.415 | 6
Out-Vendor | Z | 885 | 0 | 3.184 | 2.108 | 46.803 | 1
Out-Vendor | Z | 888 | 0 | 0.003 | 0.006 | 0.799 | 1
Out-Vendor | Z | 890 | 0 | 0 | 0 | 311.741 | 8
Out-Vendor | Z | 893 | 0 | 30.134 | 0 | 66.72 | 2
Out-Vendor | Z | 899 | 0 | 0 | 0 | 254.817 | 27
Out-Vendor | Z | 901 | 0 | 0 | 0 | 11.293 | 1
Out-Vendor | Z | 905 | 0 | 0 | 0 | 39.165 | 1
Out-Vendor | Z | 907 | 0 | 96.875 | 18.355 | 414.763 | 11
Out-Vendor | Z | 908 | 0 | 0.483 | 0.476 | 16.539 | 2
Out-Vendor | Z | 914 | 0 | 0.326 | 0.148 | 22.586 | 4
Out-Vendor | Z | 920 | 0 | 0 | 0 | 7.149 | 1
Out-Vendor | Z | 921 | 0 | 1.727 | 11.77 | 745.848 | 6
Out-Vendor | Z | 924 | 0 | 0 | 0 | 4.648 | 3
Out-Vendor | Z | 933 | 0 | 0 | 0 | 14.264 | 2
Out-Vendor SUMMARY
Total Release Balance |  |  | 255.714 | 255.714
Under Production |  |  |  | 1400.739
Total Yard | [5 empty] | 5203.803
Operation Weight |  |  |  | 6604.542
Grand Total Weight |  |  |  | 6860.256
TOTAL |  |  | 625.412 | 2156.111 | 671.802 | 12683.635

## E - Ready Not Dispatched
Side | Project | MFC Batch | Release Balance (MT) | Fab+Galva (MT) | Yard (MT) | Structures
In-House | 941 | B | 0 | 251.795 | 108.901 | 10
TOTAL |  |  | 0 | 251.795 | 108.901