## Sheet1
Sorting
7
Activity
8
Contractor | with subtotal
2
Section
1
Mark No.
9 | highlight for over 15 days
Last Op Date

## Summary
7 | 2 | 1 | 3 | 4 | 5 | 6 | 8 | 9 | 10 | Delete | Delete | Delete | Delete | Delete | Delete | Delete | Delete | Delete | Delete | Delete | Delete | Delete
Activity | Section | Mark No. | Length | Width | Balance Qty | Balance Wt (kg) | Contractor | Last Op Date | Ageing (days) | Cumulative Target (days) | Overrun (days) | Consumed % | Days to Target | Lifecycle Status | Stalled | Velocity Status | Days / Stage | ETA (days) | ETA Gap (days) | Trend | Section Type | Hole Operation
C | PLATE 8 MM MS | 933 \ 2AF10M \ 328P | 280 | 50 | 8 | 7.032 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 6 MM MS | 933 \ 2AF10M \ 345 | 281 | 60 | 32 | 25.408 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 10 MM MS | 933 \ 2AF10M \ 369 | 225 | 200 | 8 | 28.264 | METAL PARK (UNIT-II - JAIN PLATE) |  | 99 | 15 | 84 | 660 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 10 MM MS | 933 \ 2AF10M \ 378 | 335 | 200 | 8 | 42.08 | METAL PARK (UNIT-II - JAIN PLATE) |  | 99 | 15 | 84 | 660 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 10 MM MS | 933 \ 2AF10M \ 380 | 290 | 50 | 12 | 13.656 | METAL PARK (UNIT-II - JAIN PLATE) |  | 99 | 15 | 84 | 660 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 10 MM MS | 933 \ 2AF10M \ 385 | 225 | 200 | 8 | 28.264 | METAL PARK (UNIT-II - JAIN PLATE) |  | 99 | 15 | 84 | 660 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | 45X45X5 MS | 933 \ 2AF10M \ 386 | 2783 |  | 1 | 9.434 | SRIJAN ENTERPRISES (UNIT-II) |  | 41 | 15 | 26 | 273 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | PLATE 8 MM MS | 933 \ 2AF3 \ 208P | 170 | 50 | 44 | 23.496 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 12 MM MS | 933 \ 2AF3 \ 247 | 130 | 50 | 44 | 26.928 | JAIN ASSOCIATES |  | 113 | 15 | 98 | 753 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 20 MM MS | 933 \ 2AF3 \ 286P | 56 | 136 | 44 | 52.624 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 74 | 15 | 59 | 493 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 20 MM MS | 933 \ 2AF3 \ 287P | 96 | 56 | 44 | 37.136 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 74 | 15 | 59 | 493 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 6 MM MS | 933 \ 2AF3 \ 3 | 422 | 165 | 11 | 36.08 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | A 75X75X8 MS | 933 \ 2AF3 \ 32 | 162 |  | 264 | 384.912 | CNC APM 1616 |  | 45 | 15 | 30 | 300 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | PLATE 8 MM MS | 933 \ 2AF3 \ 328P | 280 | 50 | 352 | 309.408 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 20 MM MS | 933 \ 2AF3 \ 329P | 56 | 96 | 44 | 37.136 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 74 | 15 | 59 | 493 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 6 MM MS | 933 \ 2AF3 \ 330 | 100 | 170 | 66 | 52.866 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 6 MM MS | 933 \ 2AF3 \ 345 | 60 | 281 | 176 | 139.744 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 6 MM MS | 933 \ 2AF3 \ 4 | 175 | 119 | 22 | 21.582 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 12 MM MS | 933 \ 2AF3 \ 5 | 500 | 140 | 11 | 72.534 | JAIN ASSOCIATES |  | 113 | 15 | 98 | 753 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 8 MM MS | 933 \ 2AF5M \ 328P | 280 | 50 | 8 | 7.032 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | 45X45X5 MS | 933 \ 2AF5M \ 339 | 2430 |  | 3 | 24.714 | SRIJAN ENTERPRISES (UNIT-II) |  | 41 | 15 | 26 | 273 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | 200X200X20 MS | 933 \ 2AF5M \ 341S | 5016 |  | 2 | 601.518 | CNC TADM 2532 |  | 45 | 15 | 30 | 300 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
C | PLATE 6 MM MS | 933 \ 2AF5M \ 345 | 281 | 60 | 16 | 12.704 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 12 MM MS | 933 \ 2AF5M \ 357 | 410 | 211 | 4 | 32.596 | JAIN ASSOCIATES |  | 113 | 15 | 98 | 753 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 10 MM MS | 933 \ 2AF5M \ 369 | 225 | 200 | 8 | 28.264 | METAL PARK (UNIT-II - JAIN PLATE) |  | 99 | 15 | 84 | 660 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 6 MM MS | 933 \ 2DF-5 \ 12 | 189 | 129 | 16 | 18.368 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | 130X130X12 MS | 933 \ 2DF-5 \ 121 | 436 |  | 16 | 163.584 | SRIJAN ENTERPRISES |  | 91 | 15 | 76 | 607 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | PLATE 6 MM MS | 933 \ 2DF-5 \ 13 | 145 | 115 | 16 | 12.56 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 2 MM MS | 933 \ 2DF-5 \ 166P | 200 | 115 | 64 | 23.104 | SRIJAN ENTERPRISES (UNIT-II) |  | 74 | 15 | 59 | 493 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 20 MM MS | 933 \ 2DF-5 \ 180 | 105 | 60 | 8 | 7.912 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 74 | 15 | 59 | 493 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 24 MM MS | 933 \ 2DF-5 \ 217 | 122 | 60 | 16 | 22.064 | METAL PARK (UNIT-II - JAIN PLATE) |  | 6 | 15 | -9 | 40 | 9 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 20 MM MS | 933 \ 2DF-5 \ 218P | 186 | 56 | 16 | 26.16 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 74 | 15 | 59 | 493 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 20 MM MS | 933 \ 2DF-5 \ 225P | 136 | 56 | 16 | 19.136 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 74 | 15 | 59 | 493 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 24 MM MS | 933 \ 2DF-5 \ 245 | 121 | 60 | 48 | 65.664 | METAL PARK (UNIT-II - JAIN PLATE) |  | 6 | 15 | -9 | 40 | 9 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 24 MM MS | 933 \ 2DF-5 \ 246 | 121 | 60 | 64 | 87.552 | METAL PARK (UNIT-II - JAIN PLATE) |  | 6 | 15 | -9 | 40 | 9 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 8 MM MS | 933 \ 2DF-5 \ 271 | 150 | 50 | 96 | 45.216 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 8 MM MS | 933 \ 2DF-5 \ 291 | 131 | 50 | 288 | 118.368 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 6 MM MS | 933 \ 2DF-5 \ 3 | 169 | 120 | 8 | 7.64 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | A 75X75X8 MS | 933 \ 2DF-5 \ 32 | 300 |  | 48 | 129.6 | CNC APM 1616 |  | 45 | 15 | 30 | 300 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | 200X200X20 MS | 933 \ 2DF-5 \ 336 | 402 |  | 20 | 482.08 | CNC TADM 2532 |  | 45 | 15 | 30 | 300 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
C | PLATE 8 MM MS | 933 \ 2DF-5 \ 339 | 131 | 50 | 96 | 39.456 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 6 MM MS | 933 \ 2DF-5 \ 4 | 429 | 148 | 4 | 11.96 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 6 MM MS | 933 \ 2DF3 \ 12 | 189 | 129 | 44 | 50.512 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 6 MM MS | 933 \ 2DF3 \ 13 | 145 | 115 | 44 | 34.54 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 2 MM MS | 933 \ 2DF3 \ 166P | 200 | 115 | 176 | 63.536 | SRIJAN ENTERPRISES (UNIT-II) |  | 74 | 15 | 59 | 493 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 20 MM MS | 933 \ 2DF3 \ 180 | 105 | 60 | 22 | 21.758 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 74 | 15 | 59 | 493 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 24 MM MS | 933 \ 2DF3 \ 217 | 122 | 60 | 44 | 60.676 | METAL PARK (UNIT-II - JAIN PLATE) |  | 6 | 15 | -9 | 40 | 9 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 20 MM MS | 933 \ 2DF3 \ 218P | 186 | 56 | 44 | 71.94 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 74 | 15 | 59 | 493 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 20 MM MS | 933 \ 2DF3 \ 225P | 136 | 56 | 44 | 52.624 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 74 | 15 | 59 | 493 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 24 MM MS | 933 \ 2DF3 \ 245 | 121 | 60 | 132 | 180.576 | METAL PARK (UNIT-II - JAIN PLATE) |  | 6 | 15 | -9 | 40 | 9 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 24 MM MS | 933 \ 2DF3 \ 246 | 121 | 60 | 176 | 240.768 | METAL PARK (UNIT-II - JAIN PLATE) |  | 6 | 15 | -9 | 40 | 9 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 8 MM MS | 933 \ 2DF3 \ 271 | 150 | 50 | 264 | 124.344 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 8 MM MS | 933 \ 2DF3 \ 291 | 131 | 50 | 792 | 325.512 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 6 MM MS | 933 \ 2DF3 \ 3 | 169 | 120 | 22 | 21.01 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | A 100X100X10 MS | 933 \ 2DF3 \ 321 | 3075 |  | 88 | 4069.824 | UNIT-I |  | 4 | 15 | -11 | 27 | 11 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | A 100X100X10 MS | 933 \ 2DF3 \ 322 | 4316 |  | 44 | 2856.172 | UNIT-I |  | 4 | 15 | -11 | 27 | 11 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | A 100X100X10 MS | 933 \ 2DF3 \ 322A | 4316 |  | 44 | 2856.172 | UNIT-I |  | 4 | 15 | -11 | 27 | 11 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | 100X100X8 MS | 933 \ 2DF3 \ 330 | 348 |  | 88 | 373.032 | CNC APM 1010 |  | 23 | 15 | 8 | 153 | 0 | Breach 2 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | PLATE 8 MM MS | 933 \ 2DF3 \ 331 | 308 | 60 | 176 | 204.336 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | 200X200X20 MS | 933 \ 2DF3 \ 336 | 402 |  | 54 | 1301.616 | CNC TADM 2532 |  | 45 | 15 | 30 | 300 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
C | PLATE 8 MM MS | 933 \ 2DF3 \ 339 | 131 | 50 | 264 | 108.504 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 6 MM MS | 933 \ 2DF3 \ 4 | 429 | 148 | 11 | 32.89 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | 65X65X6 MS | 933 \ 2DF5M \ 176 | 425 |  | 9 | 22.608 | SRIJAN ENTERPRISES (UNIT-II) |  | 84 | 15 | 69 | 560 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | 100X100X8 MS | 933 \ 2DF5M \ 330 | 348 |  | 8 | 33.912 | CNC APM 1010 |  | 23 | 15 | 8 | 153 | 0 | Breach 2 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | PLATE 8 MM MS | 933 \ 2DF5M \ 331 | 60 | 308 | 16 | 18.576 | METAL PARK (UNIT-II - JAIN ASSOCIATES) |  | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | 50X50X5 MS | 933 \ IS-933 \ 2AF1 \ 07 | 2184 |  | 28 | 231.756 | SRIJAN ENTERPRISES |  | 17 | 15 | 2 | 113 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | 50X50X5 MS | 933 \ IS-933 \ 2AF1 \ 08 | 2142 |  | 28 | 227.304 | SRIJAN ENTERPRISES |  | 17 | 15 | 2 | 113 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | PLATE 16 MM MS | 933 \ SC-933 \ 2AF3 \ 267 | 145 | 472 | 1 | 8.596 | METAL PARK (UNIT-II - JAIN PLATE) |  | 10 | 15 | -5 | 67 | 5 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | 50X50X5 MS | 933 \ SC-933 \ 2AF3 \ 308 | 1082 |  | 1 | 4.101 | DASHMESH ENTERPRISES (UNIT-II) |  | 10 | 15 | -5 | 67 | 5 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | 75X75X8 MS | 933 \ SC-933 \ 2AF5M \ 353A | 2991 |  | 1 | 26.919 | DASHMESH ENTERPRISES (UNIT-II) |  | 10 | 15 | -5 | 67 | 5 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | 100X100X10 MS | 933 \ SC-933 \ 2DF \ 5\123 | 2768 |  | 1 | 41.631 | DASHMESH ENTERPRISES (UNIT-II) |  | 10 | 15 | -5 | 67 | 5 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | 200X200X16 MS | 933 \ SC-933 \ 2DF \ 5\205 | 472 |  | 1 | 22.906 | CNC APM 2020 |  | 16 | 15 | 1 | 107 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
C | PLATE 10 MM MS | 933 \ SC-933 \ 2DF \ 5\232 | 457 | 225 | 1 | 8.072 | METAL PARK (UNIT-II - JAIN PLATE) |  | 10 | 15 | -5 | 67 | 5 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | 150X150X12 MS | 933 \ SC-933 \ 2DF3 \ 164L | 390 |  | 1 | 10.643 | DASHMESH ENTERPRISES (UNIT-II) |  | 10 | 15 | -5 | 67 | 5 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 200X200X20 MS | 933 \ 2AF10M \ 341 | 5016 |  | 2 | 601.518 | CNC TADM 2532 |  | 38 | 29 | 9 | 131 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 200X200X20 MS | 933 \ 2AF10M \ 341S | 5016 |  | 2 | 601.518 | CNC TADM 2532 |  | 38 | 29 | 9 | 131 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 65X65X6 MS | 933 \ 2AF10M \ 344 | 316 |  | 16 | 29.888 | SRIJAN ENTERPRISES (UNIT-II) |  | 30 | 29 | 1 | 103 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 75X75X8 MS | 933 \ 2AF10M \ 352 | 4213 |  | 4 | 151.668 | SRIJAN ENTERPRISES (UNIT-II) |  | 30 | 29 | 1 | 103 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 75X75X8 MS | 933 \ 2AF10M \ 352A | 4213 |  | 4 | 151.668 | SRIJAN ENTERPRISES (UNIT-II) |  | 30 | 29 | 1 | 103 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 75X75X8 MS | 933 \ 2AF10M \ 353 | 2991 |  | 4 | 107.676 | SRIJAN ENTERPRISES (UNIT-II) |  | 30 | 29 | 1 | 103 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 75X75X8 MS | 933 \ 2AF10M \ 353A | 2991 |  | 4 | 107.676 | SRIJAN ENTERPRISES (UNIT-II) |  | 30 | 29 | 1 | 103 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 65X65X6 MS | 933 \ 2AF10M \ 354 | 1331 |  | 8 | 62.928 | SRIJAN ENTERPRISES (UNIT-II) |  | 73 | 29 | 44 | 252 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 65X65X6 MS | 933 \ 2AF10M \ 356 | 2473 |  | 8 | 116.92 | SRIJAN ENTERPRISES (UNIT-II) |  | 73 | 29 | 44 | 252 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 65X65X6 MS | 933 \ 2AF10M \ 358 | 1716 |  | 8 | 81.136 | SRIJAN ENTERPRISES (UNIT-II) |  | 73 | 29 | 44 | 252 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 200X200X20 MS | 933 \ 2AF10M \ 370 | 4939 |  | 2 | 592.284 | CNC TADM 2532 |  | 38 | 29 | 9 | 131 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 200X200X20 MS | 933 \ 2AF10M \ 370S | 4939 |  | 2 | 592.284 | CNC TADM 2532 |  | 38 | 29 | 9 | 131 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 75X75X8 MS | 933 \ 2AF10M \ 371 | 4458 |  | 4 | 160.488 | SRIJAN ENTERPRISES (UNIT-II) |  | 30 | 29 | 1 | 103 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 75X75X8 MS | 933 \ 2AF10M \ 371A | 4458 |  | 4 | 160.488 | SRIJAN ENTERPRISES (UNIT-II) |  | 30 | 29 | 1 | 103 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 75X75X8 MS | 933 \ 2AF10M \ 372 | 3215 |  | 4 | 115.74 | SRIJAN ENTERPRISES (UNIT-II) |  | 30 | 29 | 1 | 103 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 75X75X8 MS | 933 \ 2AF10M \ 372A | 3215 |  | 4 | 115.74 | SRIJAN ENTERPRISES (UNIT-II) |  | 30 | 29 | 1 | 103 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 65X65X6 MS | 933 \ 2AF10M \ 373 | 1508 |  | 8 | 71.296 | SRIJAN ENTERPRISES (UNIT-II) |  | 73 | 29 | 44 | 252 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 65X65X6 MS | 933 \ 2AF10M \ 376 | 1821 |  | 8 | 86.096 | SRIJAN ENTERPRISES (UNIT-II) |  | 73 | 29 | 44 | 252 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | PLATE 16 MM MS | 933 \ 2AF3 \ 31 | 500 | 305 | 132 | 2528.328 | METAL PARK (UNIT-II - JAIN PLATE) |  | 72 | 29 | 43 | 248 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
RFI | 65X65X6 MS | 933 \ 2AF3 \ 344 | 316 |  | 88 | 164.384 | SRIJAN ENTERPRISES (UNIT-II) |  | 30 | 29 | 1 | 103 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 200X200X20 MS | 933 \ 2AF5M \ 341 | 5016 |  | 2 | 601.518 | CNC TADM 2532 |  | 43 | 29 | 14 | 148 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 65X65X6 MS | 933 \ 2AF5M \ 344 | 316 |  | 24 | 44.832 | SRIJAN ENTERPRISES (UNIT-II) |  | 30 | 29 | 1 | 103 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 75X75X8 MS | 933 \ 2AF5M \ 353A | 2991 |  | 4 | 107.676 | CNC APM 1010 |  | 48 | 29 | 19 | 166 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 65X65X6 MS | 933 \ 2AF5M \ 354 | 1331 |  | 6 | 47.196 | SRIJAN ENTERPRISES (UNIT-II) |  | 73 | 29 | 44 | 252 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 100X100X10 MS | 933 \ 2DF-5 \ 101S | 5379 |  | 4 | 323.6 | CNC APM 1616 |  | 86 | 29 | 57 | 297 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 130X130X12 MS | 933 \ 2DF-5 \ 166 | 416 |  | 64 | 624.32 | SRIJAN ENTERPRISES |  | 35 | 29 | 6 | 121 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 65X65X6 MS | 933 \ 2DF-5 \ 176 | 425 |  | 468 | 1175.616 | SRIJAN ENTERPRISES (UNIT-II) |  | 60 | 29 | 31 | 207 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 200X200X16 MS | 933 \ 2DF-5 \ 204X | 472 |  | 16 | 366.496 | CNC APM 2020 |  | 55 | 29 | 26 | 190 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | PLATE 10 MM MS | 933 \ 2DF-5 \ 22 | 285 | 125 | 8 | 22.376 | SRIJAN ENTERPRISES (UNIT-II) |  | 65 | 29 | 36 | 224 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
RFI | A 50X50X6 MS | 933 \ 2DF-5 \ 23 | 360 |  | 48 | 77.568 | DASHMESH ENTERPRISES (UNIT-II) |  | 88 | 29 | 59 | 303 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 200X200X16 MS | 933 \ 2DF-5 \ 248L | 162 |  | 8 | 62.896 | CNC APM 2020 |  | 54 | 29 | 25 | 186 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 200X200X16 MS | 933 \ 2DF-5 \ 248R | 162 |  | 8 | 62.896 | CNC APM 2020 |  | 54 | 29 | 25 | 186 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 200X200X16 MS | 933 \ 2DF-5 \ 249L | 162 |  | 8 | 62.896 | CNC APM 2020 |  | 54 | 29 | 25 | 186 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 200X200X16 MS | 933 \ 2DF-5 \ 249R | 162 |  | 8 | 62.896 | CNC APM 2020 |  | 54 | 29 | 25 | 186 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | PLATE 10 MM MS | 933 \ 2DF-5 \ 293 | 135 | 136 | 96 | 138.336 | SRIJAN ENTERPRISES (UNIT-II) |  | 65 | 29 | 36 | 224 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
RFI | PLATE 16 MM MS | 933 \ 2DF-5 \ 31 | 480 | 230 | 48 | 665.568 | METAL PARK (UNIT-II - JAIN PLATE) |  | 65 | 29 | 36 | 224 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
RFI | 110X110X8 MS | 933 \ 2DF-5 \ 328 | 378 |  | 32 | 162.08 | CNC APM 2020 (A) |  | 73 | 29 | 44 | 252 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 200X200X20 MS | 933 \ 2DF-5 \ 336 | 402 |  | 12 | 289.248 | CNC TADM 2532 |  | 38 | 29 | 9 | 131 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 45X45X5 MS | 933 \ 2DF-5 \ 340 | 2360 |  | 4 | 32 | SRIJAN ENTERPRISES (UNIT-II) |  | 27 | 29 | -2 | 93 | 2 | Pre-warning 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | A 50X50X6 MS | 933 \ 2DF-5 \ 82 | 365 |  | 48 | 78.672 | DASHMESH ENTERPRISES (UNIT-II) |  | 88 | 29 | 59 | 303 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | A 50X50X6 MS | 933 \ 2DF-5 \ 84 | 682 |  | 32 | 97.984 | DASHMESH ENTERPRISES (UNIT-II) |  | 88 | 29 | 59 | 303 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | A 50X50X6 MS | 933 \ 2DF-5 \ 84X | 681 |  | 16 | 48.928 | DASHMESH ENTERPRISES (UNIT-II) |  | 88 | 29 | 59 | 303 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 50X50X6 MS | 933 \ 2DF-5 \ 91AX | 3221 |  | 4 | 57.848 | SRIJAN ENTERPRISES (UNIT-II) |  | 39 | 29 | 10 | 134 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 50X50X6 MS | 933 \ 2DF-5 \ 91X | 3221 |  | 4 | 57.848 | SRIJAN ENTERPRISES (UNIT-II) |  | 39 | 29 | 10 | 134 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 130X130X12 MS | 933 \ 2DF3 \ 166 | 416 |  | 176 | 1716.88 | CNC APM 2020 (A) |  | 35 | 29 | 6 | 121 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 65X65X6 MS | 933 \ 2DF3 \ 176 | 425 |  | 1386 | 3481.632 | SRIJAN ENTERPRISES (UNIT-II) |  | 60 | 29 | 31 | 207 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | A 50X50X6 MS | 933 \ 2DF3 \ 23 | 360 |  | 132 | 213.312 | DASHMESH ENTERPRISES (UNIT-II) |  | 88 | 29 | 59 | 303 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | PLATE 16 MM MS | 933 \ 2DF3 \ 31 | 480 | 230 | 132 | 1830.312 | METAL PARK (UNIT-II - JAIN PLATE) |  | 77 | 29 | 48 | 266 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
RFI | A 75X75X8 MS | 933 \ 2DF3 \ 32 | 300 |  | 60 | 162 | CNC APM 1616 |  | 25 | 29 | -4 | 86 | 4 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | A 75X75X8 MS | 933 \ 2DF3 \ 32 | 300 |  | 40 | 108 | CNC APM 1616 |  | 44 | 29 | 15 | 152 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | A 75X75X8 MS | 933 \ 2DF3 \ 32 | 300 |  | 32 | 86.4 | CNC APM 1616 |  | 32 | 29 | 3 | 110 | 0 | Breach 2 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 200X200X20 MS | 933 \ 2DF3 \ 336 | 402 |  | 14 | 337.456 | CNC TADM 2532 |  | 20 | 29 | -9 | 69 | 9 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 200X200X20 MS | 933 \ 2DF3 \ 336 | 402 |  | 20 | 482.08 | CNC TADM 2532 |  | 21 | 29 | -8 | 72 | 8 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 45X45X5 MS | 933 \ 2DF3 \ 340 | 2360 |  | 11 | 88 | SRIJAN ENTERPRISES (UNIT-II) |  | 27 | 29 | -2 | 93 | 2 | Pre-warning 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | A 50X50X6 MS | 933 \ 2DF3 \ 82 | 365 |  | 132 | 216.348 | DASHMESH ENTERPRISES (UNIT-II) |  | 88 | 29 | 59 | 303 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | A 50X50X6 MS | 933 \ 2DF3 \ 84X | 681 |  | 44 | 134.552 | DASHMESH ENTERPRISES (UNIT-II) |  | 88 | 29 | 59 | 303 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | A 50X50X6 MS | 933 \ 2DF3 \ 86X | 997 |  | 44 | 196.988 | DASHMESH ENTERPRISES (UNIT-II) |  | 88 | 29 | 59 | 303 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 200X200X16 MS | 933 \ 2DF5M \ 204 | 472 |  | 8 | 183.248 | CNC APM 2020 |  | 54 | 29 | 25 | 186 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 200X200X16 MS | 933 \ 2DF5M \ 205 | 472 |  | 8 | 183.248 | CNC APM 2020 |  | 54 | 29 | 25 | 186 | 0 | Breach 3 |  | Moving |  |  |  | Stalled | ANGLE | Drilling
RFI | 200X200X16 MS | 933 \ 2DF5M \ 290 | 136 |  | 12 | 79.2 | CNC APM 2020 |  | 53 | 29 | 24 | 183 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 200X200X16 MS | 933 \ 2DF5M \ 341 | 143 |  | 5 | 34.7 | CNC APM 2020 |  | 53 | 29 | 24 | 183 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 200X200X16 MS | 933 \ 2DF5M \ 359 | 354 |  | 8 | 137.44 | CNC APM 2020 |  | 14 | 29 | -15 | 48 | 15 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 45X45X5 MS | 933 \ 2DF5M \ 362 | 2877 |  | 1 | 9.753 | SRIJAN ENTERPRISES (UNIT-II) |  | 27 | 29 | -2 | 93 | 2 | Pre-warning 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
NH | PLATE 12 MM MS | 933 \ 2AF10M \ 357 | 410 | 211 | 4 | 32.596 | JAIN ASSOCIATES |  | 34 | 36 | -2 | 94 | 2 | Pre-warning 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
NH | 150X150X12 MS | 933 \ 2DF-5 \ 158L | 366 |  | 16 | 159.808 | UNIT-I |  | 34 | 36 | -2 | 94 | 2 | Pre-warning 3 |  | Moving |  |  |  | Unknown | ANGLE | Punching
NH | 150X150X12 MS | 933 \ 2DF-5 \ 158R | 366 |  | 16 | 159.808 | UNIT-I |  | 34 | 36 | -2 | 94 | 2 | Pre-warning 3 |  | Moving |  |  |  | Unknown | ANGLE | Punching
NH | PLATE 12 MM MS | 933 \ 2DF-5 \ 5 | 500 | 140 | 4 | 26.376 | JAIN ASSOCIATES |  | 34 | 36 | -2 | 94 | 2 | Pre-warning 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
NH | 150X150X12 MS | 933 \ 2DF3 \ 158L | 366 |  | 44 | 439.472 | UNIT-I |  | 34 | 36 | -2 | 94 | 2 | Pre-warning 3 |  | Moving |  |  |  | Unknown | ANGLE | Punching
NH | 150X150X12 MS | 933 \ 2DF3 \ 158R | 366 |  | 44 | 439.472 | UNIT-I |  | 34 | 36 | -2 | 94 | 2 | Pre-warning 3 |  | Moving |  |  |  | Unknown | ANGLE | Punching
B | A 50X50X6 MS | 933 \ 2DF-5 \ 63 | 672 |  | 16 | 48.272 | UNIT-I |  | 13 | 50 | -37 | 26 | 37 | On track |  | Moving |  |  |  | Unknown | ANGLE | Punching
B | A 50X50X6 MS | 933 \ 2DF-5 \ 86 | 998 |  | 32 | 143.392 | UNIT-I |  | 13 | 50 | -37 | 26 | 37 | On track |  | Moving |  |  |  | Unknown | ANGLE | Punching
B | A 50X50X6 MS | 933 \ 2DF-5 \ 87XL | 1257 |  | 8 | 45.152 | DASHMESH ENTERPRISES (UNIT-II) |  | 30 | 50 | -20 | 60 | 20 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
B | A 50X50X6 MS | 933 \ 2DF-5 \ 87XR | 1257 |  | 8 | 45.152 | DASHMESH ENTERPRISES (UNIT-II) |  | 30 | 50 | -20 | 60 | 20 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
B | A 50X50X6 MS | 933 \ 2DF3 \ 63 | 672 |  | 44 | 132.748 | SARLA TRADING COMAPNY (BDM) |  | 13 | 50 | -37 | 26 | 37 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
B | A 50X50X6 MS | 933 \ 2DF3 \ 65 | 985 |  | 44 | 194.612 | SARLA TRADING COMAPNY (BDM) |  | 13 | 50 | -37 | 26 | 37 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
B | A 50X50X6 MS | 933 \ 2DF3 \ 87XR | 1257 |  | 14 | 79.016 | DASHMESH ENTERPRISES (UNIT-II) |  | 30 | 50 | -20 | 60 | 20 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
B | A 50X50X6 MS | 933 \ 2DF3 \ 87YL | 1261 |  | 22 | 124.564 | DASHMESH ENTERPRISES (UNIT-II) |  | 30 | 50 | -20 | 60 | 20 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
B | A 50X50X6 MS | 933 \ 2DF3 \ 87YR | 1261 |  | 22 | 124.564 | DASHMESH ENTERPRISES (UNIT-II) |  | 30 | 50 | -20 | 60 | 20 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Q | PLATE 12 MM MS | 933 \ 2AF10M \ 379 | 419 | 199 | 4 | 31.416 | UNIT-II |  | 34 | 75 | -41 | 45 | 41 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Q | A 50X50X6 MS | 933 \ 2AF3 \ 93L | 1318 |  | 22 | 130.196 | UNIT-II |  | 34 | 75 | -41 | 45 | 41 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Q | A 50X50X6 MS | 933 \ 2AF3 \ 93R | 1318 |  | 22 | 130.196 | UNIT-II |  | 34 | 75 | -41 | 45 | 41 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Q | 100X100X10 MS | 933 \ 2DF-5 \ 101S | 5379 |  | 4 | 323.6 | UNIT-I |  | 34 | 75 | -41 | 45 | 41 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Q | PLATE 12 MM MS | 933 \ 2DF-5 \ 177 | 95 | 50 | 160 | 71.52 | UNIT-II |  | 34 | 75 | -41 | 45 | 41 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Q | 150X150X12 MS | 933 \ 2DF-5 \ 221L | 343 |  | 16 | 149.76 | UNIT-I |  | 34 | 75 | -41 | 45 | 41 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Q | 150X150X12 MS | 933 \ 2DF-5 \ 224L | 339 |  | 4 | 37.004 | UNIT-I |  | 34 | 75 | -41 | 45 | 41 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Q | 100X100X10 MS | 933 \ 2DF-5 \ 68 | 2486 |  | 8 | 299.112 | UNIT-I |  | 34 | 75 | -41 | 45 | 41 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Q | PLATE 12 MM MS | 933 \ 2DF3 \ 177 | 95 | 50 | 440 | 196.68 | UNIT-I |  | 34 | 75 | -41 | 45 | 41 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Q | 150X150X12 MS | 933 \ 2DF3 \ 224R | 339 |  | 2 | 18.502 | UNIT-I |  | 34 | 75 | -41 | 45 | 41 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Q | A 200X200X20 MS | 933 \ 2DF3 \ 267S | 2845 |  | 22 | 3752.892 | UNIT-I |  | 30 | 75 | -45 | 40 | 45 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
TS | 50X50X6 MS | 933 \ 2AF3 \ 10 | 502 |  | 44 | 99.176 | UNIT-I |  | 27 | 78 | -51 | 35 | 51 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | A 50X50X6 MS | 933 \ 2AF3 \ 23 | 360 |  | 44 | 71.104 | UNIT-I |  | 76 | 78 | -2 | 97 | 2 | Pre-warning 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | PLATE 10 MM MS | 933 \ 2AF3 \ 250 | 225 | 210 | 44 | 163.196 | UNIT-I |  | 4 | 78 | -74 | 5 | 74 | On track |  | Moving |  |  |  | Unknown | PLATE | Punching
TS | PLATE 10 MM MS | 933 \ 2AF3 \ 325 | 555 | 205 | 71 | 634.101 | UNIT-I |  | 84 | 78 | 6 | 108 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
TS | A 50X50X6 MS | 933 \ 2AF3 \ 47 | 360 |  | 44 | 71.104 | UNIT-I |  | 76 | 78 | -2 | 97 | 2 | Pre-warning 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | 50X50X6 MS | 933 \ 2AF3 \ 6 | 778 |  | 1 | 3.493 | UNIT-I |  | 27 | 78 | -51 | 35 | 51 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | A 50X50X6 MS | 933 \ 2AF3 \ 68 | 360 |  | 44 | 71.104 | UNIT-I |  | 74 | 78 | -4 | 95 | 4 | Pre-warning 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | A 50X50X6 MS | 933 \ 2AF3 \ 88 | 363 |  | 88 | 143.44 | UNIT-I |  | 76 | 78 | -2 | 97 | 2 | Pre-warning 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | 75X75X8 MS | 933 \ 2DF-5 \ 14 | 466 |  | 16 | 67.104 | UNIT-I |  | 57 | 78 | -21 | 73 | 21 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | PLATE 8 MM MS | 933 \ 2DF-5 \ 329 | 333 | 60 | 64 | 80.32 | UNIT-I |  | 4 | 78 | -74 | 5 | 74 | On track |  | Moving |  |  |  | Unknown | PLATE | Punching
TS | A 50X50X6 MS | 933 \ 2DF-5 \ 41 | 181 |  | 48 | 39.024 | UNIT-I |  | 74 | 78 | -4 | 95 | 4 | Pre-warning 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | A 50X50X6 MS | 933 \ 2DF-5 \ 87YL | 1261 |  | 8 | 45.296 | UNIT-I |  | 21 | 78 | -57 | 27 | 57 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | A 50X50X6 MS | 933 \ 2DF-5 \ 87YR | 1261 |  | 8 | 45.296 | UNIT-I |  | 21 | 78 | -57 | 27 | 57 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | PLATE 10 MM MS | 933 \ 2DF3 \ 22 | 285 | 125 | 22 | 61.534 | UNIT-I |  | 4 | 78 | -74 | 5 | 74 | On track |  | Moving |  |  |  | Unknown | PLATE | Punching
TS | PLATE 8 MM MS | 933 \ 2DF3 \ 329 | 333 | 60 | 176 | 220.88 | UNIT-I |  | 4 | 78 | -74 | 5 | 74 | On track |  | Moving |  |  |  | Unknown | PLATE | Punching
TS | A 50X50X6 MS | 933 \ 2DF3 \ 41 | 181 |  | 132 | 107.316 | UNIT-I |  | 74 | 78 | -4 | 95 | 4 | Pre-warning 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | PLATE 12 MM MS | 933 \ 2DF3 \ 5 | 500 | 140 | 11 | 72.534 | UNIT-I |  | 4 | 78 | -74 | 5 | 74 | On track |  | Moving |  |  |  | Unknown | PLATE | Punching
TS | PLATE 10 MM MS | 933 \ 2DF3 \ 81P | 314 | 140 | 66 | 227.766 | UNIT-I |  | 80 | 78 | 2 | 103 | 0 | Breach 2 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
TS | A 50X50X6 MS | 933 \ 2DF3 \ 87XL | 1257 |  | 22 | 124.168 | UNIT-I |  | 21 | 78 | -57 | 27 | 57 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | A 50X50X6 MS | 933 \ 2DF3 \ 87XR | 1257 |  | 8 | 45.152 | UNIT-I |  | 21 | 78 | -57 | 27 | 57 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | PLATE 10 MM MS | 933 \ 2DF5M \ 294 | 136 | 135 | 24 | 34.584 | UNIT-I |  | 4 | 78 | -74 | 5 | 74 | On track |  | Moving |  |  |  | Unknown | PLATE | Punching
TS | PLATE 10 MM MS | 933 \ 2DF5M \ 343 | 135 | 143 | 8 | 12.12 | UNIT-I |  | 4 | 78 | -74 | 5 | 74 | On track |  | Moving |  |  |  | Unknown | PLATE | Punching
G | 65X65X6 MS | 933 \ 2AF10M \ 375 | 2821 |  | 8 | 133.376 | DASHMESH ENTERPRISES GP-2 |  | 46 | 82 | -36 | 56 | 36 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | A 50X50X6 MS | 933 \ 2AF3 \ 110 | 680 |  | 44 | 134.332 | DASHMESH ENTERPRISES GP-2 |  | 39 | 82 | -43 | 48 | 43 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | PLATE 10 MM MS | 933 \ 2AF3 \ 127L | 243 | 527 | 22 | 221.166 | DASHMESH ENTERPRISES GP-2 |  | 26 | 82 | -56 | 32 | 56 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2AF3 \ 127R | 243 | 527 | 22 | 221.166 | DASHMESH ENTERPRISES GP-2 |  | 26 | 82 | -56 | 32 | 56 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2AF3 \ 215 | 335 | 115 | 44 | 133.056 | DASHMESH ENTERPRISES GP-2 |  | 43 | 82 | -39 | 52 | 39 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2AF3 \ 248 | 180 | 210 | 2 | 5.934 | DASHMESH ENTERPRISES GP-2 |  | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | A 50X50X6 MS | 933 \ 2AF3 \ 24L | 1060 |  | 1 | 4.759 | DASHMESH ENTERPRISES GP-2 |  | 46 | 82 | -36 | 56 | 36 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | A 50X50X6 MS | 933 \ 2AF3 \ 24R | 1060 |  | 2 | 9.518 | DASHMESH ENTERPRISES GP-2 |  | 46 | 82 | -36 | 56 | 36 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | 200X200X16 MS | 933 \ 2AF3 \ 264 | 372 |  | 44 | 794.332 | DASHMESH ENTERPRISES GP-2 |  | 14 | 82 | -68 | 17 | 68 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
G | 65X65X6 MS | 933 \ 2AF3 \ 272A | 2329 |  | 3 | 41.292 | DASHMESH ENTERPRISES GP-2 |  | 49 | 82 | -33 | 60 | 33 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | 65X65X8 MS | 933 \ 2AF3 \ 273 | 2349 |  | 22 | 399.476 | DASHMESH ENTERPRISES GP-2 |  | 52 | 82 | -30 | 63 | 30 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | PLATE 12 MM MS | 933 \ 2AF3 \ 289 | 133 | 200 | 44 | 110.264 | DASHMESH ENTERPRISES GP-2 |  | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | A 200X200X20 MS | 933 \ 2AF3 \ 300 | 3430 |  | 2 | 411.326 | DASHMESH ENTERPRISES GP-2 |  | 5 | 82 | -77 | 6 | 77 | On track |  | Moving |  |  |  | Unknown | ANGLE | Drilling
G | A 200X200X20 MS | 933 \ 2AF3 \ 301S | 3430 |  | 4 | 822.652 | DASHMESH ENTERPRISES GP-2 |  | 5 | 82 | -77 | 6 | 77 | On track |  | Moving |  |  |  | Unknown | ANGLE | Drilling
G | PLATE 10 MM MS | 933 \ 2AF3 \ 331 | 205 | 260 | 44 | 184.096 | DASHMESH ENTERPRISES GP-2 |  | 31 | 82 | -51 | 38 | 51 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | A 50X50X6 MS | 933 \ 2AF3 \ 49 | 671 |  | 1 | 3.013 | DASHMESH ENTERPRISES GP-2 |  | 39 | 82 | -43 | 48 | 43 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | PLATE 10 MM MS | 933 \ 2AF3 \ 53L | 392 | 180 | 22 | 121.858 | DASHMESH ENTERPRISES GP-2 |  | 26 | 82 | -56 | 32 | 56 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2AF3 \ 53R | 392 | 180 | 22 | 121.858 | DASHMESH ENTERPRISES GP-2 |  | 26 | 82 | -56 | 32 | 56 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | A 50X50X6 MS | 933 \ 2AF3 \ 55 | 562 |  | 22 | 55.506 | DASHMESH ENTERPRISES GP-2 |  | 39 | 82 | -43 | 48 | 43 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | PLATE 10 MM MS | 933 \ 2AF3 \ 74L | 427 | 184 | 22 | 135.696 | DASHMESH ENTERPRISES GP-2 |  | 26 | 82 | -56 | 32 | 56 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2AF3 \ 74R | 427 | 184 | 22 | 135.696 | DASHMESH ENTERPRISES GP-2 |  | 26 | 82 | -56 | 32 | 56 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | A 50X50X6 MS | 933 \ 2AF3 \ 77 | 1169 |  | 2 | 10.498 | DASHMESH ENTERPRISES GP-2 |  | 39 | 82 | -43 | 48 | 43 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | A 50X50X6 MS | 933 \ 2AF3 \ 90 | 677 |  | 44 | 133.76 | DASHMESH ENTERPRISES GP-2 |  | 39 | 82 | -43 | 48 | 43 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | PLATE 10 MM MS | 933 \ 2AF3 \ 94L | 233 | 517 | 22 | 208.032 | DASHMESH ENTERPRISES GP-2 |  | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2AF3 \ 94R | 233 | 517 | 22 | 208.032 | DASHMESH ENTERPRISES GP-2 |  | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 8 MM MS | 933 \ 2AF5M \ 328P | 280 | 50 | 16 | 14.064 | DASHMESH ENTERPRISES GP-2 |  | 31 | 82 | -51 | 38 | 51 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 6 MM MS | 933 \ 2AF5M \ 345 | 281 | 60 | 32 | 25.408 | DASHMESH ENTERPRISES GP-2 |  | 31 | 82 | -51 | 38 | 51 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | 65X65X6 MS | 933 \ 2AF5M \ 354 | 1331 |  | 1 | 7.866 | DASHMESH ENTERPRISES GP-2 |  | 30 | 82 | -52 | 37 | 52 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | 65X65X6 MS | 933 \ 2AF5M \ 358 | 1716 |  | 8 | 81.136 | DASHMESH ENTERPRISES GP-2 |  | 41 | 82 | -41 | 50 | 41 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | PLATE 10 MM MS | 933 \ 2AF5M \ 369 | 225 | 200 | 16 | 56.528 | DASHMESH ENTERPRISES GP-2 |  | 31 | 82 | -51 | 38 | 51 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 112P | 170 | 50 | 16 | 10.672 | DASHMESH ENTERPRISES GP-2 |  | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 115 | 175 | 120 | 16 | 26.384 | DASHMESH ENTERPRISES GP-2 |  | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 116 | 250 | 117 | 16 | 36.736 | DASHMESH ENTERPRISES GP-2 |  | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 16 MM MS | 933 \ 2DF-5 \ 128P | 130 | 50 | 16 | 13.056 | DASHMESH ENTERPRISES GP-2 |  | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 129 | 385 | 100 | 48 | 145.056 | DASHMESH ENTERPRISES GP-2 |  | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 16 MM MS | 933 \ 2DF-5 \ 161 | 105 | 60 | 152 | 120.232 | DASHMESH ENTERPRISES GP-2 |  | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
G | 150X150X12 MS | 933 \ 2DF-5 \ 163L | 394 |  | 32 | 344.064 | DASHMESH ENTERPRISES GP-2 |  | 34 | 82 | -48 | 41 | 48 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 170 | 306 | 225 | 16 | 86.48 | DASHMESH ENTERPRISES GP-2 |  | 31 | 82 | -51 | 38 | 51 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 171 | 303 | 115 | 32 | 87.52 | DASHMESH ENTERPRISES GP-2 |  | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 174 | 335 | 299 | 16 | 125.808 | DASHMESH ENTERPRISES GP-2 |  | 53 | 82 | -29 | 65 | 29 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 178 | 275 | 115 | 16 | 39.728 | DASHMESH ENTERPRISES GP-2 |  | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 179 | 275 | 225 | 16 | 77.712 | DASHMESH ENTERPRISES GP-2 |  | 53 | 82 | -29 | 65 | 29 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | 150X150X20 MS | 933 \ 2DF-5 \ 201 | 5137 |  | 1 | 226.644 | DASHMESH ENTERPRISES GP-2 |  | 51 | 82 | -31 | 62 | 31 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 220 | 367 | 252 | 16 | 116.16 | DASHMESH ENTERPRISES GP-2 |  | 6 | 82 | -76 | 7 | 76 | On track |  | Moving |  |  |  | Unknown | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 227 | 402 | 332 | 16 | 167.632 | DASHMESH ENTERPRISES GP-2 |  | 6 | 82 | -76 | 7 | 76 | On track |  | Moving |  |  |  | Unknown | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 229 | 402 | 337 | 16 | 170.16 | DASHMESH ENTERPRISES GP-2 |  | 6 | 82 | -76 | 7 | 76 | On track |  | Moving |  |  |  | Unknown | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 233 | 457 | 115 | 16 | 66.016 | DASHMESH ENTERPRISES GP-2 |  | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 234 | 252 | 170 | 16 | 53.808 | DASHMESH ENTERPRISES GP-2 |  | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 235 | 252 | 115 | 16 | 36.4 | DASHMESH ENTERPRISES GP-2 |  | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 29L | 476 | 204 | 8 | 60.984 | DASHMESH ENTERPRISES GP-2 |  | 26 | 82 | -56 | 32 | 56 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 29R | 476 | 204 | 8 | 60.984 | DASHMESH ENTERPRISES GP-2 |  | 26 | 82 | -56 | 32 | 56 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 333 | 578 | 464 | 16 | 336.848 | DASHMESH ENTERPRISES GP-2 |  | 6 | 82 | -76 | 7 | 76 | On track |  | Moving |  |  |  | Unknown | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 337 | 412 | 402 | 16 | 208.016 | DASHMESH ENTERPRISES GP-2 |  | 7 | 82 | -75 | 9 | 75 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 44 | 283 | 128 | 16 | 45.504 | DASHMESH ENTERPRISES GP-2 |  | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | A 50X50X6 MS | 933 \ 2DF-5 \ 52 | 644 |  | 1 | 2.892 | DASHMESH ENTERPRISES GP-2 |  | 46 | 82 | -36 | 56 | 36 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | A 50X50X6 MS | 933 \ 2DF-5 \ 54 | 1335 |  | 8 | 47.952 | DASHMESH ENTERPRISES GP-2 |  | 39 | 82 | -43 | 48 | 43 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | A 50X50X6 MS | 933 \ 2DF-5 \ 62R | 1111 |  | 8 | 39.904 | DASHMESH ENTERPRISES GP-2 |  | 46 | 82 | -36 | 56 | 36 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 67L | 591 | 282 | 8 | 104.664 | DASHMESH ENTERPRISES GP-2 |  | 43 | 82 | -39 | 52 | 39 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 67R | 591 | 282 | 8 | 104.664 | DASHMESH ENTERPRISES GP-2 |  | 43 | 82 | -39 | 52 | 39 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | A 50X50X6 MS | 933 \ 2DF-5 \ 83XR | 1109 |  | 8 | 39.832 | DASHMESH ENTERPRISES GP-2 |  | 46 | 82 | -36 | 56 | 36 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | A 50X50X6 MS | 933 \ 2DF-5 \ 85XL | 1250 |  | 8 | 44.904 | DASHMESH ENTERPRISES GP-2 |  | 39 | 82 | -43 | 48 | 43 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | A 50X50X6 MS | 933 \ 2DF-5 \ 96 | 1355 |  | 24 | 146.016 | DASHMESH ENTERPRISES GP-2 |  | 39 | 82 | -43 | 48 | 43 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | PLATE 10 MM MS | 933 \ 2DF3 \ 112P | 170 | 50 | 44 | 29.348 | DASHMESH ENTERPRISES GP-2 |  | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF3 \ 116 | 250 | 117 | 2 | 4.592 | DASHMESH ENTERPRISES GP-2 |  | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF3 \ 128 | 204 | 240 | 2 | 7.686 | DASHMESH ENTERPRISES GP-2 |  | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 16 MM MS | 933 \ 2DF3 \ 128P | 130 | 50 | 44 | 35.904 | DASHMESH ENTERPRISES GP-2 |  | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
G | PLATE 16 MM MS | 933 \ 2DF3 \ 161 | 105 | 60 | 418 | 330.638 | DASHMESH ENTERPRISES GP-2 |  | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
G | PLATE 16 MM MS | 933 \ 2DF3 \ 175P | 180 | 60 | 44 | 59.664 | DASHMESH ENTERPRISES GP-2 |  | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
G | PLATE 10 MM MS | 933 \ 2DF3 \ 229 | 402 | 337 | 44 | 467.94 | DASHMESH ENTERPRISES GP-2 |  | 7 | 82 | -75 | 9 | 75 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF3 \ 240 | 402 | 120 | 69 | 261.303 | DASHMESH ENTERPRISES GP-2 |  | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF3 \ 272 | 392 | 120 | 440 | 1624.92 | DASHMESH ENTERPRISES GP-2 |  | 7 | 82 | -75 | 9 | 75 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF3 \ 29L | 476 | 204 | 22 | 167.706 | DASHMESH ENTERPRISES GP-2 |  | 26 | 82 | -56 | 32 | 56 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF3 \ 29R | 476 | 204 | 22 | 167.706 | DASHMESH ENTERPRISES GP-2 |  | 26 | 82 | -56 | 32 | 56 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | A 50X50X6 MS | 933 \ 2DF3 \ 33 | 634 |  | 3 | 8.541 | DASHMESH ENTERPRISES GP-2 |  | 46 | 82 | -36 | 56 | 36 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | PLATE 10 MM MS | 933 \ 2DF3 \ 44 | 283 | 128 | 4 | 11.376 | DASHMESH ENTERPRISES GP-2 |  | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | A 50X50X6 MS | 933 \ 2DF3 \ 52 | 644 |  | 12 | 34.704 | DASHMESH ENTERPRISES GP-2 |  | 46 | 82 | -36 | 56 | 36 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | PLATE 10 MM MS | 933 \ 2DF3 \ 67L | 591 | 282 | 22 | 287.826 | DASHMESH ENTERPRISES GP-2 |  | 26 | 82 | -56 | 32 | 56 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF3 \ 67R | 591 | 282 | 22 | 287.826 | DASHMESH ENTERPRISES GP-2 |  | 26 | 82 | -56 | 32 | 56 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | A 130X130X12 MS | 933 \ 2DF3 \ 90X | 2436 |  | 2 | 114.248 | DASHMESH ENTERPRISES GP-2 |  | 34 | 82 | -48 | 41 | 48 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | PLATE 10 MM MS | 933 \ IS-933 \ 2DF1 \ 014 | 135 | 144 | 7 | 10.682 | DASHMESH ENTERPRISES GP-2 |  | 63 | 82 | -19 | 77 | 19 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ IS-933 \ 2DF2A \ 905 | 205 | 457 | 1 | 7.354 | DASHMESH ENTERPRISES GP-2 |  | 63 | 82 | -19 | 77 | 19 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
GB | A 75X75X8 MS | 933 \ 2AF3 \ 102 | 2227 |  | 22 | 440.946 | DASHMESH ENTERPRISES GP-2 |  | 46 | 86 | -40 | 53 | 40 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 50X50X6 MS | 933 \ 2AF3 \ 103A | 2786 |  | 11 | 137.599 | DASHMESH ENTERPRISES GP-2 |  | 26 | 86 | -60 | 30 | 60 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | A 75X75X8 MS | 933 \ 2AF3 \ 116 | 2227 |  | 22 | 440.946 | DASHMESH ENTERPRISES GP-2 |  | 46 | 86 | -40 | 53 | 40 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 50X50X6 MS | 933 \ 2AF3 \ 117A | 2758 |  | 22 | 272.426 | DASHMESH ENTERPRISES GP-2 |  | 26 | 86 | -60 | 30 | 60 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 50X50X6 MS | 933 \ 2AF3 \ 202 | 1672 |  | 1 | 7.507 | DASHMESH ENTERPRISES GP-2 |  | 30 | 86 | -56 | 35 | 56 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | PLATE 10 MM MS | 933 \ 2AF3 \ 209 | 115 | 180 | 4 | 6.5 | DASHMESH ENTERPRISES GP-2 |  | 48 | 86 | -38 | 56 | 38 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
GB | 50X50X6 MS | 933 \ 2AF3 \ 213 | 2349 |  | 22 | 232.034 | DASHMESH ENTERPRISES GP-2 |  | 26 | 86 | -60 | 30 | 60 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 65X65X6 MS | 933 \ 2AF3 \ 235A | 2370 |  | 88 | 1232.616 | DASHMESH ENTERPRISES GP-2 |  | 34 | 86 | -52 | 40 | 52 | On track | Yes | Stalled | 35.6468 | 35.6468 | -16.3532 | Stalled | ANGLE | Punching
GB | 65X65X6 MS | 933 \ 2AF3 \ 237 | 2316 |  | 4 | 54.752 | DASHMESH ENTERPRISES GP-2 |  | 46 | 86 | -40 | 53 | 40 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 65X65X6 MS | 933 \ 2AF3 \ 237A | 2316 |  | 44 | 602.272 | DASHMESH ENTERPRISES GP-2 |  | 48 | 86 | -38 | 56 | 38 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 65X65X6 MS | 933 \ 2AF3 \ 238 | 2401 |  | 1 | 14.19 | DASHMESH ENTERPRISES GP-2 |  | 34 | 86 | -52 | 40 | 52 | On track | Yes | Stalled | 35.6468 | 35.6468 | -16.3532 | Stalled | ANGLE | Punching
GB | 65X65X6 MS | 933 \ 2AF3 \ 238A | 2401 |  | 44 | 624.36 | DASHMESH ENTERPRISES GP-2 |  | 52 | 86 | -34 | 60 | 34 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 65X65X6 MS | 933 \ 2AF3 \ 241 | 2336 |  | 2 | 27.612 | DASHMESH ENTERPRISES GP-2 |  | 18 | 86 | -68 | 21 | 68 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | PLATE 10 MM MS | 933 \ 2AF3 \ 243 | 170 | 50 | 44 | 29.348 | DASHMESH ENTERPRISES GP-2 |  | 29 | 86 | -57 | 34 | 57 | On track | Yes | Stalled | 35.6468 | 35.6468 | -21.3532 | Stalled | PLATE | Punching
GB | 65X65X6 MS | 933 \ 2AF3 \ 279A | 2410 |  | 28 | 398.804 | DASHMESH ENTERPRISES GP-2 |  | 48 | 86 | -38 | 56 | 38 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 65X65X6 MS | 933 \ 2AF3 \ 279A | 2410 |  | 16 | 227.888 | DASHMESH ENTERPRISES GP-2 |  | 46 | 86 | -40 | 53 | 40 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 65X65X8 MS | 933 \ 2AF3 \ 285 | 2377 |  | 44 | 808.456 | DASHMESH ENTERPRISES GP-2 |  | 52 | 86 | -34 | 60 | 34 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | PLATE 10 MM MS | 933 \ 2AF3 \ 29L | 397 | 160 | 22 | 109.692 | DASHMESH ENTERPRISES GP-2 |  | 15 | 86 | -71 | 17 | 71 | On track | Yes | Stalled | 35.6468 | 35.6468 | -35.3532 | Stalled | PLATE | Punching
GB | PLATE 10 MM MS | 933 \ 2AF3 \ 29R | 397 | 160 | 22 | 109.692 | DASHMESH ENTERPRISES GP-2 |  | 15 | 86 | -71 | 17 | 71 | On track | Yes | Stalled | 35.6468 | 35.6468 | -35.3532 | Stalled | PLATE | Punching
GB | 200X200X16 MS | 933 \ 2AF3 \ 304 | 572 |  | 8 | 222.072 | DASHMESH ENTERPRISES GP-2 |  | 18 | 86 | -68 | 21 | 68 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
GB | 50X50X5 MS | 933 \ 2AF3 \ 308 | 1082 |  | 1 | 4.101 | DASHMESH ENTERPRISES GP-2 |  | 26 | 86 | -60 | 30 | 60 | On track | Yes | Stalled | 35.6468 | 35.6468 | -24.3532 | Stalled | ANGLE | Punching
GB | 65X65X6 MS | 933 \ 2AF3 \ 346 | 1144 |  | 2 | 13.522 | DASHMESH ENTERPRISES GP-2 |  | 41 | 86 | -45 | 48 | 45 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 50X50X6 MS | 933 \ 2AF3 \ 40A | 2710 |  | 11 | 133.848 | DASHMESH ENTERPRISES GP-2 |  | 26 | 86 | -60 | 30 | 60 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | A 50X50X6 MS | 933 \ 2AF3 \ 41 | 188 |  | 132 | 111.408 | DASHMESH ENTERPRISES GP-2 |  | 17 | 86 | -69 | 20 | 69 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | A 50X50X6 MS | 933 \ 2AF3 \ 60 | 2032 |  | 1 | 9.124 | DASHMESH ENTERPRISES GP-2 |  | 46 | 86 | -40 | 53 | 40 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | A 75X75X8 MS | 933 \ 2AF3 \ 82 | 2181 |  | 3 | 58.887 | DASHMESH ENTERPRISES GP-2 |  | 46 | 86 | -40 | 53 | 40 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 50X50X6 MS | 933 \ 2AF3 \ 83A | 2732 |  | 11 | 134.937 | DASHMESH ENTERPRISES GP-2 |  | 26 | 86 | -60 | 30 | 60 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 75X75X8 MS | 933 \ 2AF5M \ 352 | 4213 |  | 4 | 151.668 | DASHMESH ENTERPRISES GP-2 |  | 18 | 86 | -68 | 21 | 68 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 75X75X8 MS | 933 \ 2AF5M \ 352A | 4213 |  | 4 | 151.668 | DASHMESH ENTERPRISES GP-2 |  | 13 | 86 | -73 | 15 | 73 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | PLATE 10 MM MS | 933 \ 2DF-5 \ 112 | 260 | 178 | 16 | 58.128 | DASHMESH ENTERPRISES GP-2 |  | 29 | 86 | -57 | 34 | 57 | On track | Yes | Stalled | 35.6468 | 35.6468 | -21.3532 | Stalled | PLATE | Punching
GB | PLATE 10 MM MS | 933 \ 2DF-5 \ 128 | 204 | 240 | 16 | 61.488 | DASHMESH ENTERPRISES GP-2 |  | 29 | 86 | -57 | 34 | 57 | On track | Yes | Stalled | 35.6468 | 35.6468 | -21.3532 | Stalled | PLATE | Punching
GB | PLATE 10 MM MS | 933 \ 2DF-5 \ 242 | 337 | 135 | 32 | 114.272 | DASHMESH ENTERPRISES GP-2 |  | 29 | 86 | -57 | 34 | 57 | On track | Yes | Stalled | 35.6468 | 35.6468 | -21.3532 | Stalled | PLATE | Punching
GB | 200X200X16 MS | 933 \ 2DF-5 \ 290 | 136 |  | 6 | 39.6 | DASHMESH ENTERPRISES GP-2 |  | 8 | 86 | -78 | 9 | 78 | On track |  | Moving |  |  |  | Unknown | ANGLE | Drilling
GB | 200X200X16 MS | 933 \ 2DF-5 \ 290 | 136 |  | 9 | 59.4 | DASHMESH ENTERPRISES GP-2 |  | 30 | 86 | -56 | 35 | 56 | On track |  | Moving |  |  |  | Unknown | ANGLE | Drilling
GB | PLATE 10 MM MS | 933 \ 2DF-5 \ 292 | 221 | 135 | 32 | 74.944 | DASHMESH ENTERPRISES GP-2 |  | 29 | 86 | -57 | 34 | 57 | On track | Yes | Stalled | 35.6468 | 35.6468 | -21.3532 | Stalled | PLATE | Punching
GB | A 200X200X20 MS | 933 \ 2DF-5 \ 310S | 5124 |  | 3 | 921.705 | DASHMESH ENTERPRISES GP-2 |  | 41 | 86 | -45 | 48 | 45 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
GB | A 50X50X6 MS | 933 \ 2DF-5 \ 46R | 1085 |  | 8 | 38.976 | DASHMESH ENTERPRISES GP-2 |  | 30 | 86 | -56 | 35 | 56 | On track | Yes | Stalled | 35.6468 | 35.6468 | -20.3532 | Stalled | ANGLE | Punching
GB | A 75X75X8 MS | 933 \ 2DF-5 \ 81 | 4003 |  | 8 | 288.216 | DASHMESH ENTERPRISES GP-2 |  | 16 | 86 | -70 | 19 | 70 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | A 75X75X8 MS | 933 \ 2DF-5 \ 81X | 4003 |  | 8 | 288.216 | DASHMESH ENTERPRISES GP-2 |  | 16 | 86 | -70 | 19 | 70 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | A 50X50X6 MS | 933 \ 2DF-5 \ 83XL | 1109 |  | 2 | 9.958 | DASHMESH ENTERPRISES GP-2 |  | 30 | 86 | -56 | 35 | 56 | On track | Yes | Stalled | 35.6468 | 35.6468 | -20.3532 | Stalled | ANGLE | Punching
GB | A 50X50X6 MS | 933 \ 2DF-5 \ 85L | 1254 |  | 8 | 45.04 | DASHMESH ENTERPRISES GP-2 |  | 30 | 86 | -56 | 35 | 56 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | A 50X50X6 MS | 933 \ 2DF-5 \ 85R | 1254 |  | 11 | 61.93 | DASHMESH ENTERPRISES GP-2 |  | 30 | 86 | -56 | 35 | 56 | On track | Yes | Stalled | 35.6468 | 35.6468 | -20.3532 | Stalled | ANGLE | Punching
GB | 150X150X12 MS | 933 \ 2DF3 \ 223R | 346 |  | 1 | 9.442 | DASHMESH ENTERPRISES GP-2 |  | 34 | 86 | -52 | 40 | 52 | On track | Yes | Stalled | 35.6468 | 35.6468 | -16.3532 | Stalled | ANGLE | Punching
GB | 65X65X6 MS | 933 \ 2DF3 \ 284 | 732 |  | 88 | 380.688 | DASHMESH ENTERPRISES GP-2 |  | 52 | 86 | -34 | 60 | 34 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | PLATE 10 MM MS | 933 \ 2DF3 \ 289 | 392 | 136 | 11 | 46.035 | DASHMESH ENTERPRISES GP-2 |  | 44 | 86 | -42 | 51 | 42 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
GB | PLATE 10 MM MS | 933 \ 2DF3 \ 289 | 392 | 136 | 28 | 117.18 | DASHMESH ENTERPRISES GP-2 |  | 18 | 86 | -68 | 21 | 68 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | 65X65X6 MS | 933 \ 2AF10M \ 355 | 1912 |  | 8 | 90.4 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | 65X65X6 MS | 933 \ 2AF10M \ 377 | 1514 |  | 8 | 71.584 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | A 50X50X6 MS | 933 \ 2AF3 \ 108 | 365 |  | 44 | 72.116 | UNIT-II |  | 8 | 88 | -80 | 9 | 80 | On track |  | Moving |  |  |  | Unknown | ANGLE | Punching
Y | PLATE 10 MM MS | 933 \ 2AF3 \ 114L | 502 | 207 | 22 | 179.454 | UNIT-II |  | 45 | 88 | -43 | 51 | 43 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2AF3 \ 114R | 502 | 207 | 22 | 179.454 | UNIT-II |  | 45 | 88 | -43 | 51 | 43 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | 65X65X8 MS | 933 \ 2AF3 \ 115 | 1980 |  | 44 | 673.42 | UNIT-II |  | 51 | 88 | -37 | 58 | 37 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | PLATE 10 MM MS | 933 \ 2AF3 \ 209 | 115 | 180 | 8 | 13 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
Y | 65X65X6 MS | 933 \ 2AF3 \ 237 | 2316 |  | 1 | 13.688 | UNIT-II |  | 25 | 88 | -63 | 28 | 63 | On track | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
Y | 65X65X6 MS | 933 \ 2AF3 \ 237 | 2316 |  | 19 | 260.072 | UNIT-II |  | 18 | 88 | -70 | 20 | 70 | On track | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
Y | 65X65X6 MS | 933 \ 2AF3 \ 241 | 2336 |  | 1 | 13.806 | UNIT-II |  | 18 | 88 | -70 | 20 | 70 | On track | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
Y | PLATE 10 MM MS | 933 \ 2AF3 \ 246 | 204 | 250 | 14 | 56.056 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
Y | 65X65X6 MS | 933 \ 2AF3 \ 270A | 2410 |  | 3 | 42.729 | UNIT-II |  | 15 | 88 | -73 | 17 | 73 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | 65X65X6 MS | 933 \ 2AF3 \ 272A | 2329 |  | 16 | 220.224 | UNIT-II |  | 48 | 88 | -40 | 55 | 40 | Pre-warning 1 |  | Slow | 35.6468 |  |  | Unknown | ANGLE | Punching
Y | 65X65X8 MS | 933 \ 2AF3 \ 273A | 2349 |  | 22 | 399.476 | UNIT-II |  | 46 | 88 | -42 | 52 | 42 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | 65X65X8 MS | 933 \ 2AF3 \ 275 | 2377 |  | 44 | 808.456 | UNIT-II |  | 51 | 88 | -37 | 58 | 37 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | 65X65X8 MS | 933 \ 2AF3 \ 283 | 1680 |  | 22 | 285.692 | UNIT-II |  | 51 | 88 | -37 | 58 | 37 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | PLATE 12 MM MS | 933 \ 2AF3 \ 287 | 248 | 327 | 44 | 336.116 | UNIT-II |  | 66 | 88 | -22 | 75 | 22 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2AF3 \ 288 | 170 | 209 | 10 | 27.89 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
Y | PLATE 12 MM MS | 933 \ 2AF3 \ 290 | 238 | 200 | 44 | 197.296 | UNIT-II |  | 73 | 88 | -15 | 83 | 15 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | 65X65X8 MS | 933 \ 2AF3 \ 30 | 1972 |  | 22 | 335.368 | UNIT-II |  | 51 | 88 | -37 | 58 | 37 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | PLATE 16 MM MS | 933 \ 2AF3 \ 305 | 145 | 572 | 48 | 500.016 | UNIT-II |  | 48 | 88 | -40 | 55 | 40 | Pre-warning 1 | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Drilling
Y | 50X50X5 MS | 933 \ 2AF3 \ 307 | 593 |  | 18 | 40.446 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track |  | Moving |  |  |  | Unknown | ANGLE | Punching
Y | 50X50X5 MS | 933 \ 2AF3 \ 319 | 1932 |  | 1 | 7.322 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
Y | PLATE 12 MM MS | 933 \ 2AF3 \ 328 | 249 | 344 | 44 | 355.036 | UNIT-II |  | 66 | 88 | -22 | 75 | 22 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | 65X65X6 MS | 933 \ 2AF3 \ 347 | 2026 |  | 38 | 455.012 | UNIT-II |  | 31 | 88 | -57 | 35 | 57 | On track | Yes | Stalled | 29.8922 |  |  | Stalled | ANGLE | Punching
Y | A 50X50X6 MS | 933 \ 2AF3 \ 48L | 1061 |  | 22 | 104.808 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | A 50X50X6 MS | 933 \ 2AF3 \ 92 | 990 |  | 1 | 4.445 | UNIT-II |  | 38 | 88 | -50 | 43 | 50 | On track | Yes | Stalled | 32.8408 |  |  | Stalled | ANGLE | Punching
Y | 65X65X8 MS | 933 \ 2AF3 \ 95 | 2020 |  | 22 | 343.53 | UNIT-II |  | 51 | 88 | -37 | 58 | 37 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | A 50X50X6 MS | 933 \ 2AF3 \ 98 | 1152 |  | 66 | 341.352 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | A 50X50X6 MS | 933 \ 2AF3 \ 99 | 1654 |  | 32 | 237.632 | UNIT-II |  | 51 | 88 | -37 | 58 | 37 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | A 50X50X6 MS | 933 \ 2AF3 \ 99 | 1654 |  | 34 | 252.484 | UNIT-II |  | 48 | 88 | -40 | 55 | 40 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | 200X200X20 MS | 933 \ 2AF5M \ 341 | 5016 |  | 3 | 902.277 | UNIT-II |  | 41 | 88 | -47 | 47 | 47 | On track | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
Y | 200X200X20 MS | 933 \ 2AF5M \ 341S | 5016 |  | 1 | 300.759 | UNIT-II |  | 8 | 88 | -80 | 9 | 80 | On track |  | Slow | 3.6102 |  |  | Unknown | ANGLE | Drilling
Y | 75X75X8 MS | 933 \ 2AF5M \ 353 | 2991 |  | 4 | 107.676 | UNIT-II |  | 13 | 88 | -75 | 15 | 75 | On track | Yes | Stalled | 15.7591 |  |  | Stalled | ANGLE | Punching
Y | 65X65X6 MS | 933 \ 2AF5M \ 354 | 1331 |  | 17 | 133.722 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | 75X75X8 MS | 933 \ 2DF-5 \ 10 | 1716 |  | 8 | 123.552 | UNIT-II |  | 69 | 88 | -19 | 78 | 19 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 122 | 436 | 100 | 32 | 109.536 | UNIT-II |  | 67 | 88 | -21 | 76 | 21 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | 75X75X8 MS | 933 \ 2DF-5 \ 15 | 1521 |  | 16 | 219.024 | UNIT-II |  | 69 | 88 | -19 | 78 | 19 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | PLATE 12 MM MS | 933 \ 2DF-5 \ 167P | 416 | 115 | 1 | 4.507 | UNIT-II |  | 21 | 88 | -67 | 24 | 67 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 12 MM MS | 933 \ 2DF-5 \ 167P | 416 | 115 | 63 | 283.941 | UNIT-II |  | 67 | 88 | -21 | 76 | 21 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 168 | 312 | 130 | 112 | 356.608 | UNIT-II |  | 61 | 88 | -27 | 69 | 27 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 173 | 299 | 115 | 2 | 5.398 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 175 | 612 | 275 | 16 | 211.392 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | 200X200X16 MS | 933 \ 2DF-5 \ 205 | 472 |  | 17 | 389.402 | UNIT-II |  | 48 | 88 | -40 | 55 | 40 | Pre-warning 1 |  | Moving |  |  |  | Unknown | ANGLE | Drilling
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 206 | 472 | 402 | 8 | 119.16 | UNIT-II |  | 18 | 88 | -70 | 20 | 70 | On track | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 207 | 472 | 135 | 128 | 640.256 | UNIT-II |  | 67 | 88 | -21 | 76 | 21 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | 200X200X16 MS | 933 \ 2DF-5 \ 231L | 435 |  | 16 | 337.776 | UNIT-II |  | 46 | 88 | -42 | 52 | 42 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 287 | 392 | 136 | 48 | 200.88 | UNIT-II |  | 67 | 88 | -21 | 76 | 21 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | 200X200X16 MS | 933 \ 2DF-5 \ 290 | 136 |  | 112 | 739.2 | UNIT-II |  | 46 | 88 | -42 | 52 | 42 | Pre-warning 1 |  | Slow | 35.6468 |  |  | Unknown | ANGLE | Drilling
Y | 200X200X16 MS | 933 \ 2DF-5 \ 290 | 136 |  | 15 | 99 | UNIT-II |  | 3 | 88 | -85 | 3 | 85 | On track |  | Slow | 35.6468 |  |  | Unknown | ANGLE | Drilling
Y | 200X200X16 MS | 933 \ 2DF-5 \ 290 | 136 |  | 6 | 39.6 | UNIT-II |  | 8 | 88 | -80 | 9 | 80 | On track |  | Slow | 35.6468 |  |  | Unknown | ANGLE | Drilling
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 297A | 602 | 135 | 16 | 102.08 | UNIT-II |  | 44 | 88 | -44 | 50 | 44 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | A 50X50X6 MS | 933 \ 2DF-5 \ 33 | 634 |  | 8 | 22.776 | UNIT-II |  | 29 | 88 | -59 | 33 | 59 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | A 50X50X6 MS | 933 \ 2DF-5 \ 35 | 1317 |  | 8 | 47.304 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 50L | 500 | 187 | 8 | 58.72 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 50R | 500 | 187 | 8 | 58.72 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | A 50X50X6 MS | 933 \ 2DF-5 \ 52 | 644 |  | 7 | 20.244 | UNIT-II |  | 29 | 88 | -59 | 33 | 59 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | 75X75X8 MS | 933 \ 2DF-5 \ 8 | 1466 |  | 8 | 105.552 | UNIT-II |  | 28 | 88 | -60 | 32 | 60 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 81P | 314 | 140 | 24 | 82.824 | UNIT-II |  | 61 | 88 | -27 | 69 | 27 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 88L | 309 | 768 | 8 | 149.032 | UNIT-II |  | 45 | 88 | -43 | 51 | 43 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 88R | 309 | 768 | 8 | 149.032 | UNIT-II |  | 45 | 88 | -43 | 51 | 43 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 88YL | 282 | 733 | 8 | 129.808 | UNIT-II |  | 45 | 88 | -43 | 51 | 43 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 88YR | 282 | 733 | 8 | 129.808 | UNIT-II |  | 45 | 88 | -43 | 51 | 43 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | 130X130X12 MS | 933 \ 2DF-5 \ 89X | 2436 |  | 8 | 456.992 | UNIT-II |  | 58 | 88 | -30 | 66 | 30 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | 130X130X12 MS | 933 \ 2DF-5 \ 89Y | 2136 |  | 8 | 400.712 | UNIT-II |  | 41 | 88 | -47 | 47 | 47 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | 75X75X8 MS | 933 \ 2DF3 \ 10 | 1716 |  | 22 | 339.768 | UNIT-II |  | 69 | 88 | -19 | 78 | 19 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | 100X100X10 MS | 933 \ 2DF3 \ 124A | 2794 |  | 1 | 42.022 | UNIT-II |  | 21 | 88 | -67 | 24 | 67 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | 130X130X12 MS | 933 \ 2DF3 \ 155A | 2816 |  | 6 | 396.21 | UNIT-II |  | 56 | 88 | -32 | 64 | 32 | Pre-warning 1 |  | Moving |  |  |  | Unknown | ANGLE | Punching
Y | 150X150X12 MS | 933 \ 2DF3 \ 160L | 397 |  | 22 | 238.348 | UNIT-II |  | 34 | 88 | -54 | 39 | 54 | On track |  | Moving |  |  |  | Unknown | ANGLE | Punching
Y | 150X150X12 MS | 933 \ 2DF3 \ 163L | 394 |  | 1 | 10.752 | UNIT-II |  | 21 | 88 | -67 | 24 | 67 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 168 | 312 | 130 | 2 | 6.368 | UNIT-II |  | 21 | 88 | -67 | 24 | 67 | On track |  | Moving |  |  |  | Unknown | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 173 | 299 | 115 | 4 | 10.796 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
Y | 200X200X16 MS | 933 \ 2DF3 \ 204X | 472 |  | 22 | 503.932 | UNIT-II |  | 85 | 88 | -3 | 97 | 3 | Pre-warning 3 |  | Moving |  |  |  | Unknown | ANGLE | Drilling
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 207 | 472 | 135 | 240 | 1200.48 | UNIT-II |  | 67 | 88 | -21 | 76 | 21 | Pre-warning 2 |  | Moving |  |  |  | Unknown | PLATE | Punching
Y | 150X150X12 MS | 933 \ 2DF3 \ 221R | 343 |  | 2 | 18.72 | UNIT-II |  | 34 | 88 | -54 | 39 | 54 | On track | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
Y | 150X150X12 MS | 933 \ 2DF3 \ 224L | 339 |  | 12 | 111.012 | UNIT-II |  | 34 | 88 | -54 | 39 | 54 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 225 | 547 | 504 | 20 | 432.84 | UNIT-II |  | 31 | 88 | -57 | 35 | 57 | On track | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 225 | 547 | 504 | 4 | 86.568 | UNIT-II |  | 62 | 88 | -26 | 70 | 26 | Pre-warning 1 | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 237 | 255 | 115 | 8 | 18.416 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 238 | 248 | 115 | 6 | 13.434 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track |  | Slow | 25.5502 |  |  | Unknown | PLATE | Punching
Y | 200X200X16 MS | 933 \ 2DF3 \ 248L | 162 |  | 22 | 172.964 | UNIT-II |  | 78 | 88 | -10 | 89 | 10 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
Y | 200X200X16 MS | 933 \ 2DF3 \ 248R | 162 |  | 22 | 172.964 | UNIT-II |  | 78 | 88 | -10 | 89 | 10 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 251 | 360 | 149 | 44 | 185.284 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 287 | 392 | 136 | 88 | 368.28 | UNIT-II |  | 67 | 88 | -21 | 76 | 21 | Pre-warning 2 | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 289 | 392 | 136 | 29 | 121.365 | UNIT-II |  | 22 | 88 | -66 | 25 | 66 | On track | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 292 | 221 | 135 | 2 | 4.684 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 297A | 602 | 135 | 44 | 280.72 | UNIT-II |  | 44 | 88 | -44 | 50 | 44 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | 65X65X6 MS | 933 \ 2DF3 \ 323 | 1513 |  | 17 | 152.014 | UNIT-II |  | 20 | 88 | -68 | 23 | 68 | On track | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 334 | 578 | 135 | 22 | 134.75 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 338 | 402 | 145 | 26 | 118.976 | UNIT-II |  | 29 | 88 | -59 | 33 | 59 | On track | Yes | Stalled | 14.7178 |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 338 | 402 | 145 | 31 | 141.856 | UNIT-II |  | 18 | 88 | -70 | 20 | 70 | On track | Yes | Stalled | 14.7178 |  |  | Stalled | PLATE | Punching
Y | A 50X50X6 MS | 933 \ 2DF3 \ 34 | 1270 |  | 22 | 125.444 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 50L | 500 | 187 | 22 | 161.48 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 50R | 500 | 187 | 22 | 161.48 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | A 50X50X6 MS | 933 \ 2DF3 \ 52 | 644 |  | 10 | 28.92 | UNIT-II |  | 29 | 88 | -59 | 33 | 59 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | A 50X50X6 MS | 933 \ 2DF3 \ 62R | 1111 |  | 1 | 4.988 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track |  | Moving |  |  |  | Unknown | ANGLE | Punching
Y | 75X75X8 MS | 933 \ 2DF3 \ 8 | 1466 |  | 22 | 290.268 | UNIT-II |  | 53 | 88 | -35 | 60 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | A 50X50X6 MS | 933 \ 2DF3 \ 87L | 1289 |  | 22 | 127.336 | UNIT-II |  | 3 | 88 | -85 | 3 | 85 | On track |  | Moving |  |  |  | Unknown | ANGLE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 88L | 309 | 768 | 22 | 409.838 | UNIT-II |  | 45 | 88 | -43 | 51 | 43 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 88R | 309 | 768 | 22 | 409.838 | UNIT-II |  | 45 | 88 | -43 | 51 | 43 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 88XL | 340 | 743 | 22 | 436.282 | UNIT-II |  | 27 | 88 | -61 | 31 | 61 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 88XR | 340 | 743 | 22 | 436.282 | UNIT-II |  | 27 | 88 | -61 | 31 | 61 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 88YL | 282 | 733 | 22 | 356.972 | UNIT-II |  | 45 | 88 | -43 | 51 | 43 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 88YR | 282 | 733 | 22 | 356.972 | UNIT-II |  | 45 | 88 | -43 | 51 | 43 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | A 50X50X6 MS | 933 \ 2DF3 \ 92 | 1404 |  | 7 | 44.128 | UNIT-II |  | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled | 24.8672 |  |  | Stalled | ANGLE | Punching
Y | 200X200X20 MS | 933 \ 2DF5M \ 350S | 5043 |  | 2 | 604.756 | UNIT-II |  | 41 | 88 | -47 | 47 | 47 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
Y | 65X65X6 MS | 933 \ 2DF5M \ 357 | 1882 |  | 8 | 88.984 | UNIT-II |  | 41 | 88 | -47 | 47 | 47 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF10M \ 359 | 1331 |  | 8 | 62.928 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 23.7885 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF10M \ 374 | 2038 |  | 8 | 96.36 | UNIT-II |  | 21 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 107 | 110 | 229 | 22 | 43.494 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| 50X50X6 MS | 933 \ 2AF3 \ 11 | 976 |  | 44 | 192.808 | UNIT-II |  | 3 |  |  |  |  | N/A |  | Moving |  |  |  | Unknown | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 111L | 1216 |  | 22 | 120.12 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 111R | 1216 |  | 22 | 120.12 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 112 | 995 |  | 44 | 196.592 | UNIT-II |  | 12 |  |  |  |  | N/A | Yes | Stalled | 28.7989 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 124L | 1214 |  | 22 | 119.922 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 50X50X6 MS | 933 \ 2AF3 \ 203A | 2292 |  | 22 | 226.402 | UNIT-II |  | 18 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 208 | 235 | 345 | 44 | 280.016 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 209 | 115 | 180 | 76 | 123.5 | UNIT-II |  | 16 |  |  |  |  | N/A | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 210 | 115 | 180 | 88 | 143 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 211 | 180 | 185 | 44 | 115.016 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 214 | 115 | 185 | 44 | 73.48 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 22 | 110 | 229 | 44 | 86.988 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 237 | 2316 |  | 1 | 13.688 | UNIT-II |  | 25 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 239 | 2418 |  | 126 | 1800.54 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 239A | 2418 |  | 22 | 314.38 | UNIT-II |  | 12 |  |  |  |  | N/A | Yes | Stalled | 34.8556 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 241 | 2336 |  | 20 | 276.12 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 242 | 365 | 250 | 44 | 315.172 | UNIT-II |  | 15 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 244 | 130 | 175 | 88 | 157.168 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 245 | 130 | 180 | 88 | 161.656 | UNIT-II |  | 16 |  |  |  |  | N/A | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 246 | 204 | 250 | 30 | 120.12 | UNIT-II |  | 16 |  |  |  |  | N/A | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 248 | 180 | 210 | 42 | 124.614 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 249 | 1658 |  | 22 | 215.578 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 24.8672 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 24L | 1060 |  | 13 | 61.867 | UNIT-II |  | 19 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 24R | 1060 |  | 20 | 95.18 | UNIT-II |  | 19 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 25 | 670 |  | 44 | 132.352 | UNIT-II |  | 12 |  |  |  |  | N/A | Yes | Stalled | 28.7989 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 251 | 330 | 130 | 44 | 148.192 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 12 MM MS | 933 \ 2AF3 \ 265 | 372 | 125 | 88 | 385.44 | UNIT-II |  | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| 200X200X16 MS | 933 \ 2AF3 \ 266 | 472 |  | 40 | 916.24 | UNIT-II |  | 18 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| PLATE 16 MM MS | 933 \ 2AF3 \ 267 | 145 | 472 | 87 | 747.852 | UNIT-II |  | 18 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Drilling
| A 50X50X6 MS | 933 \ 2AF3 \ 26L | 1194 |  | 14 | 75.054 | UNIT-II |  | 19 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 26R | 1194 |  | 17 | 91.137 | UNIT-II |  | 19 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 271 | 1730 |  | 22 | 224.928 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 23.7885 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 272 | 2329 |  | 22 | 302.808 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 272A | 2329 |  | 3 | 41.292 | UNIT-II |  | 8 |  |  |  |  | N/A |  | Slow | 35.6468 |  |  | Unknown | ANGLE | Punching
| 65X65X8 MS | 933 \ 2AF3 \ 274 | 2377 |  | 59 | 1084.066 | UNIT-II |  | 15 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 65X65X8 MS | 933 \ 2AF3 \ 277 | 2312 |  | 44 | 786.368 | UNIT-II |  | 15 |  |  |  |  | N/A | Yes | Stalled | 29.8922 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 280 | 1720 |  | 22 | 223.63 | UNIT-II |  | 28 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 281A | 2329 |  | 22 | 302.808 | UNIT-II |  | 25 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 65X65X8 MS | 933 \ 2AF3 \ 282 | 2355 |  | 44 | 800.976 | UNIT-II |  | 15 |  |  |  |  | N/A | Yes | Stalled | 29.8922 |  |  | Stalled | ANGLE | Punching
| 65X65X8 MS | 933 \ 2AF3 \ 284 | 2280 |  | 44 | 775.456 | UNIT-II |  | 15 |  |  |  |  | N/A | Yes | Stalled | 29.8922 |  |  | Stalled | ANGLE | Punching
| PLATE 12 MM MS | 933 \ 2AF3 \ 286 | 258 | 202 | 44 | 215.996 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 288 | 170 | 209 | 34 | 94.826 | UNIT-II |  | 16 |  |  |  |  | N/A | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
| 200X200X16 MS | 933 \ 2AF3 \ 304 | 572 |  | 72 | 1998.648 | UNIT-II |  | 18 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| PLATE 16 MM MS | 933 \ 2AF3 \ 305 | 145 | 572 | 76 | 791.692 | UNIT-II |  | 15 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Drilling
| 50X50X5 MS | 933 \ 2AF3 \ 309 | 1044 |  | 88 | 348.216 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 50X50X5 MS | 933 \ 2AF3 \ 311 | 599 |  | 1 | 2.27 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 50X50X5 MS | 933 \ 2AF3 \ 312 | 748 |  | 2 | 5.67 | UNIT-II |  | 30 |  |  |  |  | N/A |  | Slow | 22.4987 |  |  | Unknown | ANGLE | Punching
| 50X50X5 MS | 933 \ 2AF3 \ 313 | 1457 |  | 88 | 485.936 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 50X50X5 MS | 933 \ 2AF3 \ 315 | 1217 |  | 48 | 221.376 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 50X50X5 MS | 933 \ 2AF3 \ 316 | 748 |  | 2 | 5.67 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 50X50X5 MS | 933 \ 2AF3 \ 319 | 1932 |  | 31 | 226.982 | UNIT-II |  | 14 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 50X50X5 MS | 933 \ 2AF3 \ 320 | 1721 |  | 88 | 574.024 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 50X50X5 MS | 933 \ 2AF3 \ 321 | 1576 |  | 88 | 525.624 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled | 23.7885 |  |  | Stalled | ANGLE | Punching
| 50X50X5 MS | 933 \ 2AF3 \ 322 | 941 |  | 30 | 106.98 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 75X75X8 MS | 933 \ 2AF3 \ 323 | 5329 |  | 1 | 47.961 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| PLATE 12 MM MS | 933 \ 2AF3 \ 324 | 244 | 337 | 44 | 340.824 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 325 | 555 | 205 | 17 | 151.827 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 327 | 205 | 580 | 88 | 821.392 | UNIT-II |  | 31 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| A 75X75X8 MS | 933 \ 2AF3 \ 343 | 3003 |  | 1 | 27.027 | UNIT-II |  | 28 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 346 | 1144 |  | 86 | 581.446 | UNIT-II |  | 34 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 347 | 2026 |  | 50 | 598.7 | UNIT-II |  | 15 |  |  |  |  | N/A | Yes | Stalled | 29.8922 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 348 | 2097 |  | 88 | 1090.584 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| PLATE 12 MM MS | 933 \ 2AF3 \ 349 | 237 | 409 | 44 | 401.764 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 351 | 1144 |  | 88 | 594.968 | UNIT-II |  | 34 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 360 | 205 | 553 | 44 | 391.556 | UNIT-II |  | 31 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 37 | 1623 |  | 22 | 160.314 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 38 | 2017 |  | 22 | 199.232 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| A 75X75X8 MS | 933 \ 2AF3 \ 39 | 2132 |  | 22 | 422.136 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 51 | 981 |  | 44 | 193.82 | UNIT-II |  | 21 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 56 | 1164 |  | 22 | 114.972 | UNIT-II |  | 21 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 58 | 1589 |  | 22 | 156.97 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 59 | 1638 |  | 1 | 7.355 | UNIT-II |  | 19 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 50X50X6 MS | 933 \ 2AF3 \ 6 | 778 |  | 43 | 150.199 | UNIT-II |  | 3 |  |  |  |  | N/A |  | Moving |  |  |  | Unknown | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 60 | 2032 |  | 21 | 191.604 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| A 75X75X8 MS | 933 \ 2AF3 \ 61 | 2152 |  | 22 | 426.096 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 67 | 110 | 229 | 22 | 43.494 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 70 | 669 |  | 44 | 132.176 | UNIT-II |  | 12 |  |  |  |  | N/A | Yes | Stalled | 28.7989 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 71L | 1196 |  | 22 | 118.14 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 73R | 1345 |  | 22 | 132.858 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 65X65X8 MS | 933 \ 2AF3 \ 75 | 1978 |  | 22 | 336.38 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 77 | 1169 |  | 20 | 104.98 | UNIT-II |  | 21 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 80 | 1655 |  | 22 | 163.482 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled | 23.7885 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 81 | 2057 |  | 22 | 203.192 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| A 75X75X8 MS | 933 \ 2AF3 \ 82 | 2181 |  | 19 | 372.951 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 87 | 240 | 110 | 44 | 91.168 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| 50X50X6 MS | 933 \ 2AF3 \ 9 | 2201 |  | 44 | 434.808 | UNIT-II |  | 11 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 91L | 1217 |  | 22 | 120.208 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 92 | 990 |  | 43 | 191.135 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled | 32.8408 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 96 | 585 |  | 5 | 13.135 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 200X200X20 MS | 933 \ 2AF5M \ 341 | 5016 |  | 1 | 300.759 | UNIT-II |  | 12 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| 200X200X20 MS | 933 \ 2AF5M \ 341S | 5016 |  | 3 | 902.277 | UNIT-II |  | 8 |  |  |  |  | N/A |  | Slow | 3.6102 |  |  | Unknown | ANGLE | Drilling
| 75X75X8 MS | 933 \ 2AF5M \ 352 | 4213 |  | 8 | 303.336 | UNIT-II |  | 18 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 75X75X8 MS | 933 \ 2AF5M \ 352A | 4213 |  | 8 | 303.336 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 75X75X8 MS | 933 \ 2AF5M \ 353 | 2991 |  | 8 | 215.352 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 15.7591 |  |  | Stalled | ANGLE | Punching
| 75X75X8 MS | 933 \ 2AF5M \ 353A | 2991 |  | 8 | 215.352 | UNIT-II |  | 14 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF5M \ 355 | 1912 |  | 24 | 271.2 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled | 32.8408 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF5M \ 356 | 2473 |  | 24 | 350.76 | UNIT-II |  | 12 |  |  |  |  | N/A | Yes | Stalled | 34.8556 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF5M \ 358 | 1716 |  | 16 | 162.272 | UNIT-II |  | 24 |  |  |  |  | N/A | Yes | Stalled | 25.5502 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF5M \ 359 | 1331 |  | 24 | 188.784 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled | 32.8408 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 113 | 263 | 85 | 32 | 56.16 | UNIT-II |  | 14 |  |  |  |  | N/A | Yes | Stalled | 12.7201 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 114 | 264 | 85 | 32 | 56.384 | UNIT-II |  | 14 |  |  |  |  | N/A | Yes | Stalled | 12.7201 |  |  | Stalled | PLATE | Punching
| 100X100X10 MS | 933 \ 2DF-5 \ 123 | 2768 |  | 1 | 41.631 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 129A | 385 | 100 | 16 | 48.352 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 131 | 315 | 282 | 16 | 111.568 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 12 MM MS | 933 \ 2DF-5 \ 159 | 422 | 306 | 16 | 194.624 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 19.7384 |  |  | Stalled | PLATE | Punching
| 150X150X12 MS | 933 \ 2DF-5 \ 160L | 397 |  | 16 | 173.344 | UNIT-II |  | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF-5 \ 160R | 397 |  | 16 | 173.344 | UNIT-II |  | 99 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 162 | 422 | 303 | 32 | 321.184 | UNIT-II |  | 12 |  |  |  |  | N/A | Yes | Stalled | 28.7989 |  |  | Stalled | PLATE | Punching
| 150X150X12 MS | 933 \ 2DF-5 \ 163R | 394 |  | 32 | 344.064 | UNIT-II |  | 99 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF-5 \ 164L | 390 |  | 16 | 170.288 | UNIT-II |  | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF-5 \ 164R | 390 |  | 16 | 170.288 | UNIT-II |  | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 167 | 416 | 312 | 20 | 203.78 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 169 | 306 | 115 | 16 | 44.192 | UNIT-II |  | 14 |  |  |  |  | N/A | Yes | Stalled | 12.7201 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 173 | 299 | 115 | 14 | 37.786 | UNIT-II |  | 16 |  |  |  |  | N/A | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
| 200X200X16 MS | 933 \ 2DF-5 \ 204 | 472 |  | 52 | 1191.112 | UNIT-II |  | 18 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF-5 \ 206 | 472 | 402 | 28 | 417.06 | UNIT-II |  | 15 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| A 75X75X8 MS | 933 \ 2DF-5 \ 20X | 4285 |  | 8 | 308.52 | UNIT-II |  | 7 |  |  |  |  | N/A | Yes | Stalled | 6.7265 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 218 | 612 | 457 | 16 | 351.28 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| 150X150X12 MS | 933 \ 2DF-5 \ 219L | 548 |  | 16 | 239.28 | UNIT-II |  | 99 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF-5 \ 219R | 548 |  | 16 | 239.28 | UNIT-II |  | 99 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF-5 \ 221R | 343 |  | 16 | 149.76 | UNIT-II |  | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 222 | 367 | 255 | 16 | 117.536 | UNIT-II |  | 12 |  |  |  |  | N/A | Yes | Stalled | 28.7989 |  |  | Stalled | PLATE | Punching
| 150X150X12 MS | 933 \ 2DF-5 \ 223R | 346 |  | 16 | 151.072 | UNIT-II |  | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF-5 \ 224L | 339 |  | 12 | 111.012 | UNIT-II |  | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF-5 \ 224R | 339 |  | 16 | 148.016 | UNIT-II |  | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 200X200X16 MS | 933 \ 2DF-5 \ 228R | 429 |  | 16 | 333.104 | UNIT-II |  | 15 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| 200X200X16 MS | 933 \ 2DF-5 \ 230R | 434 |  | 16 | 336.992 | UNIT-II |  | 15 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| 200X200X16 MS | 933 \ 2DF-5 \ 231R | 435 |  | 16 | 337.776 | UNIT-II |  | 15 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF-5 \ 232 | 457 | 225 | 16 | 129.152 | UNIT-II |  | 18 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 236 | 255 | 170 | 16 | 54.448 | UNIT-II |  | 14 |  |  |  |  | N/A | Yes | Stalled | 15.7591 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 237 | 255 | 115 | 16 | 36.832 | UNIT-II |  | 16 |  |  |  |  | N/A | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 238 | 248 | 115 | 16 | 35.824 | UNIT-II |  | 16 |  |  |  |  | N/A | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 239 | 504 | 135 | 32 | 170.912 | UNIT-II |  | 6 |  |  |  |  | N/A |  | Moving |  |  |  | Unknown | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 240 | 402 | 120 | 48 | 181.776 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 243 | 331 | 275 | 16 | 114.32 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 244 | 331 | 135 | 16 | 56.128 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 247 | 692 | 153 | 16 | 132.976 | UNIT-II |  | 29 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 250 | 149 | 135 | 16 | 25.264 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 12.7201 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 251 | 360 | 149 | 16 | 67.376 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 252 | 380 | 248 | 16 | 118.368 | UNIT-II |  | 31 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| A 200X200X20 MS | 933 \ 2DF-5 \ 268 | 2862 |  | 2 | 343.212 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF-5 \ 272 | 392 | 120 | 100 | 369.3 | UNIT-II |  | 29 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | PLATE | Punching
| 65X65X6 MS | 933 \ 2DF-5 \ 277 | 1018 |  | 32 | 192.512 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled | 32.8408 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF-5 \ 278 | 545 |  | 32 | 103.072 | UNIT-II |  | 15 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 200X200X16 MS | 933 \ 2DF-5 \ 286 | 221 |  | 32 | 343.2 | UNIT-II |  | 12 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | ANGLE | Drilling
| 200X200X16 MS | 933 \ 2DF-5 \ 288 | 136 |  | 96 | 633.6 | UNIT-II |  | 7 |  |  |  |  | N/A |  | Moving |  |  |  | Unknown | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF-5 \ 289 | 392 | 136 | 96 | 401.76 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| A 50X50X6 MS | 933 \ 2DF-5 \ 28R | 1359 |  | 8 | 48.816 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 200X200X16 MS | 933 \ 2DF-5 \ 290 | 136 |  | 44 | 290.4 | UNIT-II |  | 3 |  |  |  |  | N/A |  | Slow | 35.6468 |  |  | Unknown | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF-5 \ 294 | 135 | 136 | 192 | 276.672 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 12.7201 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 297 | 602 | 135 | 16 | 102.08 | UNIT-II |  | 12 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| A 200X200X20 MS | 933 \ 2DF-5 \ 310S | 5124 |  | 2 | 614.47 | UNIT-II |  | 34 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
| 65X65X6 MS | 933 \ 2DF-5 \ 320 | 996 |  | 32 | 188.352 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled | 32.8408 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 334 | 578 | 135 | 16 | 98 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 335 | 578 | 205 | 16 | 148.816 | UNIT-II |  | 12 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 338 | 402 | 145 | 32 | 146.432 | UNIT-II |  | 6 |  |  |  |  | N/A |  | Moving |  |  |  | Unknown | PLATE | Punching
| A 50X50X6 MS | 933 \ 2DF-5 \ 34 | 1270 |  | 8 | 45.616 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF-5 \ 36 | 1844 |  | 8 | 66.24 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF-5 \ 64R | 1256 |  | 8 | 45.112 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF-5 \ 71 | 1493 |  | 8 | 53.632 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF-5 \ 74 | 1401 |  | 16 | 100.64 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 75X75X8 MS | 933 \ 2DF-5 \ 80L | 3969 |  | 1 | 35.721 | UNIT-II |  | 7 |  |  |  |  | N/A | Yes | Stalled | 6.7265 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF-5 \ 83R | 1111 |  | 16 | 79.808 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF-5 \ 85XR | 1250 |  | 8 | 44.904 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 88XL | 340 | 743 | 8 | 158.648 | UNIT-II |  | 18 |  |  |  |  | N/A | Yes | Stalled | 15.7591 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 88XR | 340 | 743 | 8 | 158.648 | UNIT-II |  | 18 |  |  |  |  | N/A | Yes | Stalled | 15.7591 |  |  | Stalled | PLATE | Punching
| 130X130X12 MS | 933 \ 2DF-5 \ 89 | 2486 |  | 8 | 466.376 | UNIT-II |  | 3 |  |  |  |  | N/A |  | Slow | 35.6468 |  |  | Unknown | ANGLE | Punching
| 75X75X8 MS | 933 \ 2DF-5 \ 9 | 2942 |  | 8 | 211.824 | UNIT-II |  | 51 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF-5 \ 95 | 1482 |  | 24 | 159.696 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF3 \ 102 | 2460 |  | 22 | 319.858 | UNIT-II |  | 12 |  |  |  |  | N/A | Yes | Stalled | 30.7329 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 112 | 260 | 178 | 44 | 159.852 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 113 | 263 | 85 | 88 | 154.44 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 12.7201 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 114 | 264 | 85 | 88 | 155.056 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 12.7201 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 115 | 175 | 120 | 44 | 72.556 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 116 | 250 | 117 | 42 | 96.432 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| 130X130X12 MS | 933 \ 2DF3 \ 121 | 436 |  | 44 | 449.856 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 122 | 436 | 100 | 88 | 301.224 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| 100X100X10 MS | 933 \ 2DF3 \ 126 | 2016 |  | 1 | 30.321 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 128 | 204 | 240 | 42 | 161.406 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 129 | 385 | 100 | 132 | 398.904 | UNIT-II |  | 12 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 129A | 385 | 100 | 44 | 132.968 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 131 | 315 | 282 | 44 | 306.812 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| 130X130X12 MS | 933 \ 2DF3 \ 156 | 2006 |  | 1 | 47.041 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| PLATE 12 MM MS | 933 \ 2DF3 \ 159 | 422 | 306 | 44 | 535.216 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 19.7384 |  |  | Stalled | PLATE | Punching
| 150X150X12 MS | 933 \ 2DF3 \ 160R | 397 |  | 44 | 476.696 | UNIT-II |  | 104 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 162 | 422 | 303 | 44 | 441.628 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| 150X150X12 MS | 933 \ 2DF3 \ 163L | 394 |  | 87 | 935.424 | UNIT-II |  | 104 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF3 \ 163R | 394 |  | 88 | 946.176 | UNIT-II |  | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF3 \ 164L | 390 |  | 44 | 468.292 | UNIT-II |  | 22 |  |  |  |  | N/A |  | Slow | 32.8408 |  |  | Unknown | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF3 \ 164R | 390 |  | 22 | 234.146 | UNIT-II |  | 105 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 167 | 416 | 312 | 46 | 468.694 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 19.7384 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 169 | 306 | 115 | 44 | 121.528 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 12.7201 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 170 | 306 | 225 | 44 | 237.82 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 171 | 303 | 115 | 88 | 240.68 | UNIT-II |  | 12 |  |  |  |  | N/A | Yes | Stalled | 28.7989 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 172 | 303 | 225 | 88 | 470.976 | UNIT-II |  | 34 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 173 | 299 | 115 | 40 | 107.96 | UNIT-II |  | 16 |  |  |  |  | N/A | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 174 | 335 | 299 | 44 | 345.972 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 175 | 612 | 275 | 44 | 581.328 | UNIT-II |  | 18 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 178 | 275 | 115 | 44 | 109.252 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 179 | 275 | 225 | 44 | 213.708 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| 200X200X16 MS | 933 \ 2DF3 \ 204 | 472 |  | 172 | 3939.832 | UNIT-II |  | 99 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
| 200X200X16 MS | 933 \ 2DF3 \ 205 | 472 |  | 80 | 1832.48 | UNIT-II |  | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF3 \ 206 | 472 | 402 | 109 | 1623.555 | UNIT-II |  | 18 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| 130X130X12 MS | 933 \ 2DF3 \ 211A | 2701 |  | 2 | 126.676 | UNIT-II |  | 3 |  |  |  |  | N/A |  | Slow | 35.6468 |  |  | Unknown | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 218 | 612 | 457 | 44 | 966.02 | UNIT-II |  | 18 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 220 | 367 | 252 | 44 | 319.44 | UNIT-II |  | 15 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| 150X150X12 MS | 933 \ 2DF3 \ 221L | 343 |  | 44 | 411.84 | UNIT-II |  | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF3 \ 221R | 343 |  | 42 | 393.12 | UNIT-II |  | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 222 | 367 | 255 | 44 | 323.224 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| 150X150X12 MS | 933 \ 2DF3 \ 223L | 346 |  | 44 | 415.448 | UNIT-II |  | 104 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF3 \ 223R | 346 |  | 14 | 132.188 | UNIT-II |  | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF3 \ 224R | 339 |  | 42 | 388.542 | UNIT-II |  | 29 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 225 | 547 | 504 | 20 | 432.84 | UNIT-II |  | 18 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| 200X200X16 MS | 933 \ 2DF3 \ 226L | 601 |  | 23 | 670.841 | UNIT-II |  | 3 |  |  |  |  | N/A |  | Moving |  |  |  | Unknown | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF3 \ 227 | 402 | 332 | 44 | 460.988 | UNIT-II |  | 12 |  |  |  |  | N/A | Yes | Stalled | 28.7989 |  |  | Stalled | PLATE | Punching
| 200X200X16 MS | 933 \ 2DF3 \ 228L | 429 |  | 44 | 916.036 | UNIT-II |  | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF3 \ 232 | 457 | 225 | 44 | 355.168 | UNIT-II |  | 18 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 233 | 457 | 115 | 44 | 181.544 | UNIT-II |  | 18 |  |  |  |  | N/A | Yes | Stalled | 14.7178 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 234 | 252 | 170 | 44 | 147.972 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 235 | 252 | 115 | 44 | 100.1 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 236 | 255 | 170 | 44 | 149.732 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 237 | 255 | 115 | 36 | 82.872 | UNIT-II |  | 16 |  |  |  |  | N/A | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 238 | 248 | 115 | 38 | 85.082 | UNIT-II |  | 1 |  |  |  |  | N/A |  | Slow | 25.5502 |  |  | Unknown | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 239 | 504 | 135 | 88 | 470.008 | UNIT-II |  | 7 |  |  |  |  | N/A |  | Moving |  |  |  | Unknown | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 240 | 402 | 120 | 63 | 238.581 | UNIT-II |  | 36 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 241 | 332 | 135 | 88 | 309.584 | UNIT-II |  | 29 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 244 | 331 | 135 | 44 | 154.352 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 247 | 692 | 153 | 44 | 365.684 | UNIT-II |  | 18 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| 200X200X16 MS | 933 \ 2DF3 \ 249L | 162 |  | 22 | 172.964 | UNIT-II |  | 8 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| 200X200X16 MS | 933 \ 2DF3 \ 249R | 162 |  | 22 | 172.964 | UNIT-II |  | 8 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF3 \ 250 | 149 | 135 | 44 | 69.476 | UNIT-II |  | 14 |  |  |  |  | N/A | Yes | Stalled | 12.7201 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 252 | 380 | 248 | 44 | 325.512 | UNIT-II |  | 31 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| A 200X200X20 MS | 933 \ 2DF3 \ 265 | 2845 |  | 1 | 170.586 | UNIT-II |  | 14 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
| A 50X50X6 MS | 933 \ 2DF3 \ 27 | 981 |  | 44 | 193.82 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF3 \ 274 | 804 |  | 88 | 418.176 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF3 \ 276 | 1647 |  | 88 | 856.592 | UNIT-II |  | 18 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF3 \ 278 | 545 |  | 88 | 283.448 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF3 \ 280 | 1015 |  | 88 | 527.912 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF3 \ 283 | 1210 |  | 88 | 629.288 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 200X200X16 MS | 933 \ 2DF3 \ 286 | 221 |  | 88 | 943.8 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF3 \ 287 | 392 | 136 | 44 | 184.14 | UNIT-II |  | 65 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| 200X200X16 MS | 933 \ 2DF3 \ 288 | 136 |  | 264 | 1742.4 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF3 \ 289 | 392 | 136 | 212 | 887.22 | UNIT-II |  | 15 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| 200X200X16 MS | 933 \ 2DF3 \ 290 | 136 |  | 792 | 5227.2 | UNIT-II |  | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF3 \ 292 | 221 | 135 | 86 | 201.412 | UNIT-II |  | 16 |  |  |  |  | N/A | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 293 | 135 | 136 | 264 | 380.424 | UNIT-II |  | 14 |  |  |  |  | N/A | Yes | Stalled | 12.7201 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 294 | 135 | 136 | 792 | 1141.272 | UNIT-II |  | 14 |  |  |  |  | N/A | Yes | Stalled | 12.7201 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 296 | 602 | 392 | 22 | 407.55 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| 65X65X6 MS | 933 \ 2DF3 \ 316 | 1254 |  | 88 | 652.168 | UNIT-II |  | 18 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF3 \ 317 | 1818 |  | 61 | 655.384 | UNIT-II |  | 15 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF3 \ 320 | 996 |  | 88 | 517.968 | UNIT-II |  | 18 |  |  |  |  | N/A | Yes | Stalled | 32.8408 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF3 \ 323 | 1513 |  | 71 | 634.882 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF3 \ 326 | 1704 |  | 88 | 886.248 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF3 \ 327 | 1254 |  | 88 | 652.168 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled | 32.8408 |  |  | Stalled | ANGLE | Punching
| 110X110X8 MS | 933 \ 2DF3 \ 328 | 378 |  | 44 | 222.86 | UNIT-II |  | 65 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 333 | 578 | 464 | 24 | 505.272 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 334 | 578 | 135 | 22 | 134.75 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 335 | 578 | 205 | 44 | 409.244 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 338 | 402 | 145 | 31 | 141.856 | UNIT-II |  | 18 |  |  |  |  | N/A | Yes | Stalled | 14.7178 |  |  | Stalled | PLATE | Punching
| 200X200X16 MS | 933 \ 2DF3 \ 341 | 143 |  | 88 | 610.72 | UNIT-II |  | 8 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF3 \ 342 | 143 | 392 | 44 | 193.6 | UNIT-II |  | 36 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 343 | 143 | 135 | 88 | 133.32 | UNIT-II |  | 3 |  |  |  |  | N/A |  | Slow | 25.5502 |  |  | Unknown | PLATE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 38 | 1304 |  | 44 | 257.62 | UNIT-II |  | 19 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 44 | 283 | 128 | 40 | 113.76 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 46R | 1085 |  | 22 | 107.184 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 47 | 980 |  | 44 | 193.6 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 54 | 1335 |  | 22 | 131.868 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 57 | 1315 |  | 44 | 259.776 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 23.7885 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 69 | 711 |  | 22 | 70.224 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 74 | 1401 |  | 44 | 276.76 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 83L | 1111 |  | 1 | 4.988 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 83XL | 1109 |  | 22 | 109.538 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 84 | 682 |  | 88 | 269.456 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 85XL | 1250 |  | 22 | 123.486 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 85XR | 1250 |  | 22 | 123.486 | UNIT-II |  | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 130X130X12 MS | 933 \ 2DF3 \ 90 | 2486 |  | 5 | 291.485 | UNIT-II |  | 64 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 92 | 1404 |  | 25 | 157.6 | UNIT-II |  | 21 |  |  |  |  | N/A | Yes | Stalled | 24.8672 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 97 | 689 |  | 66 | 204.204 | UNIT-II |  | 19 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF5M \ 206 | 402 | 472 | 4 | 59.58 | UNIT-II |  | 30 |  |  |  |  | N/A |  | Moving |  |  |  | Unknown | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF5M \ 207 | 135 | 472 | 8 | 40.016 | UNIT-II |  | 30 |  |  |  |  | N/A |  | Slow | 21.4213 |  |  | Unknown | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF5M \ 272 | 120 | 392 | 12 | 44.316 | UNIT-II |  | 30 |  |  |  |  | N/A |  | Moving |  |  |  | Unknown | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF5M \ 289 | 136 | 392 | 12 | 50.22 | UNIT-II |  | 30 |  |  |  |  | N/A |  | Slow | 21.4213 |  |  | Unknown | PLATE | Punching
| 200X200X16 MS | 933 \ 2DF5M \ 341 | 143 |  | 3 | 20.82 | UNIT-II |  | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF5M \ 342 | 143 | 392 | 4 | 17.6 | UNIT-II |  | 30 |  |  |  |  | N/A |  | Moving |  |  |  | Unknown | PLATE | Punching
| 65X65X6 MS | 933 \ 2DF5M \ 354 | 1771 |  | 8 | 83.736 | UNIT-II |  | 30 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF5M \ 355 | 2233 |  | 8 | 105.576 | UNIT-II |  | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF5M \ 358 | 1513 |  | 8 | 71.536 | UNIT-II |  | 21 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF5M \ 360 | 354 | 392 | 4 | 43.572 | UNIT-II |  | 30 |  |  |  |  | N/A |  | Moving |  |  |  | Unknown | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF5M \ 361 | 354 | 135 | 8 | 30.016 | UNIT-II |  | 30 |  |  |  |  | N/A |  | Moving |  |  |  | Unknown | PLATE | Punching
ACTIVITY-WISE SUBTOTAL
Release Balance
Assignement Balance
C |  |  |  |  | 4749 | 17043.202 |  |  | 52
RFI |  |  |  |  | 3553 | 21552.567 |  |  | 52
NH |  |  |  |  | 128 | 1257.532 |  |  | 34
B |  |  |  |  | 210 | 937.472 |  |  | 22
Q |  |  |  |  | 704 | 5140.878 |  |  | 34
TS |  |  |  |  | 993 | 2439.812 |  |  | 38
G |  |  |  |  | 2432 | 12059.092 |  |  | 37
GB |  |  |  |  | 927 | 9384.093 |  |  | 32
Y |  |  |  |  | 2493 | 23483.141 |  |  | 39
Finished Goods (FG) |  |  |  |  | 13053 | 94935.934 |  |  | 23
TOTAL |  |  |  |  | 29242 | 188233.723

## C
Activity | Section | Mark No. | Length | Width | Balance Qty | Balance Wt (kg) | Contractor | Ageing (days) | Cumulative Target (days) | Overrun (days) | Consumed % | Days to Target | Lifecycle Status | Stalled | Velocity Status | Days / Stage | ETA (days) | ETA Gap (days) | Trend | Section Type | Hole Operation
C | PLATE 8 MM MS | 933 \ 2AF10M \ 328P | 280 | 50 | 8 | 7.032 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 6 MM MS | 933 \ 2AF10M \ 345 | 281 | 60 | 32 | 25.408 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 10 MM MS | 933 \ 2AF10M \ 369 | 225 | 200 | 8 | 28.264 | METAL PARK (UNIT-II - JAIN PLATE) | 99 | 15 | 84 | 660 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 10 MM MS | 933 \ 2AF10M \ 378 | 335 | 200 | 8 | 42.08 | METAL PARK (UNIT-II - JAIN PLATE) | 99 | 15 | 84 | 660 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 10 MM MS | 933 \ 2AF10M \ 380 | 290 | 50 | 12 | 13.656 | METAL PARK (UNIT-II - JAIN PLATE) | 99 | 15 | 84 | 660 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 10 MM MS | 933 \ 2AF10M \ 385 | 225 | 200 | 8 | 28.264 | METAL PARK (UNIT-II - JAIN PLATE) | 99 | 15 | 84 | 660 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | 45X45X5 MS | 933 \ 2AF10M \ 386 | 2783 |  | 1 | 9.434 | SRIJAN ENTERPRISES (UNIT-II) | 41 | 15 | 26 | 273 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | PLATE 8 MM MS | 933 \ 2AF3 \ 208P | 170 | 50 | 44 | 23.496 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 12 MM MS | 933 \ 2AF3 \ 247 | 130 | 50 | 44 | 26.928 | JAIN ASSOCIATES | 113 | 15 | 98 | 753 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 20 MM MS | 933 \ 2AF3 \ 286P | 56 | 136 | 44 | 52.624 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 74 | 15 | 59 | 493 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 20 MM MS | 933 \ 2AF3 \ 287P | 96 | 56 | 44 | 37.136 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 74 | 15 | 59 | 493 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 6 MM MS | 933 \ 2AF3 \ 3 | 422 | 165 | 11 | 36.08 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | A 75X75X8 MS | 933 \ 2AF3 \ 32 | 162 |  | 264 | 384.912 | CNC APM 1616 | 45 | 15 | 30 | 300 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | PLATE 8 MM MS | 933 \ 2AF3 \ 328P | 280 | 50 | 352 | 309.408 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 20 MM MS | 933 \ 2AF3 \ 329P | 56 | 96 | 44 | 37.136 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 74 | 15 | 59 | 493 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 6 MM MS | 933 \ 2AF3 \ 330 | 100 | 170 | 66 | 52.866 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 6 MM MS | 933 \ 2AF3 \ 345 | 60 | 281 | 176 | 139.744 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 6 MM MS | 933 \ 2AF3 \ 4 | 175 | 119 | 22 | 21.582 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 12 MM MS | 933 \ 2AF3 \ 5 | 500 | 140 | 11 | 72.534 | JAIN ASSOCIATES | 113 | 15 | 98 | 753 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 8 MM MS | 933 \ 2AF5M \ 328P | 280 | 50 | 8 | 7.032 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | 45X45X5 MS | 933 \ 2AF5M \ 339 | 2430 |  | 3 | 24.714 | SRIJAN ENTERPRISES (UNIT-II) | 41 | 15 | 26 | 273 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | 200X200X20 MS | 933 \ 2AF5M \ 341S | 5016 |  | 2 | 601.518 | CNC TADM 2532 | 45 | 15 | 30 | 300 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
C | PLATE 6 MM MS | 933 \ 2AF5M \ 345 | 281 | 60 | 16 | 12.704 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 12 MM MS | 933 \ 2AF5M \ 357 | 410 | 211 | 4 | 32.596 | JAIN ASSOCIATES | 113 | 15 | 98 | 753 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 10 MM MS | 933 \ 2AF5M \ 369 | 225 | 200 | 8 | 28.264 | METAL PARK (UNIT-II - JAIN PLATE) | 99 | 15 | 84 | 660 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 6 MM MS | 933 \ 2DF-5 \ 12 | 189 | 129 | 16 | 18.368 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | 130X130X12 MS | 933 \ 2DF-5 \ 121 | 436 |  | 16 | 163.584 | SRIJAN ENTERPRISES | 91 | 15 | 76 | 607 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | PLATE 6 MM MS | 933 \ 2DF-5 \ 13 | 145 | 115 | 16 | 12.56 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 2 MM MS | 933 \ 2DF-5 \ 166P | 200 | 115 | 64 | 23.104 | SRIJAN ENTERPRISES (UNIT-II) | 74 | 15 | 59 | 493 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 20 MM MS | 933 \ 2DF-5 \ 180 | 105 | 60 | 8 | 7.912 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 74 | 15 | 59 | 493 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 24 MM MS | 933 \ 2DF-5 \ 217 | 122 | 60 | 16 | 22.064 | METAL PARK (UNIT-II - JAIN PLATE) | 6 | 15 | -9 | 40 | 9 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 20 MM MS | 933 \ 2DF-5 \ 218P | 186 | 56 | 16 | 26.16 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 74 | 15 | 59 | 493 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 20 MM MS | 933 \ 2DF-5 \ 225P | 136 | 56 | 16 | 19.136 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 74 | 15 | 59 | 493 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 24 MM MS | 933 \ 2DF-5 \ 245 | 121 | 60 | 48 | 65.664 | METAL PARK (UNIT-II - JAIN PLATE) | 6 | 15 | -9 | 40 | 9 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 24 MM MS | 933 \ 2DF-5 \ 246 | 121 | 60 | 64 | 87.552 | METAL PARK (UNIT-II - JAIN PLATE) | 6 | 15 | -9 | 40 | 9 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 8 MM MS | 933 \ 2DF-5 \ 271 | 150 | 50 | 96 | 45.216 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 8 MM MS | 933 \ 2DF-5 \ 291 | 131 | 50 | 288 | 118.368 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 6 MM MS | 933 \ 2DF-5 \ 3 | 169 | 120 | 8 | 7.64 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | A 75X75X8 MS | 933 \ 2DF-5 \ 32 | 300 |  | 48 | 129.6 | CNC APM 1616 | 45 | 15 | 30 | 300 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | 200X200X20 MS | 933 \ 2DF-5 \ 336 | 402 |  | 20 | 482.08 | CNC TADM 2532 | 45 | 15 | 30 | 300 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
C | PLATE 8 MM MS | 933 \ 2DF-5 \ 339 | 131 | 50 | 96 | 39.456 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 6 MM MS | 933 \ 2DF-5 \ 4 | 429 | 148 | 4 | 11.96 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 6 MM MS | 933 \ 2DF3 \ 12 | 189 | 129 | 44 | 50.512 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 6 MM MS | 933 \ 2DF3 \ 13 | 145 | 115 | 44 | 34.54 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 2 MM MS | 933 \ 2DF3 \ 166P | 200 | 115 | 176 | 63.536 | SRIJAN ENTERPRISES (UNIT-II) | 74 | 15 | 59 | 493 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 20 MM MS | 933 \ 2DF3 \ 180 | 105 | 60 | 22 | 21.758 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 74 | 15 | 59 | 493 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 24 MM MS | 933 \ 2DF3 \ 217 | 122 | 60 | 44 | 60.676 | METAL PARK (UNIT-II - JAIN PLATE) | 6 | 15 | -9 | 40 | 9 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 20 MM MS | 933 \ 2DF3 \ 218P | 186 | 56 | 44 | 71.94 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 74 | 15 | 59 | 493 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 20 MM MS | 933 \ 2DF3 \ 225P | 136 | 56 | 44 | 52.624 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 74 | 15 | 59 | 493 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 24 MM MS | 933 \ 2DF3 \ 245 | 121 | 60 | 132 | 180.576 | METAL PARK (UNIT-II - JAIN PLATE) | 6 | 15 | -9 | 40 | 9 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 24 MM MS | 933 \ 2DF3 \ 246 | 121 | 60 | 176 | 240.768 | METAL PARK (UNIT-II - JAIN PLATE) | 6 | 15 | -9 | 40 | 9 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | PLATE 8 MM MS | 933 \ 2DF3 \ 271 | 150 | 50 | 264 | 124.344 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 8 MM MS | 933 \ 2DF3 \ 291 | 131 | 50 | 792 | 325.512 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 6 MM MS | 933 \ 2DF3 \ 3 | 169 | 120 | 22 | 21.01 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | A 100X100X10 MS | 933 \ 2DF3 \ 321 | 3075 |  | 88 | 4069.824 | UNIT-I | 4 | 15 | -11 | 27 | 11 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | A 100X100X10 MS | 933 \ 2DF3 \ 322 | 4316 |  | 44 | 2856.172 | UNIT-I | 4 | 15 | -11 | 27 | 11 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | A 100X100X10 MS | 933 \ 2DF3 \ 322A | 4316 |  | 44 | 2856.172 | UNIT-I | 4 | 15 | -11 | 27 | 11 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | 100X100X8 MS | 933 \ 2DF3 \ 330 | 348 |  | 88 | 373.032 | CNC APM 1010 | 23 | 15 | 8 | 153 | 0 | Breach 2 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | PLATE 8 MM MS | 933 \ 2DF3 \ 331 | 308 | 60 | 176 | 204.336 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | 200X200X20 MS | 933 \ 2DF3 \ 336 | 402 |  | 54 | 1301.616 | CNC TADM 2532 | 45 | 15 | 30 | 300 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
C | PLATE 8 MM MS | 933 \ 2DF3 \ 339 | 131 | 50 | 264 | 108.504 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | PLATE 6 MM MS | 933 \ 2DF3 \ 4 | 429 | 148 | 11 | 32.89 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | 65X65X6 MS | 933 \ 2DF5M \ 176 | 425 |  | 9 | 22.608 | SRIJAN ENTERPRISES (UNIT-II) | 84 | 15 | 69 | 560 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | 100X100X8 MS | 933 \ 2DF5M \ 330 | 348 |  | 8 | 33.912 | CNC APM 1010 | 23 | 15 | 8 | 153 | 0 | Breach 2 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | PLATE 8 MM MS | 933 \ 2DF5M \ 331 | 60 | 308 | 16 | 18.576 | METAL PARK (UNIT-II - JAIN ASSOCIATES) | 58 | 15 | 43 | 387 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | 50X50X5 MS | 933 \ IS-933 \ 2AF1 \ 07 | 2184 |  | 28 | 231.756 | SRIJAN ENTERPRISES | 17 | 15 | 2 | 113 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | 50X50X5 MS | 933 \ IS-933 \ 2AF1 \ 08 | 2142 |  | 28 | 227.304 | SRIJAN ENTERPRISES | 17 | 15 | 2 | 113 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | PLATE 16 MM MS | 933 \ SC-933 \ 2AF3 \ 267 | 145 | 472 | 1 | 8.596 | METAL PARK (UNIT-II - JAIN PLATE) | 10 | 15 | -5 | 67 | 5 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
C | 50X50X5 MS | 933 \ SC-933 \ 2AF3 \ 308 | 1082 |  | 1 | 4.101 | DASHMESH ENTERPRISES (UNIT-II) | 10 | 15 | -5 | 67 | 5 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | 75X75X8 MS | 933 \ SC-933 \ 2AF5M \ 353A | 2991 |  | 1 | 26.919 | DASHMESH ENTERPRISES (UNIT-II) | 10 | 15 | -5 | 67 | 5 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | 100X100X10 MS | 933 \ SC-933 \ 2DF \ 5\123 | 2768 |  | 1 | 41.631 | DASHMESH ENTERPRISES (UNIT-II) | 10 | 15 | -5 | 67 | 5 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
C | 200X200X16 MS | 933 \ SC-933 \ 2DF \ 5\205 | 472 |  | 1 | 22.906 | CNC APM 2020 | 16 | 15 | 1 | 107 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
C | PLATE 10 MM MS | 933 \ SC-933 \ 2DF \ 5\232 | 457 | 225 | 1 | 8.072 | METAL PARK (UNIT-II - JAIN PLATE) | 10 | 15 | -5 | 67 | 5 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
C | 150X150X12 MS | 933 \ SC-933 \ 2DF3 \ 164L | 390 |  | 1 | 10.643 | DASHMESH ENTERPRISES (UNIT-II) | 10 | 15 | -5 | 67 | 5 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TOTAL |  |  |  |  | 4749 | 17043.202

## RFI
Activity | Section | Mark No. | Length | Width | Balance Qty | Balance Wt (kg) | Contractor | Ageing (days) | Cumulative Target (days) | Overrun (days) | Consumed % | Days to Target | Lifecycle Status | Stalled | Velocity Status | Days / Stage | ETA (days) | ETA Gap (days) | Trend | Section Type | Hole Operation
RFI | 200X200X20 MS | 933 \ 2AF10M \ 341 | 5016 |  | 2 | 601.518 | CNC TADM 2532 | 38 | 29 | 9 | 131 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 200X200X20 MS | 933 \ 2AF10M \ 341S | 5016 |  | 2 | 601.518 | CNC TADM 2532 | 38 | 29 | 9 | 131 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 65X65X6 MS | 933 \ 2AF10M \ 344 | 316 |  | 16 | 29.888 | SRIJAN ENTERPRISES (UNIT-II) | 30 | 29 | 1 | 103 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 75X75X8 MS | 933 \ 2AF10M \ 352 | 4213 |  | 4 | 151.668 | SRIJAN ENTERPRISES (UNIT-II) | 30 | 29 | 1 | 103 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 75X75X8 MS | 933 \ 2AF10M \ 352A | 4213 |  | 4 | 151.668 | SRIJAN ENTERPRISES (UNIT-II) | 30 | 29 | 1 | 103 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 75X75X8 MS | 933 \ 2AF10M \ 353 | 2991 |  | 4 | 107.676 | SRIJAN ENTERPRISES (UNIT-II) | 30 | 29 | 1 | 103 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 75X75X8 MS | 933 \ 2AF10M \ 353A | 2991 |  | 4 | 107.676 | SRIJAN ENTERPRISES (UNIT-II) | 30 | 29 | 1 | 103 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 65X65X6 MS | 933 \ 2AF10M \ 354 | 1331 |  | 8 | 62.928 | SRIJAN ENTERPRISES (UNIT-II) | 73 | 29 | 44 | 252 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 65X65X6 MS | 933 \ 2AF10M \ 356 | 2473 |  | 8 | 116.92 | SRIJAN ENTERPRISES (UNIT-II) | 73 | 29 | 44 | 252 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 65X65X6 MS | 933 \ 2AF10M \ 358 | 1716 |  | 8 | 81.136 | SRIJAN ENTERPRISES (UNIT-II) | 73 | 29 | 44 | 252 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 200X200X20 MS | 933 \ 2AF10M \ 370 | 4939 |  | 2 | 592.284 | CNC TADM 2532 | 38 | 29 | 9 | 131 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 200X200X20 MS | 933 \ 2AF10M \ 370S | 4939 |  | 2 | 592.284 | CNC TADM 2532 | 38 | 29 | 9 | 131 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 75X75X8 MS | 933 \ 2AF10M \ 371 | 4458 |  | 4 | 160.488 | SRIJAN ENTERPRISES (UNIT-II) | 30 | 29 | 1 | 103 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 75X75X8 MS | 933 \ 2AF10M \ 371A | 4458 |  | 4 | 160.488 | SRIJAN ENTERPRISES (UNIT-II) | 30 | 29 | 1 | 103 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 75X75X8 MS | 933 \ 2AF10M \ 372 | 3215 |  | 4 | 115.74 | SRIJAN ENTERPRISES (UNIT-II) | 30 | 29 | 1 | 103 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 75X75X8 MS | 933 \ 2AF10M \ 372A | 3215 |  | 4 | 115.74 | SRIJAN ENTERPRISES (UNIT-II) | 30 | 29 | 1 | 103 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 65X65X6 MS | 933 \ 2AF10M \ 373 | 1508 |  | 8 | 71.296 | SRIJAN ENTERPRISES (UNIT-II) | 73 | 29 | 44 | 252 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 65X65X6 MS | 933 \ 2AF10M \ 376 | 1821 |  | 8 | 86.096 | SRIJAN ENTERPRISES (UNIT-II) | 73 | 29 | 44 | 252 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | PLATE 16 MM MS | 933 \ 2AF3 \ 31 | 500 | 305 | 132 | 2528.328 | METAL PARK (UNIT-II - JAIN PLATE) | 72 | 29 | 43 | 248 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
RFI | 65X65X6 MS | 933 \ 2AF3 \ 344 | 316 |  | 88 | 164.384 | SRIJAN ENTERPRISES (UNIT-II) | 30 | 29 | 1 | 103 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 200X200X20 MS | 933 \ 2AF5M \ 341 | 5016 |  | 2 | 601.518 | CNC TADM 2532 | 43 | 29 | 14 | 148 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 65X65X6 MS | 933 \ 2AF5M \ 344 | 316 |  | 24 | 44.832 | SRIJAN ENTERPRISES (UNIT-II) | 30 | 29 | 1 | 103 | 0 | Breach 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 75X75X8 MS | 933 \ 2AF5M \ 353A | 2991 |  | 4 | 107.676 | CNC APM 1010 | 48 | 29 | 19 | 166 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 65X65X6 MS | 933 \ 2AF5M \ 354 | 1331 |  | 6 | 47.196 | SRIJAN ENTERPRISES (UNIT-II) | 73 | 29 | 44 | 252 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 100X100X10 MS | 933 \ 2DF-5 \ 101S | 5379 |  | 4 | 323.6 | CNC APM 1616 | 86 | 29 | 57 | 297 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 130X130X12 MS | 933 \ 2DF-5 \ 166 | 416 |  | 64 | 624.32 | SRIJAN ENTERPRISES | 35 | 29 | 6 | 121 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 65X65X6 MS | 933 \ 2DF-5 \ 176 | 425 |  | 468 | 1175.616 | SRIJAN ENTERPRISES (UNIT-II) | 60 | 29 | 31 | 207 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 200X200X16 MS | 933 \ 2DF-5 \ 204X | 472 |  | 16 | 366.496 | CNC APM 2020 | 55 | 29 | 26 | 190 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | PLATE 10 MM MS | 933 \ 2DF-5 \ 22 | 285 | 125 | 8 | 22.376 | SRIJAN ENTERPRISES (UNIT-II) | 65 | 29 | 36 | 224 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
RFI | A 50X50X6 MS | 933 \ 2DF-5 \ 23 | 360 |  | 48 | 77.568 | DASHMESH ENTERPRISES (UNIT-II) | 88 | 29 | 59 | 303 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 200X200X16 MS | 933 \ 2DF-5 \ 248L | 162 |  | 8 | 62.896 | CNC APM 2020 | 54 | 29 | 25 | 186 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 200X200X16 MS | 933 \ 2DF-5 \ 248R | 162 |  | 8 | 62.896 | CNC APM 2020 | 54 | 29 | 25 | 186 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 200X200X16 MS | 933 \ 2DF-5 \ 249L | 162 |  | 8 | 62.896 | CNC APM 2020 | 54 | 29 | 25 | 186 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 200X200X16 MS | 933 \ 2DF-5 \ 249R | 162 |  | 8 | 62.896 | CNC APM 2020 | 54 | 29 | 25 | 186 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | PLATE 10 MM MS | 933 \ 2DF-5 \ 293 | 135 | 136 | 96 | 138.336 | SRIJAN ENTERPRISES (UNIT-II) | 65 | 29 | 36 | 224 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
RFI | PLATE 16 MM MS | 933 \ 2DF-5 \ 31 | 480 | 230 | 48 | 665.568 | METAL PARK (UNIT-II - JAIN PLATE) | 65 | 29 | 36 | 224 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
RFI | 110X110X8 MS | 933 \ 2DF-5 \ 328 | 378 |  | 32 | 162.08 | CNC APM 2020 (A) | 73 | 29 | 44 | 252 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 200X200X20 MS | 933 \ 2DF-5 \ 336 | 402 |  | 12 | 289.248 | CNC TADM 2532 | 38 | 29 | 9 | 131 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 45X45X5 MS | 933 \ 2DF-5 \ 340 | 2360 |  | 4 | 32 | SRIJAN ENTERPRISES (UNIT-II) | 27 | 29 | -2 | 93 | 2 | Pre-warning 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | A 50X50X6 MS | 933 \ 2DF-5 \ 82 | 365 |  | 48 | 78.672 | DASHMESH ENTERPRISES (UNIT-II) | 88 | 29 | 59 | 303 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | A 50X50X6 MS | 933 \ 2DF-5 \ 84 | 682 |  | 32 | 97.984 | DASHMESH ENTERPRISES (UNIT-II) | 88 | 29 | 59 | 303 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | A 50X50X6 MS | 933 \ 2DF-5 \ 84X | 681 |  | 16 | 48.928 | DASHMESH ENTERPRISES (UNIT-II) | 88 | 29 | 59 | 303 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 50X50X6 MS | 933 \ 2DF-5 \ 91AX | 3221 |  | 4 | 57.848 | SRIJAN ENTERPRISES (UNIT-II) | 39 | 29 | 10 | 134 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 50X50X6 MS | 933 \ 2DF-5 \ 91X | 3221 |  | 4 | 57.848 | SRIJAN ENTERPRISES (UNIT-II) | 39 | 29 | 10 | 134 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 130X130X12 MS | 933 \ 2DF3 \ 166 | 416 |  | 176 | 1716.88 | CNC APM 2020 (A) | 35 | 29 | 6 | 121 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 65X65X6 MS | 933 \ 2DF3 \ 176 | 425 |  | 1386 | 3481.632 | SRIJAN ENTERPRISES (UNIT-II) | 60 | 29 | 31 | 207 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | A 50X50X6 MS | 933 \ 2DF3 \ 23 | 360 |  | 132 | 213.312 | DASHMESH ENTERPRISES (UNIT-II) | 88 | 29 | 59 | 303 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | PLATE 16 MM MS | 933 \ 2DF3 \ 31 | 480 | 230 | 132 | 1830.312 | METAL PARK (UNIT-II - JAIN PLATE) | 77 | 29 | 48 | 266 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
RFI | A 75X75X8 MS | 933 \ 2DF3 \ 32 | 300 |  | 60 | 162 | CNC APM 1616 | 25 | 29 | -4 | 86 | 4 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | A 75X75X8 MS | 933 \ 2DF3 \ 32 | 300 |  | 40 | 108 | CNC APM 1616 | 44 | 29 | 15 | 152 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | A 75X75X8 MS | 933 \ 2DF3 \ 32 | 300 |  | 32 | 86.4 | CNC APM 1616 | 32 | 29 | 3 | 110 | 0 | Breach 2 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 200X200X20 MS | 933 \ 2DF3 \ 336 | 402 |  | 14 | 337.456 | CNC TADM 2532 | 20 | 29 | -9 | 69 | 9 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 200X200X20 MS | 933 \ 2DF3 \ 336 | 402 |  | 20 | 482.08 | CNC TADM 2532 | 21 | 29 | -8 | 72 | 8 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 45X45X5 MS | 933 \ 2DF3 \ 340 | 2360 |  | 11 | 88 | SRIJAN ENTERPRISES (UNIT-II) | 27 | 29 | -2 | 93 | 2 | Pre-warning 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | A 50X50X6 MS | 933 \ 2DF3 \ 82 | 365 |  | 132 | 216.348 | DASHMESH ENTERPRISES (UNIT-II) | 88 | 29 | 59 | 303 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | A 50X50X6 MS | 933 \ 2DF3 \ 84X | 681 |  | 44 | 134.552 | DASHMESH ENTERPRISES (UNIT-II) | 88 | 29 | 59 | 303 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | A 50X50X6 MS | 933 \ 2DF3 \ 86X | 997 |  | 44 | 196.988 | DASHMESH ENTERPRISES (UNIT-II) | 88 | 29 | 59 | 303 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
RFI | 200X200X16 MS | 933 \ 2DF5M \ 204 | 472 |  | 8 | 183.248 | CNC APM 2020 | 54 | 29 | 25 | 186 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 200X200X16 MS | 933 \ 2DF5M \ 205 | 472 |  | 8 | 183.248 | CNC APM 2020 | 54 | 29 | 25 | 186 | 0 | Breach 3 |  | Moving |  |  |  | Stalled | ANGLE | Drilling
RFI | 200X200X16 MS | 933 \ 2DF5M \ 290 | 136 |  | 12 | 79.2 | CNC APM 2020 | 53 | 29 | 24 | 183 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 200X200X16 MS | 933 \ 2DF5M \ 341 | 143 |  | 5 | 34.7 | CNC APM 2020 | 53 | 29 | 24 | 183 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 200X200X16 MS | 933 \ 2DF5M \ 359 | 354 |  | 8 | 137.44 | CNC APM 2020 | 14 | 29 | -15 | 48 | 15 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
RFI | 45X45X5 MS | 933 \ 2DF5M \ 362 | 2877 |  | 1 | 9.753 | SRIJAN ENTERPRISES (UNIT-II) | 27 | 29 | -2 | 93 | 2 | Pre-warning 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TOTAL |  |  |  |  | 3553 | 21552.567

## NH
Activity | Section | Mark No. | Length | Width | Balance Qty | Balance Wt (kg) | Contractor | Ageing (days) | Cumulative Target (days) | Overrun (days) | Consumed % | Days to Target | Lifecycle Status | Stalled | Velocity Status | Days / Stage | ETA (days) | ETA Gap (days) | Trend | Section Type | Hole Operation
NH | PLATE 12 MM MS | 933 \ 2AF10M \ 357 | 410 | 211 | 4 | 32.596 | JAIN ASSOCIATES | 34 | 36 | -2 | 94 | 2 | Pre-warning 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
NH | 150X150X12 MS | 933 \ 2DF-5 \ 158L | 366 |  | 16 | 159.808 | UNIT-I | 34 | 36 | -2 | 94 | 2 | Pre-warning 3 |  | Moving |  |  |  | Unknown | ANGLE | Punching
NH | 150X150X12 MS | 933 \ 2DF-5 \ 158R | 366 |  | 16 | 159.808 | UNIT-I | 34 | 36 | -2 | 94 | 2 | Pre-warning 3 |  | Moving |  |  |  | Unknown | ANGLE | Punching
NH | PLATE 12 MM MS | 933 \ 2DF-5 \ 5 | 500 | 140 | 4 | 26.376 | JAIN ASSOCIATES | 34 | 36 | -2 | 94 | 2 | Pre-warning 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
NH | 150X150X12 MS | 933 \ 2DF3 \ 158L | 366 |  | 44 | 439.472 | UNIT-I | 34 | 36 | -2 | 94 | 2 | Pre-warning 3 |  | Moving |  |  |  | Unknown | ANGLE | Punching
NH | 150X150X12 MS | 933 \ 2DF3 \ 158R | 366 |  | 44 | 439.472 | UNIT-I | 34 | 36 | -2 | 94 | 2 | Pre-warning 3 |  | Moving |  |  |  | Unknown | ANGLE | Punching
TOTAL |  |  |  |  | 128 | 1257.532

## B
Activity | Section | Mark No. | Length | Width | Balance Qty | Balance Wt (kg) | Contractor | Ageing (days) | Cumulative Target (days) | Overrun (days) | Consumed % | Days to Target | Lifecycle Status | Stalled | Velocity Status | Days / Stage | ETA (days) | ETA Gap (days) | Trend | Section Type | Hole Operation
B | A 50X50X6 MS | 933 \ 2DF-5 \ 63 | 672 |  | 16 | 48.272 | UNIT-I | 13 | 50 | -37 | 26 | 37 | On track |  | Moving |  |  |  | Unknown | ANGLE | Punching
B | A 50X50X6 MS | 933 \ 2DF-5 \ 86 | 998 |  | 32 | 143.392 | UNIT-I | 13 | 50 | -37 | 26 | 37 | On track |  | Moving |  |  |  | Unknown | ANGLE | Punching
B | A 50X50X6 MS | 933 \ 2DF-5 \ 87XL | 1257 |  | 8 | 45.152 | DASHMESH ENTERPRISES (UNIT-II) | 30 | 50 | -20 | 60 | 20 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
B | A 50X50X6 MS | 933 \ 2DF-5 \ 87XR | 1257 |  | 8 | 45.152 | DASHMESH ENTERPRISES (UNIT-II) | 30 | 50 | -20 | 60 | 20 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
B | A 50X50X6 MS | 933 \ 2DF3 \ 63 | 672 |  | 44 | 132.748 | SARLA TRADING COMAPNY (BDM) | 13 | 50 | -37 | 26 | 37 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
B | A 50X50X6 MS | 933 \ 2DF3 \ 65 | 985 |  | 44 | 194.612 | SARLA TRADING COMAPNY (BDM) | 13 | 50 | -37 | 26 | 37 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
B | A 50X50X6 MS | 933 \ 2DF3 \ 87XR | 1257 |  | 14 | 79.016 | DASHMESH ENTERPRISES (UNIT-II) | 30 | 50 | -20 | 60 | 20 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
B | A 50X50X6 MS | 933 \ 2DF3 \ 87YL | 1261 |  | 22 | 124.564 | DASHMESH ENTERPRISES (UNIT-II) | 30 | 50 | -20 | 60 | 20 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
B | A 50X50X6 MS | 933 \ 2DF3 \ 87YR | 1261 |  | 22 | 124.564 | DASHMESH ENTERPRISES (UNIT-II) | 30 | 50 | -20 | 60 | 20 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TOTAL |  |  |  |  | 210 | 937.472

## Q
Activity | Section | Mark No. | Length | Width | Balance Qty | Balance Wt (kg) | Contractor | Ageing (days) | Cumulative Target (days) | Overrun (days) | Consumed % | Days to Target | Lifecycle Status | Stalled | Velocity Status | Days / Stage | ETA (days) | ETA Gap (days) | Trend | Section Type | Hole Operation
Q | PLATE 12 MM MS | 933 \ 2AF10M \ 379 | 419 | 199 | 4 | 31.416 | UNIT-II | 34 | 75 | -41 | 45 | 41 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Q | A 50X50X6 MS | 933 \ 2AF3 \ 93L | 1318 |  | 22 | 130.196 | UNIT-II | 34 | 75 | -41 | 45 | 41 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Q | A 50X50X6 MS | 933 \ 2AF3 \ 93R | 1318 |  | 22 | 130.196 | UNIT-II | 34 | 75 | -41 | 45 | 41 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Q | 100X100X10 MS | 933 \ 2DF-5 \ 101S | 5379 |  | 4 | 323.6 | UNIT-I | 34 | 75 | -41 | 45 | 41 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Q | PLATE 12 MM MS | 933 \ 2DF-5 \ 177 | 95 | 50 | 160 | 71.52 | UNIT-II | 34 | 75 | -41 | 45 | 41 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Q | 150X150X12 MS | 933 \ 2DF-5 \ 221L | 343 |  | 16 | 149.76 | UNIT-I | 34 | 75 | -41 | 45 | 41 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Q | 150X150X12 MS | 933 \ 2DF-5 \ 224L | 339 |  | 4 | 37.004 | UNIT-I | 34 | 75 | -41 | 45 | 41 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Q | 100X100X10 MS | 933 \ 2DF-5 \ 68 | 2486 |  | 8 | 299.112 | UNIT-I | 34 | 75 | -41 | 45 | 41 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Q | PLATE 12 MM MS | 933 \ 2DF3 \ 177 | 95 | 50 | 440 | 196.68 | UNIT-I | 34 | 75 | -41 | 45 | 41 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Q | 150X150X12 MS | 933 \ 2DF3 \ 224R | 339 |  | 2 | 18.502 | UNIT-I | 34 | 75 | -41 | 45 | 41 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Q | A 200X200X20 MS | 933 \ 2DF3 \ 267S | 2845 |  | 22 | 3752.892 | UNIT-I | 30 | 75 | -45 | 40 | 45 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
TOTAL |  |  |  |  | 704 | 5140.878

## TS
Activity | Section | Mark No. | Length | Width | Balance Qty | Balance Wt (kg) | Contractor | Ageing (days) | Cumulative Target (days) | Overrun (days) | Consumed % | Days to Target | Lifecycle Status | Stalled | Velocity Status | Days / Stage | ETA (days) | ETA Gap (days) | Trend | Section Type | Hole Operation
TS | 50X50X6 MS | 933 \ 2AF3 \ 10 | 502 |  | 44 | 99.176 | UNIT-I | 27 | 78 | -51 | 35 | 51 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | A 50X50X6 MS | 933 \ 2AF3 \ 23 | 360 |  | 44 | 71.104 | UNIT-I | 76 | 78 | -2 | 97 | 2 | Pre-warning 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | PLATE 10 MM MS | 933 \ 2AF3 \ 250 | 225 | 210 | 44 | 163.196 | UNIT-I | 4 | 78 | -74 | 5 | 74 | On track |  | Moving |  |  |  | Unknown | PLATE | Punching
TS | PLATE 10 MM MS | 933 \ 2AF3 \ 325 | 555 | 205 | 71 | 634.101 | UNIT-I | 84 | 78 | 6 | 108 | 0 | Breach 3 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
TS | A 50X50X6 MS | 933 \ 2AF3 \ 47 | 360 |  | 44 | 71.104 | UNIT-I | 76 | 78 | -2 | 97 | 2 | Pre-warning 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | 50X50X6 MS | 933 \ 2AF3 \ 6 | 778 |  | 1 | 3.493 | UNIT-I | 27 | 78 | -51 | 35 | 51 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | A 50X50X6 MS | 933 \ 2AF3 \ 68 | 360 |  | 44 | 71.104 | UNIT-I | 74 | 78 | -4 | 95 | 4 | Pre-warning 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | A 50X50X6 MS | 933 \ 2AF3 \ 88 | 363 |  | 88 | 143.44 | UNIT-I | 76 | 78 | -2 | 97 | 2 | Pre-warning 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | 75X75X8 MS | 933 \ 2DF-5 \ 14 | 466 |  | 16 | 67.104 | UNIT-I | 57 | 78 | -21 | 73 | 21 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | PLATE 8 MM MS | 933 \ 2DF-5 \ 329 | 333 | 60 | 64 | 80.32 | UNIT-I | 4 | 78 | -74 | 5 | 74 | On track |  | Moving |  |  |  | Unknown | PLATE | Punching
TS | A 50X50X6 MS | 933 \ 2DF-5 \ 41 | 181 |  | 48 | 39.024 | UNIT-I | 74 | 78 | -4 | 95 | 4 | Pre-warning 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | A 50X50X6 MS | 933 \ 2DF-5 \ 87YL | 1261 |  | 8 | 45.296 | UNIT-I | 21 | 78 | -57 | 27 | 57 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | A 50X50X6 MS | 933 \ 2DF-5 \ 87YR | 1261 |  | 8 | 45.296 | UNIT-I | 21 | 78 | -57 | 27 | 57 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | PLATE 10 MM MS | 933 \ 2DF3 \ 22 | 285 | 125 | 22 | 61.534 | UNIT-I | 4 | 78 | -74 | 5 | 74 | On track |  | Moving |  |  |  | Unknown | PLATE | Punching
TS | PLATE 8 MM MS | 933 \ 2DF3 \ 329 | 333 | 60 | 176 | 220.88 | UNIT-I | 4 | 78 | -74 | 5 | 74 | On track |  | Moving |  |  |  | Unknown | PLATE | Punching
TS | A 50X50X6 MS | 933 \ 2DF3 \ 41 | 181 |  | 132 | 107.316 | UNIT-I | 74 | 78 | -4 | 95 | 4 | Pre-warning 3 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | PLATE 12 MM MS | 933 \ 2DF3 \ 5 | 500 | 140 | 11 | 72.534 | UNIT-I | 4 | 78 | -74 | 5 | 74 | On track |  | Moving |  |  |  | Unknown | PLATE | Punching
TS | PLATE 10 MM MS | 933 \ 2DF3 \ 81P | 314 | 140 | 66 | 227.766 | UNIT-I | 80 | 78 | 2 | 103 | 0 | Breach 2 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
TS | A 50X50X6 MS | 933 \ 2DF3 \ 87XL | 1257 |  | 22 | 124.168 | UNIT-I | 21 | 78 | -57 | 27 | 57 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | A 50X50X6 MS | 933 \ 2DF3 \ 87XR | 1257 |  | 8 | 45.152 | UNIT-I | 21 | 78 | -57 | 27 | 57 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TS | PLATE 10 MM MS | 933 \ 2DF5M \ 294 | 136 | 135 | 24 | 34.584 | UNIT-I | 4 | 78 | -74 | 5 | 74 | On track |  | Moving |  |  |  | Unknown | PLATE | Punching
TS | PLATE 10 MM MS | 933 \ 2DF5M \ 343 | 135 | 143 | 8 | 12.12 | UNIT-I | 4 | 78 | -74 | 5 | 74 | On track |  | Moving |  |  |  | Unknown | PLATE | Punching
TOTAL |  |  |  |  | 993 | 2439.812

## G
Activity | Section | Mark No. | Length | Width | Balance Qty | Balance Wt (kg) | Contractor | Ageing (days) | Cumulative Target (days) | Overrun (days) | Consumed % | Days to Target | Lifecycle Status | Stalled | Velocity Status | Days / Stage | ETA (days) | ETA Gap (days) | Trend | Section Type | Hole Operation
G | 65X65X6 MS | 933 \ 2AF10M \ 375 | 2821 |  | 8 | 133.376 | DASHMESH ENTERPRISES GP-2 | 46 | 82 | -36 | 56 | 36 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | A 50X50X6 MS | 933 \ 2AF3 \ 110 | 680 |  | 44 | 134.332 | DASHMESH ENTERPRISES GP-2 | 39 | 82 | -43 | 48 | 43 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | PLATE 10 MM MS | 933 \ 2AF3 \ 127L | 243 | 527 | 22 | 221.166 | DASHMESH ENTERPRISES GP-2 | 26 | 82 | -56 | 32 | 56 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2AF3 \ 127R | 243 | 527 | 22 | 221.166 | DASHMESH ENTERPRISES GP-2 | 26 | 82 | -56 | 32 | 56 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2AF3 \ 215 | 335 | 115 | 44 | 133.056 | DASHMESH ENTERPRISES GP-2 | 43 | 82 | -39 | 52 | 39 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2AF3 \ 248 | 180 | 210 | 2 | 5.934 | DASHMESH ENTERPRISES GP-2 | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | A 50X50X6 MS | 933 \ 2AF3 \ 24L | 1060 |  | 1 | 4.759 | DASHMESH ENTERPRISES GP-2 | 46 | 82 | -36 | 56 | 36 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | A 50X50X6 MS | 933 \ 2AF3 \ 24R | 1060 |  | 2 | 9.518 | DASHMESH ENTERPRISES GP-2 | 46 | 82 | -36 | 56 | 36 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | 200X200X16 MS | 933 \ 2AF3 \ 264 | 372 |  | 44 | 794.332 | DASHMESH ENTERPRISES GP-2 | 14 | 82 | -68 | 17 | 68 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
G | 65X65X6 MS | 933 \ 2AF3 \ 272A | 2329 |  | 3 | 41.292 | DASHMESH ENTERPRISES GP-2 | 49 | 82 | -33 | 60 | 33 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | 65X65X8 MS | 933 \ 2AF3 \ 273 | 2349 |  | 22 | 399.476 | DASHMESH ENTERPRISES GP-2 | 52 | 82 | -30 | 63 | 30 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | PLATE 12 MM MS | 933 \ 2AF3 \ 289 | 133 | 200 | 44 | 110.264 | DASHMESH ENTERPRISES GP-2 | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | A 200X200X20 MS | 933 \ 2AF3 \ 300 | 3430 |  | 2 | 411.326 | DASHMESH ENTERPRISES GP-2 | 5 | 82 | -77 | 6 | 77 | On track |  | Moving |  |  |  | Unknown | ANGLE | Drilling
G | A 200X200X20 MS | 933 \ 2AF3 \ 301S | 3430 |  | 4 | 822.652 | DASHMESH ENTERPRISES GP-2 | 5 | 82 | -77 | 6 | 77 | On track |  | Moving |  |  |  | Unknown | ANGLE | Drilling
G | PLATE 10 MM MS | 933 \ 2AF3 \ 331 | 205 | 260 | 44 | 184.096 | DASHMESH ENTERPRISES GP-2 | 31 | 82 | -51 | 38 | 51 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | A 50X50X6 MS | 933 \ 2AF3 \ 49 | 671 |  | 1 | 3.013 | DASHMESH ENTERPRISES GP-2 | 39 | 82 | -43 | 48 | 43 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | PLATE 10 MM MS | 933 \ 2AF3 \ 53L | 392 | 180 | 22 | 121.858 | DASHMESH ENTERPRISES GP-2 | 26 | 82 | -56 | 32 | 56 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2AF3 \ 53R | 392 | 180 | 22 | 121.858 | DASHMESH ENTERPRISES GP-2 | 26 | 82 | -56 | 32 | 56 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | A 50X50X6 MS | 933 \ 2AF3 \ 55 | 562 |  | 22 | 55.506 | DASHMESH ENTERPRISES GP-2 | 39 | 82 | -43 | 48 | 43 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | PLATE 10 MM MS | 933 \ 2AF3 \ 74L | 427 | 184 | 22 | 135.696 | DASHMESH ENTERPRISES GP-2 | 26 | 82 | -56 | 32 | 56 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2AF3 \ 74R | 427 | 184 | 22 | 135.696 | DASHMESH ENTERPRISES GP-2 | 26 | 82 | -56 | 32 | 56 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | A 50X50X6 MS | 933 \ 2AF3 \ 77 | 1169 |  | 2 | 10.498 | DASHMESH ENTERPRISES GP-2 | 39 | 82 | -43 | 48 | 43 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | A 50X50X6 MS | 933 \ 2AF3 \ 90 | 677 |  | 44 | 133.76 | DASHMESH ENTERPRISES GP-2 | 39 | 82 | -43 | 48 | 43 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | PLATE 10 MM MS | 933 \ 2AF3 \ 94L | 233 | 517 | 22 | 208.032 | DASHMESH ENTERPRISES GP-2 | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2AF3 \ 94R | 233 | 517 | 22 | 208.032 | DASHMESH ENTERPRISES GP-2 | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 8 MM MS | 933 \ 2AF5M \ 328P | 280 | 50 | 16 | 14.064 | DASHMESH ENTERPRISES GP-2 | 31 | 82 | -51 | 38 | 51 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 6 MM MS | 933 \ 2AF5M \ 345 | 281 | 60 | 32 | 25.408 | DASHMESH ENTERPRISES GP-2 | 31 | 82 | -51 | 38 | 51 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | 65X65X6 MS | 933 \ 2AF5M \ 354 | 1331 |  | 1 | 7.866 | DASHMESH ENTERPRISES GP-2 | 30 | 82 | -52 | 37 | 52 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | 65X65X6 MS | 933 \ 2AF5M \ 358 | 1716 |  | 8 | 81.136 | DASHMESH ENTERPRISES GP-2 | 41 | 82 | -41 | 50 | 41 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | PLATE 10 MM MS | 933 \ 2AF5M \ 369 | 225 | 200 | 16 | 56.528 | DASHMESH ENTERPRISES GP-2 | 31 | 82 | -51 | 38 | 51 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 112P | 170 | 50 | 16 | 10.672 | DASHMESH ENTERPRISES GP-2 | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 115 | 175 | 120 | 16 | 26.384 | DASHMESH ENTERPRISES GP-2 | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 116 | 250 | 117 | 16 | 36.736 | DASHMESH ENTERPRISES GP-2 | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 16 MM MS | 933 \ 2DF-5 \ 128P | 130 | 50 | 16 | 13.056 | DASHMESH ENTERPRISES GP-2 | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 129 | 385 | 100 | 48 | 145.056 | DASHMESH ENTERPRISES GP-2 | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 16 MM MS | 933 \ 2DF-5 \ 161 | 105 | 60 | 152 | 120.232 | DASHMESH ENTERPRISES GP-2 | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
G | 150X150X12 MS | 933 \ 2DF-5 \ 163L | 394 |  | 32 | 344.064 | DASHMESH ENTERPRISES GP-2 | 34 | 82 | -48 | 41 | 48 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 170 | 306 | 225 | 16 | 86.48 | DASHMESH ENTERPRISES GP-2 | 31 | 82 | -51 | 38 | 51 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 171 | 303 | 115 | 32 | 87.52 | DASHMESH ENTERPRISES GP-2 | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 174 | 335 | 299 | 16 | 125.808 | DASHMESH ENTERPRISES GP-2 | 53 | 82 | -29 | 65 | 29 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 178 | 275 | 115 | 16 | 39.728 | DASHMESH ENTERPRISES GP-2 | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 179 | 275 | 225 | 16 | 77.712 | DASHMESH ENTERPRISES GP-2 | 53 | 82 | -29 | 65 | 29 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | 150X150X20 MS | 933 \ 2DF-5 \ 201 | 5137 |  | 1 | 226.644 | DASHMESH ENTERPRISES GP-2 | 51 | 82 | -31 | 62 | 31 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 220 | 367 | 252 | 16 | 116.16 | DASHMESH ENTERPRISES GP-2 | 6 | 82 | -76 | 7 | 76 | On track |  | Moving |  |  |  | Unknown | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 227 | 402 | 332 | 16 | 167.632 | DASHMESH ENTERPRISES GP-2 | 6 | 82 | -76 | 7 | 76 | On track |  | Moving |  |  |  | Unknown | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 229 | 402 | 337 | 16 | 170.16 | DASHMESH ENTERPRISES GP-2 | 6 | 82 | -76 | 7 | 76 | On track |  | Moving |  |  |  | Unknown | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 233 | 457 | 115 | 16 | 66.016 | DASHMESH ENTERPRISES GP-2 | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 234 | 252 | 170 | 16 | 53.808 | DASHMESH ENTERPRISES GP-2 | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 235 | 252 | 115 | 16 | 36.4 | DASHMESH ENTERPRISES GP-2 | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 29L | 476 | 204 | 8 | 60.984 | DASHMESH ENTERPRISES GP-2 | 26 | 82 | -56 | 32 | 56 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 29R | 476 | 204 | 8 | 60.984 | DASHMESH ENTERPRISES GP-2 | 26 | 82 | -56 | 32 | 56 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 333 | 578 | 464 | 16 | 336.848 | DASHMESH ENTERPRISES GP-2 | 6 | 82 | -76 | 7 | 76 | On track |  | Moving |  |  |  | Unknown | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 337 | 412 | 402 | 16 | 208.016 | DASHMESH ENTERPRISES GP-2 | 7 | 82 | -75 | 9 | 75 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 44 | 283 | 128 | 16 | 45.504 | DASHMESH ENTERPRISES GP-2 | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | A 50X50X6 MS | 933 \ 2DF-5 \ 52 | 644 |  | 1 | 2.892 | DASHMESH ENTERPRISES GP-2 | 46 | 82 | -36 | 56 | 36 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | A 50X50X6 MS | 933 \ 2DF-5 \ 54 | 1335 |  | 8 | 47.952 | DASHMESH ENTERPRISES GP-2 | 39 | 82 | -43 | 48 | 43 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | A 50X50X6 MS | 933 \ 2DF-5 \ 62R | 1111 |  | 8 | 39.904 | DASHMESH ENTERPRISES GP-2 | 46 | 82 | -36 | 56 | 36 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 67L | 591 | 282 | 8 | 104.664 | DASHMESH ENTERPRISES GP-2 | 43 | 82 | -39 | 52 | 39 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF-5 \ 67R | 591 | 282 | 8 | 104.664 | DASHMESH ENTERPRISES GP-2 | 43 | 82 | -39 | 52 | 39 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | A 50X50X6 MS | 933 \ 2DF-5 \ 83XR | 1109 |  | 8 | 39.832 | DASHMESH ENTERPRISES GP-2 | 46 | 82 | -36 | 56 | 36 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | A 50X50X6 MS | 933 \ 2DF-5 \ 85XL | 1250 |  | 8 | 44.904 | DASHMESH ENTERPRISES GP-2 | 39 | 82 | -43 | 48 | 43 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | A 50X50X6 MS | 933 \ 2DF-5 \ 96 | 1355 |  | 24 | 146.016 | DASHMESH ENTERPRISES GP-2 | 39 | 82 | -43 | 48 | 43 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | PLATE 10 MM MS | 933 \ 2DF3 \ 112P | 170 | 50 | 44 | 29.348 | DASHMESH ENTERPRISES GP-2 | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF3 \ 116 | 250 | 117 | 2 | 4.592 | DASHMESH ENTERPRISES GP-2 | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF3 \ 128 | 204 | 240 | 2 | 7.686 | DASHMESH ENTERPRISES GP-2 | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 16 MM MS | 933 \ 2DF3 \ 128P | 130 | 50 | 44 | 35.904 | DASHMESH ENTERPRISES GP-2 | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
G | PLATE 16 MM MS | 933 \ 2DF3 \ 161 | 105 | 60 | 418 | 330.638 | DASHMESH ENTERPRISES GP-2 | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
G | PLATE 16 MM MS | 933 \ 2DF3 \ 175P | 180 | 60 | 44 | 59.664 | DASHMESH ENTERPRISES GP-2 | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Drilling
G | PLATE 10 MM MS | 933 \ 2DF3 \ 229 | 402 | 337 | 44 | 467.94 | DASHMESH ENTERPRISES GP-2 | 7 | 82 | -75 | 9 | 75 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF3 \ 240 | 402 | 120 | 69 | 261.303 | DASHMESH ENTERPRISES GP-2 | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF3 \ 272 | 392 | 120 | 440 | 1624.92 | DASHMESH ENTERPRISES GP-2 | 7 | 82 | -75 | 9 | 75 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF3 \ 29L | 476 | 204 | 22 | 167.706 | DASHMESH ENTERPRISES GP-2 | 26 | 82 | -56 | 32 | 56 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF3 \ 29R | 476 | 204 | 22 | 167.706 | DASHMESH ENTERPRISES GP-2 | 26 | 82 | -56 | 32 | 56 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | A 50X50X6 MS | 933 \ 2DF3 \ 33 | 634 |  | 3 | 8.541 | DASHMESH ENTERPRISES GP-2 | 46 | 82 | -36 | 56 | 36 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | PLATE 10 MM MS | 933 \ 2DF3 \ 44 | 283 | 128 | 4 | 11.376 | DASHMESH ENTERPRISES GP-2 | 47 | 82 | -35 | 57 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | A 50X50X6 MS | 933 \ 2DF3 \ 52 | 644 |  | 12 | 34.704 | DASHMESH ENTERPRISES GP-2 | 46 | 82 | -36 | 56 | 36 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | PLATE 10 MM MS | 933 \ 2DF3 \ 67L | 591 | 282 | 22 | 287.826 | DASHMESH ENTERPRISES GP-2 | 26 | 82 | -56 | 32 | 56 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ 2DF3 \ 67R | 591 | 282 | 22 | 287.826 | DASHMESH ENTERPRISES GP-2 | 26 | 82 | -56 | 32 | 56 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | A 130X130X12 MS | 933 \ 2DF3 \ 90X | 2436 |  | 2 | 114.248 | DASHMESH ENTERPRISES GP-2 | 34 | 82 | -48 | 41 | 48 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
G | PLATE 10 MM MS | 933 \ IS-933 \ 2DF1 \ 014 | 135 | 144 | 7 | 10.682 | DASHMESH ENTERPRISES GP-2 | 63 | 82 | -19 | 77 | 19 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
G | PLATE 10 MM MS | 933 \ IS-933 \ 2DF2A \ 905 | 205 | 457 | 1 | 7.354 | DASHMESH ENTERPRISES GP-2 | 63 | 82 | -19 | 77 | 19 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
TOTAL |  |  |  |  | 2432 | 12059.092

## GB
Activity | Section | Mark No. | Length | Width | Balance Qty | Balance Wt (kg) | Contractor | Ageing (days) | Cumulative Target (days) | Overrun (days) | Consumed % | Days to Target | Lifecycle Status | Stalled | Velocity Status | Days / Stage | ETA (days) | ETA Gap (days) | Trend | Section Type | Hole Operation
GB | A 75X75X8 MS | 933 \ 2AF3 \ 102 | 2227 |  | 22 | 440.946 | DASHMESH ENTERPRISES GP-2 | 46 | 86 | -40 | 53 | 40 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 50X50X6 MS | 933 \ 2AF3 \ 103A | 2786 |  | 11 | 137.599 | DASHMESH ENTERPRISES GP-2 | 26 | 86 | -60 | 30 | 60 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | A 75X75X8 MS | 933 \ 2AF3 \ 116 | 2227 |  | 22 | 440.946 | DASHMESH ENTERPRISES GP-2 | 46 | 86 | -40 | 53 | 40 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 50X50X6 MS | 933 \ 2AF3 \ 117A | 2758 |  | 22 | 272.426 | DASHMESH ENTERPRISES GP-2 | 26 | 86 | -60 | 30 | 60 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 50X50X6 MS | 933 \ 2AF3 \ 202 | 1672 |  | 1 | 7.507 | DASHMESH ENTERPRISES GP-2 | 30 | 86 | -56 | 35 | 56 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | PLATE 10 MM MS | 933 \ 2AF3 \ 209 | 115 | 180 | 4 | 6.5 | DASHMESH ENTERPRISES GP-2 | 48 | 86 | -38 | 56 | 38 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
GB | 50X50X6 MS | 933 \ 2AF3 \ 213 | 2349 |  | 22 | 232.034 | DASHMESH ENTERPRISES GP-2 | 26 | 86 | -60 | 30 | 60 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 65X65X6 MS | 933 \ 2AF3 \ 235A | 2370 |  | 88 | 1232.616 | DASHMESH ENTERPRISES GP-2 | 34 | 86 | -52 | 40 | 52 | On track | Yes | Stalled | 35.6468 | 35.6468 | -16.3532 | Stalled | ANGLE | Punching
GB | 65X65X6 MS | 933 \ 2AF3 \ 237 | 2316 |  | 4 | 54.752 | DASHMESH ENTERPRISES GP-2 | 46 | 86 | -40 | 53 | 40 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 65X65X6 MS | 933 \ 2AF3 \ 237A | 2316 |  | 44 | 602.272 | DASHMESH ENTERPRISES GP-2 | 48 | 86 | -38 | 56 | 38 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 65X65X6 MS | 933 \ 2AF3 \ 238 | 2401 |  | 1 | 14.19 | DASHMESH ENTERPRISES GP-2 | 34 | 86 | -52 | 40 | 52 | On track | Yes | Stalled | 35.6468 | 35.6468 | -16.3532 | Stalled | ANGLE | Punching
GB | 65X65X6 MS | 933 \ 2AF3 \ 238A | 2401 |  | 44 | 624.36 | DASHMESH ENTERPRISES GP-2 | 52 | 86 | -34 | 60 | 34 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 65X65X6 MS | 933 \ 2AF3 \ 241 | 2336 |  | 2 | 27.612 | DASHMESH ENTERPRISES GP-2 | 18 | 86 | -68 | 21 | 68 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | PLATE 10 MM MS | 933 \ 2AF3 \ 243 | 170 | 50 | 44 | 29.348 | DASHMESH ENTERPRISES GP-2 | 29 | 86 | -57 | 34 | 57 | On track | Yes | Stalled | 35.6468 | 35.6468 | -21.3532 | Stalled | PLATE | Punching
GB | 65X65X6 MS | 933 \ 2AF3 \ 279A | 2410 |  | 28 | 398.804 | DASHMESH ENTERPRISES GP-2 | 48 | 86 | -38 | 56 | 38 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 65X65X6 MS | 933 \ 2AF3 \ 279A | 2410 |  | 16 | 227.888 | DASHMESH ENTERPRISES GP-2 | 46 | 86 | -40 | 53 | 40 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 65X65X8 MS | 933 \ 2AF3 \ 285 | 2377 |  | 44 | 808.456 | DASHMESH ENTERPRISES GP-2 | 52 | 86 | -34 | 60 | 34 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | PLATE 10 MM MS | 933 \ 2AF3 \ 29L | 397 | 160 | 22 | 109.692 | DASHMESH ENTERPRISES GP-2 | 15 | 86 | -71 | 17 | 71 | On track | Yes | Stalled | 35.6468 | 35.6468 | -35.3532 | Stalled | PLATE | Punching
GB | PLATE 10 MM MS | 933 \ 2AF3 \ 29R | 397 | 160 | 22 | 109.692 | DASHMESH ENTERPRISES GP-2 | 15 | 86 | -71 | 17 | 71 | On track | Yes | Stalled | 35.6468 | 35.6468 | -35.3532 | Stalled | PLATE | Punching
GB | 200X200X16 MS | 933 \ 2AF3 \ 304 | 572 |  | 8 | 222.072 | DASHMESH ENTERPRISES GP-2 | 18 | 86 | -68 | 21 | 68 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
GB | 50X50X5 MS | 933 \ 2AF3 \ 308 | 1082 |  | 1 | 4.101 | DASHMESH ENTERPRISES GP-2 | 26 | 86 | -60 | 30 | 60 | On track | Yes | Stalled | 35.6468 | 35.6468 | -24.3532 | Stalled | ANGLE | Punching
GB | 65X65X6 MS | 933 \ 2AF3 \ 346 | 1144 |  | 2 | 13.522 | DASHMESH ENTERPRISES GP-2 | 41 | 86 | -45 | 48 | 45 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 50X50X6 MS | 933 \ 2AF3 \ 40A | 2710 |  | 11 | 133.848 | DASHMESH ENTERPRISES GP-2 | 26 | 86 | -60 | 30 | 60 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | A 50X50X6 MS | 933 \ 2AF3 \ 41 | 188 |  | 132 | 111.408 | DASHMESH ENTERPRISES GP-2 | 17 | 86 | -69 | 20 | 69 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | A 50X50X6 MS | 933 \ 2AF3 \ 60 | 2032 |  | 1 | 9.124 | DASHMESH ENTERPRISES GP-2 | 46 | 86 | -40 | 53 | 40 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | A 75X75X8 MS | 933 \ 2AF3 \ 82 | 2181 |  | 3 | 58.887 | DASHMESH ENTERPRISES GP-2 | 46 | 86 | -40 | 53 | 40 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 50X50X6 MS | 933 \ 2AF3 \ 83A | 2732 |  | 11 | 134.937 | DASHMESH ENTERPRISES GP-2 | 26 | 86 | -60 | 30 | 60 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 75X75X8 MS | 933 \ 2AF5M \ 352 | 4213 |  | 4 | 151.668 | DASHMESH ENTERPRISES GP-2 | 18 | 86 | -68 | 21 | 68 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | 75X75X8 MS | 933 \ 2AF5M \ 352A | 4213 |  | 4 | 151.668 | DASHMESH ENTERPRISES GP-2 | 13 | 86 | -73 | 15 | 73 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | PLATE 10 MM MS | 933 \ 2DF-5 \ 112 | 260 | 178 | 16 | 58.128 | DASHMESH ENTERPRISES GP-2 | 29 | 86 | -57 | 34 | 57 | On track | Yes | Stalled | 35.6468 | 35.6468 | -21.3532 | Stalled | PLATE | Punching
GB | PLATE 10 MM MS | 933 \ 2DF-5 \ 128 | 204 | 240 | 16 | 61.488 | DASHMESH ENTERPRISES GP-2 | 29 | 86 | -57 | 34 | 57 | On track | Yes | Stalled | 35.6468 | 35.6468 | -21.3532 | Stalled | PLATE | Punching
GB | PLATE 10 MM MS | 933 \ 2DF-5 \ 242 | 337 | 135 | 32 | 114.272 | DASHMESH ENTERPRISES GP-2 | 29 | 86 | -57 | 34 | 57 | On track | Yes | Stalled | 35.6468 | 35.6468 | -21.3532 | Stalled | PLATE | Punching
GB | 200X200X16 MS | 933 \ 2DF-5 \ 290 | 136 |  | 6 | 39.6 | DASHMESH ENTERPRISES GP-2 | 8 | 86 | -78 | 9 | 78 | On track |  | Moving |  |  |  | Unknown | ANGLE | Drilling
GB | 200X200X16 MS | 933 \ 2DF-5 \ 290 | 136 |  | 9 | 59.4 | DASHMESH ENTERPRISES GP-2 | 30 | 86 | -56 | 35 | 56 | On track |  | Moving |  |  |  | Unknown | ANGLE | Drilling
GB | PLATE 10 MM MS | 933 \ 2DF-5 \ 292 | 221 | 135 | 32 | 74.944 | DASHMESH ENTERPRISES GP-2 | 29 | 86 | -57 | 34 | 57 | On track | Yes | Stalled | 35.6468 | 35.6468 | -21.3532 | Stalled | PLATE | Punching
GB | A 200X200X20 MS | 933 \ 2DF-5 \ 310S | 5124 |  | 3 | 921.705 | DASHMESH ENTERPRISES GP-2 | 41 | 86 | -45 | 48 | 45 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
GB | A 50X50X6 MS | 933 \ 2DF-5 \ 46R | 1085 |  | 8 | 38.976 | DASHMESH ENTERPRISES GP-2 | 30 | 86 | -56 | 35 | 56 | On track | Yes | Stalled | 35.6468 | 35.6468 | -20.3532 | Stalled | ANGLE | Punching
GB | A 75X75X8 MS | 933 \ 2DF-5 \ 81 | 4003 |  | 8 | 288.216 | DASHMESH ENTERPRISES GP-2 | 16 | 86 | -70 | 19 | 70 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | A 75X75X8 MS | 933 \ 2DF-5 \ 81X | 4003 |  | 8 | 288.216 | DASHMESH ENTERPRISES GP-2 | 16 | 86 | -70 | 19 | 70 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | A 50X50X6 MS | 933 \ 2DF-5 \ 83XL | 1109 |  | 2 | 9.958 | DASHMESH ENTERPRISES GP-2 | 30 | 86 | -56 | 35 | 56 | On track | Yes | Stalled | 35.6468 | 35.6468 | -20.3532 | Stalled | ANGLE | Punching
GB | A 50X50X6 MS | 933 \ 2DF-5 \ 85L | 1254 |  | 8 | 45.04 | DASHMESH ENTERPRISES GP-2 | 30 | 86 | -56 | 35 | 56 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | A 50X50X6 MS | 933 \ 2DF-5 \ 85R | 1254 |  | 11 | 61.93 | DASHMESH ENTERPRISES GP-2 | 30 | 86 | -56 | 35 | 56 | On track | Yes | Stalled | 35.6468 | 35.6468 | -20.3532 | Stalled | ANGLE | Punching
GB | 150X150X12 MS | 933 \ 2DF3 \ 223R | 346 |  | 1 | 9.442 | DASHMESH ENTERPRISES GP-2 | 34 | 86 | -52 | 40 | 52 | On track | Yes | Stalled | 35.6468 | 35.6468 | -16.3532 | Stalled | ANGLE | Punching
GB | 65X65X6 MS | 933 \ 2DF3 \ 284 | 732 |  | 88 | 380.688 | DASHMESH ENTERPRISES GP-2 | 52 | 86 | -34 | 60 | 34 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
GB | PLATE 10 MM MS | 933 \ 2DF3 \ 289 | 392 | 136 | 11 | 46.035 | DASHMESH ENTERPRISES GP-2 | 44 | 86 | -42 | 51 | 42 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
GB | PLATE 10 MM MS | 933 \ 2DF3 \ 289 | 392 | 136 | 28 | 117.18 | DASHMESH ENTERPRISES GP-2 | 18 | 86 | -68 | 21 | 68 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
TOTAL |  |  |  |  | 927 | 9384.093

## Y
Activity | Section | Mark No. | Length | Width | Balance Qty | Balance Wt (kg) | Contractor | Ageing (days) | Cumulative Target (days) | Overrun (days) | Consumed % | Days to Target | Lifecycle Status | Stalled | Velocity Status | Days / Stage | ETA (days) | ETA Gap (days) | Trend | Section Type | Hole Operation
Y | 65X65X6 MS | 933 \ 2AF10M \ 355 | 1912 |  | 8 | 90.4 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | 65X65X6 MS | 933 \ 2AF10M \ 377 | 1514 |  | 8 | 71.584 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | A 50X50X6 MS | 933 \ 2AF3 \ 108 | 365 |  | 44 | 72.116 | UNIT-II | 8 | 88 | -80 | 9 | 80 | On track |  | Moving |  |  |  | Unknown | ANGLE | Punching
Y | PLATE 10 MM MS | 933 \ 2AF3 \ 114L | 502 | 207 | 22 | 179.454 | UNIT-II | 45 | 88 | -43 | 51 | 43 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2AF3 \ 114R | 502 | 207 | 22 | 179.454 | UNIT-II | 45 | 88 | -43 | 51 | 43 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | 65X65X8 MS | 933 \ 2AF3 \ 115 | 1980 |  | 44 | 673.42 | UNIT-II | 51 | 88 | -37 | 58 | 37 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | PLATE 10 MM MS | 933 \ 2AF3 \ 209 | 115 | 180 | 8 | 13 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
Y | 65X65X6 MS | 933 \ 2AF3 \ 237 | 2316 |  | 1 | 13.688 | UNIT-II | 25 | 88 | -63 | 28 | 63 | On track | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
Y | 65X65X6 MS | 933 \ 2AF3 \ 237 | 2316 |  | 19 | 260.072 | UNIT-II | 18 | 88 | -70 | 20 | 70 | On track | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
Y | 65X65X6 MS | 933 \ 2AF3 \ 241 | 2336 |  | 1 | 13.806 | UNIT-II | 18 | 88 | -70 | 20 | 70 | On track | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
Y | PLATE 10 MM MS | 933 \ 2AF3 \ 246 | 204 | 250 | 14 | 56.056 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
Y | 65X65X6 MS | 933 \ 2AF3 \ 270A | 2410 |  | 3 | 42.729 | UNIT-II | 15 | 88 | -73 | 17 | 73 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | 65X65X6 MS | 933 \ 2AF3 \ 272A | 2329 |  | 16 | 220.224 | UNIT-II | 48 | 88 | -40 | 55 | 40 | Pre-warning 1 |  | Slow | 35.6468 |  |  | Unknown | ANGLE | Punching
Y | 65X65X8 MS | 933 \ 2AF3 \ 273A | 2349 |  | 22 | 399.476 | UNIT-II | 46 | 88 | -42 | 52 | 42 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | 65X65X8 MS | 933 \ 2AF3 \ 275 | 2377 |  | 44 | 808.456 | UNIT-II | 51 | 88 | -37 | 58 | 37 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | 65X65X8 MS | 933 \ 2AF3 \ 283 | 1680 |  | 22 | 285.692 | UNIT-II | 51 | 88 | -37 | 58 | 37 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | PLATE 12 MM MS | 933 \ 2AF3 \ 287 | 248 | 327 | 44 | 336.116 | UNIT-II | 66 | 88 | -22 | 75 | 22 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2AF3 \ 288 | 170 | 209 | 10 | 27.89 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
Y | PLATE 12 MM MS | 933 \ 2AF3 \ 290 | 238 | 200 | 44 | 197.296 | UNIT-II | 73 | 88 | -15 | 83 | 15 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | 65X65X8 MS | 933 \ 2AF3 \ 30 | 1972 |  | 22 | 335.368 | UNIT-II | 51 | 88 | -37 | 58 | 37 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | PLATE 16 MM MS | 933 \ 2AF3 \ 305 | 145 | 572 | 48 | 500.016 | UNIT-II | 48 | 88 | -40 | 55 | 40 | Pre-warning 1 | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Drilling
Y | 50X50X5 MS | 933 \ 2AF3 \ 307 | 593 |  | 18 | 40.446 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track |  | Moving |  |  |  | Unknown | ANGLE | Punching
Y | 50X50X5 MS | 933 \ 2AF3 \ 319 | 1932 |  | 1 | 7.322 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
Y | PLATE 12 MM MS | 933 \ 2AF3 \ 328 | 249 | 344 | 44 | 355.036 | UNIT-II | 66 | 88 | -22 | 75 | 22 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | 65X65X6 MS | 933 \ 2AF3 \ 347 | 2026 |  | 38 | 455.012 | UNIT-II | 31 | 88 | -57 | 35 | 57 | On track | Yes | Stalled | 29.8922 |  |  | Stalled | ANGLE | Punching
Y | A 50X50X6 MS | 933 \ 2AF3 \ 48L | 1061 |  | 22 | 104.808 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | A 50X50X6 MS | 933 \ 2AF3 \ 92 | 990 |  | 1 | 4.445 | UNIT-II | 38 | 88 | -50 | 43 | 50 | On track | Yes | Stalled | 32.8408 |  |  | Stalled | ANGLE | Punching
Y | 65X65X8 MS | 933 \ 2AF3 \ 95 | 2020 |  | 22 | 343.53 | UNIT-II | 51 | 88 | -37 | 58 | 37 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | A 50X50X6 MS | 933 \ 2AF3 \ 98 | 1152 |  | 66 | 341.352 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | A 50X50X6 MS | 933 \ 2AF3 \ 99 | 1654 |  | 32 | 237.632 | UNIT-II | 51 | 88 | -37 | 58 | 37 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | A 50X50X6 MS | 933 \ 2AF3 \ 99 | 1654 |  | 34 | 252.484 | UNIT-II | 48 | 88 | -40 | 55 | 40 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | 200X200X20 MS | 933 \ 2AF5M \ 341 | 5016 |  | 3 | 902.277 | UNIT-II | 41 | 88 | -47 | 47 | 47 | On track | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
Y | 200X200X20 MS | 933 \ 2AF5M \ 341S | 5016 |  | 1 | 300.759 | UNIT-II | 8 | 88 | -80 | 9 | 80 | On track |  | Slow | 3.6102 |  |  | Unknown | ANGLE | Drilling
Y | 75X75X8 MS | 933 \ 2AF5M \ 353 | 2991 |  | 4 | 107.676 | UNIT-II | 13 | 88 | -75 | 15 | 75 | On track | Yes | Stalled | 15.7591 |  |  | Stalled | ANGLE | Punching
Y | 65X65X6 MS | 933 \ 2AF5M \ 354 | 1331 |  | 17 | 133.722 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | 75X75X8 MS | 933 \ 2DF-5 \ 10 | 1716 |  | 8 | 123.552 | UNIT-II | 69 | 88 | -19 | 78 | 19 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 122 | 436 | 100 | 32 | 109.536 | UNIT-II | 67 | 88 | -21 | 76 | 21 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | 75X75X8 MS | 933 \ 2DF-5 \ 15 | 1521 |  | 16 | 219.024 | UNIT-II | 69 | 88 | -19 | 78 | 19 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | PLATE 12 MM MS | 933 \ 2DF-5 \ 167P | 416 | 115 | 1 | 4.507 | UNIT-II | 21 | 88 | -67 | 24 | 67 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 12 MM MS | 933 \ 2DF-5 \ 167P | 416 | 115 | 63 | 283.941 | UNIT-II | 67 | 88 | -21 | 76 | 21 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 168 | 312 | 130 | 112 | 356.608 | UNIT-II | 61 | 88 | -27 | 69 | 27 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 173 | 299 | 115 | 2 | 5.398 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 175 | 612 | 275 | 16 | 211.392 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | 200X200X16 MS | 933 \ 2DF-5 \ 205 | 472 |  | 17 | 389.402 | UNIT-II | 48 | 88 | -40 | 55 | 40 | Pre-warning 1 |  | Moving |  |  |  | Unknown | ANGLE | Drilling
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 206 | 472 | 402 | 8 | 119.16 | UNIT-II | 18 | 88 | -70 | 20 | 70 | On track | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 207 | 472 | 135 | 128 | 640.256 | UNIT-II | 67 | 88 | -21 | 76 | 21 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | 200X200X16 MS | 933 \ 2DF-5 \ 231L | 435 |  | 16 | 337.776 | UNIT-II | 46 | 88 | -42 | 52 | 42 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 287 | 392 | 136 | 48 | 200.88 | UNIT-II | 67 | 88 | -21 | 76 | 21 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | 200X200X16 MS | 933 \ 2DF-5 \ 290 | 136 |  | 112 | 739.2 | UNIT-II | 46 | 88 | -42 | 52 | 42 | Pre-warning 1 |  | Slow | 35.6468 |  |  | Unknown | ANGLE | Drilling
Y | 200X200X16 MS | 933 \ 2DF-5 \ 290 | 136 |  | 15 | 99 | UNIT-II | 3 | 88 | -85 | 3 | 85 | On track |  | Slow | 35.6468 |  |  | Unknown | ANGLE | Drilling
Y | 200X200X16 MS | 933 \ 2DF-5 \ 290 | 136 |  | 6 | 39.6 | UNIT-II | 8 | 88 | -80 | 9 | 80 | On track |  | Slow | 35.6468 |  |  | Unknown | ANGLE | Drilling
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 297A | 602 | 135 | 16 | 102.08 | UNIT-II | 44 | 88 | -44 | 50 | 44 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | A 50X50X6 MS | 933 \ 2DF-5 \ 33 | 634 |  | 8 | 22.776 | UNIT-II | 29 | 88 | -59 | 33 | 59 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | A 50X50X6 MS | 933 \ 2DF-5 \ 35 | 1317 |  | 8 | 47.304 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 50L | 500 | 187 | 8 | 58.72 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 50R | 500 | 187 | 8 | 58.72 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | A 50X50X6 MS | 933 \ 2DF-5 \ 52 | 644 |  | 7 | 20.244 | UNIT-II | 29 | 88 | -59 | 33 | 59 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | 75X75X8 MS | 933 \ 2DF-5 \ 8 | 1466 |  | 8 | 105.552 | UNIT-II | 28 | 88 | -60 | 32 | 60 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 81P | 314 | 140 | 24 | 82.824 | UNIT-II | 61 | 88 | -27 | 69 | 27 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 88L | 309 | 768 | 8 | 149.032 | UNIT-II | 45 | 88 | -43 | 51 | 43 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 88R | 309 | 768 | 8 | 149.032 | UNIT-II | 45 | 88 | -43 | 51 | 43 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 88YL | 282 | 733 | 8 | 129.808 | UNIT-II | 45 | 88 | -43 | 51 | 43 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF-5 \ 88YR | 282 | 733 | 8 | 129.808 | UNIT-II | 45 | 88 | -43 | 51 | 43 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | 130X130X12 MS | 933 \ 2DF-5 \ 89X | 2436 |  | 8 | 456.992 | UNIT-II | 58 | 88 | -30 | 66 | 30 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | 130X130X12 MS | 933 \ 2DF-5 \ 89Y | 2136 |  | 8 | 400.712 | UNIT-II | 41 | 88 | -47 | 47 | 47 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | 75X75X8 MS | 933 \ 2DF3 \ 10 | 1716 |  | 22 | 339.768 | UNIT-II | 69 | 88 | -19 | 78 | 19 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | 100X100X10 MS | 933 \ 2DF3 \ 124A | 2794 |  | 1 | 42.022 | UNIT-II | 21 | 88 | -67 | 24 | 67 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | 130X130X12 MS | 933 \ 2DF3 \ 155A | 2816 |  | 6 | 396.21 | UNIT-II | 56 | 88 | -32 | 64 | 32 | Pre-warning 1 |  | Moving |  |  |  | Unknown | ANGLE | Punching
Y | 150X150X12 MS | 933 \ 2DF3 \ 160L | 397 |  | 22 | 238.348 | UNIT-II | 34 | 88 | -54 | 39 | 54 | On track |  | Moving |  |  |  | Unknown | ANGLE | Punching
Y | 150X150X12 MS | 933 \ 2DF3 \ 163L | 394 |  | 1 | 10.752 | UNIT-II | 21 | 88 | -67 | 24 | 67 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 168 | 312 | 130 | 2 | 6.368 | UNIT-II | 21 | 88 | -67 | 24 | 67 | On track |  | Moving |  |  |  | Unknown | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 173 | 299 | 115 | 4 | 10.796 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
Y | 200X200X16 MS | 933 \ 2DF3 \ 204X | 472 |  | 22 | 503.932 | UNIT-II | 85 | 88 | -3 | 97 | 3 | Pre-warning 3 |  | Moving |  |  |  | Unknown | ANGLE | Drilling
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 207 | 472 | 135 | 240 | 1200.48 | UNIT-II | 67 | 88 | -21 | 76 | 21 | Pre-warning 2 |  | Moving |  |  |  | Unknown | PLATE | Punching
Y | 150X150X12 MS | 933 \ 2DF3 \ 221R | 343 |  | 2 | 18.72 | UNIT-II | 34 | 88 | -54 | 39 | 54 | On track | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
Y | 150X150X12 MS | 933 \ 2DF3 \ 224L | 339 |  | 12 | 111.012 | UNIT-II | 34 | 88 | -54 | 39 | 54 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 225 | 547 | 504 | 20 | 432.84 | UNIT-II | 31 | 88 | -57 | 35 | 57 | On track | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 225 | 547 | 504 | 4 | 86.568 | UNIT-II | 62 | 88 | -26 | 70 | 26 | Pre-warning 1 | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 237 | 255 | 115 | 8 | 18.416 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 238 | 248 | 115 | 6 | 13.434 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track |  | Slow | 25.5502 |  |  | Unknown | PLATE | Punching
Y | 200X200X16 MS | 933 \ 2DF3 \ 248L | 162 |  | 22 | 172.964 | UNIT-II | 78 | 88 | -10 | 89 | 10 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
Y | 200X200X16 MS | 933 \ 2DF3 \ 248R | 162 |  | 22 | 172.964 | UNIT-II | 78 | 88 | -10 | 89 | 10 | Pre-warning 2 | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 251 | 360 | 149 | 44 | 185.284 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 287 | 392 | 136 | 88 | 368.28 | UNIT-II | 67 | 88 | -21 | 76 | 21 | Pre-warning 2 | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 289 | 392 | 136 | 29 | 121.365 | UNIT-II | 22 | 88 | -66 | 25 | 66 | On track | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 292 | 221 | 135 | 2 | 4.684 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 297A | 602 | 135 | 44 | 280.72 | UNIT-II | 44 | 88 | -44 | 50 | 44 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | 65X65X6 MS | 933 \ 2DF3 \ 323 | 1513 |  | 17 | 152.014 | UNIT-II | 20 | 88 | -68 | 23 | 68 | On track | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 334 | 578 | 135 | 22 | 134.75 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 338 | 402 | 145 | 26 | 118.976 | UNIT-II | 29 | 88 | -59 | 33 | 59 | On track | Yes | Stalled | 14.7178 |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 338 | 402 | 145 | 31 | 141.856 | UNIT-II | 18 | 88 | -70 | 20 | 70 | On track | Yes | Stalled | 14.7178 |  |  | Stalled | PLATE | Punching
Y | A 50X50X6 MS | 933 \ 2DF3 \ 34 | 1270 |  | 22 | 125.444 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 50L | 500 | 187 | 22 | 161.48 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 50R | 500 | 187 | 22 | 161.48 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | A 50X50X6 MS | 933 \ 2DF3 \ 52 | 644 |  | 10 | 28.92 | UNIT-II | 29 | 88 | -59 | 33 | 59 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | A 50X50X6 MS | 933 \ 2DF3 \ 62R | 1111 |  | 1 | 4.988 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track |  | Moving |  |  |  | Unknown | ANGLE | Punching
Y | 75X75X8 MS | 933 \ 2DF3 \ 8 | 1466 |  | 22 | 290.268 | UNIT-II | 53 | 88 | -35 | 60 | 35 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
Y | A 50X50X6 MS | 933 \ 2DF3 \ 87L | 1289 |  | 22 | 127.336 | UNIT-II | 3 | 88 | -85 | 3 | 85 | On track |  | Moving |  |  |  | Unknown | ANGLE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 88L | 309 | 768 | 22 | 409.838 | UNIT-II | 45 | 88 | -43 | 51 | 43 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 88R | 309 | 768 | 22 | 409.838 | UNIT-II | 45 | 88 | -43 | 51 | 43 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 88XL | 340 | 743 | 22 | 436.282 | UNIT-II | 27 | 88 | -61 | 31 | 61 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 88XR | 340 | 743 | 22 | 436.282 | UNIT-II | 27 | 88 | -61 | 31 | 61 | On track | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 88YL | 282 | 733 | 22 | 356.972 | UNIT-II | 45 | 88 | -43 | 51 | 43 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | PLATE 10 MM MS | 933 \ 2DF3 \ 88YR | 282 | 733 | 22 | 356.972 | UNIT-II | 45 | 88 | -43 | 51 | 43 | Pre-warning 1 | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
Y | A 50X50X6 MS | 933 \ 2DF3 \ 92 | 1404 |  | 7 | 44.128 | UNIT-II | 30 | 88 | -58 | 34 | 58 | On track | Yes | Stalled | 24.8672 |  |  | Stalled | ANGLE | Punching
Y | 200X200X20 MS | 933 \ 2DF5M \ 350S | 5043 |  | 2 | 604.756 | UNIT-II | 41 | 88 | -47 | 47 | 47 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
Y | 65X65X6 MS | 933 \ 2DF5M \ 357 | 1882 |  | 8 | 88.984 | UNIT-II | 41 | 88 | -47 | 47 | 47 | On track | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
TOTAL |  |  |  |  | 2493 | 23483.141

## Finished Goods (FG)
Activity | Section | Mark No. | Length | Width | Balance Qty | Balance Wt (kg) | Contractor | Ageing (days) | Cumulative Target (days) | Overrun (days) | Consumed % | Days to Target | Lifecycle Status | Stalled | Velocity Status | Days / Stage | ETA (days) | ETA Gap (days) | Trend | Section Type | Hole Operation
| 65X65X6 MS | 933 \ 2AF10M \ 359 | 1331 |  | 8 | 62.928 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 23.7885 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF10M \ 374 | 2038 |  | 8 | 96.36 | UNIT-II | 21 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 107 | 110 | 229 | 22 | 43.494 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| 50X50X6 MS | 933 \ 2AF3 \ 11 | 976 |  | 44 | 192.808 | UNIT-II | 3 |  |  |  |  | N/A |  | Moving |  |  |  | Unknown | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 111L | 1216 |  | 22 | 120.12 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 111R | 1216 |  | 22 | 120.12 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 112 | 995 |  | 44 | 196.592 | UNIT-II | 12 |  |  |  |  | N/A | Yes | Stalled | 28.7989 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 124L | 1214 |  | 22 | 119.922 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 50X50X6 MS | 933 \ 2AF3 \ 203A | 2292 |  | 22 | 226.402 | UNIT-II | 18 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 208 | 235 | 345 | 44 | 280.016 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 209 | 115 | 180 | 76 | 123.5 | UNIT-II | 16 |  |  |  |  | N/A | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 210 | 115 | 180 | 88 | 143 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 211 | 180 | 185 | 44 | 115.016 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 214 | 115 | 185 | 44 | 73.48 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 22 | 110 | 229 | 44 | 86.988 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 237 | 2316 |  | 1 | 13.688 | UNIT-II | 25 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 239 | 2418 |  | 126 | 1800.54 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 239A | 2418 |  | 22 | 314.38 | UNIT-II | 12 |  |  |  |  | N/A | Yes | Stalled | 34.8556 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 241 | 2336 |  | 20 | 276.12 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 242 | 365 | 250 | 44 | 315.172 | UNIT-II | 15 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 244 | 130 | 175 | 88 | 157.168 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 245 | 130 | 180 | 88 | 161.656 | UNIT-II | 16 |  |  |  |  | N/A | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 246 | 204 | 250 | 30 | 120.12 | UNIT-II | 16 |  |  |  |  | N/A | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 248 | 180 | 210 | 42 | 124.614 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 249 | 1658 |  | 22 | 215.578 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 24.8672 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 24L | 1060 |  | 13 | 61.867 | UNIT-II | 19 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 24R | 1060 |  | 20 | 95.18 | UNIT-II | 19 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 25 | 670 |  | 44 | 132.352 | UNIT-II | 12 |  |  |  |  | N/A | Yes | Stalled | 28.7989 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 251 | 330 | 130 | 44 | 148.192 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 12 MM MS | 933 \ 2AF3 \ 265 | 372 | 125 | 88 | 385.44 | UNIT-II | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| 200X200X16 MS | 933 \ 2AF3 \ 266 | 472 |  | 40 | 916.24 | UNIT-II | 18 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| PLATE 16 MM MS | 933 \ 2AF3 \ 267 | 145 | 472 | 87 | 747.852 | UNIT-II | 18 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Drilling
| A 50X50X6 MS | 933 \ 2AF3 \ 26L | 1194 |  | 14 | 75.054 | UNIT-II | 19 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 26R | 1194 |  | 17 | 91.137 | UNIT-II | 19 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 271 | 1730 |  | 22 | 224.928 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 23.7885 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 272 | 2329 |  | 22 | 302.808 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 272A | 2329 |  | 3 | 41.292 | UNIT-II | 8 |  |  |  |  | N/A |  | Slow | 35.6468 |  |  | Unknown | ANGLE | Punching
| 65X65X8 MS | 933 \ 2AF3 \ 274 | 2377 |  | 59 | 1084.066 | UNIT-II | 15 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 65X65X8 MS | 933 \ 2AF3 \ 277 | 2312 |  | 44 | 786.368 | UNIT-II | 15 |  |  |  |  | N/A | Yes | Stalled | 29.8922 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 280 | 1720 |  | 22 | 223.63 | UNIT-II | 28 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 281A | 2329 |  | 22 | 302.808 | UNIT-II | 25 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 65X65X8 MS | 933 \ 2AF3 \ 282 | 2355 |  | 44 | 800.976 | UNIT-II | 15 |  |  |  |  | N/A | Yes | Stalled | 29.8922 |  |  | Stalled | ANGLE | Punching
| 65X65X8 MS | 933 \ 2AF3 \ 284 | 2280 |  | 44 | 775.456 | UNIT-II | 15 |  |  |  |  | N/A | Yes | Stalled | 29.8922 |  |  | Stalled | ANGLE | Punching
| PLATE 12 MM MS | 933 \ 2AF3 \ 286 | 258 | 202 | 44 | 215.996 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 288 | 170 | 209 | 34 | 94.826 | UNIT-II | 16 |  |  |  |  | N/A | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
| 200X200X16 MS | 933 \ 2AF3 \ 304 | 572 |  | 72 | 1998.648 | UNIT-II | 18 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| PLATE 16 MM MS | 933 \ 2AF3 \ 305 | 145 | 572 | 76 | 791.692 | UNIT-II | 15 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Drilling
| 50X50X5 MS | 933 \ 2AF3 \ 309 | 1044 |  | 88 | 348.216 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 50X50X5 MS | 933 \ 2AF3 \ 311 | 599 |  | 1 | 2.27 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 50X50X5 MS | 933 \ 2AF3 \ 312 | 748 |  | 2 | 5.67 | UNIT-II | 30 |  |  |  |  | N/A |  | Slow | 22.4987 |  |  | Unknown | ANGLE | Punching
| 50X50X5 MS | 933 \ 2AF3 \ 313 | 1457 |  | 88 | 485.936 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 50X50X5 MS | 933 \ 2AF3 \ 315 | 1217 |  | 48 | 221.376 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 50X50X5 MS | 933 \ 2AF3 \ 316 | 748 |  | 2 | 5.67 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 50X50X5 MS | 933 \ 2AF3 \ 319 | 1932 |  | 31 | 226.982 | UNIT-II | 14 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 50X50X5 MS | 933 \ 2AF3 \ 320 | 1721 |  | 88 | 574.024 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 50X50X5 MS | 933 \ 2AF3 \ 321 | 1576 |  | 88 | 525.624 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled | 23.7885 |  |  | Stalled | ANGLE | Punching
| 50X50X5 MS | 933 \ 2AF3 \ 322 | 941 |  | 30 | 106.98 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 75X75X8 MS | 933 \ 2AF3 \ 323 | 5329 |  | 1 | 47.961 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| PLATE 12 MM MS | 933 \ 2AF3 \ 324 | 244 | 337 | 44 | 340.824 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 325 | 555 | 205 | 17 | 151.827 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 327 | 205 | 580 | 88 | 821.392 | UNIT-II | 31 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| A 75X75X8 MS | 933 \ 2AF3 \ 343 | 3003 |  | 1 | 27.027 | UNIT-II | 28 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 346 | 1144 |  | 86 | 581.446 | UNIT-II | 34 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 347 | 2026 |  | 50 | 598.7 | UNIT-II | 15 |  |  |  |  | N/A | Yes | Stalled | 29.8922 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 348 | 2097 |  | 88 | 1090.584 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| PLATE 12 MM MS | 933 \ 2AF3 \ 349 | 237 | 409 | 44 | 401.764 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| 65X65X6 MS | 933 \ 2AF3 \ 351 | 1144 |  | 88 | 594.968 | UNIT-II | 34 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 360 | 205 | 553 | 44 | 391.556 | UNIT-II | 31 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 37 | 1623 |  | 22 | 160.314 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 38 | 2017 |  | 22 | 199.232 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| A 75X75X8 MS | 933 \ 2AF3 \ 39 | 2132 |  | 22 | 422.136 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 51 | 981 |  | 44 | 193.82 | UNIT-II | 21 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 56 | 1164 |  | 22 | 114.972 | UNIT-II | 21 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 58 | 1589 |  | 22 | 156.97 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 59 | 1638 |  | 1 | 7.355 | UNIT-II | 19 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 50X50X6 MS | 933 \ 2AF3 \ 6 | 778 |  | 43 | 150.199 | UNIT-II | 3 |  |  |  |  | N/A |  | Moving |  |  |  | Unknown | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 60 | 2032 |  | 21 | 191.604 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| A 75X75X8 MS | 933 \ 2AF3 \ 61 | 2152 |  | 22 | 426.096 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 67 | 110 | 229 | 22 | 43.494 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 70 | 669 |  | 44 | 132.176 | UNIT-II | 12 |  |  |  |  | N/A | Yes | Stalled | 28.7989 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 71L | 1196 |  | 22 | 118.14 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 73R | 1345 |  | 22 | 132.858 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 65X65X8 MS | 933 \ 2AF3 \ 75 | 1978 |  | 22 | 336.38 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 77 | 1169 |  | 20 | 104.98 | UNIT-II | 21 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 80 | 1655 |  | 22 | 163.482 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled | 23.7885 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 81 | 2057 |  | 22 | 203.192 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| A 75X75X8 MS | 933 \ 2AF3 \ 82 | 2181 |  | 19 | 372.951 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2AF3 \ 87 | 240 | 110 | 44 | 91.168 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| 50X50X6 MS | 933 \ 2AF3 \ 9 | 2201 |  | 44 | 434.808 | UNIT-II | 11 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 91L | 1217 |  | 22 | 120.208 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 92 | 990 |  | 43 | 191.135 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled | 32.8408 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2AF3 \ 96 | 585 |  | 5 | 13.135 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 200X200X20 MS | 933 \ 2AF5M \ 341 | 5016 |  | 1 | 300.759 | UNIT-II | 12 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| 200X200X20 MS | 933 \ 2AF5M \ 341S | 5016 |  | 3 | 902.277 | UNIT-II | 8 |  |  |  |  | N/A |  | Slow | 3.6102 |  |  | Unknown | ANGLE | Drilling
| 75X75X8 MS | 933 \ 2AF5M \ 352 | 4213 |  | 8 | 303.336 | UNIT-II | 18 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 75X75X8 MS | 933 \ 2AF5M \ 352A | 4213 |  | 8 | 303.336 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 75X75X8 MS | 933 \ 2AF5M \ 353 | 2991 |  | 8 | 215.352 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 15.7591 |  |  | Stalled | ANGLE | Punching
| 75X75X8 MS | 933 \ 2AF5M \ 353A | 2991 |  | 8 | 215.352 | UNIT-II | 14 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF5M \ 355 | 1912 |  | 24 | 271.2 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled | 32.8408 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF5M \ 356 | 2473 |  | 24 | 350.76 | UNIT-II | 12 |  |  |  |  | N/A | Yes | Stalled | 34.8556 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF5M \ 358 | 1716 |  | 16 | 162.272 | UNIT-II | 24 |  |  |  |  | N/A | Yes | Stalled | 25.5502 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2AF5M \ 359 | 1331 |  | 24 | 188.784 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled | 32.8408 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 113 | 263 | 85 | 32 | 56.16 | UNIT-II | 14 |  |  |  |  | N/A | Yes | Stalled | 12.7201 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 114 | 264 | 85 | 32 | 56.384 | UNIT-II | 14 |  |  |  |  | N/A | Yes | Stalled | 12.7201 |  |  | Stalled | PLATE | Punching
| 100X100X10 MS | 933 \ 2DF-5 \ 123 | 2768 |  | 1 | 41.631 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 129A | 385 | 100 | 16 | 48.352 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 131 | 315 | 282 | 16 | 111.568 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 12 MM MS | 933 \ 2DF-5 \ 159 | 422 | 306 | 16 | 194.624 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 19.7384 |  |  | Stalled | PLATE | Punching
| 150X150X12 MS | 933 \ 2DF-5 \ 160L | 397 |  | 16 | 173.344 | UNIT-II | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF-5 \ 160R | 397 |  | 16 | 173.344 | UNIT-II | 99 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 162 | 422 | 303 | 32 | 321.184 | UNIT-II | 12 |  |  |  |  | N/A | Yes | Stalled | 28.7989 |  |  | Stalled | PLATE | Punching
| 150X150X12 MS | 933 \ 2DF-5 \ 163R | 394 |  | 32 | 344.064 | UNIT-II | 99 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF-5 \ 164L | 390 |  | 16 | 170.288 | UNIT-II | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF-5 \ 164R | 390 |  | 16 | 170.288 | UNIT-II | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 167 | 416 | 312 | 20 | 203.78 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 169 | 306 | 115 | 16 | 44.192 | UNIT-II | 14 |  |  |  |  | N/A | Yes | Stalled | 12.7201 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 173 | 299 | 115 | 14 | 37.786 | UNIT-II | 16 |  |  |  |  | N/A | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
| 200X200X16 MS | 933 \ 2DF-5 \ 204 | 472 |  | 52 | 1191.112 | UNIT-II | 18 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF-5 \ 206 | 472 | 402 | 28 | 417.06 | UNIT-II | 15 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| A 75X75X8 MS | 933 \ 2DF-5 \ 20X | 4285 |  | 8 | 308.52 | UNIT-II | 7 |  |  |  |  | N/A | Yes | Stalled | 6.7265 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 218 | 612 | 457 | 16 | 351.28 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| 150X150X12 MS | 933 \ 2DF-5 \ 219L | 548 |  | 16 | 239.28 | UNIT-II | 99 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF-5 \ 219R | 548 |  | 16 | 239.28 | UNIT-II | 99 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF-5 \ 221R | 343 |  | 16 | 149.76 | UNIT-II | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 222 | 367 | 255 | 16 | 117.536 | UNIT-II | 12 |  |  |  |  | N/A | Yes | Stalled | 28.7989 |  |  | Stalled | PLATE | Punching
| 150X150X12 MS | 933 \ 2DF-5 \ 223R | 346 |  | 16 | 151.072 | UNIT-II | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF-5 \ 224L | 339 |  | 12 | 111.012 | UNIT-II | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF-5 \ 224R | 339 |  | 16 | 148.016 | UNIT-II | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 200X200X16 MS | 933 \ 2DF-5 \ 228R | 429 |  | 16 | 333.104 | UNIT-II | 15 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| 200X200X16 MS | 933 \ 2DF-5 \ 230R | 434 |  | 16 | 336.992 | UNIT-II | 15 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| 200X200X16 MS | 933 \ 2DF-5 \ 231R | 435 |  | 16 | 337.776 | UNIT-II | 15 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF-5 \ 232 | 457 | 225 | 16 | 129.152 | UNIT-II | 18 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 236 | 255 | 170 | 16 | 54.448 | UNIT-II | 14 |  |  |  |  | N/A | Yes | Stalled | 15.7591 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 237 | 255 | 115 | 16 | 36.832 | UNIT-II | 16 |  |  |  |  | N/A | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 238 | 248 | 115 | 16 | 35.824 | UNIT-II | 16 |  |  |  |  | N/A | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 239 | 504 | 135 | 32 | 170.912 | UNIT-II | 6 |  |  |  |  | N/A |  | Moving |  |  |  | Unknown | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 240 | 402 | 120 | 48 | 181.776 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 243 | 331 | 275 | 16 | 114.32 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 244 | 331 | 135 | 16 | 56.128 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 247 | 692 | 153 | 16 | 132.976 | UNIT-II | 29 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 250 | 149 | 135 | 16 | 25.264 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 12.7201 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 251 | 360 | 149 | 16 | 67.376 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 252 | 380 | 248 | 16 | 118.368 | UNIT-II | 31 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| A 200X200X20 MS | 933 \ 2DF-5 \ 268 | 2862 |  | 2 | 343.212 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF-5 \ 272 | 392 | 120 | 100 | 369.3 | UNIT-II | 29 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | PLATE | Punching
| 65X65X6 MS | 933 \ 2DF-5 \ 277 | 1018 |  | 32 | 192.512 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled | 32.8408 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF-5 \ 278 | 545 |  | 32 | 103.072 | UNIT-II | 15 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 200X200X16 MS | 933 \ 2DF-5 \ 286 | 221 |  | 32 | 343.2 | UNIT-II | 12 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | ANGLE | Drilling
| 200X200X16 MS | 933 \ 2DF-5 \ 288 | 136 |  | 96 | 633.6 | UNIT-II | 7 |  |  |  |  | N/A |  | Moving |  |  |  | Unknown | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF-5 \ 289 | 392 | 136 | 96 | 401.76 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| A 50X50X6 MS | 933 \ 2DF-5 \ 28R | 1359 |  | 8 | 48.816 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 200X200X16 MS | 933 \ 2DF-5 \ 290 | 136 |  | 44 | 290.4 | UNIT-II | 3 |  |  |  |  | N/A |  | Slow | 35.6468 |  |  | Unknown | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF-5 \ 294 | 135 | 136 | 192 | 276.672 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 12.7201 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 297 | 602 | 135 | 16 | 102.08 | UNIT-II | 12 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| A 200X200X20 MS | 933 \ 2DF-5 \ 310S | 5124 |  | 2 | 614.47 | UNIT-II | 34 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
| 65X65X6 MS | 933 \ 2DF-5 \ 320 | 996 |  | 32 | 188.352 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled | 32.8408 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 334 | 578 | 135 | 16 | 98 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 335 | 578 | 205 | 16 | 148.816 | UNIT-II | 12 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 338 | 402 | 145 | 32 | 146.432 | UNIT-II | 6 |  |  |  |  | N/A |  | Moving |  |  |  | Unknown | PLATE | Punching
| A 50X50X6 MS | 933 \ 2DF-5 \ 34 | 1270 |  | 8 | 45.616 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF-5 \ 36 | 1844 |  | 8 | 66.24 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF-5 \ 64R | 1256 |  | 8 | 45.112 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF-5 \ 71 | 1493 |  | 8 | 53.632 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF-5 \ 74 | 1401 |  | 16 | 100.64 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 75X75X8 MS | 933 \ 2DF-5 \ 80L | 3969 |  | 1 | 35.721 | UNIT-II | 7 |  |  |  |  | N/A | Yes | Stalled | 6.7265 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF-5 \ 83R | 1111 |  | 16 | 79.808 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF-5 \ 85XR | 1250 |  | 8 | 44.904 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 88XL | 340 | 743 | 8 | 158.648 | UNIT-II | 18 |  |  |  |  | N/A | Yes | Stalled | 15.7591 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF-5 \ 88XR | 340 | 743 | 8 | 158.648 | UNIT-II | 18 |  |  |  |  | N/A | Yes | Stalled | 15.7591 |  |  | Stalled | PLATE | Punching
| 130X130X12 MS | 933 \ 2DF-5 \ 89 | 2486 |  | 8 | 466.376 | UNIT-II | 3 |  |  |  |  | N/A |  | Slow | 35.6468 |  |  | Unknown | ANGLE | Punching
| 75X75X8 MS | 933 \ 2DF-5 \ 9 | 2942 |  | 8 | 211.824 | UNIT-II | 51 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF-5 \ 95 | 1482 |  | 24 | 159.696 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF3 \ 102 | 2460 |  | 22 | 319.858 | UNIT-II | 12 |  |  |  |  | N/A | Yes | Stalled | 30.7329 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 112 | 260 | 178 | 44 | 159.852 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 113 | 263 | 85 | 88 | 154.44 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 12.7201 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 114 | 264 | 85 | 88 | 155.056 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 12.7201 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 115 | 175 | 120 | 44 | 72.556 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 116 | 250 | 117 | 42 | 96.432 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| 130X130X12 MS | 933 \ 2DF3 \ 121 | 436 |  | 44 | 449.856 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 122 | 436 | 100 | 88 | 301.224 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| 100X100X10 MS | 933 \ 2DF3 \ 126 | 2016 |  | 1 | 30.321 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 128 | 204 | 240 | 42 | 161.406 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 129 | 385 | 100 | 132 | 398.904 | UNIT-II | 12 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 129A | 385 | 100 | 44 | 132.968 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 131 | 315 | 282 | 44 | 306.812 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| 130X130X12 MS | 933 \ 2DF3 \ 156 | 2006 |  | 1 | 47.041 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| PLATE 12 MM MS | 933 \ 2DF3 \ 159 | 422 | 306 | 44 | 535.216 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 19.7384 |  |  | Stalled | PLATE | Punching
| 150X150X12 MS | 933 \ 2DF3 \ 160R | 397 |  | 44 | 476.696 | UNIT-II | 104 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 162 | 422 | 303 | 44 | 441.628 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| 150X150X12 MS | 933 \ 2DF3 \ 163L | 394 |  | 87 | 935.424 | UNIT-II | 104 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF3 \ 163R | 394 |  | 88 | 946.176 | UNIT-II | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF3 \ 164L | 390 |  | 44 | 468.292 | UNIT-II | 22 |  |  |  |  | N/A |  | Slow | 32.8408 |  |  | Unknown | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF3 \ 164R | 390 |  | 22 | 234.146 | UNIT-II | 105 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 167 | 416 | 312 | 46 | 468.694 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 19.7384 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 169 | 306 | 115 | 44 | 121.528 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 12.7201 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 170 | 306 | 225 | 44 | 237.82 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 171 | 303 | 115 | 88 | 240.68 | UNIT-II | 12 |  |  |  |  | N/A | Yes | Stalled | 28.7989 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 172 | 303 | 225 | 88 | 470.976 | UNIT-II | 34 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 173 | 299 | 115 | 40 | 107.96 | UNIT-II | 16 |  |  |  |  | N/A | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 174 | 335 | 299 | 44 | 345.972 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 175 | 612 | 275 | 44 | 581.328 | UNIT-II | 18 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 178 | 275 | 115 | 44 | 109.252 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 179 | 275 | 225 | 44 | 213.708 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| 200X200X16 MS | 933 \ 2DF3 \ 204 | 472 |  | 172 | 3939.832 | UNIT-II | 99 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
| 200X200X16 MS | 933 \ 2DF3 \ 205 | 472 |  | 80 | 1832.48 | UNIT-II | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF3 \ 206 | 472 | 402 | 109 | 1623.555 | UNIT-II | 18 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| 130X130X12 MS | 933 \ 2DF3 \ 211A | 2701 |  | 2 | 126.676 | UNIT-II | 3 |  |  |  |  | N/A |  | Slow | 35.6468 |  |  | Unknown | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 218 | 612 | 457 | 44 | 966.02 | UNIT-II | 18 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 220 | 367 | 252 | 44 | 319.44 | UNIT-II | 15 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| 150X150X12 MS | 933 \ 2DF3 \ 221L | 343 |  | 44 | 411.84 | UNIT-II | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF3 \ 221R | 343 |  | 42 | 393.12 | UNIT-II | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 222 | 367 | 255 | 44 | 323.224 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| 150X150X12 MS | 933 \ 2DF3 \ 223L | 346 |  | 44 | 415.448 | UNIT-II | 104 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF3 \ 223R | 346 |  | 14 | 132.188 | UNIT-II | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 150X150X12 MS | 933 \ 2DF3 \ 224R | 339 |  | 42 | 388.542 | UNIT-II | 29 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 225 | 547 | 504 | 20 | 432.84 | UNIT-II | 18 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| 200X200X16 MS | 933 \ 2DF3 \ 226L | 601 |  | 23 | 670.841 | UNIT-II | 3 |  |  |  |  | N/A |  | Moving |  |  |  | Unknown | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF3 \ 227 | 402 | 332 | 44 | 460.988 | UNIT-II | 12 |  |  |  |  | N/A | Yes | Stalled | 28.7989 |  |  | Stalled | PLATE | Punching
| 200X200X16 MS | 933 \ 2DF3 \ 228L | 429 |  | 44 | 916.036 | UNIT-II | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF3 \ 232 | 457 | 225 | 44 | 355.168 | UNIT-II | 18 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 233 | 457 | 115 | 44 | 181.544 | UNIT-II | 18 |  |  |  |  | N/A | Yes | Stalled | 14.7178 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 234 | 252 | 170 | 44 | 147.972 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 235 | 252 | 115 | 44 | 100.1 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 236 | 255 | 170 | 44 | 149.732 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 237 | 255 | 115 | 36 | 82.872 | UNIT-II | 16 |  |  |  |  | N/A | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 238 | 248 | 115 | 38 | 85.082 | UNIT-II | 1 |  |  |  |  | N/A |  | Slow | 25.5502 |  |  | Unknown | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 239 | 504 | 135 | 88 | 470.008 | UNIT-II | 7 |  |  |  |  | N/A |  | Moving |  |  |  | Unknown | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 240 | 402 | 120 | 63 | 238.581 | UNIT-II | 36 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 241 | 332 | 135 | 88 | 309.584 | UNIT-II | 29 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 244 | 331 | 135 | 44 | 154.352 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 247 | 692 | 153 | 44 | 365.684 | UNIT-II | 18 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| 200X200X16 MS | 933 \ 2DF3 \ 249L | 162 |  | 22 | 172.964 | UNIT-II | 8 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| 200X200X16 MS | 933 \ 2DF3 \ 249R | 162 |  | 22 | 172.964 | UNIT-II | 8 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF3 \ 250 | 149 | 135 | 44 | 69.476 | UNIT-II | 14 |  |  |  |  | N/A | Yes | Stalled | 12.7201 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 252 | 380 | 248 | 44 | 325.512 | UNIT-II | 31 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| A 200X200X20 MS | 933 \ 2DF3 \ 265 | 2845 |  | 1 | 170.586 | UNIT-II | 14 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
| A 50X50X6 MS | 933 \ 2DF3 \ 27 | 981 |  | 44 | 193.82 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF3 \ 274 | 804 |  | 88 | 418.176 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF3 \ 276 | 1647 |  | 88 | 856.592 | UNIT-II | 18 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF3 \ 278 | 545 |  | 88 | 283.448 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF3 \ 280 | 1015 |  | 88 | 527.912 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF3 \ 283 | 1210 |  | 88 | 629.288 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 200X200X16 MS | 933 \ 2DF3 \ 286 | 221 |  | 88 | 943.8 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF3 \ 287 | 392 | 136 | 44 | 184.14 | UNIT-II | 65 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| 200X200X16 MS | 933 \ 2DF3 \ 288 | 136 |  | 264 | 1742.4 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF3 \ 289 | 392 | 136 | 212 | 887.22 | UNIT-II | 15 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| 200X200X16 MS | 933 \ 2DF3 \ 290 | 136 |  | 792 | 5227.2 | UNIT-II | 34 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF3 \ 292 | 221 | 135 | 86 | 201.412 | UNIT-II | 16 |  |  |  |  | N/A | Yes | Stalled | 25.5502 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 293 | 135 | 136 | 264 | 380.424 | UNIT-II | 14 |  |  |  |  | N/A | Yes | Stalled | 12.7201 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 294 | 135 | 136 | 792 | 1141.272 | UNIT-II | 14 |  |  |  |  | N/A | Yes | Stalled | 12.7201 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 296 | 602 | 392 | 22 | 407.55 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| 65X65X6 MS | 933 \ 2DF3 \ 316 | 1254 |  | 88 | 652.168 | UNIT-II | 18 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF3 \ 317 | 1818 |  | 61 | 655.384 | UNIT-II | 15 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF3 \ 320 | 996 |  | 88 | 517.968 | UNIT-II | 18 |  |  |  |  | N/A | Yes | Stalled | 32.8408 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF3 \ 323 | 1513 |  | 71 | 634.882 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF3 \ 326 | 1704 |  | 88 | 886.248 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF3 \ 327 | 1254 |  | 88 | 652.168 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled | 32.8408 |  |  | Stalled | ANGLE | Punching
| 110X110X8 MS | 933 \ 2DF3 \ 328 | 378 |  | 44 | 222.86 | UNIT-II | 65 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 333 | 578 | 464 | 24 | 505.272 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 334 | 578 | 135 | 22 | 134.75 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 335 | 578 | 205 | 44 | 409.244 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 21.4213 |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 338 | 402 | 145 | 31 | 141.856 | UNIT-II | 18 |  |  |  |  | N/A | Yes | Stalled | 14.7178 |  |  | Stalled | PLATE | Punching
| 200X200X16 MS | 933 \ 2DF3 \ 341 | 143 |  | 88 | 610.72 | UNIT-II | 8 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF3 \ 342 | 143 | 392 | 44 | 193.6 | UNIT-II | 36 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 343 | 143 | 135 | 88 | 133.32 | UNIT-II | 3 |  |  |  |  | N/A |  | Slow | 25.5502 |  |  | Unknown | PLATE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 38 | 1304 |  | 44 | 257.62 | UNIT-II | 19 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF3 \ 44 | 283 | 128 | 40 | 113.76 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | PLATE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 46R | 1085 |  | 22 | 107.184 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 47 | 980 |  | 44 | 193.6 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 54 | 1335 |  | 22 | 131.868 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 57 | 1315 |  | 44 | 259.776 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 23.7885 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 69 | 711 |  | 22 | 70.224 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 74 | 1401 |  | 44 | 276.76 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 83L | 1111 |  | 1 | 4.988 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 83XL | 1109 |  | 22 | 109.538 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 84 | 682 |  | 88 | 269.456 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 85XL | 1250 |  | 22 | 123.486 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 85XR | 1250 |  | 22 | 123.486 | UNIT-II | 20 |  |  |  |  | N/A | Yes | Stalled | 22.4987 |  |  | Stalled | ANGLE | Punching
| A 130X130X12 MS | 933 \ 2DF3 \ 90 | 2486 |  | 5 | 291.485 | UNIT-II | 64 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 92 | 1404 |  | 25 | 157.6 | UNIT-II | 21 |  |  |  |  | N/A | Yes | Stalled | 24.8672 |  |  | Stalled | ANGLE | Punching
| A 50X50X6 MS | 933 \ 2DF3 \ 97 | 689 |  | 66 | 204.204 | UNIT-II | 19 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF5M \ 206 | 402 | 472 | 4 | 59.58 | UNIT-II | 30 |  |  |  |  | N/A |  | Moving |  |  |  | Unknown | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF5M \ 207 | 135 | 472 | 8 | 40.016 | UNIT-II | 30 |  |  |  |  | N/A |  | Slow | 21.4213 |  |  | Unknown | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF5M \ 272 | 120 | 392 | 12 | 44.316 | UNIT-II | 30 |  |  |  |  | N/A |  | Moving |  |  |  | Unknown | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF5M \ 289 | 136 | 392 | 12 | 50.22 | UNIT-II | 30 |  |  |  |  | N/A |  | Slow | 21.4213 |  |  | Unknown | PLATE | Punching
| 200X200X16 MS | 933 \ 2DF5M \ 341 | 143 |  | 3 | 20.82 | UNIT-II | 22 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Drilling
| PLATE 10 MM MS | 933 \ 2DF5M \ 342 | 143 | 392 | 4 | 17.6 | UNIT-II | 30 |  |  |  |  | N/A |  | Moving |  |  |  | Unknown | PLATE | Punching
| 65X65X6 MS | 933 \ 2DF5M \ 354 | 1771 |  | 8 | 83.736 | UNIT-II | 30 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF5M \ 355 | 2233 |  | 8 | 105.576 | UNIT-II | 13 |  |  |  |  | N/A | Yes | Stalled | 35.6468 |  |  | Stalled | ANGLE | Punching
| 65X65X6 MS | 933 \ 2DF5M \ 358 | 1513 |  | 8 | 71.536 | UNIT-II | 21 |  |  |  |  | N/A | Yes | Stalled |  |  |  | Stalled | ANGLE | Punching
| PLATE 10 MM MS | 933 \ 2DF5M \ 360 | 354 | 392 | 4 | 43.572 | UNIT-II | 30 |  |  |  |  | N/A |  | Moving |  |  |  | Unknown | PLATE | Punching
| PLATE 10 MM MS | 933 \ 2DF5M \ 361 | 354 | 135 | 8 | 30.016 | UNIT-II | 30 |  |  |  |  | N/A |  | Moving |  |  |  | Unknown | PLATE | Punching
TOTAL |  |  |  |  | 13053 | 94935.934